## Attch 5 - Installation Plan
Attachment 5 - Installation Plan
Laboratory Info | Manufacturer/type and # of instrument(s) to be delivered & installed | Manufacturer/type and # of water system(s) to be delivered & installed | Identify the # of work station(s) and equipment provided for data mngmt | Installation Schedule
Indianpolis Consolidated lab |  |  |  | 15 -20 business days after kick-off meeting
U.S. Courthouse
46 East Ohio St., Suite 101
Indianapolis, IN 46204
Central Islip Probation lab |  |  |  | 20-25 business days after kick-off meeting
U.S. Courthouse
202 Federal Plaza
2nd Floor
Central Islip, NY 11722
NY City (Pearl St) Pretrial lab |  |  |  | 20-25 business days after kick-off meeting
U.S. Courthouse
500 Pearl St., Room 550
New York, NY 10007
NY City (Pearl St) Probation lab |  |  |  | 20-25 business days after kick-off meeting
U.S. Courthouse
500 Pearl St., 7th floor
New York, NY 70007
Brooklyn Probation lab |  |  |  | 20-25 business days after kick-off meeting
U.S. Probation Office
27 Johnson St., Room 1525
Brooklyn, NY 11201
Chicago Pretrial lab |  |  |  | 25-28 business days after kick-off meeting
U.S. Courthouse
219 S. Dearborn, Suite 15100
Chicago, IL 60630
Miami Consolidated lab |  |  |  | 25-28 business days after kick-off meeting
Wilkie D. Ferguson Federal Courthouse
400 N. Miami Ave., 9th floor N
Miami, FL 33128
Charlotte Consolidated lab |  |  |  | 25-28 business days after kick-off meeting
U.S. Probation Office
401 W. Trade St., Ste. 1100
Charlotte, NC 28202
Jacksonville Pretrial lab |  |  |  | 28 -31 business days after kick-off meeting
U.S. Courthouse
300 N, Hogan St., Ste 2-200
Jacksonville, FL 32202
San Antonio Pretrial regional lab |  |  |  | 28 -31 business days after kick-off meeting
U.S. Pretrial Services Office
262 W. Nueva, Ste. 1-200
San Antonio, TX 78207-4529
Seattle Consolidated lab |  |  |  | 28 -31 business days after kick-off meeting
U.S. District Court
700 Stewart St., Ste. 10101
Seattle, WA 98101
San Diego Pretrial regional lab |  |  |  | 31 - 35 business days after kick-off meeting
U.S. Pretrial Laboratory
333 W. Broadway, Ste. 600
San Diego, CA 92101
Alexandria Consolidated lab |  |  |  | 31 - 35 business days after kick-off meeting
Albert V. Bryan Courthouse
401 Courthouse Square, 3rd floor
Alexandria, VA 22314
St. Louis Probation regional lab |  |  |  | 35 - 39 business days after kick-off meeting
U.S. Probation Office
111 S. 10th Street, Ste. 1.424
St. Louis, MO 63102
Buffalo Consolidated regional lab |  |  |  | 35 - 39 business days after kick-off meeting
U.S. Courthouse
2 Niagara Square, Room 140
Buffalo, NY 14224
Albuquerque Consolidated regional lab |  |  |  | 39 - 42 business days after kick-off meeting
Dennis Chavez Federal Building
500 Gold Ave., Ste. 10226
Albuquerque, NM 87102
Taunton Consolidated regional lab |  |  |  | 42 - 45 business days after kick-off meeting
U.S. Courthouse
104 Dean St., Ste. 102
Taunton, MA 02780
San Juan Consolidated lab |  |  |  | 42 - 45 business days after kick-off meeting
Federico Degetau Federal Bldg
150 Carlos Chardon Ave, Room G1051
San Juan, PR 00198