## Sheet1
FY26 Construction Forecast: Jefferson Barracks ANGS, St. Louis MO
Project Number | Project Title | Description | Disclosure of Magnitude | Solicitation No. | Solicitation Method | Set-Aside | Status/Anticipated Solicitation Release
LTUY202005 | Construct Vehicle Operations Covered Parking | Construct two covered parking structures with rooftop solar panels in existing parking lot adjacent to Building 41, Jefferson Barracks ANGS. The performance period for completion will be 260 days after issue of NTP. | Between $1M and $5M | W50S8K26QA002 | Commercial Simplified Procedures RFQ (RFO FAR) | Small Business | FY26 Q3
LTUY202057 | Repair Roof, Roads & Grounds Facility, B99 | Replace roofing shingles, restore siding to historical appearance, added vented soffits to roof structure, and make misc. repairs to Building 99, Jefferson Barracks ANGS. The performance period for completion will be 180 days after issue of NTP. | Between $500K and $1M | TBD | Commercial Simplified Procedures RFQ (RFO FAR) | Small Business | FY26 Q3
LTUY202129 | Repair B290 Boiler | Replace existing boiler and make associated repairs to mechanical room piping in Building 290, Jefferson Barracks ANGS. The performance period for completion will be 60 days after issue of NTP. | Between $25K and $100K | W50S8K26RA001 | Simplified Acquisition Request for Proposal | Small Business | Awarded
LTUY232044 | Bldg 1, 28 and 36 Windows, 37 Dormer Repair | Repair/replace damaged windows in multiple buildings and make repairs to water damaged dormer on Building 37, Jefferson Barracks ANGS. The performance period for completion will be 120 days after issue of NTP. | Between $25K and $100K | TBD | Commercial Simplified Procedures RFQ (RFO FAR) | TBD | FY26 Q3
LTUY242008 | Replace B28 and B280 Shower Stalls | Replace shower stall finishes in multiple buildings for quality of life improvements for AOG personnel in Buildings 28 & 280, Jefferson Barracks ANGS. The performance period for completion will be 90 days after issue of NTP. | Less than $25K | TBD | Commercial Simplified Procedures RFQ (RFO FAR) | TBD | FY26 Q4
LTUY252017 | Repair Bldg 50 for CES and CBCS Consolidation | Renovate building interior to configure space for consolidated power production shop of 131st Civil Engineer Squadron and 239th Combat Communications Squadron at Building 50, Jefferson Barracks ANGS. The performance period for completion will be 120 days after issue of NTP. | Between $25K and $100K | TBD | Commercial Simplified Procedures RFQ (RFO FAR) | TBD | FY26 Q3
LTUY252022 | Repair B37 ATS Reprogramming | Repair automatic transfer switch wiring so genrator properly turns on during power outages to Building 37, Jefferson Barracks ANGS. The performance period for completion will be 45 days after issue of NTP. | Less than $25K | W50S8K26QA001 | Commercial Simplified Procedures RFQ (RFO FAR) | Small Business | FY26 Q3
LTUY262003 | Replace Bldg 37 AHU | Replace HVAC air handling unit in Building 37, Jefferson Barracks ANGS. The performance period for completion will be 60 days after issue of NTP. | Less than $25K | N/A | Simplified Acquisition Request for Proposal | Small Business | Awarded - Internal IDIQ