Performance Work Statement (PWS)

U.S. Energy and Employment Report

Office of Policy

Office of Energy Jobs

As of 03/24/2026

- BACKGROUND

The Office of Policy (OP) supports the Secretary of Energy, Deputy Secretary, Under Secretaries, and the entire Department of Energy (DOE or Department), by providing analysis and guidance on domestic energy policy and related integration of energy systems. Working in coordination with the White House, Capitol Hill, other federal agencies, and local stakeholders, OP aims to facilitate an affordable, reliable, and secure energy economy. To do so, OP works collaboratively across the Department and federal government, leveraging existing capabilities of program offices and national labs to achieve policy analysis objectives and build long-term analytical capabilities.

The Office serves as a focal point for policy coordination within the Department on the analysis, formulation, development, and advancement of Secretarial and Administrative priorities; and related programmatic options and initiatives that support the path to American energy dominance. OP coordinates policy and strategic cross-cutting functions across DOE elements and shapes and guides strategy and policy implementation consistent with the Secretary’s vision for DOE. Much of OP’s work is connected to expertise or information in the various program offices across the Department, and OP works closely with other offices to harmonize activities, maximize results, and avoid duplication.

The Office of Energy Jobs, housed in OP, serves as a hub for the Department’s workforce development strategy and conducts vital research and analysis on the energy labor market. The Office of Energy Jobs leads efforts to align energy workforce development programs across the Department, manages the 21st Century Energy Workforce Advisory Board, and publishes the annual U.S. Energy and Employment Report.

- GENERAL DESCRIPTION

The U.S. Energy and Employment Report (USEER) is a published comprehensive overview of the energy labor market. The USEER offers unique insights into the individuals and employers who meet the nation’s energy needs, identifies important trends and skillsets for the 21st century energy workforce, and provides data on employment trends in five major energy sectors — Electric Power Generation; Transmission, Distribution, and Storage; Fuels; Energy Efficiency; and Motor Vehicles.

The Supplemental Wage survey explores energy sector wages, employment benefits, and the overall geographic distribution of energy jobs in the United States. The Wage Report also discusses how hourly wages for energy jobs compare to national medians across both energy sub-sectors, such as coal, oil, natural gas, energy efficiency, solar, and wind, as well as industry segments, such as mining, construction, manufacturing, utilities, wholesale trade, and professional services. The report will evolve in its analysis of wage trends to include more geographic and occupational insight. It will also capture current and emerging impacts of changes in the energy sector, including the geographic distribution of energy employment and the demographic composition of the workforce.

Per 42 USC 18841, Congress requires the development and publication of the annual USEER as the authoritative source for energy jobs data in the United States. The USEER helps to guide decision making and policy in the energy sector.

- CONTRACT TYPE

The contract type is a firm fixed-price (FFP) contract.

- PERIOD OF PERFORMANCE

The period of performance is TBD upon award The contract will consist of a 12-month base period/year, and four (4) year option periods.

- SCOPE

The Contractor will provide personnel, equipment, supplies, facilities, transportation, tools, materials, supervision, and other items and non-personal services necessary to design a supplemental survey methodology, develop survey data bases, and engage in data collection & analysis activities necessary to produce the annual USEER. Contractor tasks are identified below.

5.1 Task 1 - Data Collection: The Contractor will propose a methodology of data collection that will be approved by the Office of Energy Jobs and by the Office of Management and Budget (OMB). The Contractor will utilize existing Bureau of Labor Statistics Quarterly Census on Employment and Wages (QCEW) sampling frame for the data collection required under the contract, maintain employer databases, as required by the Contracting Officer (CO), use a supplemental survey based on an analysis of the North American Industrial Classification System (NAICS), and deploy data collection strategies and methods that adhere to the best Federal statistical agencies practices and which are consistent with the U.S. Bureau of Labor Statistics (BLS) methodologies. This includes including the data will reflect energy jobs in U.S. states, counties, the U.S. Virgin Islands, Puerto Rico, and other U.S. territories to the extent possible.

Contractor performance requirements include:

- Provide a plan showing clear processes and timeline for contacting respondents, with details on modalities of contact, i.e. phone, text, e-mail, etc. Plans should include contingencies for non-response and a protocol for follow-ups. For example, there can be a plan to target under-represented establishments, using firm characteristics approved by OEJ, with additional recruitment efforts, or different modes (phone, in-person). This auxiliary data can be used to for statistical adjustments to survey nonresponse. Annual construction of the sampling frame and update of employer databases, following the sampling plan.

- Provide weekly updates to the Office of Energy Jobs on the status of data collection, including number of outreaches, number of responses, complete and partial, and percentage of budget.

- Provide clear documentation, of how samples are constructed and developed, so that it is clear how the sample differs from the universe of establishments tracked in the QCEW. Provide a description of the likely respondents, including the estimated number of likely respondents, and proposed frequency of response to the collection of information; also including a written and statistical description of how likely respondents differ in characteristics from the universe of potential respondents based on previous USEER survey collection results.

- Estimate the total annual reporting and recordkeeping time burden from the collection of information, and potential uses of technology to reduce the reporting burden.

- Establish a secure system for data collection and storage to comply with federal data security regulations.

- Annually administer the survey instrument provided in a manner consistent with that set forth in the Supporting Statement to OMB.

- When appropriate, perhaps after data collection, initiate pilot testing of survey instrument, including testing of survey instrument in different modalities, if applicable, for future documentation and updates about how the survey instrument can be improved in future data collection efforts. Administer supplemental data collection in close consultation with the Office of Energy Jobs; supplemental data collection can be used to address nonresponses from respondents and nonresponses to survey questions. Ensure data integrity in advance of report generation.

Data Collection Schedule:

- A Kick-off Meeting shall be held to discuss specifications as outlined in Section 4 above. This meeting will be held at the DOE office in Washington, DC, or via phone conference. The kick-off meeting will be held within five (5) working days after award.

- Contractors should provide weekly reports regarding the data collection effort beginning the first week after the data collection period begins, which will include discussion about general survey non-response and non-response of questions or sections in the survey instrument.

- Contractor shall provide a final report on the data collection within two (2) days after the completion of the data collection period that includes a discussion and potential statistical analysis of nonresponse to the survey and to questions or sections of the survey instrument.

- Contractor shall transfer any requested data that was collected and other relevant information relating to the data collection to DOE by December 31, of each year this contract is in effect using secure processes according to standard practices established by BLS and other federal statistical agencies while maintaining compliance with the Confidential Information Protection and Statistical Efficiency Act (CIPSEA) (See Section 7.1).

- Contractor shall be available as needed to answer questions about data collection processes.

5.2 Task 2 – Update the USEER Sampling Plan and Conduct Sampling: The Contractor shall construct a sampling plan that will create and support the long-term viability of the USEER sample. The USEER must be of sufficient sample size such that it elicits a similar number of responses from businesses in each State as were received in previous USEERs. Language in the survey instrument needs to be updated and improved upon to ensure that recipients fully understand the questions being asked and an updated sampling plan will ensure that employers in the affected industries receive the survey. The USEER sampling plan is built from plans of previous years. New sampling that does not have precedents may require additional sampling necessary for industries and technologies that are not in the report.

Contractor performance requirements include:

- Documentation about the methodology for constructing the sample and the sampling plan;

- Conduct an annual review and update of the respondent list prior to the data collection process; changes in sample characteristics shall be noted via a written and statistical description of establishment characteristics; and

- Assist with review and any modification to the survey instrument; and evaluate effects of new sample on publication level data.

The Contractor will conduct sampling within specified NAICS codes to ensure accurate and reliable results with a statistical margin of error of +/-4% or less on a national level and at a 95% confidence interval. Contractor will consult with Office of Energy Jobs about the appropriate NAICS codes.

5.3 Task 3 – Produce, Maintain, and Improve USEER Survey Instrument: The annual survey instrument must be developed in a manner to capture employment data and report on at least the areas as outlined in 42 USC 18841(2)(A)(B) and any other areas identified by DOE and approved by OMB. The exact names and definitions of these areas may change in accordance with the OMB approved document and Department guidance:

- Electric Power Generation, differentiating between employment in the following types of electric power generation: Bioenergy/Biomass, Coal, Combined Heat and Power, Distributive Generation Systems, Geothermal, Natural Gas (Advanced, On-shore, and Off-shore), Nuclear, Oil and other Petroleum, Solar, Wind, Hydroelectric (Low-impact, Hydrokinetic and Marine, Traditional), use of Carbon Capture and Sequestration, and other generation.

- Electric Power Transmission, Distribution, and Storage, differentiating between Traditional Transmission and Distribution, Storage, and Smart Grid, Load Management and Frequency Regulation Systems.

- Energy Efficiency, including Heating, Cooling, and Building Envelope, to include: Energy savings appliances; advanced lighting controls and building management, Computational fluid dynamics (CFL) and Other Efficient Lighting; traditional heating, ventilation, and air conditioning (HVAC) goods and services; High annual fuel utilization efficiency (AFUE) HVAC; Water and/or air cooled electric chillers; Renewable Heating and Cooling; and Advanced Building Materials Air and /Insulation.

- Fuels, differentiating between jobs involved in Biodiesel, Coal, Corn Ethanol, Nuclear, Non-Woody Biomass (including algae), On and Off-shore Natural Gas, On and Off-shore Petroleum (including gasoline and diesel), Renewable Diesel, Waste Fuels, Woody Biomass/Cellulosic Biofuel, Other Biofuels, Other Ethanol, Other Fossil Fuel.

- Motor Vehicles and Component Parts, differentiating between Gasoline and Diesel (excluding freight trucking), light duty vehicles and component parts, Hybrid and Plug-In Hybrid Vehicles, Electric Vehicles, Natural Gas Vehicles, Hydrogen Vehicles, and Fuel Cell Vehicles.

- The USEER will also report jobs and establishments by primary value chain activity, including but not limited to: Research and Development; Manufacturing; Sales and Distribution; Installation, Repair, and Maintenance; Construction; and Professional Services.

Improvements to the Survey Instrument can include, but are not limited to the following:

- Collecting information about survey nonresponse and item nonresponse.

- Collecting information on firm size and market structure.

- Capturing employment related to the use of technology in the workplace; the construction and operations of AI Infrastructure and associated power generation; mining and processing of critical minerals and materials.

- Identifying expected employer decisions such as planning to raise wages and benefits, offering bonuses, and number of jobs openings.

- Capturing an estimate of the relative number of rates of voluntary separations.

- Identify employer perspectives on difficulty of hiring of workers in construction, manufacturing, utility, STEM, or professional occupations.

- Identify employer perspectives of the in-demand or deficient skills associated with construction manufacturing, utility, STEM, or professional workers.

- Identify employer expectations of additional or declining employment in the future.

- Address descriptions of how new workers are recruited and evaluated for potential employment and employment and training pathways.

- Capturing hours worked to facilitate the translating of temporary and part-time work hours to Full-Time Equivalence (FTE).

With guidance from the Office of Energy Jobs, Contractor shall conduct survey instrument testing through pilot studies or other methodology approved by the Office of Energy Jobs. Testing shall focus on respondent burden, respondent understanding of questions and respondent’s ability to answer questions, particularly new questions.

The Contractor will also conduct analysis of survey modality to understand response rate and response quality of electronic surveys and phone surveys. The Contractor will share a report of findings and meta-data about frequency and modality of contacts with potential respondents.

5.4 Task 4 – Supplemental Wage Survey and Report

The supplemental wage survey will help to better understand factors in job quality across the United States in a range of technologies including Electric Power Generation, Fuels, Transmission, Distribution, and Storage, Energy Efficiency, and Motor Vehicles. Additionally, they will measure premiums and discounts, provision of employer-paid benefits such as vacation, retirement, and healthcare, and other key metrics. It can also use Occupational Employment and Wage Statistic (OEWS) data from BLS but customized via survey to be aligned with the USEER, which relies on OEWS data. With guidance from the Office of Energy Jobs, the Contractor will report wage and benefit data controlling for geography and possibly occupation depending on data availability. These reports will include a discussion about non-response bias and, with guidance from the Office of Energy Jobs, and statistical adjustments accounting for nonresponse bias. If using OEWS data, the Contractor will utilize the most recent data available and provide an update to the data when more current data is released if requested by the CO.

5.5 Task 5 – Calculate Results and Prepare Deliverables: The Contractor will clean and process,  the survey responses to generate employment estimates for the report, calculating results using the BLS QCEW data. Processing includes flagging of survey (unit) and item nonresponse. The data will be provided in a table summary as well as summary statistics by state, county, and territory. The results will be incorporated into the USEER.

5.6 Task 6 – Conduct Analysis and Create Data Crosswalks: The Contractor will conduct an analysis of the data, in collaboration with the Office of Energy Jobs, and utilizing external data sources and desktop research.

Examples of requested analysis include:

- Conduct analysis on survey (unit) nonresponse and item nonresponse.

- Conduct analysis on trends and wages and employment levels by sector, industry, and occupation, firm size (i.e. at least small, media, and large) and geography using available geographic resolution.

- Conduct preliminary analysis on impacts of market structure on labor market tightness and job quality measures in coordination with the Office of Energy Jobs. Contextualize labor market trends using data from the Bureau of Labor Statistics (BLS) and Energy Information Administration (EIA). Differentiate between seasonal / temporary jobs (construction, installation) and permanent jobs.

- Analyze occupational trends using BLS OOH and OEWS data (employment projections, wages, etc.).

- Analyze employer perceived reasons for hiring difficulty with labor demand using CES and BLS JOLTS data, as well as with geographic data.

- Compare growth of industries (by employment, investment, and/or production) with wages and benefits to understand labor supply conditions and job quality.

- Create occupational profiles of in-demand occupations including barriers to entry, typical entry-level education requirements, and skills, to understand potential for long-term investments (using O*NET and BLS OEWS data).

- Conduct a landscape study of available data and conduct an analysis of consistency and inconsistency of published data and the data collected for the USEER.

- Conduct IO analysis to understand the economic impact of employment in the energy sector, in consultation with the Office of Energy Jobs. Examples of requested data crosswalks include:

- Provide data breakdowns and totals of technologies that cut across multiple sectors in energy production.

- Provide mapping of surveyed employers to 6-digit NAICS codes.

- Provide mapping of occupational data to SOC codes.

- If requested, ensure safe transfer of all CIPSEA-protected USEER survey microdata in contractor’s possession to the Office of Energy Jobs.

- If requested, provide statistically accurate tabulations of any and all USEER microdata in contractor’s possession to the Office of Energy Jobs.

- If requested, provide statistical analysis of any and all USEER microdata in contractor’s possession to the Office of Energy Jobs.

- If requested, provide training on navigating USEER microdata to approved Office of Energy Jobs analysts.

5.7 Task 7 – Deliver Final USEER: The Contractor shall provide all aspects of the USEER, including writing, editing, graphic design, illustration and infographic design, accessibility and 508 compliance, print-ready graphic production services with pagination, and report design and production. This will include design, layout, copy editing, and production of print-ready and hyperlinked electronic report versions. The Contractor will also provide a comprehensive slide deck on USEER findings and results, comparing current year to past data to depict key trends, contextualizing with aggregate wage and inflation trends using data from BLS and controlling geographic differences.

Contractor performance requirements include:

- The Contractor shall provide a detailed outline of the USEER, which will be reviewed and approved by the CO.

- Draft text must be written utilizing Plain Language and reviewed and approved by the CO. The Contractor shall provide thorough editing (proofreading, checking for typographical errors, appropriate hyphenation, consistent utilization of capitals, ensure spacing accuracies, etc.) to produce the report.

- The Contractor shall correct obvious spelling and usage errors and assure that abbreviations and acronyms are spelled consistently and defined as appropriate. All documents shall be reviewed to ensure that subjects and verbs agree and that no punctuation is missing and that corrections have been made regarding scientific nomenclature, literature citations, or other content discrepancies.

- The Contractor shall reconcile text references to figures, tables, maps, appendices, and other elements to ensure that the references are present and accurate. The Contractor shall check copy to assure that website references and URLs are current and accurate. The Contractor shall ensure that the report is visually appealing, containing infographics (which combine charts, graphs, and icons) as well as other visual representations of data such as maps and charts. These shall be approved by the CO.

- The Contractor shall conduct 508 compliances on all the documents that will be publicly available, ensuring federal accessibility requirements.

- The Contractor shall provide the final report in both print-ready and hyperlinked electronic-only formats. The Contractor will not release the report. DOE will provide directions to the contractor regarding the appropriate release method and date.

- The Contractor shall provide a comprehensive slide deck including a summary of all technology areas and key findings and providing comparisons of current year’s findings with historic findings to show trends.

- The Contractor shall provide DOE access to all micro-data available with consideration to CIPSEA requirements at the finest geographic resolution available.

- MILESTONE SCHEDULE

The following is a general outline of a sample milestone schedule for Task 7 as described above. Actual schedule may be modified after initial kick-off meeting. Final schedule will be determined by the Contractor and the CO.

August 17: DOE-Contractor Kickoff Meeting to be held in August on a mutually acceptable date.

November 20: Contractor shall present outline of USEER and Supplemental Wage Survey, which may be subject to refinement.

January 15: Contractor shall provide access to the micro-data, with consideration to CIPSEA requirements, and a memo with initial findings of the USEER to OP.

February 1: Contractor shall provide draft of one (1) chapter of the USEER to OP. Based on feedback received, the Contractor shall apply feedback to the other chapters of the USEER.

March 1: Contractor shall provide draft of all chapters of the USEER to OP. Based on feedback received, the contractor shall complete no more than six (6) rounds of edits.

April 15: Contractor shall provide all data and draft report in Excel and PDF by data tables including, by national, state, county and territory, technologies and growth trends, to the OP.

April 15: Contractor shall provide virtual briefing(s) on the USEER and Supplemental Wage Survey before the internal DOE approval process and final round of edits, and after the report release.

June 1: Pending release of BLS wage data, Contractor shall provide the draft Supplemental Wage Report to OP. Based on feedback received, the contractor shall complete no more than three (3) rounds of edits.

June 25: OP shall provide final edits and approval of draft report.

June 25: Contractor shall provide final version of Supplemental Wage Report to OP.

June 30: Contractor shall provide a clean draft in electronic hyperlinked PDF and print-ready Word formats to OP. OP will provide final DOE approval of both versions to Contractor.

July 30: Contractor shall deliver proposed revisions to federal data collection, including sampling and survey instruments.

July 30: Contractor shall provide compiled survey data from the data collection activities and associate statistical information with the OP.

- DATA SECURITY & CONFIDENTIALITY

The contractor shall enforce strict procedures for assuring data confidentiality and security. All data files and related documentation associated with the design and execution of the contract (e.g., field test data, locating data, sampling data, weighting and imputation data, assessment score files, public-use data, and restricted-use data) shall be stored by the contractor in secure locations as detailed by the contractor in the data security plan. These files shall be maintained in such a form as they can be easily provided to OP on request.

7.1 Confidential Information Protection and Statistical Efficiency Act (CIPSEA)

Data shall be collected that allows and requires the DOE and its agents to protect identifiable data from disclosure or release to unauthorized parties for non-statistical purposes. Therefore, as an integral part of the task, the Contractor shall always maintain confidentiality of the data and provide CIPSEA training and certification for all Contractor staff.

7.2 Secure File Transfer Protocol

The contractor will maintain a secure file transfer protocol (FTP) site for the easy transfer of data and documentation between contractors and DOE.

Once the contract is complete or terminated, or at an earlier time if required by the CO, the contractor shall coordinate with the CO to either return records to the agency, destroy the records, or transfer custody of the records to an alternate entity.

Examples of records created by the contractor are detailed below:

- Survey Methodology Files records:

  - Procedural manuals

  - Technical memorandums

  - All data collectors’ training materials

  - Communication related to survey issues (such as discussions about sample representativeness, interview sample priorities, etc.)

- Program Subject Files records include:

  - Planning documents

  - Internal explanatory statements regarding objectives, strategy, and methodology\

  - Monthly progress reports

  - Documentation related to any procedural problems and recommendations

  - Weighting plans

  - Created variable plans

- Master Database documentation / Output Files records include:

  - Full public use dataset without PII

  - Data codebooks

7.3 Statistical Disclosure Control

The contractor will ensure that any information disseminated is subject to statistical disclosure control (SDC). The contractor will follow the necessary set of techniques used to protect the confidentiality of individuals in statistical data while allowing for the release of useful information.

If requested by the Office of Energy Jobs, the Contractor will facilitate DOE personnel access to the Contractor’s data system.

- ORGANIZATIONAL CONFLICT OF INTEREST

For any work related to this contract, the contractor warrants that to the best of its knowledge and belief and except for as otherwise disclosed, neither it nor its employees have any organizational conflict of interest.

The contractor agrees that if after award it discovers an organizational conflict of interest by it or its employees with respect to this contract, it shall make an immediate and full disclosure in writing to the Contracting Officer that shall include a description of the action that the contractor has taken or intends to take to eliminate or neutralize the conflict. The government may, however, terminate the contract for the convenience of the government if doing so would be in the best interests of the government.

In the event the contractor was aware of an organizational conflict of interest before the award of this contract and intentionally did not disclose the conflict to the Contracting Officer, the government may terminate the contract for default.

All provisions shall be included in all subcontracts and consulting agreements wherein the work to be performed is like the service provided by the prime contractor. The contractor shall include in such subcontracts and consulting agreements any necessary provisions to eliminate or neutralize conflicts of interest.

The data collected through this work may not be sold commercially. Micro-data and non-publicly released data will not be provided to or utilized by additional entities unless explicitly directed and approved by the Contracting Officer.

- QUALITY ASSURANCE PLAN

A Quality Assurance Surveillance Plan (QASP) will be developed by the Contractor and used to evaluate and monitor Contractor actions while implementing the requirements of this contract. The QASP is designed to provide an effective surveillance method of monitoring the Contractor's performance for each listed deliverable.

The COR will monitor services through random data checks, weekly status reports with the Contractor or other methods as deemed necessary in to ensure that performance is acceptable and quality services are being provided and in accordance with the PWS. The COR will determine the method in which weekly status reports should occur (e.g. via teleconference call, email, etc.). The Contractor's performance will be evaluated and documented at the completion of the Contract.

The Contractor, and not the Government, is responsible for management and quality control actions to meet the terms of the Contract. The Government is responsible for evaluating and monitoring the Contractor's actions to ensure applicable performance standards are achieved.

Unacceptable performance will be recorded, and the Contractor shall be required to correct the unacceptable condition. If the Contractor does not correct the unacceptable condition, the COR will notify the CO who will take appropriate administrative action for unacceptable performance.

| Task | Performance Standard | Maximum Allowable Degree of Deviation from Requirement | Method of Surveillance | Incentive/Disincentive |
| --- | --- | --- | --- | --- |
| Kick-off Meeting | Contractor shall attend a kick-off meeting within 5 days of award date, prior to commencement of work | 0% deviation | 100% Inspection | Incentive: If Contractor performs requirement in accordance with performance standard/AQL, favorable comments will be documented on Contractor’s Past Performance Disincentive: If Contractor does not perform requirement in accordance with performance standard/AQL, unfavorable comments will be documented |
| Contract deliverables in sections 5.1 through 5.7 of this PWS | Contractor shall complete all deliverables on time and in accordance with section 5.0 of the contract | 0% deviation | 100% Inspection | Incentive: If Contractor performs requirement in accordance with performance standard/AQL, favorable comments will be documented on Contractor’s Past Performance Disincentive: If Contractor does not perform requirement in accordance with performance standard/AQL, unfavorable comments will be documented |
| Weekly Status Report in accordance with section 5.1-Task 1 of this PWS | Contractor shall electronically submit a Weekly Status Report to the OP each Friday by 1700 (5:00pm ET). | 0% deviation | 100% Inspection | Incentive: If Contractor performs requirement in accordance with performance standard/AQL, favorable comments will be documented on Contractor’s Past Performance Disincentive: If Contractor does not perform requirement in accordance with performance standard/AQL, unfavorable comments will be documented |

- COMMUNICATION ACTIVITIES

The Contractor shall contact respondents for a variety of activities, such as pre-data collection communication, to resolve non-response and data quality issues. All such communication must be approved by DOE and will be documented.

- DATA USE AGREEMENTS

As directed by the Office of Energy Jobs, the Contractor shall format and share the public data prior to report publication with organizations subject to a Data Use Agreement (DUA), or Memorandum of Understanding (MOU), with DOE. The Contractor will coordinate with these organizations to share the survey with their membership, as outlined in the DUA.

- . QUALIFICATIONS

The Contractor’s team shall include an individual who shall serve as a Project Manager and be responsible for the performance of the work. The name of the Project Manager and an alternate who shall act for the Contractor when the Project Manager is absent shall be designated in writing to the CO. Qualifications for the Project Manager for the performance of the work follow:

Minimum Qualifications:

Education:

- Master’s Degree in a field of study directly applicable to the objectives of this contract (i.e. statistics, actuarial science, economics)

Experience:

- Demonstrated experience designing and implementing high quality U.S. establishment or firm data collection involving a large number of respondents across a wide variety of sectors, firm sizes, and geographies.

- Demonstrated experience in use, analysis, review and application of the North American Industry Classification System, Bureau of Labor Statistics Occupational classifications, and deep knowledge of the Quarterly Census on Employment and Wages, and other similar issuances, data, and labor statistical information.

- Demonstrated experience with quantitative survey-based employment studies. Demonstrated experience in federal and state energy or infrastructure related incentives and policy initiatives.

- Demonstrated experience in labor market analysis based on BLS data.

- Demonstrated experience leading and directing an interdisciplinary project similar in scope and complexity to that specified in this Contract, including the following activities: project planning; budgeting and cost monitoring; quality surveillance and problem resolution; on-schedule delivery of products and services and activity status reporting; and staff recruiting, hiring, and development. Such experience must include leading and directing multiple complex Task Orders simultaneously.

- Five years of project management or related experience on Federal Government contracts or similar contracts with a non-profit organization, foundation, trade association or the private sector.

- Excellent oral and written communications skills.

Additional Preferred Experience, Knowledge, Skills, and Abilities:

  - Extensive knowledge of the administrative policies of the Contractor and of the Federal Acquisitions Regulations and the Federal Government budgeting process.

  - Ability to work and effectively communicate with the wide range of expected participants on this Contract, including Contracting Officer, Contracting Officer’s Representative(s), Contracting Officer Technical Representative(s), technical managers, contractor and subcontractor task managers, staff, and others.

  - Ability to assemble and lead the full range of technical and administrative staff necessary to accomplish the full spectrum of work to be performed under this Contract.

  - Demonstrated ability to approach projects with a focus toward process improvement and introducing innovative solutions.

  - Sound technical experience in the following areas:

    - Survey development

    - Familiarity with calculating estimators accounting for survey design, unit and item non-response, and calibration

    - Collecting and analyzing survey non-response and item nonresponse in large scale surveys

    - Large-scale labor market statistical surveys, preferably energy based

    - Outreach, communication, and promotion of products and services.

    - Information technology, specifically database and software application development.

    - Demonstrated writing and communications skills

Other Contractor Employees performing work under this solicitation shall have the following minimum qualifications:

Education:

- Bachelor’s degree in business management or in a field of study directly applicable to the objectives of this contract.

Experience:

- Demonstrated experience implementing high quality U.S. establishment or firm data collection involving a large number of respondents across a wide variety of sectors, firm sizes, and geographies

- Demonstrated experience in use, analysis, review and application of the North American Industry Classification System, Bureau of Labor Statistics Occupational classifications, and deep knowledge of the Quarterly Census on Employment and Wages, and other similar issuances, data, and labor statistical information.

- Demonstrated experience managing projects similar in scope and complexity to those specified under this Contract, including the following activities: project planning; budgeting and cost monitoring; quality surveillance and problem resolution; on-schedule delivery of products and services and activity status reporting; and staff recruiting, hiring, and development.

- Three (3) years of project management experience on Federal Government contracts.

Additional Preferred Experience, Knowledge, Skills, and Abilities:

- Knowledge of the administrative policies of the Contractor and of the Federal Acquisitions Regulations and Federal Government budgeting processes.

- Demonstrated ability to effectively manage a diverse technical staff necessary to successfully accomplish projects of the scope and complexity to be awarded under this Contract. Also, the ability to work effectively with the various participants on this Contract; including Contracting Officer, Contracting Officer’s Representative(s), Contracting Officer Technical Representative(s), technical managers, contractor(s) and subcontractor task managers, staff, and others.

- Project management experience with an emphasis on processes improvement.

- Knowledge and experience in the areas of large-scale labor market statistical surveys, energy market analysis, modeling and forecasting, data integration, service and product dissemination, records management, and software application and database development.

- Excellent oral and written communications skills.

- Experience utilizing Census establishment micro-data.

- Experience with federal statistical Research Data Centers.

- Previous or current Special Sworn Status.

- Expertise in cognitive studies and/or social psychological impacts of survey design.

The Contractor shall identify an Information Security Officer. The Project Manager can perform in this role. The designated personnel must meet the following:

Experience:

- Contractor personnel performing this role shall have experience in the Federal IT environment. Personnel shall also have experience ensuring information security compliance standards relating to CIPSEA and federal regulations are implemented, documented, and monitored.

- Experience developing, implementing, and maintaining security policies and procedures for security of facilities, computer systems, telecommunications/Internet connectivity, data, personnel, and system administration.

- Experience enforcing security controls on and during the system design, system testing, system implementation, system maintenance, and system disposal.

- Experience documenting/correcting/mitigating all security defects and deficiencies. Experience ensuring subcontractors meet the security requirements described herein.

Identification of Contractor Employees: All Contractor personnel attending meetings and working in other situations where their contractor status is not obvious to third parties are required to identify themselves as such to avoid creating an impression in the minds of members of the public that they are Government officials.

- DATA PROCESSING AND DOCUMENTATION

The contractor shall prepare a dataset with a well-organized and thoroughly documented logical structure, along with metadata for each data element that consistently applies to a defined standard. Data files shall not be allowed to expire, be released without direct written consent by the CO, be overwritten, or otherwise destroyed.

Documentation shall be clear, comprehensive, and user-friendly providing all the necessary information to understand the USEER data collection methods, data editing, sampling, weighting, statistical estimation (including standard errors) and using the data.

All data files and related documentation associated with the design and execution of the contract (e.g., field test data, locating data, sampling data, weighting and imputation data, assessment score files, public-use data, and restricted-use data) shall be stored by the contractor in secure locations as detailed by the contractor in the data security plan. These files should be maintained in such a form as they can be easily provided to the OP on request.

- GOVERNMENT FURNISHED INFORMATION (GFI)

The Contractor will be granted rights to the Hyperlinked Version and PDFs for informational purposes.

- RECORDS MANAGEMENT OBLIGATIONS

A.  Applicability

This clause applies to all Contractors whose employees create, work with, or otherwise handle Federal records, as defined in Section B, regardless of the medium in which the record exists.

B.  Definitions

“Federal record” as defined in 44 U.S.C. § 3301, includes all recorded information, regardless of form or characteristics, made or received by a Federal agency under Federal law or in connection with the transaction of public business and preserved or appropriate for preservation by that agency or its legitimate successor as evidence of the organization, functions, policies, decisions, procedures, operations, or other activities of the United States Government or because of the informational value of data in them.

The term Federal record:

- Includes Department of Energy (DOE) records.

- Does not include personal materials.

- Applies to records created, received, or maintained by Contractors pursuant to their DOE contract.

- May include deliverables and documentation associated with deliverables.

C.  Requirements

- Contractor shall comply with all applicable records management laws and regulations, as well as National Archives and Records Administration (NARA) records policies, including but not limited to the Federal Records Act (44 U.S.C. chapters. 21, 29, 31, 33), NARA regulations at 36 CFR Chapter XII Subchapter B, and those policies associated with the safeguarding of records covered by the Privacy Act of 1974 (5 U.S.C. 552a). These policies include the preservation of all records, regardless of form or characteristics, mode of transmission, or state of completion.

- In accordance with 36 CFR 1222.32, all data created for Government use and delivered to, or falling under the legal control of, the Government are Federal records subject to the provisions of 44 U.S.C. chapters 21, 29, 31, and 33, the Freedom of Information Act (FOIA) (5 U.S.C. 552), as amended, and the Privacy Act of 1974 (5 U.S.C. 552a), as amended and must be managed and scheduled for disposition only as permitted by statute or regulation.

- In accordance with 36 CFR 1222.32, Contractor shall maintain all records created for Government use or created while performing the contract and/or delivered to, or under the legal control of the Government and must be managed in accordance with Federal law. Electronic records and associated metadata must be accompanied by sufficient technical documentation to permit understanding and use of the records and data.

- DOE and its contractors are responsible for preventing the alienation or unauthorized destruction of records, including all forms of mutilation. Records may not be removed from the legal custody of DOE or destroyed except for in accordance with the provisions of the agency records schedules and with the written concurrence of the Head of the Contracting Activity. Willful and unlawful destruction, damage or alienation of Federal records is subject to the fines and penalties imposed by 18 U.S.C. 2701. In the event of any unlawful or accidental removal, defacing, alteration, or destruction of records, Contractor must report to DOE. The agency must report promptly to NARA in accordance with 36 CFR 1230.

- The Contractor shall immediately notify the appropriate Contracting Officer upon discovery of any inadvertent or unauthorized disclosures of information, data, documentary materials, records or equipment. Disclosure of non-public information is limited to authorized personnel with need-to-know as described in the contract. The Contractor shall ensure that the appropriate personnel, administrative, technical, and physical safeguards are established to ensure the security and confidentiality of this information, data, documentary material, records and/or equipment are properly protected. The Contractor shall not remove material from Government facilities or systems, or facilities or systems operated or maintained on the Government’s behalf, without the express written permission of the Head of the Contracting Activity. When information, data, documentary material, records and/or equipment are no longer required, it shall be returned to DOE control or the Contractor must hold it until otherwise directed. Items returned to the Government shall be hand carried, mailed, emailed, or securely electronically transmitted to the Contracting Officer or address prescribed in the contract. Destruction of records is EXPRESSLY PROHIBITED unless in accordance with Paragraph (4).

- The Contractor is required to obtain the Contracting Officer's approval prior to engaging in any contractual relationship (sub-contractor) in support of this contract requiring the disclosure of information, documentary material and/or records generated under, or relating to, contracts. The Contractor (and any sub-contractor) is required to abide by Government and DOE guidance for protecting sensitive, proprietary information, classified, and controlled unclassified information.

- The Contractor shall only use Government IT equipment for purposes specifically tied to or authorized by the contract and in accordance with DOE policy.

- The Contractor shall not create or maintain any records containing any non-public DOE information that is not specifically tied to or authorized by the contract.

- The Contractor shall not retain, use, sell, or disseminate copies of any deliverable that contains information covered by the Privacy Act of 1974 or that which is generally protected from public disclosure by an exemption to the Freedom of Information Act.

- The DOE owns the rights to all data and records produced as part of this contract. All deliverables under the contract are the property of the U.S. Government for which DOE shall have unlimited rights to use, dispose of, or disclose such data contained therein as it determines to be in the public interest. Any Contractor rights in the data or deliverables must be identified as required by FAR 52.227-11 through FAR 52.227-20.

- Training. All Contractor employees assigned to this contract who create, work with, or otherwise handle records are required to take DOE provided records management training. The Contractor is responsible for confirming training has been completed according to agency policies, including initial training and any annual or refresher training.

D.  Flow down of requirements to subcontractors

- The Contractor shall incorporate the substance of this clause, its terms and requirements including this paragraph, in all subcontracts under this contract, and require written subcontractor acknowledgment of same.

- Violation by a subcontractor of any provision set forth in this clause will be attributed to the Contractor.