National Environmental Satellite, Data, and Information Service (NESDIS)

Office of Satellite and Product Operations (OSPO)

and

Office of Common Services (OCS)

NESDIS Consolidated Antenna and Ground System (NCAGSS)

Task Order 4- Antenna Ground System Sustainment

Performance Work Statement (PWS)

April 2026

Prepared by:

U.S. Department of Commerce

National Oceanic and Atmospheric Administration (NOAA)

National Environmental Satellite, Data, and Information Service (NESDIS)

Table of Contents

1.0 Overview	2

2.0 Scope	3

2.1 Place of Performance	5

2.2 References	6

3.0 Requirements	6

3.1 Project Management	6

3.1.1 Quality Assurance	9

3.2 Contract Transition	10

3.3 Sustainment	11

3.3.1 General	11

3.3.2 Antenna and Radio Frequency (RF) Equipment	15

3.3.2.1 Antenna Equipment	15

3.3.2.2 RF Equipment	15

3.3.2.3 Antenna and RF Equipment Systems Engineering	16

3.3.3 Technology Sustainment	17

3.3.3.1 Software Sustainment	18

3.3.3.2 System Integration, Installation, and Test	20

3.3.3.3 Hardware Sustainment	21

3.3.4 Ground System Requirements	22

3.3.4.1 Geostationary Earth Orbit (GEO) Ground Systems	22

3.3.4.2 Low Earth Orbit (LEO) Ground Systems	22

3.3.4.3 Space Weather Operations (SWO) Ground Systems	23

3.3.5 Cloud Transition	23

3.3.7 IT Security	24

3.3.8 Training	26

3.3.9 System Engineering	27

3.3.10 Risk Management	29

4.0 Contract Line Item Number (CLIN) 0001 - Study Tasks	29

5.0 Performance Requirements Summary	29

Appendix A: Initial Sustainment Antenna List	31

Appendix B: Sustainment Deliverables	32

Appendix C: Cost Exercises	41

Appendix D: Acronym Listing	43

# 1.0 Overview

The purpose of the Statement of Work (SOW) for the base Indefinite Delivery, Indefinite Quantity (IDIQ) is to describe the services the Contractor(s) shall provide to support the NESDIS Antenna as a Service (NAaaS) program. These services are essential to provide NOAA/NESDIS with the flexibility and responsiveness required to support the scope, complexity, and evolution of how NOAA/NESDIS acquires, manages, and operates antenna services. A Program Integrator (PI) Task Order (TO) will be awarded to one vendor and multiple TOs with specific service requirements (i.e., operations, maintenance, and sustainment) will be awarded within the scope of the IDIQ over the period of performance. The PI will ensure integration across all task orders supporting the NAaaS program.

The Antenna Ground System Sustainment TO4 is a sample sustainment TO that details Contractor(s) implementation of sustainment activities per the NESDIS Consolidated Antenna and Ground Systems Services (NCAGSS) (IDIQ SOW) Sections 3.1 (General Requirements) and 3.5 (Sustainment). TO4 covers the managed planning, transition/migration, and implementation activities by the Contractor(s) of legacy and new antenna ground systems from incumbent Contractor(s). Multiple antenna specific sustainment TOs will be awarded over the contract period of performance. This TO4 supports:

- Technology refresh (upgrades) to designated antenna ground systems and subsystems

- Technology refresh (upgrades) of infrastructure (e.g. operational tools) applicable to the NAaaS antenna ground systems and subsystems

- Development and implementation of new (next generation) antenna ground system capabilities

## 2.0 Scope

The NAaaS objective for using sustainment conducted under this TO is to implement a systematic effort to streamline and optimize the NAaaS antenna ground system enterprise. Sustainment activities include development leveraging technology advancements and improvements to extend the system life to meet program-life requirements.

This Antenna Ground System Sustainment TO addresses scope for technology related sustainment activities and associated deliverables. Sustainment activities include larger scale and pre-planned activities to develop, modernize, or enhance the applicable legacy antenna ground systems and subsystems. The Contractor(s) should demonstrate an ongoing commitment to innovative sustainment solutions, where applicable, that promote NESDIS enterprise architectural goals and streamline services, while minimizing associated costs and risks.

Appendix A, in this TO4, is a subset of the list in the IDIQ SOW Appendix A, which lists the Antenna Ground Systems the Office of Satellite Product Operations (OSPO) currently operates, maintains, and/or sustains. The Office of Common Services (OCS) will manage the development and acquisition of antenna services for the NAaaS program. Appendix B contains the Sustainment deliverables. Appendix C contains three sample sustainment use cases for the Contractor(s) to estimate and provide with the proposal submission. Appendix D contains the acronyms and meaning.

The Appendix A in the base IDIQ SOW contains all the current antenna ground systems that may need sustainment under this contract, however the scope may include other antennas at a future time. This sample TO pertains to general antenna ground systems sustainment requirements used to establish a pool of sustainment Contractor(s). Once the pool is developed separate antenna specific sustainment TOs will be issued based on Government priorities, Contractor(s) capabilities, and funding constraints. Sustainment TOs include designated antenna ground systems, infrastructures, upgrades and new antenna ground systems and components.

A significant focus of the NAaaS Program is the utilization of commercially available services wherever possible. The Contractor(s) shall consider as part of technology refresh analysis the utilization of commercial antenna services. Included in this analysis will be a technology evaluation, a cost benefit assessment, as well as a risk assessment.

Sustainment activities for this TO include:

- Coordinate sustainment activities with the NAaaS Program Integrator (PI) using meeting forums, reports and an active integrated approach to keeping sustainment information in a PI dashboard.

- Provide project management resources and commensurate technical subject matter experts (SMEs) to effectively manage, coordinate, and implement all sustainment activities and provide regular reporting of technical, schedule, and financial status to the Government through various means including meetings, written correspondence, and via a list of deliverables.

- Identify NAaaS antenna ground system and subsystems items for sustainment support/upgrade.

- Perform an analysis of alternatives considering build or buy options and opportunities.

- Prepare and document a plan to develop, integrate, test and implement all sustainment functional capability (hardware and software), or new sub-component(s) of existing systems following rigorous documented procedures.

- Develop detailed cost estimates for all elements of the identified sustainment solutions.

- Perform requirements analysis and design (as required) and conduct the proper reviews for all sustainment solutions (e.g. Preliminary Design Review (PDR)/ Critical Design Review (CDR), action items, etc.) following the review process.

- Review all hardware on site for inclusion in sustainment planning and incorporated into the Integrated Sustainment Plan authored by the PI.

- Procure all hardware equipment and software to implement the sustainment solutions.

- Deliver software compliant with NOAA/NESDIS standards and approved Contractor(s) standards.

- Working with the Government, perform all integration and testing and modify and/or port existing software to new hardware platforms that interface with existing operational systems.

- Conduct all required hardware/software reviews for sustainment solutions including requirements review, interfaces, software code, testing for planned software release, and capability verification (factory acceptance and site acceptance testing, pre-ship review, as required) and (if any) fixes to ensure all the capabilities function as intended.

- Deliver a Transition to Operations package [D-TO4-041] for new sustainment solutions.

- Support all sustainment planning, integration and test activities to ensure the requirements, configuration, test, and verification of all capabilities are approved for implementation.

- Provide all training for the sustainment solutions implemented under the TO.

- Conduct product transition sustainment support on antenna ground system components that have migrated to the cloud environment.

- Investigate, evaluate and recommend new antenna ground system capabilities aligned with enterprise objectives to include adoption of pertinent commercial capabilities.

- Align cybersecurity practices and compliance with Department of Commerce IT Security laws, regulations and standards to protect sensitive data and information systems from cyber threats.

- Implement and demonstrate IT security controls that ensure data confidentiality, integrity and availability thereby reducing legal, financial and reputational risks.

Develop an inventory of parts to be included in the TO4 sample Sustainment Plan and the NAaaS Integrated Sustainment Plan authored by the PI. The inventory shall include details of specific antenna ground system assets to be refreshed, plans for new antenna ground system and antenna development, and system hardware and software components within three (3) years of obsolescence. Individual system inventories, drawings, descriptions, interfaces and recommendations are available in the NCGASS Acquisition Document Library.

The PI will be developing a Release Backlog detailing future modifications, enhancements, and features and the priority for implementing sustainment activities within funding constraints, government priorities, discretion and/or timing. Sustainment Contractor(s) are expected to coordinate sustainment activities with the Government and NAaaS PI and keep the Release Backlog up to date.

### 2.1 Place of Performance

The National Environmental Satellite, Data, and Information Service (NESDIS) Ground Enterprise (NGE) primary work locations are listed below but additional locations/sites such as CONUS and OCONUS may be added.

- NOAA Satellite Operations Facility (NSOF) located in Suitland, Maryland

- The NESDIS Consolidated Backup Unit (CBU) located in Fairmont, West Virginia

- NESDIS Command and Data Acquisition (CDA) Station located in Wallops, Virginia

- NESDIS Command and Data Acquisition (CDA) Station located in Fairbanks, Alaska

- McMurdo Station located on Ross Island, Antarctica

- NASA White Sands Complex (WSGT/WSC) Les Cruces, New Mexico

### 2.2 References

The most current edition of the following reference documents is included in the NCGASS Acquisition Document Library and apply to this TO:

- OSPO System Descriptions

- OSPO System Inventories

- OCS Change and Configuration Management Process

- OCS Systems Engineering Process Document, OCS 5820.01A October 3, 2016, Version 0.5

- Satellite Products and Services Review Board Process

- NESDIS Ground Enterprise (NGE) Technical Architecture (TA) User’s Guide, Version 2.0, 03 April 2019

- NESDIS Antenna RF Handbook (Redacted)

- NESDIS IT Systems Component Inventory Management Policy and Procedures

- OCS Systems Engineering Process Document, OCS 5820.01A October 3, 2016, Version 0.5

- NESDIS Ground Enterprise (NGE) Technical Architecture (TA) User’s Guide, Version 2.0, 03 April 2019

- NESDIS Antenna RF Handbook (Redacted)

- OSPO Configuration Management Plan

- NESDIS Antenna-as-a-Service (NAaaS) Requirements Document

## 3.0 Requirements

In addition to the requirements in the IDIQ SOW Section 3.1 (General Requirements) and 3.5 (Sustainment) the following requirements are specific to this TO.

## 3.1 Project Management

Project management for TO4 is defined in the IDIQ SOW Section 3.1.1 (Program/Project Management). In addition, the following project management requirements apply to TO4 for Antenna Ground System Sustainment:

PWS-TO4-PM01: The Contractor(s) shall ensure that sustainment projects comply within the Government constraints in terms of cost, schedule, and technical scope.

PWS-TO4-PM02: The Contractor(s) shall manage all sustainment activities to ensure work is completed in a timely manner. This includes documenting all work performed, staff management communications (e.g., ensuring correct skill mix assignments, correct understanding of risks, etc.) per the Sustainment Deliverables in Appendix B.

PWS-TO4-PM03: Achieving the desired goals for the contract will require joint coordination between the Contractor(s), Government team, and NAaaS PI. The Government will provide a set of priorities, as part of the NCAGSS transition. The Contractor(s) shall coordinate with the NAaaS PI Release Backlog activities detailing sustainment future modifications, enhancements, and features. All planned implementation of priorities from the Release Backlog shall be reflected in the Antenna Systems Sustainment Project Plan and the status of implementations shall be reported monthly.

PWS-TO4-PM04: The Contractor(s) shall generate Contractor Metric Performance Reports [D-TO4-008] on items in the Performance Requirements Summary (PRS) table in Section 5 of this TO. The Contractor Metric Performance Report shall be delivered to the Government and PI as part of the weekly status report and aggregated in a monthly report.

- Hardware and software sustainment

- Documentation

- Performance

- Product or service evaluations

- Verification and validation results

- Incidents and problems from CCR administration.

PWS-TO4-PM05: The Contractor(s) shall deliver a Monthly Progress Report [D-TO4-029] and provide it to the PI. The report shall include:

- Executive summary

- Project details

- Project scope and adjustments

- Progress updates and milestones

- Review of key performance indicators

- Risk and opportunity management

- Budget and financial performance

- Stakeholder communications

- Next steps and action items

- Ground systems and antenna anomalies, incidents, and discrepancies as defined in the OSPO Incident Report Plan

PWS-TO4-PM06: The Contractor(s) shall provide, individually to the contracting officer, a Contract Financial Report [D-TO4-030] from sustainment task orders  toinclude spend plans, invoicing, fund status, engineering assessments (EAs) and travel management. The Contractor(s) may adjust cost performance data from prior months only for a) the correction of administrative errors, b) routine accounting adjustments, or c) customer-directed changes. All such prior months’ adjustments shall be implemented in the current month and addressed in that month’s Consolidated Contract Financial Report by the PI.

PWS-TO4-PM07: The Contractor(s) shall provide an Associate Contractor Agreement (ACA) [D-TO4-031] for any portion of the NCAGSS contract requiring joint participation in the NAaaS related activities. The agreements should include the basis for sharing information, data, technical knowledge, expertise, schedules, and risks in accordance with Section H of the NCAGSS IDIQ Contract. The Sustainment ACAs shall be maintained by the PI.

PWS-TO4-PM08: The Contractor(s) shall provide an antenna ground system Sustainment Contractor Spend Plan [D-TO4-032] as detailed in the IDIQ SOW Section 3.1 k (General Requirements).

PWS-TO4-PM09: The Contractor(s) shall notify the Government of conduct project kickoff meetings reporting on progress, punch lists, schedule, sustainment activities, contract transition

and provide meeting notes within 5 business days.

PWS-TO4-PM10: The Contractor(s) shall provide, report, and track contract performance metrics on items detailed in the Contractor(s)’s Service Level Agreement (SLA) as part of the monthly program management review conducted by the PI. Metrics shall be mutually agreed at the start of the contract, and may include modified or new metrics, as required, to accurately reflect contract performance.

PWS-TO4-PM11: The Contractor(s) shall conduct a monthly NAaaS Contract Review to review sustainment TO contracts planned or in work. The Contract Review shall be coordinated with the PI and involves analyzing the contract's language, assessing its enforceability, and confirming that it aligns with the NAaaS project objectives.

PWS-TO4-PM12: The Contractor(s) shall submit Class I and II changes to the Government for approval prior to implementation of change in accordance with the OSPO CM Plan.

PWS-TO4-PM13:. The Contractor(s) shall conduct studies and analyses on topics identified by the Government throughout the period of performance. The Contractor(s) shall document the results of the study tasks through a NAaaS Study Report [D-TO4-046).

PWS-TO4-PM14: The Contractor(s) shall conduct a project Kickoff meeting [D-TO4-047] within 10 days of the NCAGSS award. The project Kickoff meeting shall be conducted in person at the NOAA-Satellite-Operations-Facility (NSOF) and facilitate virtual participation

PWS-TO4-PM15: The Contractor(s) shall coordinate with the Government meetings with working groups, product teams, and vendor partners.

PWS-TO4-PM16: The Contractor(s) shall participate in Government required meetings or working groups as directed by the Government.

PWS-TO4-PM17: The Contractor shall conduct engineering peer reviews (EPR) on technical topics with participation with the Government and PI.

- PWS-TO4-PM18: The Contractor(s) shall adhere to the NAaaS Safety Program as developed by the PI in accordance with the NOAA Safety and Environmental Compliance (SECO). Information can be found at https://sites.google.com/noaa.gov/occupational-safety-health
/home?pli=1

PWS-TO4-PM19: The Contractor(s) shall conduct a Project Management Review [D-TO4-048] mid-month on a monthly basis that provides status of technical, schedule and cost performance, risks and issues to the Government. The PMR package shall be provided to the Government and PI 10 days prior to the review.

PWS-TO4-PM20: The Contractor(s) shall coordinate with the PI to ensure requirements from all NAaaS performance work statements, functional and performance specifications, contract deliverables, and any applicable documentation are flowed down to subcontractors performing work under each task order.

PWS-TO4-PM21: The Contractor(s) shall develop and deliver a NAaaS Sustainment Project Management Plan (PMP) [D-TO4-051] and coordinate with the PI.

### 3.1.1 Quality Assurance

PWS-TO4-QA01: The Contractor(s) shall provide and follow their project Quality Assurance Plan (QAP) [D-TO4-035] and project Quality Assurance Standard Operating Procedures (QASP) [D-TO4-036] when performing activities detailed in this TO. The QASP is coordinated with the PI, and explicitly describes Contractor processes and measures for subcontractor/ vendor performance and deliverables

PWS-TO4-QA02: The Contractor(s) shall plan and implement technical quality assurance in the project that encompasses hardware, software, and processes.

PWS-TO4-QA03: The Contractor(s) shall provide Quality Assurance Standard Operating Procedures (SOP) [D-TO4-037] at the start of the contract and update it annually or as requested by the CO.

PWS-TO4-QA04: The Contractor(s) shall provide, report, and track contract performance metrics as part of the monthly program management review conducted by the PI. Metrics shall be mutually agreed at the start of the contract, and may include modified or new metrics, as required, to accurately reflect contract performance.

PWS-TO4-QA05: The Contractor(s) shall participate in the Government’s process improvement activities. The Government will provide a SharePoint-based Action Information Management System (AIMS) or like system, for organizing its data calls, as well as Government approved tools such as JIRA for the Integrated Master Schedule (IMS).

PWS-TO4-QA06: The Contractor(s) shall support organizational data call requests.

PWS-TO4-QA07: The Contractor(s) shall follow NESDIS processes for sustainment activities closure to include removal of all items, to include equipment cabling after a sustainment refresh, upgrade or new development has been completed.

PWS-TO4-QA08: The Contractor(s) shall decommission, excess, or dispose of NAaaS ground system accountable hardware following refresh in accordance with the NOAA Property Manager and in coordination with the PI.

- PWS-TO4-QA09: The Contractor(s) shall maintain reports and other data electronically on a Government system such a JIRA, or similar tool, that is interfaced with the Program Integrator dashboard to ensure collaboration and coordination of activities.

## 3.2 Contract Transition

Transition related requirements for TO4 activities are specified and to be managed by the Contractor(s) under the IDIQ SOW Section 3.2.8 and Program Integrator TO1.

PWS-TO4-CT01: The Contractor(s) shall provide a Contract Phase-In Transition Plan [D-TO4-002] with a checklist for the PI of all required tasks and activities to complete the transition successfully. The initial Phase-in Transition Plan shall be submitted with the proposal response, and a final after contract award. Transition plans shall include:

- Proposed Contractor Staffing and Government support staffing levels.

- Staffing, including Government site access, as appropriate.

- Training and general knowledge transfer.

- Process for completion of in-progress Work Requests under development by the incumbent contractor.

- Transfer of operations, inventory, and assets.

- Transfer of accounts, passwords, and permissions.

- Access to Government Configuration Management systems.

- Transfer and establishment of a controlled Factory baseline representing the deployed system

- Configuration control, administration, software scripts, documentation, procedures, and checklists.

- Establishment, installation, and checkout of a Contractor Operational Support Location (OSL), Factory Development Environment (FDE), and Factory Test Environment (FTE).

- Confirmation of the ability of the Contractor OSL to interface with the Government system at the deployed sites.

- Confirmation of the ability of the FDE and FTE to test new or modified software with the return of test data back to NAaaS.

- Management of hardware and software licenses, warranty and recommended spares activity for Contractor managed property.

- Monitoring of sustainment activities to include IT security activities

  - List of existing sustainment efforts addressed (completed or in work) in NCAGSS contract

  - List of sustainment efforts addressed (completed or in work) by legacy contracts

  - List of new sustainment efforts addressed in NCAGSS contract

PWS-TO4-CT02: The Contractor(s) shall deliver a preliminary Contract Phase-Out Transition Plan [D-TO4-003] with a checklist and final plan submitted to Government and PI for approval one year prior to the end of the contract to the PMO.

## 3.3 Sustainment

### 3.3.1 General

PWS-TO4-GS01: The Contractor(s) shall provide a general Sustainment Plan [D-TO4-033] where an initial draft is submitted with the proposal response and a baseline of the individual plans comprising it shall be delivered after contract award. The Contractor(s) shall provide quarterly updates to the individual deliverables that comprise the general Sustainment Plan. The general Sustainment Plans will be incorporated into the TO1, PI Integrated Sustainment Plan. The general Sustainment Plan shall contain the following deliverables detailed below:

- Sustainment Project Milestone Plan [PWS-TO4-GS04]

- Software Sustainment Plan [PWS-T04-SS01]

- Hardware Sustainment Plan [PWS-TO4-HW01]

- Obsolescence Management Plan [PWS-TO4-SER02]

PWS-TO4-GS02: In collaboration with the PI, the Contractor(s) shall document and deliver a detailed Antenna Systems Sustainment Project Plan [D-TO4-001] that contains a project plan for each of the antenna ground systems for Government approval. This plan shall include all items for sustainment, proposed hardware/software sustainment solution by subsystem and location, tasks required to implement, and task schedule. With collaboration from the PI, implementation tasks for the Antenna Systems Sustainment Project Plan shall include the following:

- Complete an initial draft submitted with the proposal response, and a final document delivered after contract award as part of the general Sustainment Plan.

- Hardware/firmware sustainment solution (or consolidation approach; build vs. buy).

- Approach for all software modifications (Commercial Off the Shelf (COTS) and custom code, as applicable).

- List of documentation impacted (e.g. requirements documentation, support or license agreements, design documentation, testing documentation, updated system baseline documents, or configuration documents, etc.), generated or modified for configuration management purposes.

- Develop test procedures and seek Government approval within 30 days of testing.

- Milestones planned for sustainment activities (key reviews, technical reviews supporting code, requirements verification, transition to operations, etc.) as detailed in the Integrated Sustainment Schedule (ISS).

- Testing approach applicable for each sustainment solution.

- Evaluation of proposed sustainment activities covering planned term after sustainment solutions are implemented (support agreement terms for hardware maintenance and software license, and recommended spares).

- Travel planned to support sustainment activities.

PWS-TO4-GS03: The Contractor(s) shall receive sustainment requirements exclusively from the NAaaS program. Government points of contacts may include international partners. The Contractor(s) shall establish a Sustainment Stakeholder Contact List [D-TO4-004] as part of the general Sustainment Plan where an initial draft is submitted with the proposal response in the general Sustainment Plan, and a final delivered after contract award.

PWS-TO4-GS04: The Contractor(s) shall create and maintain a three to five-year Sustainment Project Milestone Plan (PMP) [D-TO4-016] for planned work. The initial draft is submitted with the proposal response and a final delivered after contract award. The PMP is a separate deliverable from the TO1 Program Integrator, Integrated Master Schedule (IMS) but critical sustainment milestones from the PMP shall be integrated into the TO1 IMS. Factors to be considered for the PMP are those that impact system availability to include critical weather days, launch and post-launch checkout, IT-related “hard and soft” system freezes, and COOP exercises.

The ISS shall encompass the five-year period of performance for TO4. Sustainment milestones shall include (but not be limited to) contract deliverables, engineering assessment dates, sustainment solution development and implementation key dates, technology refresh dates, license and maintenance agreement renewals, software releases, testing dates or periods, key technical review dates (e.g. pre-ship, factory acceptance, site acceptance, Operational Readiness Review (ORR)’s etc.).

The Contractor(s) shall provide an Integrated Sustainment Schedule [D-T04-005] per month to the Government Project Manager (PM) and Contracting Officer’s Representative (COR), and PI, or as requested. Critical milestone dates should reflect key deliverables, key decision points, system readiness or availability. All milestones having external dependencies shall reflect a readiness date relative to the actual completion of the external dependency.

PWS-TO4-GS05: The Contractor(s) shall conduct a Sustainment Inventory Baseline [D-TO4-006] of sustainment assets for each of the antennas ground systems detailed in Appendix A of this TO. This information shall be documented in the general Sustainment Plan where an initial draft is submitted with the proposal response and a final delivered after contract award. The Contractor(s) shall document the schedule and status of the technology refresh for each of the hardware, software and firmware components of the ground systems to the end of the sustainment TO. The Contractor shall coordinate with the PI to support the program NAaaS Asset Inventory Report.

PWS-TO4-GS06: The Contractor(s) shall prepare and deliver documentation and services listed in Appendix B, Deliverables List for TO4, as scheduled.

PWS-TO4-GS07: The Contractor(s) shall plan and execute sustainment transition activities detailed in Section 3.5 of the IDIQ SOW.

PWS-TO4-GS08: The Contractor(s) shall coordinate migration of sustainment requirements for ground systems with existing contracts.

PWS-TO4-GS09: The Contractor(s) shall provide sustainment and sustainment planning of ground station antennas and support antenna equipment at the primary and work locations/sites detailed in Section 2.1 of this TO.

PWS-TO4-GS10: The Contractor(s) shall plan for, and sustain software as needed at all locations/sites identified in Section 2.1 of this TO.

PWS-TO4-GS11: The Contractor(s) shall plan for, and sustain hardware as needed at all locations/sites identified in Section 2.1 of this TO.

PWS-TO4-GS12: The Contractor(s) shall coordinate with Government facility owners using the OCS Change and Configuration Management Process before implementation of new hardware, software or firmware, networks, antennas and RF equipment.

PWS-TO4-GS13: The Contractor(s) shall provide management support for the sustainment of continuity of operations (COOP) assets of this TO.

PWS-TO4-GS14: The Contractor(s) shall meet or exceed existing Ground System performance standards and requirements for all sustainment activities conducted under TO4, Section 4.0.

PWS-TO4-GS15: The Contractor(s) shall identify, plan for, and execute a refresh of each asset itemized in the Sustainment Inventory Baseline, in accordance with the refresh timeline as established in the general Sustainment Plan.

PWS-TO4-GS16: The Contractor(s) shall employ deployment strategies that will minimize the risk of interference, loss of downtime (to include critical weather days), or compromise system operations while performing sustainment activities.

PWS-TO4-GS17: The Contractor(s) shall be compliant with IT security requirements and follow configuration management (CM) practices to sustain building out any additions with the mandated security controls in place including but not limited to hardening the system to required standards, applying anti-malware, closing unused ports, and applying the principles of least access.

PWS-TO4-GS18: The Contractor(s) shall obtain approval from the PI, for changes and implementation through an approved NESDIS CM process. NAaaS antenna ground systems that have been changed shall be scanned for vulnerabilities and corrected prior to connecting back into an operational network. Input to required IT security documentation, such as changes to any security documentation, shall be provided by the Contractor(s). If the change results in a recertification of the system, then the Contractor(s) shall provide supporting documentation.

PWS-TO4-GS19: The Contractor(s) shall provide a weekly and monthly sustainment status report and include the following for sustainment related activities:

- Sustainment Weekly Status Report [D-TO4-034] describes activities and accomplishments, planned activities, technical issues, risk register, sustainment integrated schedule, resource planning and action items.

- Sustainment Monthly Status Report [D-TO4-038] shall provide one report per month that is an aggregate of the weekly reports to provide management level security review of status and trending of near-term activities, issues, and risks. The monthly report shall also contain project plan schedule, work performed, status of schedule (indicating completion percentage for each item), sustainment activities status (estimates, percent complete broken out by function level modules/components), detailed financial data, risks (changes/updates to the risk registers, and updated milestones), staffing levels, performance metrics, status of IT security compliance, action items, and issues for NOAA attention. All milestone dates should reflect deliverables and key decision points.

- The Contractor(s) shall conduct monthly and weekly sustainment status report meetings. The Contractor(s) shall also provide meeting support to include meeting minutes and agendas [D-TO4-039].

PWS-TO4-GS20: The Contractor(s) shall conduct a Technology Refresh Analysis [D-TO4-007] as needed, to include an analysis of commercial services options, technology evaluation, cost benefit assessment and a risk assessment.

PWS-TO4-GS21: The Contractor(s) shall provide a Transition to Operations package  to the Government and PI when a sustainment development activity is complete. The package shall include:

- As Built vendor information

- Recommended maintenance procedures

- Operations manual

- Training documentation

- Part inventory

- Preventative Maintenance Instructions

- Recommended Maintenance Procedures

PWS-TO4-GS22: Appendix C contains three sample sustainment use cases representing an antenna upgrade, build out, and decommission; transitioning to a service based Software Defined Radio (SDR), and assessing the feasibility of exploring phased array antenna technology. For all use cases, the Contractor(s) shall provide, with the proposal submission, a fully burdened cost estimate [D-TO4-043] for all labor, material, and other direct costs. Please list all assumptions in these efforts.

PWS-TO4-GS23: The Contractor shall recommend or use a Government defined requirements management system to define, implement and maintain NAaaS requirements with PI and Government coordination.

PWS-TO4-GS24: The Contractor shall ensure User and Design manuals are kept up to date.

### 3.3.2 Antenna and Radio Frequency (RF) Equipment

The general Sustainment Plan shall include engineering sustainment processes specific to antennas and radio frequency equipment for ground stations and sites.

#### 3.3.2.1 Antenna Equipment

PWS-TO4-AN01: The Contractor(s) shall conduct all sustainment activities necessary for antennas identified in this TO Appendix A.

PWS-TO4-AN02: The Contractor(s) shall execute the construction of any new antenna assets and related RF ground system support equipment as required by the Government and tied to the general Sustainment Plan.

PWS-TO4-AN03: The Contractor(s) shall provide sustainment support of obsolete antenna systems, or subsystems and/or components by reverse engineering, or other engineering methods. Equivalent Commercial Off-the-Shelf (COTS) products or prototyping the latest technology for replacement shall be specified. This task includes development or procurement of prototype units, testing and integration.

PWS-TO4-AN03: The Contractor(s) shall conduct removal and safe disposal of identified antenna assets in compliance with all pertinent Government regulations, guidelines and safety standards.

PWS-TO4-AN04: The Contractor(s) shall conduct regular antenna calibration intervals verifying an antenna's performance and accurately measuring its signal characteristics. The calibration intervals shall occur at a minimum every [12 or 18] months.

#### 3.3.2.2 RF Equipment

PWS-T04-RF01: The Contractor(s) shall provide all system engineering and technical support to sustainment activities for RF equipment. This includes integration and upgrade of High-Power Amplifiers (HPAs), Low Noise Amplifiers (LNAs), Low Noise Block Down Convertors (LNBs), Antenna Control Systems (ACS), RF fiber optic transceivers, RF components, receivers, command modulators, antenna-tracking receivers, antenna mechanical and drive components and any other associated antenna equipment as directed by the Government.

PWS-TO4-RF02: The Contractor(s) shall provide support to test and calibrate all intended RF equipment for sustainment prior to being integrated into the operational system. The Contractor(s) shall make the types of measurements and calibrations pertinent to the equipment installed. Typical measurements and calibration include, but are not limited to frequency, attenuation, gain, bandwidth, noise figure, and antenna noise temperature. Test and Calibration Reports [D-TO4-040] of all testing and calibration conducted shall be delivered to the Government no more than two weeks after acceptance by the Government.

PWS-T03-RF03: The Contractor(s) shall verify that electromagnetic emissions from any newly installed RF equipment for the purposes of sustainment conform to all applicable National Telecommunication and Information Administration (NTIA)/ Federal Communication Commission (FCC) and the International Telecommunication Union (ITU) regulations.

#### 3.3.2.3 Antenna and RF Equipment Systems Engineering

PWS-TO4-SER01: The Contractor(s) shall detail in the general Sustainment Plan all prioritized support for engineering expertise, labor, materials, documentation services, and calibration required for the installation, test, and checkout (ITCO) in accordance with the OSPO CM Plan of new or replacement equipment, modification, major repair, and/or overhaul of existing equipment, alteration and construction to accomplish the specified technical refresh sustainment objectives. The Contractor(s) shall deliver to the Government test deliverables 30 days before the tests.

PWS-TO4-SER02: The Contractor(s) shall work with the Government and PI to manage, monitor and forecast hardware and software obsolescence and document the approach in an Obsolescence Management Plan [D-TO4-023]. The Contractor(s) shall:

- Develop a Computerized Maintenance Management System (CMMS) or similar tool, approved by the Government, to manage obsolescence software or to manage End-of-Life cycles of other physical assets.

- Maintain an active list of the hardware and software deployed in the NAaaS program with associated end-of-support (EOS) and end-of-life (EOL) dates.

- Notify the Government when vendors provide notification of changes in EOS and EOL dates.

- Present to the Government and PI a quarterly summary of the NAaaS assets obsolescence, including the status of upcoming EOS and EOL dates, and recommendations for a path forward on each item with an EOS date within the next three (3) years. Recommended options should include acceptance with risk mitigation, replacement, or retirement.

- Review obsolescence items by priority with the Government and develop and deploy replacement components, as directed by the Government.

- In coordination with the Government, identify obsolescence and technology refresh trades as a part of the Common Ground System (CGS) system recapitalization and refresh.

- Assess each system component for technology refresh necessity on a case-by-case basis.

- The general Sustainment Plans will be incorporated into the TO1, PI Integrated Sustainment Plan.

PWS-TO4-SER03: The Contractor(s) shall conduct antenna design, RF link analysis, system architecture revision activities, including detailed block diagrams, interface specifications, cabling diagrams, component recommendations, and obtaining vendor pricing necessary to support sustainment requirements.

PWS-TO4-SER04: The Contractor(s) shall perform analysis and assessment of all RF Ground System network infrastructure, provide network optimization recommendations, and proposed solutions for implementation that improve network data routing, data transfer efficiency, data integrity, and delivery assurance via NOAA N-Wave-to-SOCC, ESPC and NOAA data centers (i.e., data compression, network accelerator, data transfer assurance algorithm, or protocol etc.).

PWS-TO4-SER05: The Contractor(s) shall support the government by performing trade studies, technical feasibility of proposed solutions based on reliability and past performance of similar development tasks and/or delivered products. Additional tasks may be assigned as new requirements are defined and funded.

PWS-TO4-SER06: The Contractor(s) shall perform RF analysis and feasibility studies as required by the Government necessary to define upgrade requirements for antennas supporting future missions and new capabilities such as phased arrays and optical link technologies.

PWS-TO4-SER07: The Government may identify antenna assets for removal predicated on mission EOL, antenna utilization, study findings, obsolescence, or other relevant factors.

PWS-TO4-SER08: The Contractor(s) shall perform risk analysis and mitigation planning on antenna subsystems.

PWS-TO4-SER09: The Contractor(s) shall obtain all approvals in accordance with local, state, federal, international laws and regulations, including those affecting local labor mandates, any tariffs imposed on materials and labor. The Contractor(s) shall deliver regulatory reports to include references, regulations, and approval.

PWS-TO4-SER10: The Contractor(s) shall identify, prepare, and obtain permission from the appropriate regulatory bodies for any required on-site construction permits in fulfillment of sustainment requirements.

PWS-TO4-SER11: All RF sustainment equipment installations must comply with applicable international, national, state, and local codes and ordinances. The Contractor(s) shall advise the Government, on a site-by-site basis, of the specific codes to which compliance is proposed and must be responsible for obtaining all required approval from responsible Government organizations. The Contractor(s) shall take all necessary actions to ensure compliance and approval. This includes obtaining and maintaining any NTIA, FCC, or other governmental, or international authorizations for the operation of any communications network installed to support a sustainment solution.

### 3.3.3 Technology Sustainment

Sustainment activities include the modernization (or refreshing) of existing hardware and software and adding new capabilities to meet Government requirements. Activities include support for software and hardware sustainment solutions depending on the scope and magnitude of the need. Sustainment activities may also encompass agile development of cloud-based software.

#### 3.3.3.1 Software Sustainment

PWS-TO4-SS01: The Contractor(s) shall deliver a Software Sustainment Plan [D-TO4-009] where the initial draft is submitted with the proposal response in the general Sustainment Plan, and a final delivered after contract award. The Software Sustainment plan shall detail software support of the following including existing source code modifications. The Contractor(s) shall identify source code and/or database changes, ensure a clean software compile, and fully document the changes per the configuration management processes detailed in the OCS Change and Configuration Management Process and OCS Systems Engineering Process Document, OCS 5820.01A October 3, 2016, Version 0.5.

Test and baseline of all changes shall be in accordance with a Government approved source code control sustainment standard operating procedure and approved by the PI. Sustainment test plans and modified source code [D-TO4-013] shall be delivered as required and reviewed by the Government. Testing shall be in accordance with an approved software development guide prior to submitting modified code for integration and test. The Government will perform an ORR before the Contractor(s) is allowed to implement any modified code in the operations environment. The Contractor(s) shall submit Configuration Change Requests (CCRs) [D-TO4-014] with all required documentation for all changes made during sustainment of any software and coordinate with the PI. The Contractor(s) shall document operational impacts for any CCR that affects operations and immediately report these impacts to the Project Manager and COR.

PWS-TO4-SS02: The Contractor(s) shall provide weekly updates for open CCRs and report progress of CCR closure in the Configuration Change Requests Report under [D-TO4-015). The Contractor(s) shall perform all required activities to close CCRs per the agreed schedule and elevate or expedite any activities required to maintain the CCR closure schedule. Ninety percent (90%) of CCRs shall have no open problem reports (PRs) at an ORR; any open PRs shall have an approved resolution plan.

PWS-TO4-SS03: The Contractor(s) shall deliver a Software Sustainment Life-Cycle Plan [D-TO4-025] supporting software development and test to be delivered after award as part of the Software Sustainment Plan. Software assurance practices must address trustworthiness, dependability (correct and predictable execution), conformance, and viability.

PWS-TO4-SS04: The Government will review the Contractor(s) developer’s processes, standards, tools, and tool options/configurations to determine if the processes, standards, tools, and tool options/configurations selected and employed can satisfy the requirements for a system test and development environment.

PWS-TO4-SS05: The Contractor(s) shall follow a documented development process for approved software changes that:

- Explicitly addresses security requirements.

- Identifies the standards and tools used in the development process (for example, programming languages).

- Documents the specific tool options and tool configurations used in the development process.

- Documents, manages, and ensures the integrity of changes to the process and/or tools used in development to enable accurate supply chain risk assessment and mitigation, and requires robust configuration control throughout the lifecycle (including design, development, transport, delivery, integration, and maintenance) to track authorized changes and prevent unauthorized changes.

- Supply chain risk assessments and mitigations need to be coordinated with the Government and PI.

PWS-TO4-SS06: Software development and test for NAaaS antenna systems sustainment shall be in accordance with a Contractor(s) general Sustainment Plan as defined in PWS-TO4-GS01.

PWS-TO4-SS07: The Contractor(s) shall define software builds at the key sustainment solution review (e.g. CDR, if applicable) in a logical sequence for implementation. Each build shall meet a specific and identifiable set of requirements and provide capabilities that can be demonstrated to the Government via a comprehensive build test. A description of all associated binaries, libraries, and scripts shall be included. The Contractor(s) shall give an overview of how builds will be distributed and patches applied.

PWS-TO4-SS08: The Contractor(s) shall use established NESDIS, NOAA, and Department of Commerce [DOC) Enterprise licensing agreements for COTS products. There are also mandatory use policies in place for some products. The determination of use for a particular software package will be made on a case-by-case basis, with an emphasis toward meeting established Enterprise-wide software mandates.

PWS-TO4-SS9: The Contractor(s) shall request permission from the Government prior to using open source, shareware or freeware software in any product or system delivered under this contract. The Contractor(s) shall identify any project dependencies on such software. Any request to use any unsupported software should include a statement of risk incurred by its use. The statement of risk shall at a minimum, address options for licensing and maintenance support. Whenever possible, shareware and freeware should be compiled from source code and delivered to NOAA.

PWS-TO4-SS10: The Contractor(s) shall ensure that all provided or developed source code undergoes static or dynamic code scanning for security vulnerabilities as part of Security Test and Evaluation (ST&E) testing. Identified vulnerabilities shall be remediated, and the final scan results shall be submitted to the Information System Security Officer (ISSO) for approval prior to the code's operational deployment.

PWS-TO4-SS11: The Contractor(s) shall plan for and sustain software licenses in coordination with the PI, supporting NAaaS ground systems as well as at locations and backup sites. For new antennas, software licenses information shall be coordinated with the PI and Maintenance Contractor’s (TO3) Software and Hardware License Status reporting.

PWS-TO4-SS13: The Contractor(s) shall support new software sustainment code reviews and testing for scheduled sustainment related software releases, and any fixes to ensure they function as intended

PWS-TO4-SS14: The Contractor(s) shall support deployment and checkout operations, beginning with deployment to the on-site I&T environment and provide software releases and patches as a Software Delivery Package [D-TO4-049] and coordinated with the PI.

#### 3.3.3.2 System Integration, Installation, and Test

PWS-TO4-SI01: The Contractor(s) shall conduct a project to test and demonstrate system compliance through verification and validation of requirements. Following the Contractor(s) internal test plan and procedures, the Contractor(s) shall perform the following formal tests during the acceptance of the developed/re-hosted software/hardware elements:

- Targeted ST&E at the Contractor(s) site, prior to the Pre-shipment Test (PST)

- PST at the Contractor(s) site

- Integration Level Test (ILT) at the NOAA site

- Parallel Operations Testing (POT) at the NOAA Site

- Final Acceptance Test (FAT)

The Government may determine that its best interests are served by having the Contractor(s) perform some or all this work remotely when appropriate. On a case-by-case basis, the Contractor(s) shall provide justification and shall obtain written Government approval prior to conducting any/all remote testing.

PWS-TO4-SI02: The Contractor(s) shall submit sustainment Integration and Test (I&T) Plans [D-TO4-017] to manage and execute system level requirements driven I&T tasks as applicable. The Contractor(s) shall deliver the I&T plan for Government review and approval. Initial drafts shall be submitted two weeks prior to the sustainment solution technical review meeting (e.g. CDR). Any Government comments shall be submitted to the government 30 days prior to the test and Government comments shall be incorporated into the final test two weeks prior to test. Each test plan shall comply with the following:

- All requirements being tested have clearly identified success criteria.

- All requirements have an associated verification method.

- Testing performed from accounts with “least privilege” and using the account profile expected to be used by the end-user of the function being tested or demonstrated.

- Input data shall be actual operational data, wherever possible.

- Include a description of the impact on site operations and personnel during the installation, ILT, and FAT phases.

- Identify all NOAA facilities and personnel support required to perform the tests.

- Integration risks

PWS-TO4-SI03: The Contractor(s) shall submit a draft Sustainment Installation Plan [D-TO4-018] two weeks prior to the sustainment solution technical review meeting, and at a minimum include:

- Installation timeline

- Procedures to be followed

- Coordination with the Government System Engineer regarding location availability for the review

#### 3.3.3.3 Hardware Sustainment

Ground station antennas enable satellite mission communications to Ground Systems via Radio Frequency (RF) equipment and supporting ground infrastructure.

PWS-TO4-HW01: The Contractor(s) shall deliver a Hardware Sustainment Plan [D-TO4-019] where an initial draft is submitted with the proposal response in the general Sustainment Plan, and a final delivered after contract award. The Hardware Sustainment Plan captures sustainment support of hardware items to include antennas, RF equipment and facilities.

PWS-TO4-HW02: The Contractor(s) shall provide procurement support to purchase all hardware to implement sustainment solutions.

PWS-TO4-HW03: The Contractor(s) shall perform (in collaboration with the Government and PI) all integration and testing, modifications and/or porting of existing software to new hardware platforms that interface with existing operational systems.

PWS-TO4-HW04: The Contractor(s) shall provide support in the development of any acquisition packages necessary to acquire hardware for sustainment solutions and technology refreshes, as needed.

PWS-TO4-HW05: The Contractor(s) shall support the planning for sustainment activities for hardware licenses for antenna ground systems, for all identified work sites under section 2.1 of this TO.

PWS-TO4-HW06: The Contractor(s) shall support new hardware item technical reviews and testing for scheduled deployment and provide any required fixes to ensure the solution for deployment functions as intended.

PWS-TO4-HW07: The Contractor(s) shall support sustainment activities related to reconfiguration of hardware and/or network devices, if needed.

PWS-TO4-HW08: The Contractor(s) shall provide power, cooling, and product design specification estimates for any sustainment hardware solution to the government for approval. The Contractor(s) shall develop work requests and all CCRs required to install equipment in NOAA facilities.

PWS-TO4-HW09: For new antennas, hardware licenses information shall be coordinated with the Maintenance Contractor’s (TO3) Software and Hardware License Status reporting.

### 3.3.4 Ground System Requirements

The antenna ground system supports spacecraft in various orbital regimes including Geostationary Earth Orbit (GEO), Low Earth Orbit (LEO), and Lagrange Point One Space Weather (SWO) Orbits used by both NOAA and its partners. The NOAA/NESDIS antenna ground systems simultaneously support satellites throughout all phases of their operational lifecycle to provide satellite communications, nominal operations, on-orbit storage and decommissioning. Ground systems include antenna ground stations, antenna scheduling and control functionality, networks, and site infrastructure. In addition, there may be other related assets that require interface sustainment supporting NAaaS satellites communication needs.

PWS-TO4-GSR1: The Contractor(s) shall provide ground system interface support for the NAaaS Federal Information Security Management (FISMA) boundary and development of new and future boundaries.

PWS-TO4-GSR2: The Contractor(s) shall provide NAaaS antenna ground systems support for antenna monitor and control, and configuration of network and software.

PWS-TO4-GSR3: The Contractor(s) shall provide sustainment for pertinent aspects of the GEO, LEO and SWO antenna ground systems as directed.

#### 3.3.4.1 Geostationary Earth Orbit (GEO) Ground Systems

A GEO ground system consists of a network of ground stations and control centers that manage satellites and process data. Since geostationary satellites remain in a fixed position relative to the Earth's surface, the ground system can be geographically consolidated or distributed across different sites for redundancy. NOAA’s Geostationary Operational Environmental Satellites (GOES) currently provides advanced imagery and atmospheric measurements, real-time mapping of lightning activity, and monitoring of space weather. Future development efforts include expansion of Geostationary Extended Observations (GeoXO) and adoption of digital ground capabilities and/or transition to cloud-based Mission Operations (telemetry, tracking and command (TT&C), planning and scheduling).

The GEO ground system is composed of the NOAA Satellite Operations Facility (NSOF), the Wallops Command and Data Acquisition Station (WCDAS), Consolidated Backup (CBU) Facility and Fairbanks Command and Data Acquisition (FCDAS). The GOES-R Ground System Fact Sheet can be found in the NCAGSS Acquisition Document Library as well as additional GEO ground system sustainment artifacts.

#### 3.3.4.2 Low Earth Orbit (LEO) Ground Systems

The LEO ground system consists of a network of ground stations, gateways, and control centers that manage satellite operations and connect the satellite network to terrestrial networks. This system is critical for low-latency communication because LEO satellites move constantly and are only visible to a single ground station for a short period of time.

LEO missions and other scientific missions are operated through multiple control and launch facilities including NESDIS CDASat Fairbanks, Alaska (FCDAS), and Wallops, Virginia (WCDAS). Its core functions are to perform TT&C and download science mission from LEO satellites. The LEO ground systems support satellites and partner satellites.

FCDAS also acts as a backup for the WCDAS and supports GEO and SWO ground stations where applicable and as needed.

#### 3.3.4.3 Space Weather Operations (SWO) Ground Systems

The Space Weather Operations (SWO) ground system supports satellites orbiting between Earth and the sun, observing and providing advanced warning of particles and magnetic fields emitted by the sun (known as the solar wind) which can affect power grids, communications systems, and satellites close to Earth.

The SWO ground system includes a Mission Operations Center (MOC) located at the NOAA Satellite Operations Facility (NSOF) to command, process and distribute data from NASA missions to the Space Weather Prediction Center (SWPC). Upcoming mission requirements include partner missions such as Interstellar Mapping and Acceleration Probe (IMAP) and SOLAR A/B and other potential GEO based SWO missions.

### 3.3.5 Cloud Transition

Launched in 2020, the NESDIS Common Cloud Framework (NCCF) provides NOAA with a secure, scalable, and cost-efficient cloud-based infrastructure. NCCF facilitates the flow of data from various sources including NOAA satellites, commercial partners, and other data providers through a comprehensive production pipeline. Currently implemented with Amazon Web Services (AWS) NCCF includes a suite of integrated services designed to streamline NOAA’s ground system operations, encompassing secure ingest, product generation, and dissemination services. The NESDIS Innovation Hub (NIH) is a collaborative environment where NESDIS develops and transitions emerging technologies, particularly Artificial Intelligence (AI) and Machine Learning (ML) into operational services.

Future tasks may be written under the NCGASS contract to implement antenna ground system functions, services and capabilities as well as commercial services into the cloud environment. Commercial cloud services include cloud-based software defined radio (SDR), and an Enterprise Antenna Scheduling Implementation (EASI) architecture started with LEO and is the (current) enterprise planning and scheduling capability for all NESDIS LEO, GEO and SWO missions.

PWS-TO4-CS01: The Contractor(s) shall sustain NAaaS cloud implementations to include the implementation of cloud interfaces supporting future antenna services, capabilities, and initiatives.

PWS-TO4-CS02: The Contractor(s) shall support development and sustainment of the new NAaaS antenna FISMA boundary.

PWS-TO4-CS03: The Contractor(s) shall incorporate agile and incremental testing methodologies and leverage Continuous Integration/Continuous Deployment (CI/CD) approaches where practical in their integration, test and verification approach.

### 3.3.7 IT Security

PWS-TO4-ITS01: The Contractor(s) shall perform IT security integration activities for DOC/NOAA/NESDIS provided solutions as part of IDIQ Section 3.1.4 Cybersecurity.

PWS-TO4-ITS02: The Contractor(s) shall perform all necessary cybersecurity sustainment activities for the support of Plan of Action and Milestones (POA&M). These activities include research, plan, monitor, coordinate, track, execute, implement, and report on all POA&Ms to OSPO/OCS stakeholders, and PI.

PWS-TO4-ITS03: The Contractor(s) shall provide IT engineering services and implementation to ensure the security Enterprise Services in NOAA are implemented throughout the OSPO systems. The Contractor(s) shall consider the NESDIS systems architectures, determine the implementation and roll-out strategy, configure, test, integrate, troubleshoot, implement, and ensure the Enterprise services are operationally accepted on OSPO systems. Enterprise services are those designated by DOC, NOAA, and/or NESDIS to be Enterprise Services and include but are not limited to Homeland Security Presidential Directive - 12 (HSPD-12), Enterprise Continuous Monitoring and Operations (ECMO), Secure Active Directory, ArcSight, Microsoft Sentinel (cloud-native SIEM), Privilege Access Management (PAM), and vulnerability scanning (e.g. Nessus and WebInspect).

PWS-TO4-ITS04: The Contractor(s) shall evaluate commercially available cloud-based security services for integration activities.

PWS-TO4-ITS05: The Contractor(s) shall build specific security controls—as specified by the Government and based on the recommendations of the most recent revision of NIST Special Publication (SP) 800-53, Recommended Security Controls for Federal Information Systems and Organizations —into the system/component at the level required by the system’s FIPS 199 security categorizations.

PWS-TO4-ITS06: The Contractor(s) shall follow security engineering principles (including secure coding practices and code review for software development) consistent with NIST SP 800-27, Engineering Principles for Information Technology Security (A Baseline for Achieving Security), to follow a configuration management process in accordance with NIST SP 800-128, Guide for Security-Focused Configuration Management of Information Systems, and to perform security testing and evaluation before delivery to the government, specifically, developer/Contractor(s) shall:

- Create and implement a Configuration Management Plan [D-TO4-042].

- Create and implement a security test and evaluation plan.

- Implement a verifiable flaw remediation process to correct weaknesses and deficiencies identified during the security testing and evaluation process; and

- Document the results of the security testing/evaluation and flaw remediation processes in a Security Test and Evaluation Plan, Requirement, Objectives, and Results Report.

PWS-TO4-ITS07: The Contractor(s) shall, to the extent technically possible, incorporate products that have been tested, evaluated, and validated by the government. NIST SP 800-23, Guidelines to Federal Organizations on Security Assurance and Acquisition/Use of Tested/Evaluated Products, provides guidance on the acquisition and use of tested/evaluated information technology products. NIST SP 800-36, Guide to Selecting Information Technology Security Products, provides guidance on the selection of information security products.

PWS-TO4-ITS08: The Contractor(s) shall provide the government with adequate documentation of the system/component developed, to include a narrative description of the system operating environment, architecture (including diagrams and hardware/software inventories), and user/operator manuals. The documentation shall address user and systems administrator guidance and information regarding the implementation of the security controls in the information system. The documentation shall include, but is not limited to:

- Vendor supplied documentation of software.

- Supporting narratives as required by the government to prepare a comprehensive system security plan.

- Standard operating procedures.

- Emergency procedures.

- User rules/procedures.

- User and Administrator manuals

- Backup procedures.

PWS-TO4-ITS09:  The Contractor(s) shall develop and test software in accordance with the Department of Homeland Security’s Build Security In best practices (online at https://buildsecurityin.us-cert.gov/). Software shall be resilient across the development, acquisition, and operational lifecycle; as such, Software assurance practices must address trustworthiness, dependability (correct and predictable execution), conformance, and survivability.

PWS-TO4-ITS10: The Contractor(s) shall provide user-level, system administrator, and other training on the correct use and operation of the implemented security functions, controls, and/or mechanisms. Training of personnel is an essential element to ensure the effectiveness of security controls implemented within organizational information systems.

PWS-TO4-ITS11: The Contractor(s) shall formulate and draft a plan for security patching [D-TO4-044]  to include antenna and enterprise infrastructures for implementation after concurrence with the OSPO Cybersecurity Division.

PWS-TO4-ITS12: The Contractor(s) shall maintain and sustain non-NOAA site equipment, consistent with the subsystem ICDs and Operations and Maintenance manuals based on changes to the system design or maintenance approach.

PWS-TO4-IT13: The Contractor(s) shall ensure that the appropriate security posture is maintained for each system/subsystem. The Contractor shall therefore ensure system owners implement, sustain, and provide continuous monitoring on IT Security, via Continuous Monitoring Reports [D-TO4-050], in accordance with NOAA/NESDIS policy.

PWS-TO4-IT14: The Contractor(s) shall support annual IT security audits and collect, manage and integrate, all requested Security Control Assessment (SCA) artifacts with the PI and audit team.

3.3.7.1 IT Security Other Direct Costs

The Government has allocated certain IT services for purchase under the NCGASS contract as Other Direct Costs (ODCs). The Government will define purchases of IT Services to the Contractor(s) in a Bill of Materials (BOM).

PWS-TO4-ITS15: The Contractor(s) shall develop estimates for the total costs for acquisition of the requested IT Security Services Bill of Materials (BOM). The Contractor(s) shall submit the BOM cost estimate [D-TO4-021] to the COR and PM within two weeks of receipt of BOM.

PWS-TO4-ITS16: Upon approval of the BOM estimate, the Contractor(s) shall procure and deliver all referenced BOM items to the Security POCs along with associated documentation. Associated documentation may include invoices, quotes, warranties, licenses, and limitations.

### 3.3.8 Training

Training sessions and related media shall be provided to Government and Contractor(s) personnel performing spacecraft mission operations, software maintenance, hardware maintenance, and systems and network administration. Training includes a mix of classroom presentations, hands-on activities, videos and may be administered remotely via web session or designated tool. Training shall be administered to all applicable work locations and sites, identified in Section 2.1 of this TO.

PWS-TO4-T01: The Contractor(s) shall provide sustainment of ad-hoc training of technology refreshed legacy NAaaS ground system capabilities.

PWS-TO4-T02: The Contractor(s) shall provide training applicable for any changes to software, hardware or processes instantiated during sustainment activities.

PWS-TO4-T03: The Contractor(s) shall develop and provide all training materials and media [D-TO4-022] as needed to support any training sessions 30-days prior to conducting the training. The Contractor(s) shall provide the training materials and media to the PI to include in the training repository.

PWS-TO4-T04: The Contractor(s) shall coordinate with personnel at all work locations and sites to schedule training sessions to accommodate all attendees’ schedules.

PWS-TO4-T05: The Contractor(s) shall conduct all training sessions. Training sessions shall be scheduled as agreed between the project office and Contractor(s) and communicated in the monthly sustainment project review status meeting. Training shall support 24/7 operations crew without/limited overtime for Government employees meaning a minimum of four training sessions for each type of training. Travel associated with any training sessions shall be identified in advance and approved by the COR.

PWS-TO4-T06: The Contractor(s) shall provide training for System Administrators, and for end users, software maintenance, user training, and hardware training for any new hardware delivered within 30 days prior to the System Acceptance Review (SAR).

### 3.3.9 System Engineering

The Contractor(s) shall implement disciplined, repeatable System Engineering (SE) processes to ensure that sustainment projects remain compliant within budget, schedule, performance requirements and/or performance standards. Contractor(s) processes shall employ a methodical, multi-disciplinary approach for the design, implementation, technical management, operations and maintenance, and retirement of a ground system. SE processes shall also be applied to antenna and radio frequency (RF) equipment supporting ground systems. The Contractor(s) shall adhere to the following reference documents for SE support:

- OCS Systems Engineering Process Document, OCS 5820.01A October 3, 2016, 	Version 0.5

- OCS Change and Configuration Management Process

- Satellite Products and Services Review Board Process

- NESDIS Ground Enterprise (NGE) Technical Architecture (TA) User’s Guide, Version 2.0, 03 April 2019

PWS-TO4-SE01: The Contractor(s) shall designate a Chief Systems Engineer to conduct and coordinate day-to-day systems engineering activities, oversee implementation of activities in accordance with the Contractor’s Systems Engineering Management Plan and act as the technical interface with the Government’s engineers.

PWS-TO4-SE02: The Contractor(s) shall ensure that sustainment projects remain within their commitments and constraints in terms of budget, schedule, technical scope and quality in accordance with NESDIS procedural requirements per OCS Systems Engineering Process Document, OCS 5820.01A October 3, 2016, Version 0.5.

PWS-TO4-SE03: The Contractor(s) shall provide and maintain requirements management process and related documentation in coordination with the NAaaS Program Integrator. A Sustainment Requirements Baseline [D-TO4-010] shall be delivered as an initial draft submitted with the proposal response and a final delivered after contract award. The Sustainment Requirements Baseline shall include performance requirements established and maintained throughout the contract period of performance. This baseline shall contain performance requirements and/or performance standard, security requirements, and facilities requirements for each ground system detailed in the scope of this TO.

PWS-TO4-SE04: The Contractor(s) shall provide a System Engineering Management Plan (SEMP) if directed by the Government for inclusion in Day 1 TOs. [D-TO4-011]. The SEMP shall address sustainment processes covering operations, integration and test of hardware and software items, approved change requests, and testing (including regression, functional, stress, and system and end-to-end testing), and shall be delivered after contract award.

PWS-TO4-SO05: The Contractor(s) shall formulate and draft a plan for regression testing [D-TO4-045] that include options for not impacting antenna down time.

PWS-TO4-SE06: The Contractor(s) shall provide a Sustainment Life-Cycle Cost Prediction Report [D-TO4-012] for sustainment ground systems to be delivered after contract award. The Contractor(s) shall support OCS in supplying data and artifacts when requested.

PWS-TO4-SE07: The Contractor(s) shall identify ground system components that may have become obsolete to reduce ongoing costs, and/or other opportunities to reduce the operational cost. These items shall be coordinated with and approved by the Government.

PWS-TO4-SE08: The Contractor(s) shall assist the Government with the support of interface control documents (ICD) by assessing proposed changes. The Contractor(s) shall provide ICD updates and/or modification information [D-TO4-026] from the implementation of sustainment capabilities. At a minimum, each ICD shall define:

- Interface mechanisms

- Network connectivity

- Protocols, error recovery, and security

- Any applicable file naming conventions

- Transaction content and formats

- Confirmation and reconciliation reporting

PWS-TO4-SE09: The Contractor(s) shall provide artifacts that support engineering assessment (EA) and cost estimation, if requested. EAs identified and approved by the COR shall include details related to system performance analysis, capacity planning, and related cost over the performance period. Deliverables from engineering assessments may result in technical direction letters or contract modifications depending on the scope and magnitude of the request.

PWS-TO4-SE10: The Contractor(s) shall develop work requests and configuration change requests for sustainment hardware solutions for primary and remote work locations/site and sites detailed in Section 2.1 in this TO.

PWS-TO4-SE11: The Contractor(s) shall provide system engineering support for integration and testing for sustainment activities, including new or modified functionality or infrastructure in the NAaaS.

PWS-TO4-SE12: The Contractor(s) shall conduct Design Modification Reviews (DMR) with the Government and PI, to present significant changes to the design baseline. The DMR shall include details on architectural impacts, security impacts, software/hardware impacts, deployment plans and operational impacts from the change under review in accordance with the OCS Systems Engineering Process Document, OCS 5820.01A October 3, 2016, Version 0.5.

PWS-TO4-SE13: The Contractor(s) shall support the PI in the preparation, documentation, and implementation of a Reliability, Maintainability, and Availability (RMA) program.

### 3.3.10 Risk Management

PWS-TO4-RM01: The Contractor(s) shall comply with the OSPO Risk Management Plan.

PWS-TO4-RM02: The Contractor(s) shall prepare an Electronic Documentation Repository [D-TO4-027] listing the Contractor’s view of initial sustainment risks for review and consideration by the Government with recommended mitigations as part of its proposal submission. Subsequent updates to be coordinated with the Government monthly.

PWS-TO4-RM03: The Contractor(s) shall support the Government in the risk management activities and maintaining risk related data in the Government-provided risk management tool.

PWS-TO4-RM04: The Contractor(s) shall collaborate with the Government and PI on Risk Management activities and report risk status at the Monthly Contract Review.

PWS-TO4-RM02: The Contractor(s) shall prepare a Risk Management Report [D-TO4-028] listing the Contractor’s view of initial Operational risks for review and consideration by the Government with recommended mitigations as part of its proposal submission. Subsequent updates to be coordinated with the Government monthly.

## 4.0 Contract Line Item Number (CLIN) 0001 - Study Tasks

PWS-TO4-CL01: The Contractor(s) shall conduct studies and analysis on topics identified by the Government throughout the period of performance.

## 5.0 Performance Requirements Summary

The Contractor’s service requirements are summarized into performance objectives that relate directly to mission essential items. The performance threshold briefly describes the minimum acceptable levels of service required for each requirement. These thresholds are critical to mission success.

| PWS Section (Requirement) | Performance Objectives | Minimum Acceptable Quality Level (AQL) | Monitoring Method |
| --- | --- | --- | --- |
| PWS-TO4-GS14 | Ground System performance standards | Meet or exceed existing Ground System performance standards and requirements for all sustainment activities | Inspection/Review of Contractor(s) Performance Metrics Reports |
| PWS-TO4-GS19 | Contractor(s) shall provide accurate and complete Sustainment Monthly Status Reports | Less than 5% errors or missing data | Monthly Inspection and project review for completeness, accuracy and compliance with project baseline |
| PWS-TO4-PM04 | Contractor(s) shall provide and maintain an integrated sustainment schedule | Less than 5% errors or missing data | Monthly Inspection and project review for completeness, accuracy and compliance with project baseline |
| PWS-TO4-SER04, PWS-TO4-CT02 | Transition completeness of all transfer elements and action items are dispositioned | Contractor(s) shall identify transfer and receipt of critical elements in the monthly project management review package. | Regular Inspection during status meetings and monthly project review package |
| PWS-TO4-PM04 | The Contractor(s) shall provide regular reports and metrics on Release Backlog requirements.This is applicable to each ground system detailed in this TO. | Less than 5% errors or missing data | Inspection/Review of Contractor(s) Performance Metrics Reports |
| PWS-TO4-SS02 | Contractor(s) provides documentation for sustainment system operational readiness (e.g. new hardware items, software code reviews and testing, operation readiness). | 90% of CCRs have no open priority 1 reports at ORR; any open problem reports shall have an approved resolution plan | Inspection of ORR reports and schedules resolution approach |
| PWS-TO4-SS01, PWS-TO4-SS10 | The Contractor(s) shall provide Database change reporting regarding code changes compiling success, testing source control shall be documented in a detailed report and provide metrics. | 100 % of all included CCRS for any releaser Metrics: Urgent- Resolved within 48 hours- Out of release cycle, and approved out of board. Critical – Resolved by agreed to date Required out of board approval; point release will be created. High- Must be included in the next scheduled release or no later than 2 weeks for hardware CCRS. Medium- Has specific need date but not in the next release or within 1 month for hardware CCRS. | Inspection of CCR reports, CM reports and Contractor(s) Metrics Report |

# Appendix A: Initial Sustainment Antenna List

| Antenna ID | Location | Ownership | Size | Tx Bands | Rx Bands |
| --- | --- | --- | --- | --- | --- |
| CL1 | CBU | NOAA | 13m | S | S, X |
| HR7 | CBU | NOAA | 16.4m | S, X | S, L, X |
| HR8 | CBU | NOAA | 16.4m | S, X | S, L, X |
| HR9 | CBU | NOAA | 16.4m | S, X | S, L, X |
| FCA​ | FCDAS​ | NOAA | 13m​ | S​ | S, L, X​ |
| FCB​ | FCDAS​ | NOAA | 13m​ | S​ | S, L, X​ |
| FCC​ | FCDAS​ | NOAA | 13m​ | S​ | S, L, X​ |
| FCKa​ | FCDAS​ | NOAA | 4m​ | None​ | S, Ka (dual band) |
| MC1​ | McMurdo​ | NOAA | 4m​ | None​ | S, Ka (dual band) |
| MC2​ | McMurdo​ | NOAA | 4m​ | None​ | S, Ka (dual band) |
| MC3​ | McMurdo​ | NOAA | 4m​ | None​ | S, Ka (dual band) |
| 9.1m | NSOF | NOAA | 9.1m | None | L |
| 9.1m | NSOF | NOAA | 9.1m | None | L |
| 9.1m | NSOF | NOAA | 9.1m | None | L |
| 9.1m | NSOF | NOAA | 9.1m | None | L |
| N1 | NSOF | NOAA | 9m | None | L |
| N2 | NSOF | NOAA | 9m | None | L |
| N3 | NSOF | NOAA | 9m | None | L |
| N4 | NSOF | NOAA | 9m | None | L |
| SG4​ | Svalbard​ | NOAA | 13m​ | S​ | S, L, X​ |
| SG60​ | Svalbard​ | NOAA | 4m​ | None​ | Ka (dual band) S (not configured) |
| HR2 | WCDAS | NOAA | 16.4 | S | L, S |
| WL1 | WCDAS | NOAA | 13m | S | S, X |
| A | WCDAS | NOAA | 13m | L, S | L, S, X |
| B | WCDAS | NOAA | 13m | L, S | L, S, X |
| 14m | WCDAS | NOAA | 14.2m | S | UHF, L, S, X |
| HR4 | WCDAS | NOAA | 16.4m | S, X | S, L, X |
| HR5 | WCDAS | NOAA | 16.4m | S, X | S, L, X |
| HR6 | WCDAS | NOAA | 16.4m | S, X | S, L, X |
| 18m A | WCDAS | NOAA | 18m | S | S |
| 26m | WCDAS | NOAA | 26m | None | UHF, L, S |
| UHF-1 | WCDAS | NOAA | 3.8m | UHF | UHF |
| UHF-2 | WCDAS | NOAA | 3.8m | None | UHF |
| UHF-3 | WCDAS | NOAA | 3.8m | None | UHF |
| 7.2m | WCDAS | NOAA | 7.2m | None | C |
| D | WCDAS | NOAA | 8m | S | L |
| HR1 | WCDAS | NOAA | 16.4 | S | L, S |

# Appendix B: Sustainment Deliverables

| Deliverable ID # | Deliverable | Frequency | Distribution | PWS Reference Section(s) (Requirement ID) |
| --- | --- | --- | --- | --- |
| D-TO4-001 | Antenna Systems Sustainment Project Plan | Initial draft submitted with proposal; a final submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS02) |
| D-TO4-002 | NAaaS Sustainment Phase-In Transition Plan | Initial draft plan submitted with proposal; a final plan submitted within 60 days after contract award | Electronic Documentation Repository | 3.3.11 Contract Transition (PWS-TO41-CT01) |
| D-TO4-003 | NAaaS Sustainment Phase-In Transition Plan Status Report | Monthly - on the first business day of the month | Electronic Documentation Repository | Integrate 3.3.11 Contract Transition (PWS-TO4-CT02) |
| D-TO4-004 | Sustainment Stakeholder Contact List | Initial draft submitted with proposal; a final submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS03) |
| D-TO4-005 | Integrated Sustainment Schedule | Initial draft submitted with proposal; a final submitted within 120 days after contract award, and updates monthly | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS04) |
| D-TO4-006 | Sustainment Inventory Baseline | Initial draft submitted with proposal; a final submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3 Sustainment (PWS-TO4-GS15) |
| D-TO4-007 | Technology Refresh Analysis | As required | Electronic Documentation Repository | 3.3.1 Sustainment (PWS-TO4-GS20) |
| D-TO4-008 | Contractor Metric Performance Report | Weekly - on the first business day of the week and aggregated in a monthly report on the first business day of the month | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM04) |
| D-TO4-009 | Software Sustainment Plan | Initial draft submitted with proposal; a final document submitted within 120 days | Electronic Documentation Repository | 3.3.3.1 Software Sustainment (PWS-TO4-SS01) |
| D-TO4-010 | Sustainment Requirements Baseline | Initial draft submitted with proposal; a final submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3.9 System Engineering (PWS-TO4-SE03) |
| D-TO4-011 | System Engineering Management Plan Tailored Sustainment | Initial submitted with proposal; a final tailored SEMP within 60 days after contract award | Electronic Documentation Repository | 3.3.9 System Engineering (PWS-TO4-SE04) |
| D-TO4-012 | Sustainment Life-Cycle Cost Prediction Report | Submitted within 120 days after contract award | Electronic Documentation Repository | 3.3.9 System Engineering (PWS-TO4-SE06) |
| D-TO4-013 | Modified source code | As required per each CCR | Configuration Management Repository | 3.3.3.1 Software Sustainment (PWS-TO4-SS01) |
| D-TO4-014 | Configuration Change Requests (CCRs) | As required | ECMT | 3.3.3.1 Software Sustainment (PWS-TO4-SS01) |
| D-TO4-015 | Configuration Change Requests Report | As required | ECMT | 3.3.3.1 Software Sustainment (PWS-TO4-SS02) |
| D-TO4-016 | Sustainment Project Milestone Plan | Initial draft submitted with proposal; a final submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS04) |
| D-TO4-017 | Integration and Test Plans | Two weeks prior to sustainment solution technical review meeting; a final due no later than 2 weeks prior to the test | Electronic Documentation Repository | 3.3.3.1 Software Sustainment (PWS-TO4-SS01) |
| D-TO4-018 | Sustainment Installation Plan | Two weeks prior to the technical review meeting | Electronic Documentation Repository | 3.3.3.2 System Integration, Installation and Test (PWS-TO4-SI03) |
| D-TO4-019 | Hardware Sustainment Plan | Initial draft submitted with proposal; a final document submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3 Sustainment Hardware (PWS-TO4-HW01) |
| D-TO4-020 | Test and Calibration Reports | No more than 2 weeks after Government acceptance | Electronic Documentation Repository | 3.3.6.2 Radio Frequency Equipment (PWS-TO4-RF02) |
| D-TO4-021 | IT Security Services BOM Cost Estimate | Within 2 weeks of receipt of BOM | Electronic Documentation Repository | 3.3.7.1 IT Security Other Direct Costs (PWS-TO4-ITS15) |
| D-TO4-022 | Training Materials and Media | 2 weeks prior to conducting the training | Electronic Documentation Repository | 3.3.8 Training (PWS-TO4-T03) |
| D-TO4-023 | Obsolescence Management Plan | Initial draft submitted with proposal; a final document submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3.2 Antenna and Radio Frequency Equipment (PWS-TO4-SER02) |
| D-TO4-024 | Release Backlog Report | Monthly - on the first business day of the month | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM03) |
| D-TO4-025 | Software Sustainment Life-Cycle Plan | To be delivered within 120 days after award as part of the Software Sustainment Plan. | Electronic Documentation Repository | 3.3.3.1 Software Sustainment (PWS-TO4-SS03) |
| D-TO4-026 | Interface Control Documents (ICD) | Within 45 days from implementation of sustainment capabilities. | Electronic Documentation Repository | 3.3.9 System Engineering (PWS-TO4-SE08) |
| D-TO4-027 | Electronic Documentation Repository containing initial sustainment risks with recommendations | Part of proposal submission and updates monthly | TBD | 3.3.10 Risk Management (PWS-TO4-RM02) |
| D-TO4-028 | Risk Management Report | Monthly - no later than the 10th of the month | Electronic Documentation Repository | 3.3.10 Risk Management (PWS-TO4-RM02) |
| D-TO4-029 | Monthly Progress Report | Monthly - no later than the 10th of the month | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM05) |
| D-TO4-030 | Contract Financial Report | Monthly- no later than the 10th of each month | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM06) |
| SOW Ref 3.1 D-TO4-031 | Associate Contractor Agreement (ACA) | Initial submitted with proposal Final consolidated plan 30 days after contract award | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM07) |
| SOW Ref 3.1 k. D-TO4-032 | Contractor Spend Plan | Initial submitted 60 days after award, annually thereafter. | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM08) |
| D-TO4-033 | General Sustainment Plan | Initial draft submitted with proposal; a final document submitted within 120 days after contract award, and updates quarterly | Electronic Documentation Repository | 3.3.2.3 Antenna and RF Equipment Systems Engineering (PWS-TO4-SER01) |
| D-TO4-034 | Weekly Status Report | Weekly | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS19) |
| D-TO4-035 | Quality Assurance Plan | Initial with proposal, updated as required (with the issuance of any new task order) | Electronic Documentation Repository | 3.1.1 Quality Assurance (PWS-TO4-QA01) |
| D-TO4-036 | Quality Assurance Surveillance Plan (QASP) | Initial with proposal, updated as required (with the issuance of any new TOs) | Electronic Documentation Repository | 3.1.1 Quality Assurance (PWS-TO4-QA03) |
| D-TO4-037 | Quality Assurance Standard Operating Procedures (SOP) | 60 days after contract award, updated annually no later than May 29th, or as requested by the Government | Electronic Documentation Repository | 3.1.1 Quality Assurance (PWS-TO4-QA03) |
| D-TO4-038 | Sustainment Status Report | Monthly- no later than the 10th of each month | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS19) |
| D-TO4-039 | Meeting minutes, agendas, action item lists, lessons learned, etc. | One week after the meeting or one day prior to the next scheduled meeting, whichever is less | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS19) |
| D-TO4-040 | Test and Calibration Report | No more than 2 weeks after Government acceptance | Electronic Documentation Repository | 3.3.2.1 RF Equipment (PWS-TO4-RF02] |
| D-TO4-041 | Transition to Operations Package | Upon completion of new sustainment solution | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS21) |
| D-TO4-042 | Sustainment Configuration Management Plan | Initial with proposal, updated as required (with the issuance of any new TOs) | Electronic Documentation Repository | 3.3.7 IT Security Sustainment (PWS-TO4-ITS06) |
| D-TO4-043 | Use Case Cost Estimates | With proposal submission | Electronic Documentation Repository | 3.3.1 General (PWS-TO4-GS22) |
| D-TO4-044 | Security Patching Plan | 60 days after contract award | Electronic Documentation Repository | 3.3.5 IT Security Sustainment (PWS-TO4-ITS11) |
| D-TO4-045 | Regression Testing Plan | 60 days after contract award | Electronic Documentation Repository | 3.3.9 System Engineering (PWS-TO4-SE05) |
| D-TO4-046 | NAaaS Study Reports | As requested | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM13) |
| D-TO4-047 | Project Kickoff Meeting | Within 10 days of contract award | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM14) |
| D-TO4-048 | Project Management Review | Monthly- no later than the 10th of each month | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM19) |
| D-TO4-049 | Software Review Package | As requested | Electronic Documentation Repository | 3.3.3.1 Software Sustainment (PWS-TO4-SS14) |
| D-TO4-050 | Continuous Monitoring Reports | Monthly- no later than the 10th of each month | Electronic Documentation Repository | 3.3.7 IT Security (PWS-TO4-IT13) |
| D-TO4-051 | Project Management Plan | 60 days after contract award | Electronic Documentation Repository | 3.1 Project Management (PWS-TO4-PM21) |

# Appendix C: Cost Exercises

1.0 Introduction

These use cases are provided to evaluate the offerors ability in providing innovative solutions, determining a fair and reasonable price, evaluating competitiveness, and verifying prices are realistic. The price estimates should include fully burdened labor, material and Other Direct Costs (ODCs) in the scope of each use case.

Use Case 1: There is significant cost savings by upgrading and building new antennas with modern technology and retiring under-utilized antenna assets. Provide cost estimates and assumptions for all three antenna use cases. For the upgrade and build out enable frequency bands of S and X, and the antenna needs to withstand hurricane rated winds of 120 miles per hour (mph). Antenna descriptions can be found in the RF Antenna Handbook in the NCAGSS Acquisition Technical Library.

  - Upgrade a 21-meter (m) antenna at Fairbanks, Alaska, Fairbanks Command and Data Acquisition Station (FCDAS). The purpose of this effort is to upgrade an outdated Antenna Control Systems (ACS) on a NESDIS 21m antenna system at Fairbanks, Alaska. The upgrade is to replace the currently installed General Dynamics ACS Model 133 to a General Dynamics ACS Model 990 or equivalent. The ACS Model 990 consists of an antenna control unit (ACU), a power drive unit (PDU) and a tracking receiver unit (TRU) that directs the movement and positioning of the physical antenna structure. Frequency bands shall be S and X

The price will include replacement of the current ACU, PDU and TRU hardware with modern technologies that are compatible with the current antenna system. (assumes software is embedded), installation in labor hours and labor categories, freight, recommended spares and a 12-month warranty on the upgraded hardware. No other prices are expected in this use case

  - Build out a 13m antenna at the NESDIS Consolidated Back Up (CBU) facility in Fairmont, West Virginia. The purpose of this effort is to build a new 13m antenna at the CBU. The antenna system needs to provide tracking, command, and the ability to receive mission telemetry and remote sensing data from NOAA LEO satellites. Assume an undeveloped CBU site has been chosen by the Government. The cost estimate shall include site clearing, and pad foundation preparation and concrete foundation.

The price will include the 13m antenna, an antenna control unit (ACU), a power drive unit (PDU) and a tracking receiver unit (TRU) that directs the movement and positioning of the physical antenna structure. In addition to the hardware (including embedded software), include project management, installation, integration, testing, documentation and training (in labor hours/categories), freight, (1) spare  and a 12-month warranty. No other prices are expected in this exercise.

  - Decommission a 26m at Fairbanks, Alaska, FCDAS. The purpose of this effort is to decommission a 26m antenna system at Fairbanks, Alaska. The decommissioning of an antenna is the systematic and controlled process of permanently removing an antenna system and its associated infrastructure from active service.

The price will include demolition to include labor hours and labor categories/   The demolition activities do not include pad removal, site remediation, or environmental remediation. No other prices should be included in this exercise except for demolition.

Use Case 2: NAaaS seeks to further enterprise objectives through adoption of next generation Software Defined Radio (SDR) capabilities. LEO/GEO/SWO and OSPO are all utilizing non-homogeneous solutions to include outmoded hardware radios. As a service, NESDIS operates, the vendor provides sustainment, security scan patches, and two updates per year.

  - Establish a model implementation plan using an existing NOAA antenna ground system at FCDAS. Document goals such as proposed SDR solution to consolidate hardware, improving frequency agility, and minimizing program specific hardware like front end processors (FEP). Determine what cloud platform could be used to implement next generation SDR capabilities.

  - Provide plans, assumptions and proposed cost to transition to single source enterprise common service to a cloud based SDR for an antenna ground system at FCDAS. The price should include 1 year warranty, support, installation, training, direct modulation and sequential tone ranging.

Use Case 3: NAasS seeks to provide comprehensive coverage through the integration of a single source, multi-mission steerable, multibeam phased array antenna. The antenna needs to be suitable for Arctic deployments such as FCDAS and McMurdo, enable frequency bands, S, X and L, but not a Ka band, and withstand hurricane rated winds up to 120 mph.

  - Address the limitations of a legacy NAaaS antenna at FCDAS or McMurdo by replacing mechanical steering with electronic beamforming. Provide a comprehensive coverage solution that includes costs, cost savings, and advantages over legacy antennas. Include advancements in phased array antennas for Arctic resilience by eliminating mechanical vulnerability while introducing specialized materials and electronics capable of withstanding extreme cold and volatile weather.

  - The cost will also include hardware (including embedded software), project management, installation, integration, testing, documentation and training (in labor hours/categories), freight, (1) spare and a 12-month warranty.

# Appendix D: Acronym Listing

| ACS | Antenna Control System |
| --- | --- |
| AI | Antenna Infrastructure |
| AIMS | Action Information Management System |
| ARM | Active Risk Management |
| BOM | Bill of Materials |
| CBU | Consolidated Backup Unit |
| CDAS | Command and Data Acquisition Stations |
| CGS | Common Ground System |
| CI/CD | Continuous Integration/Continuous Development |
| CO | Contracting Officer |
| COR | Contracting Officer Representative |
| COSI | Common Operating System Image |
| COTS | Commercial Off-the-Shelf |
| DMR | Design Modification Review |
| EA | Engineering Assessment |
| EASI | Enterprise Antenna Scheduling Implementation |
| ECMO | Enterprise Continuous Monitoring and Operations |
| EOL | End of Life |
| EOS | End of Service |
| EPR | Engineering Peer Reviews |
| FAT | Factory Acceptance Testing |
| FCC | Federal Communication Commission |
| FISMA | Federal Information Security Management Act |
| GEO | Geostationary |
| GOES | Geostationary Operational Environmental Satellite |
| GOES N/O/P/R | Geostationary Operational Environmental Satellite (Series N, O, P and R) |
| HSPD | Homeland Security Presidential Directive |
| IDIQ | Indefinite Delivery, Indefinite Quantity |
| ILT | Integration Level Test |
| I&T | Integration and Test Plan |
| IMAP | Interstellar Mapping and Acceleration Probe |
| IMS | Integrated Master Schedule |
| LEO | Low Earth Orbit |
| NESDIS | National Environmental Satellite, Data, and Information Service |
| NGE | NESDIS Ground Enterprise |
| NJGS | NOAA Jason Ground System |
| NLT | No Later Than |
| NOAA | National Oceanic and Atmospheric Administration |
| NCGASS | NESDIS Consolidated Antenna & Ground System |
| NGE | NESDIS Ground Equipment |
| NPP | National Polar-orbiting Partnership |
| NSOF | NOAA Satellite Operations Facility |
| OCS | Office of Common Services |
| ODC | Other Direct Costs |
| OSAAP | Office of Satellite Architecture and Advanced Planning |
| OCS | Office of Satellite Ground Services |
| PAM | Privilege Access Management |
| POT | Parallel Operations Testing |
| PRS | Performance Requirement Summary |
| NTIA | National Telecommunication and Information Administration |
| ORR | Operational Readiness Review |
| OS | Operating System |
| OSPO | Office of Satellite and Product Operations |
| OTS | Off The Shelf |
| PGS | Polar Ground System |
| PM | Project Management |
| PMO | Project Management Office |
| POA&M | Plan of Action and Milestones |
| PSDI | Product System Development and Integration |
| PST | Pre-Shipment Test |
| PWS | Performance Work Statement |
| QAP | Quality Assurance Plan |
| RF | Radio Frequency |
| SAR | System Acceptance Review |
| SDR | Software Designed Radio |
| SE | Systems Engineering |
| S/EA | Security Engineering Architecture |
| SME | Subject Matter Expert |
| S-NPP | Suomi National Polar-Orbiting Partnership |
| SOP | Standard Operating Procedures |
| SOW | Statement of Work |
| SSP | Solid State Power |
| ST&E | Security Test & Evaluation |
| SWFO | Space Weather Follow-On |
| SWPC | Space Weather Prediction Center |
| TA | Technical Architecture |
| TBD | To be Determined |
| TT&C | Telemetry, Tracking and Command |
| WCDAS | Wallops Command and Data Acquisition Station |
| WSGT/WSC | White Sands Ground Terminal/White Sands Complex |