## SubCLIN Summary
TABLE 2 - Schedule B (DRAFT)
Installation | Site | CLIN/Sub-CLIN Number | CLIN/Sub-CLIN Description | Projected Award Date (Pending availability of funding and bona fide need) | Section F Date Start* | Section F Date End | Contract PoP Start | 2026-08-17
N/A | N/A | 0001 | Complete Project Management Plan (PMP) |  |  |  | Contract PoP End | 2036-08-16
N/A | N/A | 0001CA | Complete PMP | Base Period (FY26) | 8/17/2026 | 8/16/2027
N/A | N/A | 0001CB | Update PMP | Optional Task (FY28)
N/A | N/A | 0001CC | Update PMP | Optional Task (FY30)
| N/A | 0001CD | Complete ORC Transition Plan 2034 | Optional Task (FY34)
N/A | N/A | 0002 | Develop Integrated Master Schedule (IMS)/Milestone Payment Schedule (MPS) and Update Monthly
N/A | N/A | 0002CA | Develop IMS/MPS and Update Monthly | Base Period (FY26) | 8/17/2026 | 8/16/2027
N/A | N/A | 0002CB | Update IMS/MPS Monthly - OY1 | OY1 (FY27)
N/A | N/A | 0002CC | Update IMS/MPS Monthly - OY2 | OY2 (FY28)
N/A | N/A | 0002CD | Update IMS/MPS Monthly - OY3 | OY3 (FY29)
N/A | N/A | 0002CE | Update IMS/MPS Monthly - OY4 | OY4 (FY30)
N/A | N/A | 0002CF | Update IMS/MPS Monthly - OY5 | OY5 (FY31)
N/A | N/A | 0002CG | Update IMS/MPS Monthly - OY6 | OY6 (FY32)
N/A | N/A | 0002CH | Update IMS/MPS Monthly - OY7 | OY7 (FY33)
N/A | N/A | 0002CJ | Update IMS/MPS Monthly - OY8 | OY8 (FY34)
N/A | N/A | 0003 | Complete IRP Basewide Quality Program Plans (QPPs)
N/A | N/A | 0003CA | Complete IRP Basewide QPP | Base Period (FY26) | 8/17/2026 | 8/16/2027
N/A | N/A | 0003CB | Update IRP Basewide QPP | Optional Task (FY27)
N/A | N/A | 0003CC | Update IRP Basewide QPP | Optional Task (FY28)
Fairchild AFB | N/A | 0004 | Restoration Advisory Board (RAB) Support
Fairchild AFB | N/A | 0004CA | Restoration Advisory Board Support | Base Period (FY26) | 8/17/2026 | 8/16/2027
Fairchild AFB | N/A | 0004CB | Restoration Advisory Board Support - OY1 | OY1 (FY27)
Fairchild AFB | N/A | 0004CC | Restoration Advisory Board Support - OY2 | OY2 (FY28)
Fairchild AFB | N/A | 0004CD | Restoration Advisory Board Support - OY3 | OY3 (FY29)
Fairchild AFB | N/A | 0004CE | Restoration Advisory Board Support - OY4 | OY4 (FY30)
Fairchild AFB | N/A | 0004CF | Restoration Advisory Board Support - OY5 | OY5 (FY31)
Fairchild AFB | N/A | 0004CG | Restoration Advisory Board Support - OY6 | OY6 (FY32)
Fairchild AFB | N/A | 0004CH | Restoration Advisory Board Support - OY7 | OY7 (FY33)
Fairchild AFB | N/A | 0004CJ | Restoration Advisory Board Support - OY8 | OY8 (FY34)
Fairchild AFB | N/A | 0005 | Update Community Involvement Plan
Fairchild AFB | All Open Sites (IRP, MMRP, PFAS, etc) | 0005CA | Update Community Involvement Plan | Base Period (FY26) | 8/17/2026 | 8/16/2027
Fairchild AFB | All Open Sites (IRP, MMRP, PFAS, etc) | 0005CB | Update Community Involvement Plan | OY5 (FY31)
Fairchild AFB | N/A | 0006 | Complete 1,4-Dioxane Step 1
Fairchild AFB | N/A | 0006AA | Complete 1,4-Dioxane Step 1 Investigation | Base Period (FY26) | 8/17/2026 | 8/16/2028
Fairchild AFB | N/A | 0007 | Complete 1,4-Dioxane Step 2
Fairchild AFB | N/A | 0007AA | Complete 1,4-Dioxane Step 2 Nature and Extent Determination | Optional Task (FY27)
Fairchild AFB | N/A | 0008 | Complete 1,4-Dioxane Step 3
Fairchild AFB | N/A | 0008AA | Complete 1,4-Dioxane Step 3 Risk Assessment | Optional Task (FY28)
Fairchild AFB | N/A | 0009 | Revise, and Update Land Use Control Implementation Plan (LUCIP)
Fairchild AFB | N/A | 0009CA | Update LUCIP | Optional Task (FY28)
Fairchild AFB | N/A | 0009CB | Update LUCIP | Optional Task (FY30)
Fairchild AFB | N/A | 0009CC | Update LUCIP | Optional Task (FY32)
Fairchild AFB | N/A | 0009CD | Update LUCIP | Optional Task (FY34)
Fairchild AFB | N/A | 0010 | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report
Fairchild AFB | N/A | 0010AA | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report | Base Period (FY26) | 8/17/2026 | 8/16/2027
Fairchild AFB | N/A | 0010AB | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY1 | OY1 (FY27)
Fairchild AFB | N/A | 0010AC | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY2 | OY2 (FY28)
Fairchild AFB | N/A | 0010AD | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY3 | OY3 (FY29)
Fairchild AFB | N/A | 0010AE | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY4 | OY4 (FY30)
Fairchild AFB | N/A | 0010AF | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY5 | OY5 (FY31)
Fairchild AFB | N/A | 0010AG | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY6 | OY6 (FY32)
Fairchild AFB | N/A | 0010AH | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY7 | OY7 (FY33)
Fairchild AFB | N/A | 0010AJ | Conduct Basewide LUC Inspections and Prepare Annual Basewide LUC Report - OY8 | OY8 (FY34)
Fairchild AFB | N/A | 0011 | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps)
Fairchild AFB | N/A | 0011AA | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) | Base Period (FY26) | 8/17/2026 | 8/16/2027
Fairchild AFB | N/A | 0011AB | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY1 | OY1 (FY27)
Fairchild AFB | N/A | 0011AC | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY2 | OY2 (FY28)
Fairchild AFB | N/A | 0011AD | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY3 | OY3 (FY29)
Fairchild AFB | N/A | 0011AE | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY4 | OY4 (FY30)
Fairchild AFB | N/A | 0011AF | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY5 | OY5 (FY31)
Fairchild AFB | N/A | 0011AG | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY6 | OY6 (FY32)
Fairchild AFB | N/A | 0011AH | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY7 | OY7 (FY33)
Fairchild AFB | N/A | 0011AJ | Basewide Monitoring Well Network Inventory, Inspection, and Repair Annual Report (to include Basewide Maps) - OY8 | OY8 (FY34)
Fairchild AFB | DP064 | 0012 | Achieve ROD
Fairchild AFB | DP064 | 0012AA | Achieve Proposed Plan | Optional Task (FY26)
Fairchild AFB | DP064 | 0012AB | Achieve ROD | Optional Task (FY27)
Fairchild AFB | FT004 | 0013 | Remove Treatment System
Fairchild AFB | FT004 | 0013AA | Remove Treatment System and Provide System Abandonment Completion Report | Optional Task (FY26)
Fairchild AFB | LF001 | 0014 | Conduct LTM
Fairchild AFB | LF001 | 0014CA | Conduct LTM in accordance with the approved ROD/DD and Groundwater Monitoring ahead of Five Year Review - OY2 | OY2 (FY28)
Fairchild AFB | LF001 | 0014CB | Conduct LTM in accordance with the approved ROD/DD and Groundwater Monitoring ahead of Five Year Review - OY7 | OY7 (FY33)
Fairchild AFB | LF002 | 0015 | Conduct RA-O
Fairchild AFB | LF002 | 0015AA | Restart Remediation System | Optional Task (FY26)
Fairchild AFB | LF002 | 0015CA | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | LF002 | 0015CB | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY1 | OY1 (FY27)
Fairchild AFB | LF002 | 0015CC | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY2 | OY2 (FY28)
Fairchild AFB | LF002 | 0015CD | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | LF002 | 0015CE | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | LF002 | 0015CF | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | LF002 | 0015CG | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | LF002 | 0015CH | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | LF002 | 0015CJ | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY8 | OY8 (FY34)
Fairchild AFB | LF002 | 0015CK | Conduct O&M of remediation system after restart | Optional Task (FY26)
Fairchild AFB | LF002 | 0015CL | Conduct O&M of remediation system after restart | Optional Task (FY27)
Fairchild AFB | LF002 | 0015CM | Conduct O&M of remediation system after restart | Optional Task (FY28)
Fairchild AFB | LF002 | 0015CN | Conduct O&M of remediation system after restart | Optional Task (FY29)
Fairchild AFB | LF002 | 0015CP | Conduct O&M of remediation system after restart | Optional Task (FY30)
Fairchild AFB | LF002 | 0015CQ | Conduct O&M of remediation system after restart | Optional Task (FY31)
Fairchild AFB | LF002 | 0015CR | Conduct O&M of remediation system after restart | Optional Task (FY32)
Fairchild AFB | LF002 | 0015CS | Conduct O&M of remediation system after restart | Optional Task (FY33)
Fairchild AFB | LF002 | 0015CT | Conduct O&M of remediation system after restart | Optional Task (FY34)
Fairchild AFB | OW058 | 0016 | Achieve ROD
Fairchild AFB | OW058 | 0016AA | Achieve ROD | Optional Task (FY26)
Fairchild AFB | SD037 | 0017 | Conduct RA-O and Achieve Alternate Objective
Fairchild AFB | SD037 | 0017AA | Achieve Supplemental Site Investigation Work Plan | Optional Task (FY26)
Fairchild AFB | SD037 | 0017AB | Achieve Advanced Site Characterization including Supplemental Site Investigation, Revised 3-D Conceptual Site Model, and Updated Groundwater Monitoring Program | Optional Task (FY27)
Fairchild AFB | SD037 | 0017AC | Achieve Remedy Evaluation and Recommendation Report | Optional Task (FY28)
Fairchild AFB | SD037 | 0017AD | Complete Pilot Study(ies)/Treatability Test(s) | Optional Task (FY29)
Fairchild AFB | SD037 | 0017AE | Achieve Revised Decision Document | Optional Task (FY30)
Fairchild AFB | SD037 | 0017CA | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | SD037 | 0017CB | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY1 | OY1 (FY27)
Fairchild AFB | SD037 | 0017CC | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY2 | OY2 (FY28)
Fairchild AFB | SD037 | 0017CD | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | SD037 | 0017CE | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | SD037 | 0017CF | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | SD037 | 0017CG | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | SD037 | 0017CH | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | SD037 | 0017CJ | Conduct RA-O in accordance with the approved ROD/DD and evaluate performance model - OY8 | OY8 (FY34)
Fairchild AFB | SS009 | 0018 | Achieve Corrective Measure Study/Corrective Action Plan
Fairchild AFB | SS009 | 0018AA | Achieve Supplemental Investigation/Corrective Measures Study | Base Period (FY26)
Fairchild AFB | SS009 | 0018AB | Achieve Corrective Action Plan | Optional Task (FY28)
Fairchild AFB | SS009 | 0018CA | Conduct LTM in accordance with the approved CAP - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | SS009 | 0018CB | Conduct LTM in accordance with the approved CAP - OY1 | OY1 (FY27)
Fairchild AFB | SS009 | 0018CC | Conduct LTM in accordance with the approved CAP - OY2 | OY2 (FY28)
Fairchild AFB | SS009 | 0018CD | Conduct LTM in accordance with the approved CAP - OY3 | OY3 (FY29)
Fairchild AFB | SS009 | 0018CE | Conduct LTM in accordance with the approved CAP - OY4 | OY4 (FY30)
Fairchild AFB | SS009 | 0018CF | Conduct LTM in accordance with the approved CAP - OY5 | OY5 (FY31)
Fairchild AFB | SS009 | 0018CG | Conduct LTM in accordance with the approved CAP - OY6 | OY6 (FY32)
Fairchild AFB | SS009 | 0018CH | Conduct LTM in accordance with the approved CAP - OY7 | OY7 (FY33)
Fairchild AFB | SS009 | 0018CJ | Conduct LTM in accordance with the approved CAP - OY8 | OY8 (FY34)
Fairchild AFB | SS039 | 0019 | Conduct (I)RA-O and Achieve Alternate Objective
Fairchild AFB | SS039 | 0019AA | Achieve Advanced Site Characterization including Supplemental Site Investigation, Revised 3-D Conceptual Site Model, and Updated Groundwater Monitoring Program | Optional Task (FY27)
Fairchild AFB | SS039 | 0019AB | Achieve Advanced Site Characterization including Supplemental Site Investigation, Revised 3-D Conceptual Site Model, and Updated Groundwater Monitoring Program | Optional Task (FY30)
Fairchild AFB | SS039 | 0019AC | Achieve Advanced Site Characterization including Supplemental Site Investigation, Revised 3-D Conceptual Site Model, and Updated Groundwater Monitoring Program | Optional Task (FY34)
Fairchild AFB | SS039 | 0019CA | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | SS039 | 0019CB | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY1 | OY1 (FY27)
Fairchild AFB | SS039 | 0019CC | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY2 | OY2 (FY28)
Fairchild AFB | SS039 | 0019CD | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | SS039 | 0019CE | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | SS039 | 0019CF | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | SS039 | 0019CG | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | SS039 | 0019CH | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | SS039 | 0019CJ | Conduct (I)RA-O in accordance with the interim ROD/DD and evaluate performance model - OY8 | OY8 (FY34)
Fairchild AFB | ST006 | 0020 | Remove Treatment System and Provide System Abandonment Completion Report
Fairchild AFB | ST006 | 0020AA | Remove Treatment System and Provide System Abandonment Completion Report | Optional Task (FY26)
Fairchild AFB | TU500 | 0021 | Conduct RA-O
Fairchild AFB | TU500 | 0021CA | Conduct RA-O in accordance with the approved CAP and evaluate performance model - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | TU500 | 0021CB | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY1 | OY1 (FY27)
Fairchild AFB | TU500 | 0021CC | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY2 | OY2 (FY28)
Fairchild AFB | TU500 | 0021CD | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | TU500 | 0021CE | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | TU500 | 0021CF | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | TU500 | 0021CG | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | TU500 | 0021CH | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | TU500 | 0021CJ | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY8 | OY8 (FY34)
Fairchild AFB | TU502 | 0022 | Achieve Remedy in Place
Fairchild AFB | TU502 | 0022AA | Achieve CAP | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | TU502 | 0022AB | Achieve Remedy in Place | Optional Task (FY28)
Fairchild AFB | TU502 | 0022CA | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | TU502 | 0022CB | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | TU502 | 0022CC | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | TU502 | 0022CD | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | TU502 | 0022CE | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | TU502 | 0022CF | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY8 | OY8 (FY34)
Fairchild AFB | TU506 | 0023 | Conduct RA-O
Fairchild AFB | TU506 | 0023CA | Conduct RA-O in accordance with the approved CAP and evaluate performance model - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | TU506 | 0023CB | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY1 | OY1 (FY27)
Fairchild AFB | TU506 | 0023CC | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY2 | OY2 (FY28)
Fairchild AFB | TU506 | 0023CD | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | TU506 | 0023CE | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | TU506 | 0023CF | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | TU506 | 0023CG | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | TU506 | 0023CH | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | TU506 | 0023CJ | Conduct RA-O in accordance with the approved CAP and evaluate performance model - OY8 | OY8 (FY34)
Fairchild AFB | WP003 | 0024 | Achieve RC (Achieve Remedial Action Completion Report) and Conduct RA-O
Fairchild AFB | WP003 | 0024AA | Remove Treatment System and Provide System Abandonment Completion Report | Optional Task (FY26)
Fairchild AFB | WP003 | 0024AB | Achieve PP/ROD Amendment | Optional Task (FY26)
Fairchild AFB | WP003 | 0024CA | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - Base Year | Base Period (FY26) | 8/17/2026 | 8/16/2029
Fairchild AFB | WP003 | 0024CB | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY1 | OY1 (FY27)
Fairchild AFB | WP003 | 0024CC | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY2 | OY2 (FY28)
Fairchild AFB | WP003 | 0024CD | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY3 | OY3 (FY29)
Fairchild AFB | WP003 | 0024CE | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY4 | OY4 (FY30)
Fairchild AFB | WP003 | 0024CF | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY5 | OY5 (FY31)
Fairchild AFB | WP003 | 0024CG | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY6 | OY6 (FY32)
Fairchild AFB | WP003 | 0024CH | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY7 | OY7 (FY33)
Fairchild AFB | WP003 | 0024CJ | Conduct (I) RA-O in accordance with the approved ROD/DD and evaluate performance model - OY8 | OY8 (FY34)
*Section F dates are based on the projected award date of 8/17/2026
Option Year (OY) designation in column E indicate projected award dates for each of the associated Sub-CLINs. Meeting these annual award dates is necessary to maintain compliance with AF legal obligations, including Records of Decision (RODs), permits, and other agreements. These dates should not be confused with the time to obtain final regulatory approval of the reports associated with these annually funded events. Final reports generally take more than 12 months so these events, while funded annually, are non-severable in nature.