SECTION C

DESCRIPTION/SPECIFICATIONS/WORK STATEMENT

TABLE OF CONTENTS

| ARTICLE NUMBER | ARTICLE NAME | PAGE NO. |
| --- | --- | --- |
| C.1 | SCOPE OF WORK.................................................................................................. | 2 |
| C.2 | EXTENT OF SERVICES ........................................................................................ | 2 |
| C.3 | DEFINITIONS......................................................................................................... | 4 |
| C.4 | REFERENCE MATERIALS ................................................................................... | 12 |
| C.5 | GENERAL REQUIREMENTS ............................................................................... | 12 |
| C.6 | INFORMATION MANAGEMENT ........................................................................ | 13 |
| C.7 | PROGRESS REPORTS AND RECORDS .............................................................. | 13 |
| C.8 | SITE OFFICE FACILITIES..................................................... | 14 |
| C.9 | CONTRACTOR PERSONNEL STAFFING AND ASSIGNMENTS..................... | 14 |
| C.10 | SPECIAL PERSONNEL QUALIFICATIONS.......................................................... | 14 |
| C.11 | FAILURE TO PROVIDE QUALIFIED PERSONNEL........................................... | 14 |
| C.12 | ORIENTATION OF PERSONNEL......................................................................... | 15 |
| C.13 | PROCUREMENT PHASE SERVICES................................................................... | 15 |
| C.14 | PROJECT MANAGEMENT SERVICES AND DELIVERABLES..................... | 18 |
| C.15 | POST-AWARD SERVICES AND DELIVERABLES........................................... | 17 |
| C.16 | CMa ADDITIONAL SERVICES............................................................................. | 27 |
| C.17 | CMa PROGRAM MANAGEMENT SERVICES ................................................... | 28 |

SECTION C

DESCRIPTION/SPECIFICATIONS/WORK STATEMENT

# SCOPE OF WORK

## As a Construction Manager as Advisor (CMa), the contractor shall provide Program Management, Project Management, and Construction Management services for projects performed by construction contractors for NAVFAC Washington. Services include pre-award planning, design, procurement, and post-award construction & post-construction of facilities and infrastructure projects defined by Task Orders in the NAVFAC Washington AOR.  CMa services shall include the management of quality, cost, time, communications and administration. The projects are typically located at any of the installations within the NAVFAC Washington area of responsibility (AOR). The NAVFAC Washington area of responsibility comprises the following:

### Naval Support Activity Washington, DC

### Naval Support Activity Bethesda, Maryland

### Naval Support Activity Annapolis, Maryland

### Naval Support Facility Indian Head, Maryland

### Naval Support Facility Dahlgren, Maryland

### Naval Air Station Patuxent River, Maryland

### Joint Base Andrews, Camp Springs, Maryland

### Joint Base Anacostia Bolling, Washington, District of Columbia

### Naval Support Facility Thurmont, Maryland

### Marine Corps Base Quantico, Virginia

## In addition, the CMa will be responsible, as required, to supply certain classes of personnel to be selected by NAVFAC Washington for assignments. These may be individuals or teams of people supplied to work on projects. Classifications of individuals or teams include construction-industry specific specialties such as:

### Project Manager

### Construction Manager

### Engineering Technician

### Scheduler/Planner

### Cost Estimator

### Claims Analyst

# EXTENT OF SERVICES

## Construction Manager Advisor Services.

## The services provided under this contract shall be performed by a company entity, not an individual, to support NAVFAC in its execution of facility projects. The scope of services is divided into two primary phases: pre-award and post-award of the main construction contract. These services will be provided across a range of project types, including Military Construction (MILCON) for the Navy, Marine Corps, and other Defense agencies; Facilities Sustainment, Restoration, and Modernization (FSRM) projects for

## CNIC and the Marine Corps; and reimbursable (REIM) project work for various Supported Commands.  It is understood that the funding for these pre-award and post-award support services varies depending on the project type, as detailed in the matrix below. The services described herein are distinct from Program Management (PgM), which is the collective oversight of multiple projects for a single stakeholder (e.g., DHA, NSWC) and are aligned with the NAVFAC definition of Project Management (PM) for a singular project, although contractor personnel may be assigned to support multiple projects.

## A core principle of the services sought is the clear delineation between contractor support functions and Inherently Governmental Functions (IGF), which are exclusively reserved for Federal employees. The contractor shall perform the preparatory work, analysis, documentation, and coordination required to support Government officials in their decision-making. However, all final determinations, approvals, and official commitments are inherently governmental. This includes, but is not limited to, the determination of Federal program priorities; the initiation, processing, and commitment of funds via contract award or modification; the approval of contract documents; the final acceptance or rejection of contractor products; and the official approval of schedule delays or extensions. Any CMa recommendations regarding payments to other vendors will be provided to the designated Government Contracting Officer's Representative (COR) for their exclusive determination and action.

## As a Construction Manager as Advisor (CMa), the contractor will provide comprehensive project management support. The CMa’s Project Oversight role in the post-award phase will include supporting the Government's administration of construction contracts by reviewing submittals, tracking Requests for Information (RFIs), facilitating modification negotiations with the Contracting Officer, and coordinating project closeout activities. Post-award technical consultation and assessment will be provided by staff with relevant pre-award experience. The CMa shall view Risk Management as a critical component of Project Governance and integrate it into all services.

## Contract task orders will delineate whether the CMa shall act as a program/project’s primary Program Manager, Project Manager, Construction Manager, or combination thereof.  In all scenarios, the CMa is responsible for ensuring overall project success and the project is executed in accordance with NAVFAC policies and construction contract requirements including but not limited to quality, cost, and schedule control. The CMa shall function as a collaborative member of the combined project team and shall provide guidance and expertise throughout all phases of the project. The Government shall enter directly into contractual agreements with designers, construction contractors, commissioning agents and providers of other services; however, the CMa shall be responsible for coordination and communications amongst all project stakeholders while ensuring that entities contracted with the Government meet the obligations of their contracts with the Government. Only the Government Contracting Officer is authorized to make modifications to Government contracts, including this contract with the CMa. The CMa shall provide to the Government expert guidance in relation to modifications to Government contracts.  When CMa communicates with Construction Contractors and other Government Contractors, the CMa must ensure it is understood that only the Contracting Officer has the authority to make modifications to contracts. Furthermore, CMa must advise the Construction Contractors and other Government Contractors that if they interpret a communication from the CMa to represent a change to their contract with the Government, they must not proceed with that potential change and must notify the Contracting Officer of their interpretation and request direction.

The CMa is acting as the Government’s Advisor and shall always uphold the best interest of the Government.  The CMa shall consistently demonstrate competence and ethical behavior while complying with all applicable laws and regulations. The CMa is responsible for determining the resources required to provide the required services and deliverables. The CMa should be prepared to be flexible and adapt to changing project needs.   The CMa shall avoid any action representing a conflict of interest or gives the appearance of a conflict of interest.

## Brooks Act.

## This contract is for Construction Management Advisor services and does not include architectural or engineering design services; and is therefore not subject to requirements of the Brooks Act.

## Davis-Bacon Act.

## This contract is for Construction Management Advisor services and does not include construction, alteration, or repair of public buildings or public works; and is therefore not subject to requirements of the Davis-Bacon Act.

## Fund Source Matrix

| Project Category | Pre-Award Services Funding Source | Post-Award Services (PCAS) Funding Source |
| --- | --- | --- |
| Navy MILCON (MCON) | MCON Design (MCON-D) Funds | MCON Construction (MCON-C) Funds |
| Marine Corps MILCON (MCON) | MCON Design (MCON-D) Funds | MCON Construction (MCON-C) Funds |
| Other Defense Agency MILCON | Reimbursable (REIM) funding from the specific agency (e.g., MCA, DLA) | Reimbursable (REIM) funding from the specific agency |
| CNIC FSRM (O&M Funded) | Operations & Maintenance, Navy (O&MN) - Direct or Reimbursable | Operations & Maintenance, Navy (O&MN) - Reimbursable |
| Marine Corps FSRM (O&M Funded) | Operations & Maintenance, Marine Corps (O&M, MC) - Reimbursable | Operations & Maintenance, Marine Corps (O&M, MC) - Reimbursable |
| Supported Command REIM Projects | Reimbursable (REIM) funding from the specific Supported Command | Reimbursable (REIM) funding from the specific Supported Command |

# DEFINITIONS

## Architects/Engineers (A/Es). The professional services contractors responsible for designing the projects. The A/Es may perform other services during the construction phases, which are not included in the task orders for the CMa, the construction contractors, or other firms associated with the project.

## Construction Manager as Advisor (CMa). The CMa is selected to assist NAVFAC WASHINGTON by performing required work in the Procurement Phase, Planning Phase, Design Phase, Construction Phase, Claims, Post-Construction, Program Management, and Additional Services as specified in the contract. In providing the project services described in the contract, the CMa shall maintain a working relationship with and other contractors supporting the Government. Nothing in this contract shall be construed to mean that the CMa assumes any of the contractual responsibilities or duties of the architects/engineers or construction contractors. The construction contractors are solely responsible for construction means, methods, sequences and procedures used in the construction of the projects, and for related performance in accordance with their contracts with the Government. The architects/engineers are solely responsible for the project designs and shall perform all design-related services in accordance with their contracts with the Government.

## Contracting Officer. The Contracting Officer is the warranted federal employee with the legal authority to enter into, administer, modify, or terminate contracts on behalf of the Government. They are the authorized agents responsible for soliciting proposals, negotiating terms, and ensuring that all acquisitions comply with federal laws and regulations.

## Contracting Officer's Representative (COR).  The COR is the Contracting Officer’s Representative assigned to this contract with the CMa.   Roles and authorities of the COR are further described in this contract.  The COR for this CMa contract may or may not be the same individual assigned as COR on individual task orders as issued.

## Construction Manager-Contracting Officer's Representative (CM-COR). The CM-COR is the Contracting Officer’s Representative assigned to the Government’s contract with the Construction Contractor or other Government Contracts, particularly during the phase of the project after award of the construction contract.  Roles and authorities of the CM-COR are identical to those of a COR as described in this contract.  The CM-COR assigned to a particular contract with a Construction Contractor or other Government Contract may or may not be the same individual assigned as COR.

## Project Manager/Design Manager-Contracting Officer's Representative (PM/DM-COR). The PM/DM-COR is the Contracting Officer’s Representative assigned to the Government’s contract with the Designer of Record or other Government Contracts, particularly during the phase of the project prior to award of the construction contract.  Roles and authorities of the PM/DM-COR are identical to those of a COR as described in this contract.  The PM/DM-COR assigned to a particular contract with a Designer of Record or other Government Contract may or may not be the same individual assigned as COR or CM-COR.

## Home Office Area. This term means the cities/states/counties in which the CMa's active office(s) is/are located. If the CMa's active office(s) is/are located in metropolitan areas consisting of more than one county, the metropolitan area shall be considered the Home Office Area.

## Key Personnel. The following personnel are considered “Key Personnel”; Construction Executive, Senior Construction Managers, Senior Scheduler/Analyst, Senior Claims Analyst, and Senior Program Mangager. The task order key persons will act as a liaison between any subcontractors utilized under the task order and NAVFAC Washington. All Personnel shall have the minimum experience identified under Labor Categories in “DEFINITIONS”.

## Level of Effort. The CMa is totally responsible for its performance and deliverables. The Government retains the authority to require work acceleration to maintain its obligations for completion of the projects. If necessary, this may include issuing contract modifications to the CMa to provide additional services.

## Management Level. Includes persons vested with authority for decision-making, establishing commitments for the firm, documentation approvals, manpower and equipment assignments, etc.

## Labor Categories. The requirements for the labor categories are defined below.  The Government may request documentation that demonstrates compliance; however, the CMa is responsible for verifying that their staff meets the required qualifications.

| Labor Title | Responsibility Statement | Min Years Experience | Min Education | Required Certification |
| --- | --- | --- | --- | --- |
| Construction Executive (CEx) | Responsible for overall administration of the CMa contract (e.g., principal point of contact between CMa Contractor and Contracting Officer for task order submissions, reviews staff resumes prior to submitting to NAVFAC WASHINGTON for approval, handles submission of invoices, contract correspondence, etc.), coordination of CMa efforts required, general direction, and accomplishment of CMa contractual functions. This is considered a Key Person. | 15yrs | Bachelor’s Degree in Engineering, Architecture, or Construction Management, or related field or Professional Certification PE or AIA. requirement waived for 20yrs related experience. | CCM, PE or RA, NAVFAC /USACE QCM Certification |
| Senior Construction Manager | Overall post-award construction management services on MILCONs, otherwise supervises Construction Managers on non-MILCON projects. Works with Contracting Officer and CM-COR and leads CMa team to complete projects from start to finish, on-time and cost-effectively in compliance with all contract requirements. Proficiency in Primavera P6 and construction estimating software. This is considered a Key Person. | 10yrs | Bachelor’s Degree in Engineering, Architecture, or Construction Management, or related field and Professional Engineer (PE) or Professional Architecture (A.I.A) Professional Certification. PE or AIA requirement waived for 20yrs related experience. | CCM, PE or RA, NAVFAC/ USACE QCM Certification |
| Construction Manager | Overall post-award management responsibility of construction projects including schedule reviews, cost estimating, change management, submittals, RFIs constructability reviews, and responsible for professional reviews pertaining to the Procurement and Construction Phases. Project Document Control using eCMS & eContracts. | 5yrs | Bachelor’s Degree in Engineering, Construction Management, or a related field and Professional Engineer (PE) Certification. | CCM, PE, RA, or 10yrs field experience. NAVFAC / USACE QCM Certification |
| Assistant Construction Manager | Assess, process and maintain records of all contract-related correspondence in eCMS & eContracts platform. Draft recommended responses and actions for CM-COR for project actions such as RFIs, submittals, change orders, punch-lists, etc. Analyze construction trends, monitor deliverables and provide overall administrative functions. | 3yrs | Bachelor’s Degree in Engineering, Architecture, Construction Management. Waived for 10 years in the field of construction administration. | NAVFAC/ USACE QCM Certification, OSHA 30 |
| Senior Scheduler / Analyst | Creates, maintains, updates, analyzes, and reports on engineering and construction project schedules on MILCON projects; oversees and manages the efforts of subordinate Project Schedulers. Works with design engineers and construction engineers to optimize project schedules and mitigate schedule delays. Analyzes schedule related claims and change orders. Reports to Construction Manager, Project Manager, or Program Manager. Proficiency in Primavera P6 and MS Project. This is considered a Key Person. | 10 yrs with 5 yrs on projects of similar size and complexity | Bachelor’s Degree in Engineering, Architecture, or Construction Management, Business Management. | CCM |
| Scheduler / Analyst | Creates, maintains, updates, analyzes, and reports on engineering and construction project schedules; oversees and manages the efforts of subordinate Project Schedulers. Works with design engineers and construction engineers to optimize project schedules and mitigate schedule delays. Analyzes schedule related claims and change orders. Reports to Construction Manager, Project Manager, or Program Manager. Proficiency in Primavera P6 and MS Project. | 5 yrs on projects of similar size and complexity | Bachelor’s Degree in Engineering, Architecture, or Construction Management, Business Management. | CCM |
| Senior Claims Analyst | Furnishes reports with supporting information necessary to resolve disputes or defend against the claims, participates in meetings, prepares cost estimates for use in claims negotiations, prepares risk assessments/analysis related to claim exposures. This is considered a Key Person. | 15yrs | Bachelor’s Degree in Engineering, or Construction Management | CCM or PE |
| Cost Estimator | Provides accurate multi-trade estimates of time, money, materials, and labor required to construct or renovate complex buildings. | 5yrs | Bachelor’s Degree in Engineering, Architecture, Construction Management. Waived for 10 years experience in cost estimating field. | CCM, CCP, CEP or comparable national certification. |
| Senior Project Manager (SPM) | Provides Project Management services from project initiation phase through project close-out of MILCON projects including project governance, planning, design management and quality assurance, cost estimating, scheduling, funds management, project monitoring and project close-out. | 15yrs | Bachelor’s Degree in Engineering or Architecture. | PE or RA; and PMP |
| Project Manager (PM) | Provides Project Management services from project initiation phase through project close-out including project governance, planning, design management and quality assurance, cost estimating, scheduling, funds management, project monitoring and project close-out. | 10yrs | Bachelor’s Degree in Engineering or Architecture. | PE or RA |
| Planner | Develops and implements strategic plans to address organizational requirements. Coordinates development of project planning documents including DD Form 1391s, Basic Facility Requirements, budget estimates and schedules. Analyzes alternate construction methods, environmental and regulatory requirements. | 5yrs | Bachelor’s Degree in Community or Urban Planning, Urban Affairs or Public Administration | AICP |
| Procurement Tech | Assists the Contracting Officer with acquisition related functions including initial preparation of documents and coordination of acquisition meetings and processes. | 5yrs | Bachelor’s Degree and three year’s experience in Federal Government contracting processes. |  |
| Senior Program Manager (SPgM) | Oversees the operational aspects of multiple ongoing projects in a Program and is responsible for leading, organizing, budgeting, and managing CMa staff within a Program. Directly supervises execution, recruiting and training staff, providing updates and analysis on program/project status, and making sure the program cost and schedule objectives are realized. This is considered a Key Person. | 15yrs managing all phases of Federal Govt. Planning, Programming Budget, and Execution | Bachelor’s Degree in Engineering, or Architecture, or Construction/Project Management, Business Management. | CCM or PMP, PE, or RA |
| Architectural Engineering Technician | Maintains a strong background in field inspection of multi-disciplinary building facilities. Responsible for scheduling, coordinating, performing specialized field inspection for designated discipline as well as other related disciplines. Inspects work at the site(s) for contract and code compliance, proficient with construction management software (i.e. eCMS, Procore, Kahua). Recommend approvals or rejections of materials and workmanship as appropriate; monitor labor and safety requirements; complete written inspection reports, records of defects; and omissions; and similar activities. Coordinates field activities, outages and contractor access requirements. | 10yrs | Associates in Construction Related Field, Trade School or equivalent certification. Waived for 10 years in similar inspection role or trade. | NAVFAC/ USACE QCM Certification, OSHA 30 |
| Mechanical Engineering Technician | Same responsibilities as Architectural Engineering Technician and specializes in inspection of Mechanical Systems. Maintains knowledge of current industry practices for Mechanical Systems. | 10yrs | Associates in Construction Related Field, Trade School or equivalent certification. Waived for 10 years in similar inspection role or trade. | NAVFAC/ USACE QCM Certification, OSHA 30 |
| Electrical Engineering Technician | Same responsibilities as Architectural Engineering Technician and specializes in inspection of Electrical Systems. Maintains knowledge of current industry practices for Electrical Systems. | 10yrs | Associates in Construction Related Field, Trade School or equivalent certification. Waived for 10 years in similar inspection role or trade. | NAVFAC/ USACE QCM Certification, OSHA 30 |
| Concrete / Masonry Engineering Technician | Same responsibilities as Architectural Engineering Technician and specializes in inspection of Concrete/Masonry Systems. Maintains knowledge of current industry practices for Concrete/Masonry Systems. | 10yrs | Associates in Construction Related Field, Trade School or equivalent certification. Waived for 10 years in similar inspection role or trade. | NAVFAC/ USACE QCM Certification, OSHA 30 |
| Life Safety Acceptance Engineer | Provides technical oversight of Life Safety Systems to ensure essential and high-risk systems are installed and operate in accordance with design intent. Services include design review, review of Construction Contractor’s submittals, testing and inspection and final certification of acceptability. | 10yrs | Bachelor’s Degree in Engineering | QFPE |
| Roofing and Building Enclosure Acceptance Engineer | Provides technical oversight of Roofing and Building Enclosure Systems to ensure essential and high-risk systems are installed and operate in accordance with design intent. Services include design review, review of Construction Contractor’s submittals, testing and inspection and final certification of acceptability. | 10yrs | Bachelor’s Degree in Engineering or Architecture. | RA |
| Mechanical Systems Acceptance Engineer | Provides technical oversight of Mechanical Systems to ensure essential and high-risk systems are installed and operate in accordance with design intent. Services include design review, review of Construction Contractor’s submittals, testing and inspection and final certification of acceptability. | 10yrs | Bachelor’s Degree in Mechanical Engineering. | PE |
| Electrical Systems Acceptance Engineer | Provides technical oversight of Electrical Systems to ensure essential and high-risk systems are installed and operate in accordance with design intent. Services include design review, review of Construction Contractor’s submittals, testing and inspection and final certification of acceptability. | 10yrs | Bachelor’s Degree in Electrical Engineering. | PE |
| Elevator Acceptance Engineer | Provides technical oversight of Elevator and Vertical Transportation Systems to ensure essential and high-risk systems are installed and operate in accordance with design intent. Services include design review, review of Construction Contractor’s submittals, testing and inspection and final certification of acceptability. | 10yrs | Bachelor’s Degree in Science or Engineering, Architecture, Construction Management. Waived for 10 years in Elevator trade. | QEI |
| …CyCx … |  |  |  |  |

# REFERENCE MATERIALS

## The following reference materials or appropriate portions are available in the public domain and the CMa is responsible for obtaining and understanding the references, as applicable to the project, except for NAVFAC publications. NAVFAC publications will be made available upon written request. The CMa must become familiar with and use the current versions/revisions, and the CMa is required to comply with the policies and procedures set forth in all such references.

### Federal Acquisition Regulation (FAR) 48 CFR 1, Volumes 1 and 2.

### Defense Federal Acquisition Regulation Supplement (DFARS).

### NAVFAC Instructions (NAVFACINST) – Will be made available upon request.

### National Fire Protection Association (NFPA) handbooks including the NATIONAL ELECTRIC CODE.

### Occupational Safety and Health Administration (OSHA) Standards.

### International Code Council.

### American National Standards Institute (ANSI) Publications.

### National Electrical Manufacturer Association (NEMA) publications.

### Elevator Code - ANSI/ASME A17.1 Safety Code for Elevators and Escalators, & supplements.

### Uniform Federal Accessibility Standards (UFAS)

### American Disabilities Act Standards (ADA)

### US Department of Defense Unified Guide Specifications (UFGS)

### US Department of Defense Unified Facilities Criteria (UFC)

# GENERAL REQUIREMENTS

## The numbers, types, and functional involvement of the CMa's personnel and teams may vary on an as-needed basis; however, CMa’s staff commitment is required throughout the project as accepted in its proposal. No key personnel may be substituted at any time during the life of the project(s) without following the procedures outline in the article entitled, “KEY PERSONNEL”. The CMa is required to take the initiative and actively pursue the earliest possible completion of all services. The CMa must manage its staff commitments during fluctuations among external project assignments. Accordingly, the CMa shall perform any tasks described in the Scope of Services when requested by the Government, as appropriate, adequate and necessary to ensure that:

### Required work or services are performed within budget and in conformity with all applicable requirements.

### All services are completed as early as possible but will not be later than as directed by the contract.

## Project services or assignments are to be considered highly complex. Services which the CMa is required to provide include those described or specified in this Scope of Work. The services so described or specified shall not be deemed to constitute a comprehensive specification having the effect of excluding services not specifically mentioned; the CMa is required to furnish all other services necessary to fulfill the undertakings set out in this contract as negotiated with NAVFAC Washington.

## The CMa will not be held responsible for:

### Design deficiencies.

### Defective completion of construction, provided that the CMa exercised all due diligence, utilizing competent personnel within authorized limitations, to make reasonably certain that construction was performed in conformity with applicable construction contract plans and specifications.

### Time overruns provided the CMa has taken all reasonable measures to anticipate problems and delays, and to eliminate or minimize their adverse impacts on completion of construction by scheduled construction milestone dates.

## Except for miscellaneous items as stated in this contract, the CMa shall not be responsible for and shall not have control or charge of construction means, methods, techniques, sequences or procedures; safety contractors, Advisors or employees, or any other persons performing any of the work.

## The CMa agrees to furnish skills and judgment, and to perform all required services in the most effective, efficient and economical manner consistent with the interests of the Government.

## This is not a personal services contract, and representatives of the Government are not authorized to supervise the CMa’s personnel. However, non-supervisory direction and guidance from the Government is authorized. CMa’s personnel shall not directly supervise Government employees nor employees of the Government’s other contractors. The Contracting Officer’s Representative shall be advised of any issues which arise.

# INFORMATION MANAGEMENT

## The CMa must manipulate data and databases as specified herein. In turn, information will predominately be delivered to the CMa in electronic format. Any software utilized by the CMa at its home office facility and sent to NAVFAC must be compatible with NAVFAC software. The CMa shall ensure that its equipment and software is compatible with the system and software used by the Government including the latest version of Microsoft Office, AutoCAD, eCMS, eContracts iNFADS, and Primavera P6, among others.  NAVFAC maintains an official web-based construction management system named eCMS, which serves as the primary means of document control and storage for all project records.  This specific system and its name are subject to change at the discretion of the Government. The CMa will be responsible for ensuring its employees are fully trained on eCMS and other Government-designated electronic systems at no additional cost to the Government.

## All official project documentation and communications, including those that occur outside of eCMS must be loaded into eCMS for a complete project record.   The CMa shall transmit the complete project record to the Government on an annual basis and at the conclusion of each project.

# PROGRESS REPORTS AND RECORDS

## The CMa must keep accurate and detailed computerized/written records of progress on each project during all stages, and maintain frequent contacts by telephone, site visits, meetings, etc., with all parties involved in the project. The CMa must submit monthly electronic progress reports to the COR including information concerning the work of the A/E and other contractors. Initiatives taken by the CMa to preclude delays, percentages of completion, number and amounts of modifications and claims, analyses of the schedule, and other analyses necessary to compare actual performance with planned performance. The CMa must use any applicable NAVFAC forms and standard NAVFAC procedures.

## Provide computer generated progress schedules, with monthly updates reflecting actual progress of the project against previously projected progress, if required. Make periodic reports when and as required by the CM-COR. These reports will typically include Network Analysis Schedule (NAS) analysis, all Change Orders issued to that point in time, and narratives addressing potential impacts.

# SITE OFFICE FACILITIES

## The Government may provide the necessary working space for the CMa to complete their on-site work.   Working space may be onsite trailer offices or vacant office space in a building near the project site. The CMa shall provide all necessary furniture, internet connections, computers, printers, information technology equipment, office supplies, telecommunications equipment, appropriate vehicles, personal protective equipment, and all other equipment and supplies necessary to provide CMa services.

## If Task Order requires CMa to provide their own working space using temporary trailers, temporary trailer trailers shall be located as directed and the following shall apply:

### Temporary trailers must meet requirements as identified in EM 385-1-1 Section 04.

### Temporary trailers must comply with FAR 52.236-10 “Operations and Storage

### Areas.”

### Temporary trailers must be anchored to resist high winds and meet all applicable state and local building codes.

### CMa shall be responsible for safety and security of temporary trailers including security lighting.

### Trailers must present a clean and neat exterior appearance and be in a state of good repair.

### CMa shall provide all water and sanitary facilities and services necessary for temporary trailers.

### CMa shall provide all necessary utility connections as necessary for temporary trailers.

### CMa shall provide all necessary site preparation for temporary trailers and site restoration when they are removed.

## Computers or Laptops or other devices must be able to connect to the military network –currently the Navy Marine Corps Intranet (NMCI) – for use in direct contract support responsibilities.

## Reasonable amounts of utilities will be made available without charge.

# CONTRACTOR PERSONNEL STAFFING AND ASSIGNMENTS

## Assignments. The CMa agrees to provide administrative, technical, and professional personnel as required herein and as negotiated and agreed upon for performing work specified. The CMa must provide a dedicated, stable, and technically qualified staff to maintain continuity in the level of services. All Personnel shall have the minimum experience identified in “DEFINITIONS” .

## Staffing. The CMa must provide appropriate personnel as described in Section 3.11 – Labor Categories.   The Government reserves the right to request documentation of CMa personnel qualifications.

## Absences. CMa is required to advise the COR a minimum of 2 business days in advance of any scheduled CMa staff absences, and shall be prepared, if directed by COR, to provide temporary CMa personnel until the regular staff member returns. During unscheduled staff absences due to illness, emergencies, etc., after two (2) consecutive business days, CMa shall be prepared, if directed by CM-COR, to provide temporary CMa personnel until the regular staff member returns.

## Relations. The CMa must take the initiative establishing and maintaining proper business-like relations with personnel actively engaged in work within the Navy installation.

## Hierarchy.  The CMa shall conduct official business exclusively with prime contractors and shall not engage directly with subcontractors. The CMa’s personnel will not settle disputes or differences of opinion between prime contractors and their subcontractors, or between subcontractors.  Any disagreements between CMa and the Government shall be addressed privately and not discussed in the presence of Construction Contractor or their subcontractors.

## Confidentiality.  The CMa shall maintain strict confidentiality regarding all project information and shall not disclose any sensitive, confidential, potentially controversial, or unfavorable information. All information requests must be immediately forwarded to the COR for review and approval before being acted upon.

## Authority. The CMa will not issue oral instructions to, or make any agreements with, prime contractors or their representatives which affect the work in material ways, or which may result in disputes and claims.

## Artificial Intelligence (AI).   The use of Department of War authorized AI platforms is permitted.  CMa remains solely responsible for accuracy of final work product generated by AI.

# SPECIAL PERSONNEL QUALIFICATIONS

## Personnel possessing unique technical specialties may be required for supplemental services related to the scope of regular services. Such personnel shall have qualifications as required in Section 3.1. – Labor Categories.

# FAILURE TO PROVIDE QUALIFIED PERSONNEL

## Repeated failure, or excessive delays by the CMa, to provide qualified personnel, who meet the stated requirements, may be deemed sufficient reason by the Contracting Officer to terminate this contract.

# ORIENTATION OF PERSONNEL

## The CMa must send its CEx and other personnel as required to NAVFAC Washington Office for up to five (5) working days of orientation in Government policies and procedures, as required, by the COR. Subsequent to NAVFAC WASHINGTON orientation, the CMa is responsible for providing instructions to other team members working under this contract, and to ensure that all project personnel are aware of applicable Government regulations, policies, procedures, and uses of forms affecting the conduct of their work. Orientation must be initiated and arranged for by the CMa immediately after task order award.

# PROCUREMENT PHASE SERVICES

## Procurement of design, construction, and specialty contracts shall be carried out by the Government, in accordance with statutes governing NAVFAC Procurements, NAVFAC Instructions, Policies and Procedures.

## The CMa may be required to support Procurement Phase Services under this contract.  Services that may be required include:

### Verifying accuracy of lists/indexes of drawings and specifications being used.

### Assisting with document preparation including solicitation documents, Source Selection documents, amendments, and pre-proposal inquiry responses.

### Assisting with the scheduling, coordination, and documentation of pre-proposal bid conferences, pre-proposal site visits and Source Selection Evaluation Board (SSEB).

### Coordinating and reviewing technical responses (other than contract or proposal/bid issues) with A/E and the Government.

### Maintaining files of outstanding issues or details arising from questions and comments during contract procurements.

### Participate as a non-voting technical advisor to the Technical Evaluation Team (TET) and Source Selection Evaluation Board (SSEB).

NOTE: When these services are required, employees of the CMa, who are involved, are to handle all Procurement Phase material and information as Confidential and under no circumstances to be disclosed or discussed in any manner with other persons or entities other than staff on the procurement team.

# PROJECT MANAGEMENT SERVICES AND DELIVERABLES

# All services and deliverables must be on time, accurate, and complete, and will be provided in accordance with applicable NAVFAC policy. The CMa shall provide services and deliverables across all five project phases as described below, noting that all final approvals and decisions are retained by the Government. The following is the list of Services and Deliverables to be provided:

## PROJECT INITIATION PHASE

### Developing a project governance framework, for Government review and approval, including a three-tiered governance structure (Project, Senior, and Executive Leadership Teams) as required by project complexity for Government approval.

### Identifying the full project team, including members from all required NAVFAC communities, directorates, and applicable disciplines for Government approval.

### Developing a Project Charter, for Government review and approval, that documents project purpose, objectives, requirements, and stakeholder concurrence on baselines for Government approval.

### Developing the initial Project Management Plan (PMP) to serve as the roadmap for project execution, monitoring, and control.

### Developing and maintaining the Stakeholder Register.

### Developing and maintaining the project Risk Register and Escalation Matrix for Government approval.

### Developing a proposed Project Scope Baseline based on project information (e.g., draft DD 1391, draft Basic Facility Requirements) for Government approval.

### Developing a proposed Schedule and Cost Baselines for Government review and approval.

### Providing support to the Government in confirming and securing seed funding for initial project activities (to include technical, planning, and environmental funding).

### Developing an initial project acquisition strategy for Government approval.

### Analyzing and recommending the Acquisition Strategy (AE Design/In-House Design & Design-Build or Design-Bid-Build) for Government determination.

## PLANNING PHASE

### Performing Minimum Viable Project (MVP) Analysis to support the Government's affordability and acceleration campaigns.

### Conducting analyses of Alternate Construction Methods (ACMs) such as permanent modular construction, prestressed/precast concrete, tensile fabric structures, and additive manufacturing.

### Fully developing and updating all subsidiary plans within the PMP, including Scope, Schedule, Cost, Risk, Change, Quality, Resource, and Communication Management Plans for Government approval.

### Coordinating the development and validation of the DD 1391 planning documents for Government review and approval.

### Facilitating the development of the project budget and Estimated Construction Cost (ECC) for Government review and approval.

### Supporting the validation Basic Facility Requirements (BFR), asset evaluations, and Facility Planning Documents (FPD) for Government review and approval.

### Assisting in determining, identifying, and validating all required support studies (e.g., encroachment, site evaluation, lifecycle cost analysis) for Government review and approval.

### Coordinating with environmental subject matter experts to support the initiation of all National Environmental Policy Act (NEPA), State Historic Preservation Office (SHPO), and other environmental and regulatory processes.

### Maintaining all project records and reporting via eProjects and/or other Government eSystems, including the N37 record for planning activities.

## DESIGN PHASE

### Performing design quality assurance reviews to assist the Government in verifying that the Architect-Engineer/Designer of Record (AE/DOR) is compliant with UFC and other applicable codes, though the AE/DOR remains responsible for compliance for Government review and approval.

### Performing Value Engineering analyses and recommend design alternatives. Compile documentation packages for any design alternatives that necessitate UFC code exemption requests for Government review and approval.

### Providing services to support permit acquisition, expediting, and the NEPA process.

### Developing and maintaining pre-award project schedules using either MS Project or Primavera P6 for Government approval.

### Providing cost estimating services across AACE Class 1 through Class 5 estimates, utilizing the USACE MII cost estimating suite.

### Monitoring project baselines (scope, schedule, cost) and recommend action through the Government’s change control process.

### Managing and updating the project schedule, risk register, issue log, and change log.

### Tracking and reporting on all project funds that supports design services.

### Integrating all planning products into the design phase to ensure alignment.

### Facilitating design charrettes, design review meetings, and constructability reviews.

### Verifying all design deliverables meet project requirements and quality standards, and are delivered within the baselined scope, schedule, and cost.

### Providing recommendations for project acquisition and execution plans to ensure selection of the best contract vehicle, timely completion of all phases of the work within available funds and authorized scope.

### Developing technical evaluation factors to be used in the Government’s source selection plan.

### Coordinating assembly of final plans, specifications/RFP, and addenda for Government review and approval.

### Validating that Design Quality Assurance has been performed prior to award.

## CONSTRUCTION PHASE

### Coordinating and leading the internal Contract Turnover Meeting post-award.

### Coordinating the Post-Award Kick-Off (PAK) Meeting with the CM-COR and the construction contractor.

### Documenting and distribute meeting minutes for all project meetings.

### Facilitating all project governance meetings (project/senior/executive level).

### Conducting high-level briefs to top military and/or civilian personnel in support of Project Governance.

### Providing financial tracking for all project funds including contingency funds.

### Monitoring and report on the overall project schedule milestones against the established baseline in collaboration with the CM-COR.

### Providing project management support for Post-Construction Contract Award Services (PCAS) for technical support during construction.

### Providing project management support for all contracts for Collateral Equipment (FF&E, AV, etc.) and other supporting services. The coordination of Furniture, Fixtures, and Equipment (FF&E) will be performed as directed by the Government on a per-task-order basis.

### Coordinating and reporting on the performance of Acceptance Testing for critical systems.

### Coordinating and reporting on the completion of Cybersecurity Commissioning.

### Supporting the Government’s Contracting Officer’s Change Management functions including initial draft preparation of requests for proposals, proposal evaluations, pre & post negotiation memorandums, and contract modifications.  Provide coordination of technical evaluations and negotiations.  Provide tracking of potential changes and their status throughout the change management process.

## CLOSEOUT PHASE

### Facilitating the resolution of any outstanding claims, liquidated damages, or requests for equitable adjustment.

### Compiling and reviewing all final invoices and prepare contract closeout packages for Government approval. Perform all necessary data entry in financial and contract management systems (e.g., ERP, eContracts) to support the Government's final action to officially close the contracts.

### Requesting the change in eProjects Status to “Completed/Ready for Closeout”.

### Transfering Sustainability Documents, Low Impact Development (LID), PV interconnect agreements and other applicable documents to the Public Works Installation and upload to eProject Tabs.

### Providing support for the execution of financial reconciliation and reporting to ensure the project financial record is complete (CWE=OBL=ACC=PAID).

### Prepare and submit all necessary documentation for Contracting Officer review and approval to initiate the recapture and return of all unused project funds to the appropriate funding source.

### For MILCON projects, developing draft Interim DD 1354 (Transfer and Acceptance of Military Real Property) for Government approval, and coordinate distribution of the final DD 1354 to Base RPAO. Submit Final DD1354 in iNFADS.

### Drafting a final Post-Project Review and Lessons Learned documentation for Government review and approval and upload to the eProjects record.

### Preparing and submitting the formal request to the Government to change the eProjects Status from “Accepted” to "Closed."

# POST-AWARD SERVICES AND DELIVERABLES

The following services and deliverables are required on individual projects:

## CONSTRUCTION SITE VISITS AND INSPECTIONS

The CMa shall conduct construction site visits and inspections to verify construction progress and ensure construction contractor compliance with contract documents, specifications, approved submittals, safety regulations, and quality control plans.

The frequency of site visits and inspections will vary depending on the project phase, complexity, risk level, and specific requirements of the contract, as it will be dynamic and adjusted as needed based on project progress and emerging issues. Site visits should be frequent enough to ensure close monitoring and proactive identification of potential problems. Site visits shall be performed at a frequency necessary to effectively monitor the work and identify issues.  Inspector presence may be further identified in Task Order scopes. Responsibilities include:

### Conducting regular site walks to observe the progress of the work, identify potential problems, and ensure that the contractor is adhering to the contract documents and specifications.

### Construction Contractor Quality Control: Verifying that the Construction Contractor’s work meets the requirements of all applicable codes and regulations, the contract documents and approved submittals.

### Government Quality Assurance: Ensuring Construction Contractor’s Quality Control program is being implemented in accordance with the contract documents and the approved Quality Control Plan.

### Witnessing and verifying the testing of materials and equipment is conducted in accordance with contract documents.  Verify the calibration of testing equipment.  Ensure the Construction Contractor provides all testing required by the contract documents and maintains required Testing Plan and Log.

### Identifying and documenting any deficiencies or non-conformances in the work. Notify Construction Contractor of deficiencies and verify that corrective actions have been taken.  When deficiencies are not quickly corrected, issue Non-Compliance Notices (NCNs).  Track NCNs along with Construction Contractor responses and resolutions.

### Review Construction Contractor’s progress to ensure adherence to the project schedule.  Notify Construction Contractor, CM-COR, and other stakeholders as applicable when work is not proceeding in accordance with the project schedule.

### Ensuring Construction Contractor is maintaining up-to-date As-Built Drawings on site and in accordance with contract documents.

### The Construction Contractor is responsible for overall safety management.  The CMa is responsible for ensuring Construction Contractor is in compliance with the contract documents for safety including verification of Construction Contractor’s Site Safety and Health Officer (SSHO) has the required qualifications, is on site at all times work is being performed, and is meeting their responsibilities as required by the contract documents, the USACE EM385-1-1, OSHA Regulations and the Construction Contractor’s approved Accident Prevention Plan. Per NAVFAC Safety Specifications, everyone on a job site, including the CMa, is empowered to stop work when an imminent danger is evident.

## SUBMITTAL PROCESS

CMa shall manage the overall submittal process to ensure timely communication of project requirements and acceptability of Construction Contractor’s proposed products and installation procedures.  Responsibilities include:

### Reviewing all submittals to ensure that preconstruction, design, and technical submittals, materials, equipment, and methods proposed by the Construction Contractor conform to the contract documents (drawings, specifications, and other requirements), applicable codes, and standards; and to verify that the Construction Contractor fully understands the design intent.

### Coordinating the distribution of submittals to DOR and other applicable reviewers and stakeholders for their review and approvals.

### Compiling and coordinating all reviewer comments to submittals and delivering to CM-COR with clear recommendations for disposition.

### Sending reviewed submittals to appropriate stakeholders for their information and coordination.

### Reviewing the Construction Contractor’s submittal registers and logs to ensure that all required submittals are properly tracked and resolved. Ensure reviews by DOR and other applicable reviewers are expeditious to prevent delays to the project.

## REQUEST FOR INFORMATION (RFI) PROCESS

Coordinate reviews and responses to all requests for information (RFI) to efficiently manage and resolve questions, ambiguities, or conflicts in the contract documents (drawings, specifications, etc.) that arise during the construction process, ensuring clarity, avoiding delays, and maintaining the integrity of the design intent.  Responsibilities include:

### Conducting initial technical reviews of RFIs to ensure that RFIs are necessary and include essential information required for review.  Ensure Construction Contractor’s proposed solutions are technically sound and comply with specifications, codes, and industry standards.

### Coordinating the RFI review and response process with the DOR, the Construction Contractor, the Supported Command, CM-COR, and all related stakeholders.

### Assessing the potential impact of RFIs on the project schedule and budget and advise the CM-COR.

### Coordinating and compiling proposed RFI responses from all reviewers including CMa’s proposed response and delivering to CM-COR with clear recommendations for disposition.

### Reviewing the Construction Contractor’s RFI log, ensuring that all RFIs are properly tracked and resolved in a timely manner.

### RFI responses must not direct work that is outside the contract requirements.  If the CMa concludes that the appropriate RFI response will require a contract modification, the RFI may be answered; however, it must clarify that an RFP will be issued for the additional work.

## SCHEDULE REVIEW AND ANALYSIS

CMa shall provide overall project schedule management, identifying potential delays, assessing the impact of changes, and recommending corrective actions to the CM-COR to ensure timely project completion. This includes baseline schedules, regularly updated schedules, recovery schedules and look ahead schedules. The goal is to maintain schedule adherence, minimize disruptions, and provide early warnings of potential problems. Responsibilities include:

### Ensuring that the Construction Contractor's Baseline and Progress schedules comply with the contract requirements.

### Review Construction Contractor’s schedule, FRAGNET, and Time Impact Analysis (TIA) submitted with contract modification proposals and provide detailed analysis to the Government regarding schedule impact of the proposed changes or claims.

### Communicating schedule status with the CM-COR and other applicable stakeholders for project coordination and resolution of potential problems.

### Reviewing and analyzing Construction Contractor’s 3-Week Look Ahead schedules to ensure they are aligned with the Project Schedule and to facilitate coordination with affected stakeholders.

### The CMa shall use Primavera P6 scheduling software to review and analyze Primavera P6 schedules submitted by the Construction Contractor.

## COST ESTIMATING

CMa should develop accurate and reliable cost estimates for various project phases, proposed changes, value engineering, variations, and other cost-related activities. These estimates are used for budgeting, funding requests, and contract negotiations. The goal is to provide realistic cost projections that support sound financial management and informed decision-making and to provide technical expertise and cost data for specific trades or systems, ensuring that cost estimates accurately reflect the technical requirements of the project.

The CMa shall use USACE MII estimating software or compatible for cost estimating services

## TECHNICAL ANALYSIS

CMa shall provide an objective and thorough evaluation of the technical aspects of Construction Contractor proposals, ensuring the proposed solutions meet the project requirements and are technically feasible. The goal is to support a fair and informed negotiation of proposed changes or resolution of claims.  Responsibilities include:

### Evaluation of the Construction Contractor’s proposed scope of work, methods, techniques, and procedures for proposed changes to ensure the additional costs and/or time are fair and reasonable and do not represent work that is already in their contract.

### Assessment of the technical soundness and completeness of the contractor's proposed design (if Design/Build) and demonstrates a full understanding of the work and complies with the contract documents and Uniform Guide Specifications.

### In-depth review of Construction Contractor’s proposed costs and time to ensure they are fair and reasonable and are comparable to Government’s estimates and/or CMa estimates.

### Prepare Technical Analysis and assist Contracting Officer and CM-COR with preparation of Pre-Negotiation and Post-Negotiation Memos.

### Assist Contracting Officer and CM-COR with negotiation of proposed changes with the Construction Contractor.

## REVIEW OF PAYMENT REQUESTS

CMa shall provide thorough review of Requests for Payment submitted by designers, construction contractors, commissioning agent, and providers of other services that have contracted with the Government for the Task Order Projects.  CMa shall coordinate and discuss with contractors their draft versions of payment requests and recommend changes for accuracy when appropriate.  When consensus is reached, CMa shall make recommendations to the CM-COR for payment of final versions of invoices.    Reviews shall be comprehensive and include:

### Verification payment requests comply with requirements in the specifications and include all required attachments.

### Review of invoice itemization for correctness and ensure requested percentage progress does not exceed actual progress for each line item.

### Ensure payment requests for mobilization, overhead, stored materials, and retainage when applicable are in accordance with contract requirements.

### Physical inspection of work and meetings with contractors to review and discuss progress.

## SYSTEMS COMMISSIONING

Commissioning is a systematic, quality-focused process ensuring that facilities and systems are designed, installed, tested, and operated to meet the Government’s Project Requirements. Commissioning is led by a third-party Commissioning Agent contracted with either the Construction Contractor or the Government depending on how it is specified in the contract documents.   The Construction Contractor is required to coordinate the commissioning of building systems as required by the specifications.  The CMa shall ensure the Construction Contractor is meeting project requirements and provide additional coordination as required with the CM-COR, the Supported Command, building occupants and other stakeholders.   Systems requiring Commissioning will be as specified in the contract documents – typically are mechanical systems, special lighting systems, special laboratory and shop equipment and cyber security systems.

## CRITICAL SYSTEMS ACCEPTANCE

Critical Systems Acceptance is distinctly separate from Commissioning.  CMa shall provide the required technical experts as defined in the Labor Categories Table to provide Critical Systems Acceptance and all necessary coordination with all stakeholders.  Critical Systems Acceptance is an end-to-end process that begins at receipt of initial design submittals, beginning with design activities whether Design-Build (DB) Request for Proposal (RFP) or Design-Bid-Build (DBB), and is completed with final performance testing of the system prior to beneficial occupancy. NAVFAC has identified the following critical systems requiring acceptance:

## a. Heating, Ventilation, & Air-Conditioning (HVAC) Systems.

#### Ductwork Air Leakage and Tests of all, or otherwise required, air moving systems.

#### Testing, Adjusting, and Balancing of all, or otherwise required, HVAC systems.

#### Performance Verification Testing of all, or otherwise required, energy consuming systems and HVAC control systems.

#### Verification that control system cybersecurity requirements of Unified Facilities Guide Specifications (UFGS) 25 05 11 are met.

## b. Electrical Systems.

#### Single operation generator sets.

#### Automatic transfer switches.

#### Uninterruptible power supplies.

#### 400-hertz solid state frequency converters.

#### 270DC solid state frequency converters.

#### Cathodic protection.

#### Transformers.

## c. Fire Protection/Life Safety Systems.

#### Sprinkler systems (wet pipe, dry pipe, pre-action, deluge, water spray, and water mist).

#### Fire pumps and controllers.

#### Evacuation/notification detection and releasing systems.

#### Base-wide fire-reporting systems.

#### Gaseous systems.

#### Wet and dry chemical systems.

#### Foam systems.

#### Smoke control/smoke exhaust systems.

#### Emergency lighting and egress marking.

#### Spray Applied Fireproofing.

#### Opening protection (firestopping/fire dampers/fire doors)

## d. Building Enclosure and Roofing Systems.

e. Other Building Systems approved by LCO

#### Boilers

## .  (1) Vertical Transportation Equipment

#### Elevators

#### Escalators

#### Dumbwaiters

#### Handicap Lifts

#### Material Lifts

Responsibilities include:

### Review design documents throughout design process to ensure design meets the Government’s requirements.

### Visual inspection of the installed systems to verify compliance with drawings, specifications, and applicable codes.

### Witness a series of tests to verify that the systems function as intended under various operating conditions.

### Verify that Commissioning has been completed in accordance with the contract documents.

### Identify deficiencies and notify the Construction Contractor and CM-COR to ensure the deficiencies are corrected in a timely manner.

### Re-inspect and re-test the systems to verify that the deficiencies have been corrected, if applicable.

### Review all documentation related to the systems, including as-built drawings, systems acceptance and commissioning plans, commissioning reports, O&M manuals, test reports, deficiency reports, and training materials.

### Ensure Construction Contractor provides training to the owner's personnel on the operation and maintenance of the systems.

### Recommend acceptance of the systems to the CM-COR.

## STAKEHOLDER COMMUNICATION AND COORDINATION

CMa shall establish and maintain clear, consistent, and timely communication among all project stakeholders, including the Construction Contractor, DOR, CM-CO, Supported Command, and all other interested parties. The goal is to ensure that all stakeholders are informed about project progress, issues, and decisions, and that they can provide input and participate in the project. Effective communication and coordination are essential for fostering collaboration, resolving conflicts, and achieving project success.   The CMa shall be the central point of contact for all project-related communications.  If the CMa delegates communications to others, they shall ensure they maintain an awareness of all project-related communications.   CMa must keep CM-COR informed of all communications with the Supported Command and follow any additional guidance from CM-COR in this regard. Responsibilities include:

### The CMa shall develop a communication plan that outlines the communication methods, frequency, and responsibilities for each stakeholder group. The CM-COR will review and approve the communication plan.

### The CMa is responsible for communicating schedule progress and providing updates on ongoing and upcoming definable features of work being performed as well as any schedule conflicts or delays.

### The CMa is responsible for communicating design progress and providing updates during design phase, coordinating with design team to ensure project schedule is maintained and that the design of different systems and components are compatible and integrated.

### The CMa is responsible for coordinating all project related issues including but not limited to temporary facilities, project signage and barricades, occupancy plans, phasing, permits, environmental requirements, utilities, weather preparedness, off-hours work requests, outages, Construction Contractor laydown, parking, jobsite rules, worker conduct, stakeholder questions and complaints, etc.

### Project Governance: The CMa is responsible for administering Project Governance in accordance with NAVFAC Instruction 11013.41B.  The CMa’s responsibilities include the following depending on the project’s complexity score:

#### Establish and maintain Government-approved Project Management Plan, Project Charter and Stakeholder Resister

#### Create and implement Government-approved Risk Management Plan including Risk Register and Risk Matrices.

#### Create and implement Change Management Plan including tracking of all proposed changes and mods, their status and impact on project cost and completion date.   Change Management Plan shall include CMa’s responsibility to expedite the change process.

#### Create and maintain Escalation Matrix. CMa shall facilitate conflict and dispute resolution

#### Establish leadership teams; Project Leadership Team (PLT), Senior Leadership Team (SLT), and Executive Leadership Team (ELT) and facilitate their periodic meetings.

#### CMa shall ensure Formal Partnering or Informal Partnering is conducted in accordance with NAVFAC P-406 and dependent on which type of partnering is required by the project specifications.  If Formal Partnering is required, CMa shall coordinate and participate.   If Informal Partnering is required, CMa shall lead the partnering program in conjunction with the Construction Contractor’s project leader.

### Facilitate project meetings, ensuring that all stakeholders have the opportunity to participate and provide input.  CMa shall coordinate and prepare meeting agenda and minutes for all contractually required meetings including but not limited to:

#### Pre-Construction Meetings

#### Post-Award Kick-off Meetings

#### Partnering Meetings (informal and formal)

#### Coordination and Mutual Understanding Meetings

#### Preliminary Scheduling Meetings

#### O&M Manual Coordination Meetings

#### Quality Control Meetings (administered by Construction Contractor, CMa to participate)

#### Pre-Roofing Conference

#### eOMSI Coordination Meeting

#### Pre-DALT TABS Meeting (administered by Construction Contractor, CMa to participate)

#### Commissioning Coordination Meetings (administered by Commissioning Contractor, CMa to participate)

#### NAVFAC Red Zone Meetings

#### Warranty Meetings

#### ELT, PLT SLT Meetings

#### The CMa shall maintain strict confidentiality regarding all project information and shall not disclose any sensitive, confidential, potentially controversial, or unfavorable information. The CMa shall institute procedures acceptable to the Contracting Officer and fully comply with the Government’s procedures for maintaining the confidentiality of information and maintenance of Federal procurement integrity standards of performance. All CMa personnel will be required to maintain the security and confidentiality of all information that directly or indirectly comes into their possession or attention on a strict operational need-to-know basis. The CMa’s management and supervisory personnel will not seek, receive or otherwise have access to operational information or data that is being utilized by its employees in the performance of this contract where other companies, firms or contractors are involved or where such information is confidential to the interests of the U.S. Government and/or its clients and customers. All information requests from the general public or news media must be immediately forwarded to the CM-COR for review and appropriate action.

#### The CMa shall use NAVFAC’s eCMS program for all project correspondence, submittal process, RFI process, and storage of project documentation.

At no time shall the CMa provide direction to the Construction Contractor or any parties contracted directly with the Government to perform work outside the requirements of contract documents.   Only the Government Contracting Officer can direct changes to Government contracts.

## CONSTRUCTION MANAGEMENT REPORTING

The CMa shall submit to CM-COR a Construction Management Report documenting all aspects of project status on a monthly basis for as long as the project is active.   Report shall include:

### Cost Report showing original contract amount, current contract amount, projected contract amount, pending changes and modifications.

### Schedule Report indicating original Contract Completion Date (CCD), current CCD, and projected CCD.

### Summary of significant activities currently proceeding, milestones recently achieved, or activities starting soon.

### Summary of outstanding issues, key coordination activities, and action items with assigned responsibilities and due dates.

### Summary of current risks and opportunities.

### Summary of jobsite inspections, quality issues, safety issues, coordination issues, occupancy issues, etc.

### Summary of outstanding Non-Compliance Notices (NCNs), Letters of Concern, deficiencies, and corrective actions.

### Status of critical submittals and RFIs and their potential impact on schedule and cost.

### Monthly reporting of CMa’s proposed metrics and NAVFAC Key Performance Indicators (KPIs).  KPIs shall include average RFI response time, average Submittal response time, preconstruction milestone data, NCNs data, schedule growth percentages, cost growth percentages, and average PC/Mod turnaround times.

### At 75% completion, report shall include NAVFAC Red Zone POAM and summary of project close-out status.

## CONSTRUCTION CONTRACTOR ACCESS COORDINATION

CMa shall establish and maintain a secure, efficient, and compliant process for managing Construction Contractor’s and all subcontractor’s access to military installations. This includes coordinating background checks, issuing credentials, tracking personnel, and ensuring compliance with all applicable security regulations. This may also involve coordinating with site specific installation security offices. The goal is to protect the safety and security of the installation while minimizing disruption to construction activities. Responsibilities include:

### Obtaining a list of all Construction Contractor personnel who require access to the installation with appropriate supporting documentation to support the enrollment in the Defense Biometric Identification System (DBIDS).

### Coordinate DBIDS enrollment and renewals with the installation security office. Ensuring that all Construction Contractor personnel complete the required background checks and security training.

### Ensuring that all Construction Contractor personnel comply with all access control procedures.

### Serve as the primary point of contact with the installation security office.

### Reporting any security incidents or concerns to the CM-COR.

### Monitoring compliance with all applicable security regulations.

### Termination of access credentials upon project completion.

## PROJECT CLOSE-OUT

CMa shall manage the Project Close-Out Process in accordance with contract documents and NAVFAC policies and procedures:

### CMa shall ensure Construction Contractor provides timely submittal of all close-out documents including but not limited to eOMSI, Facility Data Workbook, Sustainability eNotebook, O&Ms, As-Built Drawings, Record Drawings, Warranties, and DD Form 1354’s.   CMa shall review all close-out documents to ensure correctness and contract compliance before forwarding them to the Government.

### CMa shall ensure closeout items required in eProjects are complete (i.e. Low Impact Development and Sustainability Data)

### CMa shall manage the NAVFAC Red Zone (NRZ) process to comply with contract documents including coordination with all stakeholders, preparation of NRZ POAM and Checklist, and coordination of critical NRZ activities.

### CMa shall manage the Completion Inspections process including Construction Contractor compliance with Punch-Out Inspection requirements, participating in Pre-Final and Final Inspections and providing all necessary coordination with stakeholders.   CMa shall ensure all deficiencies have been corrected prior to recommending acceptance and final payment.

### CMa shall ensure Construction Contractor compliance with contract documents for Warranty Management including submittals, warranty tags, and warranty follow-up inspections.

### CMa shall ensure Construction Contractor compliance with contract documents with respect to training of building occupants and provision of spare parts.

### CMa shall track requirements for final financial reconciliation and make recommendations to the CM-COR.

### The CMa shall ensure the complete project record comprising of all documents and communications is transferred to the Government at project completion.  CMa shall provide assistance to the CM-COR with archiving of final record documents for the project.

### CMa shall prepare draft narratives and ratings for the Contractor Performance Assessment Reporting System (CPARS) in accordance with the Government template and submit to the Government.

### CMa shall provide assistance with occupancy support including coordination of move-in activities and initial occupancy issues.

### CMa shall provide latent defect investigation including documenting and coordinating resolution of latent defects that appear after project completion, but within the liability period.

# CONSTRUCTION MANAGER AS ADVISOR - ADDITIONAL SERVICES

When required to provide additional support, the Government may authorize Additional Services such as those listed below. All such work must be authorized in advance by the Contracting Officer. Additional Services will be ordered via issuance of a modification to a task order or a new task order against this contract.

## CLAIMS SERVICES

The CMa must take the initiative and act to mitigate circumstances that could lead to claims, attempt to resolve conflicts promptly, and keep the Government advised of any potential disputes. A claim does not arise solely upon the occurrence of a dispute or controversy. For definition purposes, Claims Services apply to handling disputed matters once a Construction Contractor has made formal written demand for payment or other relief under the contract by submitting a formal Request for Equitable Adjustment (REA) to the Contracting Officer for decision in accordance with the disputes provision of the construction contract. In relation to Claims Services, the CMa shall review disputes and claims submitted by Construction Contractor(s) and provide the following assistance to the Government:

### Furnishing reports with supporting information necessary to resolve disputes or defend against the claims.

### Participation in meetings or negotiations with claimants.

### Preparation of cost estimates.

### Preparation of findings of fact and any other documentation required by the Contracting Officer.

### Evaluate Time Impact Analysis (TIA) as needed.

## MANAGEMENT OF GOVERNMENT FURNISHED EQUIPMENT (GFE)

Coordination of Government Furnished Equipment (GFE) in relation to the project.  GFE can be Government Furnished/Contractor Installed (GFCI) or Government Furnished/Government Installed (GFGI). Examples include furniture, cubicles, access controls, IT equipment, A/V equipment, lab equipment, shop equipment, kitchen equipment, etc.  CMa responsibilities include reviewing compatibility during design, coordinating dimensions and utility requirements, coordinating changes, coordinating deliveries, monitoring and communicating schedule and submittals amongst the Construction Contractor, the Supported Command, the GFE supplier and/or installer, and all other related parties.

## SPECIAL CONSULTING SERVICES AND DELIVERABLES

### Special consultants or special inspection services, such as assessments of hazardous materials, a Certified Industrial Hygienist to monitor removal of hazardous material.

### Unique services provided within six months after final settlement of the construction contract with the exception of Claims Services.

### Special studies and updates to prior studies. Other specialized services as may be requested by the Contracting Officer, such as updates to master or environmental plans, interior space planning, existing site surveys, site models, etc.

### Certification services of trade societies, institutes, organizations, etc.

### Provision of special plant facilities and equipment such as trailers, unusual testing apparatuses, etc.

### Provide support for NAVFAC briefings to other Department of the Navy (DON) agencies, Federal Government agencies, etc. as required.

### Perform surveys of the project site when required.

# CONSTRUCTION MANAGER AS ADVISOR – PROGRAM MANAGEMENT SERVICES (PgM)

When required to provide Program Management Support, the Government may authorize Program Management Services as listed below.  All such work must be authorized in advance by the Contracting Officer. Program Management Services will be ordered via issuance of a task order against this contract. The CMa shall provide expert-level Program Management Services for the execution of large, complex, and mission-critical capital improvement programs within the NAVFAC AOR to ensure the successful lifecycle management of multiple interdependent projects, align with strategic objectives, and deliver facilities programs in an efficient and fiscally responsible manner.

The CMa shall provide comprehensive program management expertise and support services across the full program lifecycle. The CMa's primary role is to serve as an expert advisor to the Government Program Manager. The CMa shall furnish the intellectual and professional capability to integrate and manage the technical, financial, logistical, and administrative aspects of assigned programs to achieve specified cost, schedule, and performance objectives. The CMa shall have no authority to make final decisions on behalf of the Government but shall provide data, analyses, and recommendations to support Government decision-making.

## PRE-AWARD PHASE: PROGRAM INITIATION, PLANNING, AND PROCUREMENT

### Program Planning & Integration

#### Develop and maintain a Program Management Plan (PgMP) for Government approval in accordance with DoD and NAVFAC guidance, detailing governance structures, Project Charter, integrated schedules, risk management approaches, and communication plans.

#### Develop for Government approval and manage a Work Breakdown Structure (WBS) and an Integrated Master Schedule (IMS) that identifies critical paths, dependencies, and resource constraints across all constituent projects and throughout the post-award phase.

#### Facilitate the development and review of DD Form 1391s (Military Construction Product Data), Certificates of Compliance, Planning Charrette Reports, NEPA planning documentation, Business Case Analyses (BCA) and Analysis of Alternatives (AoA) to support program-level decisions.

#### Organize, facilitate, and document planning meetings with Government Program Manager, Supported Command Program Managers, Senior Advisory Group (SAG) and Senior Executive Review Group (SERG).

### Requirements & Scope Management

#### Provide expert analysis to support the Government in defining and validating program requirements, ensuring alignment with mission objectives and UFC standards.

#### Provide project feasibility studies to assess project viability including site selection and initial cost estimates.

#### Develop a comprehensive master plan that outlines the entire scope of the program.

#### Develop and manage Requirements Documents and Requirements Traceability Matrix (RTM) to track requirements from conception through final delivery.

### Cost, Budget, and Financial Management:

#### Develop, maintain, and analyze Program Life Cycle Cost Estimates (LCCEs), Program Office Estimates (POEs), Cost Schedule Risk Analyses (CSRA) and Current Working Estimates (CWE).

#### Support the Government in all phases of the Planning, Programming, Budgeting, and Execution (PPBE) process, including the development of budget exhibits and justification materials. Provide support for Above and Below Threshold Reprogramming and cost variations

#### Track funding appropriation, allocation, commitment, and obligation status and provide variance analysis reports.

### Acquisition & Procurement Support:

#### Support the Government's Contracting Officer and Program Manager in the development of Acquisition Strategies, Acquisition Plans, and other pre-solicitation documentation in accordance with FAR Part 7 and DFARS Part 207.

#### Provide technical input for the creation of Statements of Work (SOW), Performance Work Statements (PWS), and Contract Data Requirements Lists (CDRLs). The CMa shall not draft these documents in their entirety but shall provide analysis and recommendations.

## POST-AWARD PHASE: PROGRAM EXECUTION, MONITORING, AND CONTROL

### Performance Monitoring & Reporting:

#### Implement and manage an Earned Value Management System (EVMS) compliant with EIA-748 standards. The CMa shall analyze CPI, SPI, and other EVM metrics to provide the Government with assessments of program health and forecast Estimates at Completion (EACs).

#### Establish and track program-level Key Performance Indicators (KPIs) and prepare monthly Program Management Reviews (PMRs) and executive-level briefings.

### Risk, Issue, and Opportunity Management:

#### Assist with establishment of a Program Risk Management Board. The CMa shall maintain the program's Risk Register, conduct qualitative and quantitative risk analyses, and develop risk mitigation and handling strategies in accordance with the DoD Risk, Issue, and Opportunity Management Guide.

### Stakeholder and Communications Management:

#### Execute the Program Communication Plan, ensuring timely and effective communication with all stakeholders, including higher headquarters, adjacent commands, and executing Advisors.

#### Organize, facilitate, and document planning meetings with Government Program Manager, Supported Command Program Managers, Senior Advisory Group (SAG) and Senior Executive Review Group (SERG).

### Quality & Configuration Management:

#### Support the Government in overseeing Construction Contractor performance, including the review of submitted deliverables (CDRLs) for contractual and technical compliance for Government approval.

#### Coordinate the program's Configuration Management process, including the evaluation and drafting for Government approval Engineering Change Proposals (ECPs) and requests for deviation/waiver.

## PROGRAM CLOSEOUT PHASE

### Transition & Turnover:

#### Support the development and execution of plans for the transition of completed facilities and systems to the end-user, including facility activation and O&M planning.

#### Ensure all contractual obligations have been met and support the Contracting Officer in the contract closeout process per FAR Part 4.804.

### Lessons Learned & Final Reporting:

#### Develop and manage a lessons-learned repository for each Task Order, and for the overall contract.

#### Prepare a final Program Closeout Report detailing overall performance against cost, schedule, and performance baselines, and documenting best practices.

END OF SECTION C