## UFGS4288.txt
TITLE: |  |  |  | B60: PRODUCTION FACILITY REPAIRS - SIOP | [7 empty] | SUBMITTAL REGISTER
JOB NAME: |  |  |  | 1740579
LOCATION:
CONTRACT NO:
CONTRACTOR:
[9 empty] | CONTRACTOR SCHEDULE DATES |  |  | CONTRACTOR ACTION |  |  | APPROVING AUTHORITY
| (a) | (b) | (c) | (d) |  |  | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r)
Line | Activity # | Transmittal # | Specification Section | SD # | Submittal Description | Item Submitted | Paragraph # | Classification: GOVT or A/E Reviewer | Submit | Approval Needed By | Material Needed By | Action Code | Date Of Action | Date FWD to APPR / Auth Date RCD From CONTR | Date FWD To Other Revwr | Date RCD From Other Reviewer | Action Code | Date Of Action | Mailed To CONTR/ Date RCD From APPR Authority | Remarks
1 |  |  | 01 11 00.00 22 | 1 | Preconstruction Submittals | Work Sequencing and Preparation Plan | (e): 1.5; (f): G
2 |  |  | 01 11 00.00 22 | 1 | Preconstruction Submittals | Salvage Plan | (e): 1.12; (f): G
3 |  |  | 01 11 00.00 22 | 11 | Closeout Submittals | RZ Checklist | (e): 1.13; (f): G
4 |  |  | 01 14 00.00 22 | 1 | Preconstruction Submittals | List of Contact Personnel | (e): 1.5.1.1; (f): G
5 |  |  | 01 14 00.00 22 | 1 | Preconstruction Submittals | Outage Plan | (e): 1.5.5; (f): G
6 |  |  | 01 14 00.00 22 | 1 | Preconstruction Submittals | Tier 1 Infrastructure Coordination Drawings | (e): 1.1; (f): G
7 |  |  | 01 20 00.00 22 | 1 | Preconstruction Submittals | Earned Value Report | (e): 1.3; (f): G
8 |  |  | 01 20 00.00 22 | 1 | Preconstruction Submittals | Accounting Summary of Unit Cost Quantities | (e): 1.7.1; (f): G
9 |  |  | 01 30 00.00 22 | 1 | Preconstruction Submittals | Facility Turnover Planning Meeting Agenda and Red Zone (RZ) Checklist-POAM | (e): 1.16.1; (f): G
10 |  |  | 01 30 00.00 22 | 1 | Preconstruction Submittals | NAVFAC PWD ME Internal Service Requirements List | (e): 1.16.3; (f): G
11 |  |  | 01 30 00.00 22 | 1 | Preconstruction Submittals | Archaeological Coordination Meeting | (e): 1.13; (f): G
12 |  |  | 01 30 00.00 22 | 1 | Preconstruction Submittals | View Location Map | (e): 1.3
13 |  |  | 01 30 00.00 22 | 1 | Preconstruction Submittals | Progress and Completion Pictures | (e): 1.4
14 |  |  | 01 30 10.00 22 | 2 | Shop Drawings | Coordination Drawings | (e): 1.4.1; (f): G
15 |  |  | 01 31 23.13 20 | 1 | Preconstruction Submittals | List of Contractor's Personnel | (e): 1.4.2; (f): G
16 |  |  | 01 32 17.00 20 | 1 | Preconstruction Submittals | Baseline NAS | (e): 1.2.2; (f): G
17 |  |  | 01 32 17.00 20 | 1 | Preconstruction Submittals | Designated Project Scheduler | (e): 1.9; (f): G
18 |  |  | 01 32 17.00 20 | 1 | Preconstruction Submittals | Three-Week Look Ahead Schedule | (e): 1.3; (f): G
19 |  |  | 01 32 17.00 20 | 1 | Preconstruction Submittals | Outage Schedule | (e): 1.4.3; (f): G
20 |  |  | 01 32 17.00 20 | 7 | Certificates | Weekly Look Ahead Schedule | (e): 1.3.1
21 |  |  | 01 32 17.00 20 | 7 | Certificates | Monthly Network Analysis Updates | (e): 1.4.1; (f): G
22 |  |  | 01 32 17.00 20 | 11 | Closeout Submittals | As-Built Schedule | (e): 1.4.2; (f): G
23 |  |  | 01 33 00.00 22 | 1 | Preconstruction Submittals | Submittal Register | (e): 1.9; (f): G
24 |  |  | 01 33 10.00 22 | 1 | Preconstruction Submittals | Procurement Substitution Request - Pre-Award (Bidding) Period | (e): 1.6; (f): G
25 |  |  | 01 33 10.00 22 | 1 | Preconstruction Submittals | Substitution Request - Post Award | (e): 1.7; (f): G
26 |  |  | 01 33 29.00 22 | 1 | Preconstruction Submittals | Preliminary High Performance and Sustainable Building Checklist | (e): 1.5.3.2; (f): G
27 |  |  | 01 33 29.00 22 | 1 | Preconstruction Submittals | Sustainability Action Plan | (e): 1.4.1; (f): G
28 |  |  | 01 33 29.00 22 | 1 | Preconstruction Submittals | Preliminary Sustainability eNotebook | (e): 1.5.3.2; (f): G
29 |  |  | 01 33 29.00 22 | 11 | Closeout Submittals | Final High Performance and Sustainable Building Checklist | (e): 1.5.3.2; (f): G
30 |  |  | 01 33 29.00 22 | 11 | Closeout Submittals | Final Sustainability eNotebook | (e): 1.5.3.2; (f): G
31 |  |  | 01 33 29.00 22 | 11 | Closeout Submittals | Amended Final Sustainability eNotebook | (e): 1.5.3.2; (f): G
32 |  |  | 01 33 29.00 22 | 11 | Closeout Submittals | Amended Final High Performance and Sustainable Building Checklist | (e): 1.5.3.2; (f): G
33 |  |  | 01 33 29.00 22 | 11 | Closeout Submittals | Third Party Certification Certificate, Assessment, or Validation and Compliance Report | bar: (f)
34 |  |  | 01 35 26.00 22 | 1 | Preconstruction Submittals | Accident Prevention Plan (APP) | bar: (f)
35 |  |  | 01 35 26.00 22 | 1 | Preconstruction Submittals | APP - Construction | (e): 1.9.1; (f): G
36 |  |  | 01 35 26.00 22 | 1 | Preconstruction Submittals | Dive Operations Plan | bar: (f)
37 |  |  | 01 35 26.00 22 | 1 | Preconstruction Submittals | Indoor Air Quality (IAQ) Management Plan | (e): 1.18; (f): G
38 |  |  | 01 35 26.00 22 | 6 | Test Reports | Monthly Exposure Reports | (e): 1.5; (f): G
39 |  |  | 01 35 26.00 22 | 6 | Test Reports | Notifications and Reports | (e): 1.14; (f): G
40 |  |  | 01 35 26.00 22 | 6 | Test Reports | Accident Reports | (e): 1.14.2; (f): G
41 |  |  | 01 35 26.00 22 | 6 | Test Reports | LHE Inspection Reports | (e): 1.14.3; (f): G
42 |  |  | 01 35 26.00 22 | 7 | Certificates | Contractor Safety Self-Evaluation Checklist | (e): 1.6; (f): G
43 |  |  | 01 35 26.00 22 | 7 | Certificates | Crane Operators/Riggers | (e): 1.8.7; (f): G
44 |  |  | 01 35 26.00 22 | 7 | Certificates | Standard Lift Plan | (e): 1.9.3.2; (f): G
45 |  |  | 01 35 26.00 22 | 7 | Certificates | Standard Lift Plan | (e): 1.14.4; (f): G
46 |  |  | 01 35 26.00 22 | 7 | Certificates | Critical Lift Plan | (e): 1.9.3.3; (f): G
47 |  |  | 01 35 26.00 22 | 7 | Certificates | Naval Architecture Analysis | (e): 1.9.3.4; (f): G
48 |  |  | 01 35 26.00 22 | 7 | Certificates | Activity Hazard Analysis (AHA) | (e): 1.1; (f): G
49 |  |  | 01 35 26.00 22 | 7 | Certificates | Confined Space Entry Permit | (e): 1.11.1; (f): G
50 |  |  | 01 35 26.00 22 | 7 | Certificates | Hot Work Permit | (e): 1.11.1; (f): G
51 |  |  | 01 35 26.00 22 | 7 | Certificates | Hot Work Permit | (e): 1.15; (f): G
52 |  |  | 01 35 26.00 22 | 7 | Certificates | Certificate of Compliance | (e): 1.14.4; (f): G
53 |  |  | 01 35 26.00 22 | 7 | Certificates | Third Party Certification of Floating Cranes and Barge-Mounted Mobile Cranes | (e): 1.14.5; (f): G
54 |  |  | 01 35 26.00 22 | 7 | Certificates | License Certificates | (e): 1.16; (f): G
55 |  |  | 01 35 26.00 22 | 7 | Certificates | Radiography Operation Planning Work Sheet | (e): 1.16.1; (f): G
56 |  |  | 01 44 00.00 22 | 1 | Preconstruction Submittals | Archaeologist Qualifications | (e): 1.4; (f): G
57 |  |  | 01 44 00.00 22 | 1 | Preconstruction Submittals | Archaeological Coordinator | (e): 1.5
58 |  |  | 01 44 00.00 22 | 1 | Preconstruction Submittals | Archaeological Monitoring Plan | (e): 1.6; (f): G
59 |  |  | 01 44 00.00 22 | 6 | Test Reports | Archaeological Resource Report | (e): 3.1; (f): G
60 |  |  | 01 44 00.00 22 | 6 | Test Reports | Archaeological Resource Report | (e): 3.2.3; (f): G
61 |  |  | 01 44 00.00 22 | 6 | Test Reports | Archaeological Monitoring Report - Monthly Progress Reports | (e): 3.2.2; (f): G
62 |  |  | 01 44 00.00 22 | 6 | Test Reports | Archaeological Monitoring Report - Draft | (e): 3.2.2; (f): G
63 |  |  | 01 44 00.00 22 | 6 | Test Reports | Archaeological Monitoring Report - Final Draft | (e): 3.2.2; (f): G
64 |  |  | 01 44 00.00 22 | 6 | Test Reports | Archaeological Monitoring Report - Final | (e): 3.2.2; (f): G
65 |  |  | 01 44 00.00 22 | 6 | Test Reports | Curated Artifacts | (e): 3.3; (f): G
66 |  |  | 01 45 00.00 22 | 1 | Preconstruction Submittals | Contractor Quality Control (CQC) Plan | (e): 1.5.2; (f): G
67 |  |  | 01 45 00.00 22 | 6 | Test Reports | Verification Statement | (e): 1.13.3
68 |  |  | 01 45 00.00 22 | 7 | Certificates | Certificate Of Readiness | (e): 1.6.5.1
69 |  |  | 01 45 35.00 22 | 1 | Preconstruction Submittals | SIOR Letter of Acceptance | (e): 3.1.1; (f): G
70 |  |  | 01 45 35.00 22 | 1 | Preconstruction Submittals | Project Manual | (e): 3.1.1; (f): G
71 |  |  | 01 45 35.00 22 | 1 | Preconstruction Submittals | Written NDT Practices | (e): 3.1.1
72 |  |  | 01 45 35.00 22 | 1 | Preconstruction Submittals | Written NDT Practices | (e): 3.1.3
73 |  |  | 01 45 35.00 22 | 6 | Test Reports | Special Inspection Daily Reports | (e): 3.1.1; (f): G
74 |  |  | 01 45 35.00 22 | 6 | Test Reports | Special Inspection Daily Reports | (e): 3.1.2; (f): G
75 |  |  | 01 45 35.00 22 | 6 | Test Reports | Special Inspection Daily Reports | (e): 3.1.3; (f): G
76 |  |  | 01 45 35.00 22 | 6 | Test Reports | Special Inspection Daily Reports | (e): 3.1.3; (f): G
77 |  |  | 01 45 35.00 22 | 6 | Test Reports | Special Inspection Biweekly Reports | (e): 3.1.1; (f): G
78 |  |  | 01 45 35.00 22 | 6 | Test Reports | Special Inspection Biweekly Reports | (e): 3.1.2; (f): G
79 |  |  | 01 45 35.00 22 | 7 | Certificates | AISC Certified Steel Fabricator | (e): 2.1; (f): G
80 |  |  | 01 45 35.00 22 | 7 | Certificates | Certificate of Compliance | (e): 2.1; (f): G
81 |  |  | 01 45 35.00 22 | 7 | Certificates | Special Inspector of Record | bar: (f)
82 |  |  | 01 45 35.00 22 | 7 | Certificates | Special Inspector | (e): 1.5; (f): G
83 |  |  | 01 45 35.00 22 | 7 | Certificates | Qualification Records for Nondestructive Testing Technicians | (e): 3.1.1; (f): G
84 |  |  | 01 45 35.00 22 | 7 | Certificates | Qualification Records for Nondestructive Testing Technicians | (e): 3.1.3; (f): G
85 |  |  | 01 45 35.00 22 | 11 | Closeout Submittals | Interim Report | (e): 3.1.1; (f): G
86 |  |  | 01 45 35.00 22 | 11 | Closeout Submittals | Interim Report | (e): 3.1.3; (f): G
87 |  |  | 01 45 35.00 22 | 11 | Closeout Submittals | Comprehensive Final Report | (e): 3.1.1; (f): G
88 |  |  | 01 45 35.00 22 | 11 | Closeout Submittals | Final Report | (e): 3.1.3; (f): G
89 |  |  | 01 50 00.00 22 | 1 | Preconstruction Submittals | Construction Site Plan | (e): 1.3; (f): G
90 |  |  | 01 50 00.00 22 | 1 | Preconstruction Submittals | Traffic Control Plan | (e): 3.4.1; (f): G
91 |  |  | 01 50 00.00 22 | 1 | Preconstruction Submittals | Contractor Computer Cybersecurity Compliance Statements | (e): 1.6.1.4; (f): G
92 |  |  | 01 50 00.00 22 | 1 | Preconstruction Submittals | Contractor Temporary Network Cybersecurity Compliance Statements | (e): 1.6.6; (f): G
93 |  |  | 01 50 00.00 22 | 1 | Preconstruction Submittals | Employee Parking Plan | (e): 1.7; (f): G
94 |  |  | 01 50 00.00 22 | 3 | Product Data | Backflow Preventers | (e): 1.4; (f): G
95 |  |  | 01 50 00.00 22 | 6 | Test Reports | Backflow Preventer Tests | (e): 3.5; (f): G
96 |  |  | 01 50 00.00 22 | 7 | Certificates | Backflow Tester | (e): 1.4.1; (f): G
97 |  |  | 01 50 00.00 22 | 7 | Certificates | Backflow Preventers | (e): 1.4; (f): G
98 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Preconstruction Survey | (e): 1.5.1; (f): G
99 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Solid Waste Management Plan | (e): 3.4.1; (f): G
100 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Regulatory Notifications | (e): 1.5.2; (f): G
101 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Environmental Management Plan (EMP) | (e): 3.1; (f): G
102 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Dirt and Dust Control Plan | (e): 3.13.1; (f): G
103 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Contractor Hazardous Material Inventory Log | (e): 3.8.1; (f): G
104 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Stormwater Management/Erosion and Sedimentation Control Plan | (e): 3.2.1; (f): G
105 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Spill Prevention, Control, and Countermeasures (SPCC) Plan | (e): 3.1; (f): G
106 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Environmental Manager Qualifications | (e): 1.5.4; (f): G
107 |  |  | 01 57 19.00 22 | 1 | Preconstruction Submittals | Employee Training Records | (e): 1.5.5; (f): G
108 |  |  | 01 57 19.00 22 | 6 | Test Reports | Laboratory Analysis | (e): 3.12.4.2; (f): G
109 |  |  | 01 57 19.00 22 | 6 | Test Reports | Disposal Requirements | (e): 3.14.2; (f): G
110 |  |  | 01 57 19.00 22 | 6 | Test Reports | Erosion and Sediment Control Inspection and Corrective Action | (e): 3.2.3; (f): G
111 |  |  | 01 57 19.00 22 | 6 | Test Reports | Monthly Solid Waste Disposal Report | (e): 3.4.2; (f): G
112 |  |  | 01 57 19.00 22 | 7 | Certificates | ECATTS Certificate Of Completion | (e): 1.4.1; (f): G
113 |  |  | 01 57 19.00 22 | 7 | Certificates | Erosion And Sediment Control Inspector | (e): 1.5.5; (f): G
114 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Stormwater Management and Erosion Control Compliance Notebook | (e): 3.2.1; (f): G
115 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Waste Determination Documentation | (e): 3.5; (f): G
116 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Disposal Documentation for Hazardous and Regulated Waste | (e): 3.12.4.5; (f): G
117 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Contractor Hazardous Material Inventory Log | (e): 3.8.1; (f): G
118 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Hazardous Waste/Debris Management | (e): 3.12.4; (f): G
119 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Regulatory Notifications | (e): 1.5.2; (f): G
120 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Asbestos Free Certification Form | (e): 3.12.4.3; (f): G
121 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Assembled Employee Training Records | (e): 1.5.5; (f): G
122 |  |  | 01 57 19.00 22 | 11 | Closeout Submittals | Sales Documentation | (e): 3.4.2; (f): G
123 |  |  | 01 58 00.00 22 | 2 | Shop Drawings | Preliminary One Line | (e): 1.3.1.1; (f): G
124 |  |  | 01 58 00.00 22 | 2 | Shop Drawings | Preliminary Drawing Indicating Layout And Text Content | (e): 1.4.1; (f): G
125 |  |  | 01 58 00.00 22 | 4 | Samples | Final Rendering | (e): 1.3.1.2; (f): G
126 |  |  | 01 58 00.00 22 | 4 | Samples | Final Framed Rendering | (e): 1.3.1.3; (f): G
127 |  |  | 01 58 00.00 22 | 4 | Samples | Facility Recognition Plaque | (e): 1.3.2; (f): G
128 |  |  | 01 74 19.00 22 | 1 | Preconstruction Submittals | Construction Waste Management Plan | (e): 1.7; (f): G
129 |  |  | 01 74 19.00 22 | 11 | Closeout Submittals | Final Construction Waste Diversion Report | (e): 1.9; (f): G
130 |  |  | 01 78 00.00 22 | 3 | Product Data | Warranty Management Plan | (e): 1.6.1
131 |  |  | 01 78 00.00 22 | 3 | Product Data | Warranty Tags | (e): 1.6.4
132 |  |  | 01 78 00.00 22 | 3 | Product Data | Final Cleaning | (e): 3.4
133 |  |  | 01 78 00.00 22 | 3 | Product Data | Spare Parts Data | (e): 1.5
134 |  |  | 01 78 00.00 22 | 8 | Manufacturer's Instructions | Instructions | (e): 1.6.1
135 |  |  | 01 78 00.00 22 | 8 | Manufacturer's Instructions | Preventative Maintenance | (e): 1.8; (f): G
136 |  |  | 01 78 00.00 22 | 8 | Manufacturer's Instructions | Condition Monitoring (Predictive Testing) | (e): 1.8; (f): G
137 |  |  | 01 78 00.00 22 | 8 | Manufacturer's Instructions | Inspection | (e): 1.8; (f): G
138 |  |  | 01 78 00.00 22 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.3; (f): G
139 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | As-Built Drawings | (e): 3.1; (f): G
140 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Record Drawings | (e): 3.2; (f): G
141 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | As-Built Record of Equipment and Materials | (e): 1.7.1; (f): G
142 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Warranted Equipment and Materials | (e): 1.6.1
143 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Certification of EPA Designated Items | (e): 2.1; (f): G
144 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Certification Of USDA Designated Items | (e): 2.2; (f): G
145 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Red Zone Documents | (e): 1.7.4; (f): G
146 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Facility Data Workbook (FDW), Final Submission | (e): 1.7.5; (f): G
147 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | Post Installation Sanitary System Survey | (e): 1.7.6; (f): G
148 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | High Performance and Sustainable Building (HPSB) Checklist | (e): 3.5.2; (f): G
149 |  |  | 01 78 00.00 22 | 11 | Closeout Submittals | List Of Installed Building Equipment Items For DD Form 1354 | (e): 3.5.2
150 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Facility Data Workbook | (e): 1.4; (f): G
151 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Training Plan | (e): 3.1.1; (f): G
152 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Training Outline | (e): 3.1.3; (f): G
153 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Training Content | (e): 3.1.2; (f): G
154 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Operation And Maintenance Manual, Progress Submittal | (e): 3.2.1; (f): G
155 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Operation And Maintenance Manual, Prefinal Submittal | (e): 3.2.2; (f): G
156 |  |  | 01 78 23.00 22 | 10 | Operation and Maintenance Data | Operation And Maintenance Manual, Final Submittal | (e): 3.2.3; (f): G
157 |  |  | 01 78 23.00 22 | 11 | Closeout Submittals | Training Video Recording | (e): 3.1.4; (f): G
158 |  |  | 01 78 23.00 22 | 11 | Closeout Submittals | Validation of Training Completion | (e): 3.1.6; (f): G
159 |  |  | 01 78 23.00 22 | 11 | Closeout Submittals | Training Plan | (e): 3.1.1; (f): G
160 |  |  | 01 78 23.00 22 | 11 | Closeout Submittals | Record Drawings And Utility Systems | (e): 1.6.6.7; (f): G
161 |  |  | 01 78 24.00 22 | 11 | Closeout Submittals | Facility Data Workbook (FDW), Progress Submittal | (e): 1.3.1; (f): G
162 |  |  | 01 78 24.00 22 | 11 | Closeout Submittals | Facility Data Workbook (FDW), Prefinal Submittal | (e): 1.3.2; (f): G
163 |  |  | 01 78 24.00 22 | 11 | Closeout Submittals | Facility Data Workbook (FDW), Final Submittal | (e): 1.3.3; (f): G
164 |  |  | 01 91 19 | 1 | Preconstruction Submittals | Building Enclosure Commissioning Specialist Qualifications | bar: (f)
165 |  |  | 01 91 19 | 1 | Preconstruction Submittals | Building Enclosure Testing Work Plan | (e): 1.8; (f): G
166 |  |  | 01 91 19 | 1 | Preconstruction Submittals | PRELIMINARY BECx PLAN | (e): 3.2; (f): G
167 |  |  | 01 91 19 | 3 | Product Data | Thermal Imaging Camera | (e): 2.3; (f): G
168 |  |  | 01 91 19 | 3 | Product Data | Test Equipment | (e): 2.1; (f): G
169 |  |  | 01 91 19 | 3 | Product Data | FINAL BECx PLAN | (e): 3.3; (f): G
170 |  |  | 01 91 19 | 5 | Design Data | Envelope Surface Area Calculations | (e): 3.7.2; (f): G
171 |  |  | 01 91 19 | 6 | Test Reports | Completed Building Envelope Inspection Checklists | bar: (f)
172 |  |  | 01 91 19 | 6 | Test Reports | Pressure Test Procedures | (e): 3.7.5; (f): G
173 |  |  | 01 91 19 | 6 | Test Reports | Air Leakage Test Report | (e): 1.12.3; (f): G
174 |  |  | 01 91 19 | 6 | Test Reports | Air Leakage Test Report | (e): 3.7.5.6; (f): G
175 |  |  | 01 91 19 | 6 | Test Reports | Diagnostic Test Report | (e): 1.12.3; (f): G
176 |  |  | 01 91 19 | 6 | Test Reports | Diagnostic Test Report | (e): 3.7.6.6; (f): G
177 |  |  | 01 91 19 | 6 | Test Reports | FINAL BECx REPORT | (e): 3.9
178 |  |  | 01 91 19 | 7 | Certificates | Pressure Test Agency | (e): 1.12.2.1
179 |  |  | 01 91 19 | 7 | Certificates | Thermographer Qualifications | (e): 1.12.2.2
180 |  |  | 01 91 19 | 7 | Certificates | Certificate of Readiness | (e): 1.14
181 |  |  | 01 91 19 | 10 | Operation and Maintenance Data | Training | (e): 3.8; (f): G
182 |  |  | 02 41 00 | 1 | Preconstruction Submittals | Demolition/Deconstruction Plan | (e): 1.2.2; (f): G
183 |  |  | 02 41 00 | 1 | Preconstruction Submittals | Existing Conditions | (e): 1.11
184 |  |  | 02 41 00 | 1 | Preconstruction Submittals | Qualifications of Jacking Contractor | (e): 3.3; (f): G
185 |  |  | 02 41 00 | 1 | Preconstruction Submittals | Photographic Documentation | (e): 3.3.1; (f): G
186 |  |  | 02 41 00 | 2 | Shop Drawings | Temporary shoring design drawings | (e): 3.2; (f): G
187 |  |  | 02 41 00 | 2 | Shop Drawings | Jacking design drawings | (e): 3.3; (f): G
188 |  |  | 02 41 00 | 5 | Design Data | Temporary shoring design calculations | (e): 3.2
189 |  |  | 02 41 00 | 5 | Design Data | Jacking design calculations | (e): 3.3; (f): G
190 |  |  | 02 41 00 | 7 | Certificates | Notification | (e): 1.7; (f): G
191 |  |  | 02 41 00 | 11 | Closeout Submittals | Receipts | (e): 3.4.4
192 |  |  | 02 42 91 | 1 | Preconstruction Submittals | Work Plan | (e): 1.2; (f): G
193 |  |  | 02 82 00.00 22 | 3 | Product Data | Amended Water | (e): 1.2.2; (f): G
194 |  |  | 02 82 00.00 22 | 3 | Product Data | Safety Data Sheets (SDS) for All Materials | (e): 1.3.9; (f): G
195 |  |  | 02 82 00.00 22 | 3 | Product Data | Encapsulants | (e): 2.1; (f): G
196 |  |  | 02 82 00.00 22 | 3 | Product Data | Respirators | (e): 3.1.2.1; (f): G
197 |  |  | 02 82 00.00 22 | 3 | Product Data | Local Exhaust Equipment | (e): 3.1.7; (f): G
198 |  |  | 02 82 00.00 22 | 3 | Product Data | Pressure Differential Automatic Recording Instrument | (e): 3.1.7; (f): G
199 |  |  | 02 82 00.00 22 | 3 | Product Data | Vacuums | (e): 3.1.8; (f): G
200 |  |  | 02 82 00.00 22 | 3 | Product Data | Glovebags | (e): 3.1.10; (f): G
201 |  |  | 02 82 00.00 22 | 6 | Test Reports | Air Sampling Results | (e): 1.5.5; (f): G
202 |  |  | 02 82 00.00 22 | 6 | Test Reports | Pressure Differential Recordings for Local Exhaust System | (e): 1.5.6; (f): G
203 |  |  | 02 82 00.00 22 | 6 | Test Reports | Clearance Sampling | (e): 3.2.14.5; (f): G
204 |  |  | 02 82 00.00 22 | 6 | Test Reports | Asbestos Disposal Quantity Report | (e): 3.3.3.2; (f): G
205 |  |  | 02 82 00.00 22 | 7 | Certificates | Employee Training | (e): 1.3.4; (f): G
206 |  |  | 02 82 00.00 22 | 7 | Certificates | Notifications | (e): 1.3.5; (f): G
207 |  |  | 02 82 00.00 22 | 7 | Certificates | Respiratory Protection Program | (e): 1.3.7; (f): G
208 |  |  | 02 82 00.00 22 | 7 | Certificates | Asbestos Hazard Abatement Plan | (e): 1.3.10; (f): G
209 |  |  | 02 82 00.00 22 | 7 | Certificates | Asbestos Hazard Abatement Plan Checklist | (e): 1.3.10; (f): G
210 |  |  | 02 82 00.00 22 | 7 | Certificates | Testing Laboratory | (e): 1.3.11; (f): G
211 |  |  | 02 82 00.00 22 | 7 | Certificates | Medical Certification | (e): 1.3.14; (f): G
212 |  |  | 02 82 00.00 22 | 7 | Certificates | Private Qualified Person Documentation | (e): 1.5.1; (f): G
213 |  |  | 02 82 00.00 22 | 7 | Certificates | Competent Person | (e): 1.5.2; (f): G
214 |  |  | 02 82 00.00 22 | 7 | Certificates | Worker's License | (e): 1.5.3; (f): G
215 |  |  | 02 82 00.00 22 | 7 | Certificates | Contractor's License | (e): 1.5.4; (f): G
216 |  |  | 02 82 00.00 22 | 7 | Certificates | Federal, State or Local Citations on Previous Projects | (e): 1.5.7; (f): G
217 |  |  | 02 82 00.00 22 | 7 | Certificates | Encapulants | (e): 1.2.15; (f): G
218 |  |  | 02 82 00.00 22 | 7 | Certificates | Equipment Used to Contain Airborne Asbestos Fibers | (e): 3.1; (f): G
219 |  |  | 02 82 00.00 22 | 7 | Certificates | Water Filtration Equipment | (e): 3.1.3.3; (f): G
220 |  |  | 02 82 00.00 22 | 7 | Certificates | Vacuums | (e): 3.1.8; (f): G
221 |  |  | 02 82 00.00 22 | 7 | Certificates | Ventilation Systems | (e): 3.1.8; (f): G
222 |  |  | 02 82 00.00 22 | 11 | Closeout Submittals | Permits | (e): 1.3.5
223 |  |  | 02 82 00.00 22 | 11 | Closeout Submittals | Licenses | (e): 1.3.5; (f): G
224 |  |  | 02 82 00.00 22 | 11 | Closeout Submittals | Notifications | (e): 1.3.5; (f): G
225 |  |  | 02 82 00.00 22 | 11 | Closeout Submittals | Respirator Program Records | (e): 1.3.7.1; (f): G
226 |  |  | 02 82 00.00 22 | 11 | Closeout Submittals | Rental Equipment | (e): 1.7.1; (f): G
227 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Competent Person | (e): 1.5.1.1; (f): G
228 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Training Certification | (e): 1.5.1.2; (f): G
229 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Occupational and Environmental Assessment Data Report | (e): 1.5.2.4; (f): G
230 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Medical Examinations | (e): 1.5.2.5; (f): G
231 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Lead, Cadmium, and Chromium (VI) Waste Management Plan | (e): 1.5.2.9; (f): G
232 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Licenses, Permits and Notifications | (e): 1.5.4; (f): G
233 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Lead, Cadmium, and Chromium (VI) Compliance Plan | (e): 1.5.2.2; (f): G
234 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Lead, Cadmium, and Chromium (VI) Compliance Plan Checklist | (e): 1.5.2.3; (f): G
235 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Waste Characterization Sampling Plan | (e): 1.5.2.10; (f): G
236 |  |  | 02 83 00.00 22 | 1 | Preconstruction Submittals | Sample Results | (e): 3.4.1.1; (f): G
237 |  |  | 02 83 00.00 22 | 3 | Product Data | Respirators | (e): 1.6.1; (f): G
238 |  |  | 02 83 00.00 22 | 3 | Product Data | Vacuum Filters | (e): 1.6.4; (f): G
239 |  |  | 02 83 00.00 22 | 3 | Product Data | Negative Air Pressure System | (e): 1.6.7; (f): G
240 |  |  | 02 83 00.00 22 | 3 | Product Data | Materials and Equipment | (e): 2.1; (f): G
241 |  |  | 02 83 00.00 22 | 3 | Product Data | Expendable Supplies | (e): 2.1.1; (f): G
242 |  |  | 02 83 00.00 22 | 3 | Product Data | Local Exhaust Equipment | (e): 3.1.1.5; (f): G
243 |  |  | 02 83 00.00 22 | 3 | Product Data | Pressure Differential Automatic Recording Instrument | (e): 3.1.1.5; (f): G
244 |  |  | 02 83 00.00 22 | 3 | Product Data | Pressure Differential Log | (e): 3.1.1.6; (f): G
245 |  |  | 02 83 00.00 22 | 6 | Test Reports | Sampling and Analysis | (e): 1.3.3; (f): G
246 |  |  | 02 83 00.00 22 | 6 | Test Reports | Occupational and Environmental Assessment Data Report | (e): 1.5.2.4; (f): G
247 |  |  | 02 83 00.00 22 | 6 | Test Reports | Sampling Results | (e): 1.5.2.4; (f): G
248 |  |  | 02 83 00.00 22 | 6 | Test Reports | Pressure Differential Recordings For Local Exhaust System | (e): 1.5.3; (f): G
249 |  |  | 02 83 00.00 22 | 7 | Certificates | Testing Laboratory | (e): 1.5.1.3; (f): G
250 |  |  | 02 83 00.00 22 | 7 | Certificates | Third Party Consultant Qualifications | (e): 1.5.1.4; (f): G
251 |  |  | 02 83 00.00 22 | 7 | Certificates | Notification of the Commencement of Work Impacting Lead, Cadmium, or Chromium (VI) | (e): 3.1.1.1; (f): G
252 |  |  | 02 83 00.00 22 | 7 | Certificates | Clearance Certification | (e): 3.5.1.1; (f): G
253 |  |  | 02 83 00.00 22 | 11 | Closeout Submittals | Turn-In Documents or Weight Tickets | (e): 3.5.2.1; (f): G
254 |  |  | 02 84 16.00 22 | 7 | Certificates | Qualifications of CIH | (e): 1.8.1; (f): G
255 |  |  | 02 84 16.00 22 | 7 | Certificates | Training Certification | (e): 1.8.1; (f): G
256 |  |  | 02 84 16.00 22 | 7 | Certificates | PCB and Lamp Removal Work Plan | (e): 1.8.2; (f): G
257 |  |  | 02 84 16.00 22 | 7 | Certificates | PCB and Lamp Disposal Plan | (e): 1.8.3; (f): G
258 |  |  | 02 84 16.00 22 | 11 | Closeout Submittals | Transporter Certification | (e): 3.5.2; (f): G
259 |  |  | 02 84 16.00 22 | 11 | Closeout Submittals | Certification of Decontamination | (e): 3.2.4
260 |  |  | 02 84 16.00 22 | 11 | Closeout Submittals | Certificate of Disposal and/or recycling | (e): 3.5.2.1
261 |  |  | 02 84 16.00 22 | 11 | Closeout Submittals | DD Form 1348-1 | (e): 3.5.3.1
262 |  |  | 02 84 33.00 22 | 1 | Preconstruction Submittals | PCB Removal Work Plan | (e): 1.7.3; (f): G
263 |  |  | 02 84 33.00 22 | 1 | Preconstruction Submittals | PCB Disposal Plan | (e): 1.7.4; (f): G
264 |  |  | 02 84 33.00 22 | 7 | Certificates | Training certification | (e): 1.7.1
265 |  |  | 02 84 33.00 22 | 7 | Certificates | Qualifications of CIH | (e): 1.7.2; (f): G
266 |  |  | 02 84 33.00 22 | 7 | Certificates | Notification | (e): 1.7.5
267 |  |  | 02 84 33.00 22 | 7 | Certificates | Transporter Certification | (e): 3.8; (f): G
268 |  |  | 02 84 33.00 22 | 7 | Certificates | Certification of Decontamination | (e): 3.5.4
269 |  |  | 02 84 33.00 22 | 7 | Certificates | Post Cleanup Sampling | (e): 3.5.5; (f): G
270 |  |  | 02 84 33.00 22 | 7 | Certificates | Certificate of Disposal | (e): 3.8.1
271 |  |  | 03 01 00 | 1 | Preconstruction Submittals | Qualifications | (e): 1.5.3; (f): G
272 |  |  | 03 01 00 | 1 | Preconstruction Submittals | Work Plan | (e): 1.5.4; (f): G
273 |  |  | 03 01 00 | 1 | Preconstruction Submittals | Work Plan | (e): 1.6.1; (f): G
274 |  |  | 03 01 00 | 1 | Preconstruction Submittals | Quality Control Plan | (e): 1.5.2; (f): G
275 |  |  | 03 01 00 | 3 | Product Data | Polymers | (e): 2.3; (f): G
276 |  |  | 03 01 00 | 3 | Product Data | Integral Color Admixture | (e): 2.3; (f): G
277 |  |  | 03 01 00 | 3 | Product Data | Miscellaneous Materials And Equipment | (e): 2.4
278 |  |  | 03 01 00 | 4 | Samples | Mockup | (e): 1.5.5; (f): G
279 |  |  | 03 01 00 | 4 | Samples | Color Chart | (e): 1.5.5; (f): G
280 |  |  | 03 01 00 | 5 | Design Data | Formwork | (e): 3.1.3; (f): G
281 |  |  | 03 01 00 | 5 | Design Data | Repair Procedures | (e): 1.5.1; (f): G
282 |  |  | 03 01 00 | 5 | Design Data | Mixture Proportioning | (e): 2.5; (f): G
283 |  |  | 03 01 00 | 6 | Test Reports | Mixture Proportioning | (e): 2.5; (f): G
284 |  |  | 03 01 00 | 6 | Test Reports | Quality Control | (e): 3.1.5; (f): G
285 |  |  | 03 01 00 | 6 | Test Reports | Quality Control | (e): 3.2.3; (f): G
286 |  |  | 03 01 00 | 6 | Test Reports | Quality Control | (e): 3.3.3; (f): G
287 |  |  | 03 01 00 | 6 | Test Reports | Polymers | (e): 2.3; (f): G
288 |  |  | 03 01 00 | 6 | Test Reports | Miscellaneous Materials and Equipment | (e): 2.4
289 |  |  | 03 01 00 | 7 | Certificates | Qualifications | (e): 1.5.3
290 |  |  | 03 01 00 | 7 | Certificates | Polymers | (e): 2.3
291 |  |  | 03 01 00 | 8 | Manufacturer's Instructions | Equipment for Concrete Preparation | (e): 2.1
292 |  |  | 03 01 00 | 8 | Manufacturer's Instructions | Polymers | (e): 2.3
293 |  |  | 03 01 00 | 8 | Manufacturer's Instructions | Miscellaneous Materials and Equipment | (e): 2.4
294 |  |  | 03 30 00 | 1 | Preconstruction Submittals | Concrete Curing Plan | (e): 1.6.3.1; (f): G
295 |  |  | 03 30 00 | 1 | Preconstruction Submittals | Quality Control Plan | (e): 1.6.5; (f): G
296 |  |  | 03 30 00 | 1 | Preconstruction Submittals | Quality Control Personnel Certifications | (e): 1.6.6; (f): G
297 |  |  | 03 30 00 | 1 | Preconstruction Submittals | Quality Control Organizational Chart | (e): 1.6.6; (f): G
298 |  |  | 03 30 00 | 1 | Preconstruction Submittals | Laboratory Accreditation | (e): 1.6.8; (f): G
299 |  |  | 03 30 00 | 2 | Shop Drawings | Reinforcing Steel | (e): 1.6.2.1; (f): G
300 |  |  | 03 30 00 | 3 | Product Data | Joint Sealants | (e): 2.4.5; (f): G
301 |  |  | 03 30 00 | 3 | Product Data | Joint Filler | (e): 2.4.4; (f): G
302 |  |  | 03 30 00 | 3 | Product Data | Formwork Materials | (e): 2.1; (f): G
303 |  |  | 03 30 00 | 3 | Product Data | Cementitious Materials | (e): 2.3.1; (f): G
304 |  |  | 03 30 00 | 3 | Product Data | Vapor Retarder | (e): 2.4.6; (f): G
305 |  |  | 03 30 00 | 3 | Product Data | Concrete Curing Materials | (e): 2.4.1; (f): G
306 |  |  | 03 30 00 | 3 | Product Data | Reinforcement | (e): 2.6; (f): G
307 |  |  | 03 30 00 | 3 | Product Data | Liquid Chemical Floor Hardeners and Sealers | (e): 2.4.3.1; (f): G
308 |  |  | 03 30 00 | 3 | Product Data | Admixtures | (e): 2.3.4; (f): G
309 |  |  | 03 30 00 | 3 | Product Data | Waterstops | (e): 2.2.2; (f): G
310 |  |  | 03 30 00 | 3 | Product Data | Biodegradable Form Release Agent | (e): 2.2.3; (f): G
311 |  |  | 03 30 00 | 3 | Product Data | Pumping Concrete | (e): 1.6.3.2; (f): G
312 |  |  | 03 30 00 | 3 | Product Data | Nonshrink Grout | (e): 2.4.2; (f): G
313 |  |  | 03 30 00 | 5 | Design Data | Concrete Mix Design | (e): 1.6.1.1; (f): G
314 |  |  | 03 30 00 | 6 | Test Reports | Concrete Mix Design | (e): 1.6.1.1; (f): G
315 |  |  | 03 30 00 | 6 | Test Reports | Aggregates | (e): 1.6.4.3; (f): G
316 |  |  | 03 30 00 | 6 | Test Reports | Compressive Strength Tests | (e): 3.13.2.3; (f): G
317 |  |  | 03 30 00 | 6 | Test Reports | Air Content | (e): 3.13.2.4; (f): G
318 |  |  | 03 30 00 | 6 | Test Reports | Slump Tests | (e): 3.13.2.1; (f): G
319 |  |  | 03 30 00 | 6 | Test Reports | Water | (e): 2.3.2; (f): G
320 |  |  | 03 30 00 | 7 | Certificates | Reinforcing Bars | (e): 2.6.1; (f): G
321 |  |  | 03 30 00 | 7 | Certificates | VOC Content for Form Release Agents, Curing Compounds, and Concrete Penetrating Sealers | (e): 1.6.3.3
322 |  |  | 03 30 00 | 7 | Certificates | Safety Data Sheets | (e): 1.6.3.4
323 |  |  | 03 30 00 | 7 | Certificates | Field Testing Technician and Testing Agency | (e): 1.6.6.1; (f): G
324 |  |  | 03 30 00 | 8 | Manufacturer's Instructions | Liquid Chemical Floor Hardeners and Sealers | (e): 2.4.3.1
325 |  |  | 03 30 00 | 8 | Manufacturer's Instructions | Joint Sealants | (e): 2.4.5
326 |  |  | 03 30 00 | 8 | Manufacturer's Instructions | Curing Compound | (e): 2.4.1
327 |  |  | 04 01 00.91 22 | 1 | Preconstruction Submittals | Masonry Quality Control Plan | (e): 1.6.1; (f): G
328 |  |  | 04 01 00.91 22 | 1 | Preconstruction Submittals | Project Training Program | (e): 1.6.1; (f): G
329 |  |  | 04 01 00.91 22 | 1 | Preconstruction Submittals | Qualifications | (e): 1.6.2; (f): G
330 |  |  | 04 01 00.91 22 | 2 | Shop Drawings | Photographic Documentation | (e): 1.6.5; (f): G
331 |  |  | 04 01 00.91 22 | 3 | Product Data | Qualifications | (e): 1.6.2; (f): G
332 |  |  | 04 01 00.91 22 | 3 | Product Data | Cleaning and Restoration Methods | (e): 1.6.6; (f): G
333 |  |  | 04 01 00.91 22 | 3 | Product Data | Cleaning Materials | (e): 2.1; (f): G
334 |  |  | 04 01 00.91 22 | 3 | Product Data | Replacement Mortar | (e): 2.2.1.1; (f): G
335 |  |  | 04 01 00.91 22 | 3 | Product Data | Replacement Mortar | (e): 2.2.1.2; (f): G
336 |  |  | 04 01 00.91 22 | 3 | Product Data | Mortar | (e): 1.3.7; (f): G
337 |  |  | 04 01 00.91 22 | 3 | Product Data | Replacement Masonry Units | (e): 1.6.8.2; (f): G
338 |  |  | 04 01 00.91 22 | 4 | Samples | Mock-ups | (e): 1.6.8; (f): G
339 |  |  | 04 01 00.91 22 | 6 | Test Reports | Testing and Matching | (e): 2.2.1.1; (f): G
340 |  |  | 04 01 00.91 22 | 7 | Certificates | Repair Materials | (e): 2.2
341 |  |  | 04 20 00 | 1 | Preconstruction Submittals | Hot Weather Procedures | (e): 1.4.1; (f): G
342 |  |  | 04 20 00 | 1 | Preconstruction Submittals | Cold Weather Procedures | (e): 1.4.2; (f): G
343 |  |  | 04 20 00 | 2 | Shop Drawings | Cut CMU | (e): 3.3.2.1; (f): G
344 |  |  | 04 20 00 | 2 | Shop Drawings | Detail Drawings | (e): 3.4.1.1; (f): G
345 |  |  | 04 20 00 | 3 | Product Data | Cement | (e): 2.2.2.2.1; (f): G
346 |  |  | 04 20 00 | 3 | Product Data | Cementitious Materials | (e): 2.4.1.1; (f): G
347 |  |  | 04 20 00 | 5 | Design Data | Masonry Compressive Strength | (e): 2.1.2; (f): G
348 |  |  | 04 20 00 | 5 | Design Data | Fire-Rated Concrete Masonry Units | (e): 2.2.2.3; (f): G
349 |  |  | 04 20 00 | 6 | Test Reports | Fire-Rated Concrete Masonry Units | (e): 2.2.2.3; (f): G
350 |  |  | 04 20 00 | 6 | Test Reports | Field Testing of Mortar | (e): 3.6.1.1; (f): G
351 |  |  | 04 20 00 | 6 | Test Reports | Field Testing of Grout | (e): 3.6.1.2; (f): G
352 |  |  | 04 20 00 | 7 | Certificates | Concrete Masonry Units (CMU) | (e): 2.2.2.2; (f): G
353 |  |  | 04 20 00 | 7 | Certificates | Concrete Brick | (e): 2.2.2.4; (f): G
354 |  |  | 04 20 00 | 8 | Manufacturer's Instructions | Admixtures for Masonry Mortar | (e): 2.4.1.3
355 |  |  | 04 20 00 | 8 | Manufacturer's Instructions | Admixtures for Grout | (e): 2.4.2.2
356 |  |  | 04 20 00 | 10 | Operation and Maintenance Data | Take-Back Program | (e): 3.8
357 |  |  | 05 12 00 | 2 | Shop Drawings | Fabrication Drawings | (e): 1.4.1; (f): G
358 |  |  | 05 12 00 | 3 | Product Data | Shop Primer | (e): 2.6.2; (f): G
359 |  |  | 05 12 00 | 3 | Product Data | Welding Electrodes and Rods | (e): 2.4.1; (f): G
360 |  |  | 05 12 00 | 3 | Product Data | Direct Tension Indicator Washers | (e): 2.3.1.3; (f): G
361 |  |  | 05 12 00 | 3 | Product Data | Non-Shrink Grout | (e): 2.4.2; (f): G
362 |  |  | 05 12 00 | 3 | Product Data | Tension Control Bolts | (e): 2.3.2; (f): G
363 |  |  | 05 12 00 | 6 | Test Reports | Bolts, Nuts, and Washers | (e): 2.3; (f): G
364 |  |  | 05 12 00 | 6 | Test Reports | Weld Inspection Reports | (e): 3.7.1.2; (f): G
365 |  |  | 05 12 00 | 6 | Test Reports | Bolt Testing Reports | (e): 3.7.2.1; (f): G
366 |  |  | 05 12 00 | 7 | Certificates | Steel | (e): 2.2; (f): G
367 |  |  | 05 12 00 | 7 | Certificates | Bolts, Nuts, and Washers | (e): 2.3; (f): G
368 |  |  | 05 12 00 | 7 | Certificates | Galvanizing | (e): 2.5; (f): G
369 |  |  | 05 12 00 | 7 | Certificates | AISC Structural Steel Fabricator Quality Certification | (e): 1.3; (f): G
370 |  |  | 05 12 00 | 7 | Certificates | Welding Procedures and Qualifications | (e): 1.4.2.1; (f): G
371 |  |  | 05 12 00 | 7 | Certificates | Welding Electrodes and Rods | (e): 2.4.1; (f): G
372 |  |  | 05 12 00 | 7 | Certificates | Certified Welding Inspector | (e): 3.7.1.1; (f): G
373 |  |  | 05 12 00 | 7 | Certificates | NDT Technician | (e): 3.7.1.2; (f): G
374 |  |  | 05 12 00 | 7 | Certificates | Welding Procedure Specifications (WPS) | (e): 3.4; (f): G
375 |  |  | 05 30 00 | 2 | Shop Drawings | Fabrication Drawings | (e): 1.3.3; (f): G
376 |  |  | 05 30 00 | 3 | Product Data | Accessories | (e): 2.2; (f): G
377 |  |  | 05 30 00 | 3 | Product Data | Deck Units | (e): 2.1; (f): G
378 |  |  | 05 30 00 | 3 | Product Data | Galvanizing Repair Paint | (e): 2.1.3; (f): G
379 |  |  | 05 30 00 | 3 | Product Data | Touch-Up Paint | (e): 2.1.3
380 |  |  | 05 30 00 | 3 | Product Data | Welding Equipment | (e): 1.3.2
381 |  |  | 05 30 00 | 3 | Product Data | Welding Rods and Accessories | (e): 1.3.2; (f): G
382 |  |  | 05 30 00 | 5 | Design Data | Deck Units | (e): 2.1; (f): G
383 |  |  | 05 30 00 | 7 | Certificates | Welder Qualifications | (e): 1.3.2; (f): G
384 |  |  | 05 30 00 | 7 | Certificates | Welding Procedures | (e): 1.3.2; (f): G
385 |  |  | 05 30 00 | 7 | Certificates | Manufacturer's Certificate | (e): 1.3.1; (f): G
386 |  |  | 05 40 00 | 2 | Shop Drawings | Framing Components | (e): 1.5.1; (f): G
387 |  |  | 05 40 00 | 3 | Product Data | Studs, Joists | (e): 2.1; (f): G
388 |  |  | 05 40 00 | 7 | Certificates | Load-Bearing Cold-Formed Metal Framing | (e): 1.4; (f): G
389 |  |  | 05 50 13 | 2 | Shop Drawings | Floor Gratings | (e): 2.3; (f): G
390 |  |  | 05 50 13 | 2 | Shop Drawings | Bollards/Pipe Guards | (e): 2.4; (f): G
391 |  |  | 05 50 13 | 2 | Shop Drawings | Attic Hatch | (e): 2.7; (f): G
392 |  |  | 05 50 13 | 3 | Product Data | Floor Gratings | (e): 2.3; (f): G
393 |  |  | 05 50 13 | 3 | Product Data | Slotted Channel Framing | (e): 2.6; (f): G
394 |  |  | 05 50 13 | 3 | Product Data | Attic Hatch | (e): 2.7; (f): G
395 |  |  | 05 51 00 | 2 | Shop Drawings | Iron and Steel Hardware | (e): 2.1; (f): G
396 |  |  | 05 51 00 | 2 | Shop Drawings | Steel Shapes, Plates, Bars, and Strips | (e): 2.1; (f): G
397 |  |  | 05 51 00 | 2 | Shop Drawings | Metal Stair System | (e): 2.2.1; (f): G
398 |  |  | 05 51 00 | 3 | Product Data | Galvanized Carbon Steel Sheets | (e): 2.4.3; (f): G
399 |  |  | 05 51 00 | 3 | Product Data | Gray Iron Castings | (e): 2.4.4; (f): G
400 |  |  | 05 51 00 | 3 | Product Data | Concrete Inserts | (e): 2.3.2; (f): G
401 |  |  | 05 51 00 | 3 | Product Data | Masonry Anchorage Devices | (e): 2.3.3; (f): G
402 |  |  | 05 51 00 | 3 | Product Data | Protective Coating | (e): 2.2.3; (f): G
403 |  |  | 05 51 00 | 3 | Product Data | Steel Pan Stairs | (e): 2.2.2; (f): G
404 |  |  | 05 51 00 | 3 | Product Data | Steel Stairs | (e): 2.3.1; (f): G
405 |  |  | 05 51 00 | 5 | Design Data | Steel Stair Calculations | (e): 1.3.2; (f): G
406 |  |  | 05 51 00 | 7 | Certificates | Welding Procedures | (e): 1.3.1; (f): G
407 |  |  | 05 51 00 | 7 | Certificates | Welder Qualification | (e): 1.3.1; (f): G
408 |  |  | 05 51 00 | 8 | Manufacturer's Instructions | Gray Iron Castings | (e): 2.4.4
409 |  |  | 05 51 00 | 8 | Manufacturer's Instructions | Protective Coating | (e): 2.2.3
410 |  |  | 05 51 00 | 8 | Manufacturer's Instructions | Masonry Anchorage Devices | (e): 2.3.3; (f): G
411 |  |  | 05 51 33 | 2 | Shop Drawings | Ladders | (e): 2.3; (f): G
412 |  |  | 05 51 33 | 3 | Product Data | Ladders | (e): 2.3; (f): G
413 |  |  | 05 51 33 | 7 | Certificates | Fabricator Certification for Ladder Assembly | (e): 1.3; (f): G
414 |  |  | 05 52 00 | 2 | Shop Drawings | Fabrication Drawings | (e): 2.1; (f): G
415 |  |  | 05 52 00 | 2 | Shop Drawings | Iron and Steel Hardware | (e): 3.2; (f): G
416 |  |  | 05 52 00 | 2 | Shop Drawings | Steel Shapes, Plates, Bars and Strips | (e): 3.2; (f): G
417 |  |  | 05 52 00 | 3 | Product Data | Structural-Steel Plates, Shapes, and Bars | (e): 2.2.1; (f): G
418 |  |  | 05 52 00 | 3 | Product Data | Structural-Steel Tubing | (e): 2.2.2; (f): G
419 |  |  | 05 52 00 | 3 | Product Data | Masonry Anchorage Devices | (e): 2.2.4; (f): G
420 |  |  | 05 52 00 | 3 | Product Data | Protective Coating | (e): 2.1.2; (f): G
421 |  |  | 05 52 00 | 3 | Product Data | Steel Railings and Handrails | (e): 2.2.6; (f): G
422 |  |  | 05 52 00 | 3 | Product Data | Anchorage and Fastening Systems | (e): 3.2; (f): G
423 |  |  | 05 52 00 | 5 | Design Data | Steel Railings and Handrail Calculations | (e): 1.3.3; (f): G
424 |  |  | 05 52 00 | 7 | Certificates | Welding Procedures | (e): 1.3.1; (f): G
425 |  |  | 05 52 00 | 7 | Certificates | Welder Qualification | (e): 1.3.2; (f): G
426 |  |  | 05 52 00 | 8 | Manufacturer's Instructions | Installation Instructions | (e): 3.2
427 |  |  | 06 10 00 | 3 | Product Data | Adhesives | (e): 2.5.1; (f): G
428 |  |  | 06 10 00 | 6 | Test Reports | Preservative-treated | (e): 1.4.3; (f): G
429 |  |  | 06 10 00 | 7 | Certificates | Certificate of Grade | (e): 1.9.1; (f): G
430 |  |  | 06 10 00 | 7 | Certificates | Preservative Treatment | (e): 1.7; (f): G
431 |  |  | 06 20 00 | 2 | Shop Drawings | Detail Drawings Indicating All Wood Assemblies | (e): 1.3; (f): G
432 |  |  | 06 20 00 | 3 | Product Data | Wood Products | (e): 2.1; (f): G
433 |  |  | 06 20 00 | 3 | Product Data | Hardware and Accessories | (e): 2.4; (f): G
434 |  |  | 06 41 16.00 10 | 2 | Shop Drawings | Shop Drawings | (e): 2.9; (f): G
435 |  |  | 06 41 16.00 10 | 2 | Shop Drawings | Installation | (e): 3.1
436 |  |  | 06 41 16.00 10 | 3 | Product Data | Wood Materials | (e): 2.1
437 |  |  | 06 41 16.00 10 | 3 | Product Data | High Pressure Decorative Laminate (HPDL) | (e): 2.3; (f): G
438 |  |  | 06 61 16 | 2 | Shop Drawings | Detail Drawings | (e): 1.4.2; (f): G
439 |  |  | 06 61 16 | 2 | Shop Drawings | Installation | (e): 3.1; (f): G
440 |  |  | 06 61 16 | 3 | Product Data | Solid Polymer Material | (e): 2.1; (f): G
441 |  |  | 06 61 16 | 3 | Product Data | Qualifications | (e): 1.4.1
442 |  |  | 06 61 16 | 3 | Product Data | Fabrications | (e): 2.3
443 |  |  | 06 61 16 | 10 | Operation and Maintenance Data | Clean-up | (e): 3.2
444 |  |  | 07 13 53 | 3 | Product Data | Manufacturer's Standard Details | (e): 1.3; (f): G
445 |  |  | 07 13 53 | 3 | Product Data | Elastomeric Waterproofing Sheet Material | (e): 2.1; (f): G
446 |  |  | 07 13 53 | 3 | Product Data | Primers, Adhesives, and Mastics | (e): 1.4; (f): G
447 |  |  | 07 13 53 | 3 | Product Data | Primers, Adhesives, and Mastics | (e): 2.1; (f): G
448 |  |  | 07 13 53 | 6 | Test Reports | Elastomeric Waterproofing Sheet Material | (e): 2.1; (f): G
449 |  |  | 07 13 53 | 6 | Test Reports | Field Quality Control | (e): 3.6; (f): G
450 |  |  | 07 13 53 | 6 | Test Reports | Protective Covering | (e): 3.7; (f): G
451 |  |  | 07 13 53 | 7 | Certificates | Elastomeric Waterproofing Sheet Material | (e): 2.1
452 |  |  | 07 13 53 | 7 | Certificates | Primers, Adhesives, and Mastics | (e): 1.4; (f): G
453 |  |  | 07 13 53 | 7 | Certificates | Primers, Adhesives, and Mastics | (e): 2.1; (f): G
454 |  |  | 07 13 53 | 7 | Certificates | Protective Coverings | (e): 1.4; (f): G
455 |  |  | 07 13 53 | 7 | Certificates | Special Warranties | (e): 1.8; (f): G
456 |  |  | 07 13 53 | 7 | Certificates | Certificates of Compliance | bar: (f)
457 |  |  | 07 13 53 | 8 | Manufacturer's Instructions | Primers, Adhesives, and Mastics | (e): 1.4; (f): G
458 |  |  | 07 13 53 | 8 | Manufacturer's Instructions | Primers, Adhesives, and Mastics | (e): 2.1; (f): G
459 |  |  | 07 21 16 | 3 | Product Data | Blanket Insulation | (e): 2.1; (f): G
460 |  |  | 07 21 16 | 3 | Product Data | Accessories | (e): 2.3
461 |  |  | 07 21 16 | 8 | Manufacturer's Instructions | Insulation | (e): 3.3.1
462 |  |  | 07 22 00 | 2 | Shop Drawings | Insulation Board Layout | (e): 1.3; (f): G
463 |  |  | 07 22 00 | 3 | Product Data | Insulation | (e): 2.1; (f): G
464 |  |  | 07 22 00 | 3 | Product Data | Fasteners | (e): 2.4; (f): G
465 |  |  | 07 22 00 | 3 | Product Data | Moisture Control | (e): 2.3; (f): G
466 |  |  | 07 22 00 | 3 | Product Data | Recycled Content For Insulation | bar: (f)
467 |  |  | 07 22 00 | 3 | Product Data | Cover Board | (e): 2.2; (f): G
468 |  |  | 07 22 00 | 6 | Test Reports | Flame Spread Rating | (e): 1.7.1
469 |  |  | 07 22 00 | 7 | Certificates | Installer Qualifications | (e): 1.6; (f): G
470 |  |  | 07 22 00 | 7 | Certificates | Indoor Air Quality For Insulation | bar: (f)
471 |  |  | 07 22 00 | 8 | Manufacturer's Instructions | Fasteners | (e): 2.4
472 |  |  | 07 22 00 | 8 | Manufacturer's Instructions | Insulation | (e): 2.1
473 |  |  | 07 31 13 | 3 | Product Data | Shingles | (e): 2.1.1
474 |  |  | 07 31 13 | 4 | Samples | Shingles | (e): 2.1.1; (f): G
475 |  |  | 07 31 13 | 8 | Manufacturer's Instructions | Application | (e): 3.3
476 |  |  | 07 31 13 | 11 | Closeout Submittals | Contractor's Warranty | (e): 1.5.1
477 |  |  | 07 42 13 | 1 | Preconstruction Submittals | Qualification of Manufacturer | (e): 1.5.3; (f): G
478 |  |  | 07 42 13 | 1 | Preconstruction Submittals | Qualification of Installation Contractor | (e): 1.5.4; (f): G
479 |  |  | 07 42 13 | 2 | Shop Drawings | Installation Drawings | (e): 1.5.1.1; (f): G
480 |  |  | 07 42 13 | 3 | Product Data | Recycled Content; | (e): 2.1; (f): G
481 |  |  | 07 42 13 | 3 | Product Data | Wall Panels | (e): 2.2.1; (f): G
482 |  |  | 07 42 13 | 3 | Product Data | Factory Color Finish | (e): 2.2.2; (f): G
483 |  |  | 07 42 13 | 3 | Product Data | Closure Materials | (e): 1.5.5; (f): G
484 |  |  | 07 42 13 | 3 | Product Data | Pressure Sensitive Tape | (e): 2.5.4.4
485 |  |  | 07 42 13 | 3 | Product Data | Sealants and Caulking | (e): 2.5.4.1
486 |  |  | 07 42 13 | 3 | Product Data | Repair Paint
487 |  |  | 07 42 13 | 3 | Product Data | Accessories | (e): 1.5.5; (f): G
488 |  |  | 07 42 13 | 3 | Product Data | Accessories | (e): 2.5; (f): G
489 |  |  | 07 42 13 | 4 | Samples | Wall Panels | (e): 2.2.1; (f): G
490 |  |  | 07 42 13 | 4 | Samples | Fasteners | (e): 2.4; (f): G
491 |  |  | 07 42 13 | 4 | Samples | Metal Closure Strips | (e): 2.5.3; (f): G
492 |  |  | 07 42 13 | 4 | Samples | Color chart | (e): 2.2.2.2; (f): G
493 |  |  | 07 42 13 | 4 | Samples | Mock-up | (e): 1.5.7; (f): G
494 |  |  | 07 42 13 | 5 | Design Data | Wind load design analysis | (e): 1.5.1.2; (f): G
495 |  |  | 07 42 13 | 6 | Test Reports | Leakage Tests | (e): 3.7.2; (f): G
496 |  |  | 07 42 13 | 6 | Test Reports | Wind Load Tests | (e): 1.3.2; (f): G
497 |  |  | 07 42 13 | 8 | Manufacturer's Instructions | Installation | (e): 3.3; (f): G
498 |  |  | 07 42 13 | 9 | Manufacturer's Field Reports | Manufacturer's Field Reports | (e): 3.8.1; (f): G
499 |  |  | 07 42 13 | 11 | Closeout Submittals | Warranty | (e): 1.8; (f): G
500 |  |  | 07 42 13 | 11 | Closeout Submittals | Maintenance Instructions | (e): 1.5.6; (f): G
501 |  |  | 07 42 13 | 11 | Closeout Submittals | 20 year 'No Dollar Limit' warranty for labor and material | (e): 1.8.1
502 |  |  | 07 42 63 | 1 | Preconstruction Submittals | Qualification of Manufacturer | (e): 1.5.3; (f): G
503 |  |  | 07 42 63 | 1 | Preconstruction Submittals | Qualification of Installer | (e): 1.5.4; (f): G
504 |  |  | 07 42 63 | 2 | Shop Drawings | Fabrication and Installation drawings | (e): 1.5.1
505 |  |  | 07 42 63 | 2 | Shop Drawings | Wall Panel Assemblies | (e): 1.5.1; (f): G
506 |  |  | 07 42 63 | 2 | Shop Drawings | Flashing and Accessories | (e): 1.5.1; (f): G
507 |  |  | 07 42 63 | 2 | Shop Drawings | Anchorage Systems | (e): 1.5.1; (f): G
508 |  |  | 07 42 63 | 3 | Product Data | sustainable acquisition | (e): 1.5.1; (f): G
509 |  |  | 07 42 63 | 3 | Product Data | Manufacturer's catalog data | (e): 1.5.1
510 |  |  | 07 42 63 | 3 | Product Data | Factory Color Finish | (e): 1.5.1; (f): G
511 |  |  | 07 42 63 | 3 | Product Data | Sub-girts and Formed Shapes | (e): 1.5.1; (f): G
512 |  |  | 07 42 63 | 3 | Product Data | Closure Materials | (e): 1.5.1; (f): G
513 |  |  | 07 42 63 | 3 | Product Data | Insulation | (e): 1.5.1; (f): G
514 |  |  | 07 42 63 | 3 | Product Data | Pressure Sensitive Tape | (e): 1.5.1
515 |  |  | 07 42 63 | 3 | Product Data | Sealants and Caulking | (e): 2.4.4.1
516 |  |  | 07 42 63 | 3 | Product Data | Accessories | (e): 1.5.1; (f): G
517 |  |  | 07 42 63 | 4 | Samples | Wall Panel Assemblies | (e): 1.5.1; (f): G
518 |  |  | 07 42 63 | 4 | Samples | manufacturer's color charts and chips | (e): 1.5.1; (f): G
519 |  |  | 07 42 63 | 4 | Samples | Mock-up | (e): 1.5.5; (f): G
520 |  |  | 07 42 63 | 5 | Design Data | Wind Design Analysis | (e): 1.5.1; (f): G
521 |  |  | 07 42 63 | 6 | Test Reports | Leakage Tests | (e): 3.7.2; (f): G
522 |  |  | 07 42 63 | 6 | Test Reports | Wind Load Tests | (e): 1.3.2; (f): G
523 |  |  | 07 42 63 | 7 | Certificates | wall system assembly wind load classification listings | (e): 1.5.1
524 |  |  | 07 42 63 | 8 | Manufacturer's Instructions | Installation of Wall Panels | (e): 1.5.1; (f): G
525 |  |  | 07 42 63 | 11 | Closeout Submittals | Warranty | (e): 1.8; (f): G
526 |  |  | 07 42 63 | 11 | Closeout Submittals | Instructions | (e): 1.5.1
527 |  |  | 07 42 63 | 11 | Closeout Submittals | Safety Data Sheets | (e): 1.5.1
528 |  |  | 07 42 63 | 11 | Closeout Submittals | 20 year 'No-Dollar-Limit' Warranty | (e): 1.5.1
529 |  |  | 07 52 00 | 2 | Shop Drawings | Roof Plan | (e): 1.4.6; (f): G
530 |  |  | 07 52 00 | 3 | Product Data | Modified Bitumen Sheets | (e): 2.2; (f): G
531 |  |  | 07 52 00 | 3 | Product Data | Cold-Applied Membrane Adhesive | (e): 2.4; (f): G
532 |  |  | 07 52 00 | 3 | Product Data | Primer | (e): 2.6; (f): G
533 |  |  | 07 52 00 | 3 | Product Data | Pre-Manufactured Accessories | (e): 2.1
534 |  |  | 07 52 00 | 3 | Product Data | Warranty | (e): 1.8; (f): G
535 |  |  | 07 52 00 | 5 | Design Data | Wind Uplift Calculations | (e): 1.4.5; (f): G
536 |  |  | 07 52 00 | 7 | Certificates | Qualification of Manufacturer | (e): 1.4.1; (f): G
537 |  |  | 07 52 00 | 7 | Certificates | Qualification of Applicator | (e): 1.4.2; (f): G
538 |  |  | 07 52 00 | 7 | Certificates | Qualification of Engineer of Record | (e): 1.4.3; (f): G
539 |  |  | 07 52 00 | 8 | Manufacturer's Instructions | Modified Bitumen Membrane Application | (e): 3.3.5; (f): G
540 |  |  | 07 52 00 | 8 | Manufacturer's Instructions | Flashing | (e): 3.3.6; (f): G
541 |  |  | 07 52 00 | 8 | Manufacturer's Instructions | Cold Adhesive Applied Modified Bitumen Membrane | (e): 3.3.3.1; (f): G
542 |  |  | 07 52 00 | 8 | Manufacturer's Instructions | Cold Weather Installation | (e): 1.6; (f): G
543 |  |  | 07 52 00 | 11 | Closeout Submittals | Warranty | (e): 1.8; (f): G
544 |  |  | 07 52 00 | 11 | Closeout Submittals | Information Card | (e): 3.8; (f): G
545 |  |  | 07 52 00 | 11 | Closeout Submittals | Instructions To Government Personnel | (e): 3.7
546 |  |  | 07 57 14 | 3 | Product Data | Sprayed (Bio-Based) Polyurethane Foam Insulation | (e): 2.1; (f): G
547 |  |  | 07 57 14 | 3 | Product Data | Protective (Ignition Barrier) Coating | (e): 2.2; (f): G
548 |  |  | 07 57 14 | 3 | Product Data | Primer | (e): 2.3
549 |  |  | 07 57 14 | 4 | Samples | Sprayed (Bio-Based) Polyurethane Foam Insulation | (e): 2.1; (f): G
550 |  |  | 07 57 14 | 7 | Certificates | Materials | (e): 2.1
551 |  |  | 07 57 14 | 7 | Certificates | Qualification of Manufacturer | (e): 1.4.1
552 |  |  | 07 57 14 | 7 | Certificates | Qualification of Applicator | (e): 1.4.2; (f): G
553 |  |  | 07 57 14 | 8 | Manufacturer's Instructions | Sprayed (Bio-Based) Polyurethane Foam Insulation | (e): 2.1
554 |  |  | 07 57 14 | 8 | Manufacturer's Instructions | Protective (Ignition Barrier) Coating | (e): 2.2
555 |  |  | 07 57 14 | 8 | Manufacturer's Instructions | Primer | (e): 2.3
556 |  |  | 07 57 14 | 8 | Manufacturer's Instructions | Surface Area Preparation | (e): 3.3
557 |  |  | 07 62 13 | 2 | Shop Drawings | Sheet Metal | (e): 2.1.6; (f): G
558 |  |  | 07 62 13 | 3 | Product Data | Contractor Quality Control | (e): 3.1
559 |  |  | 07 62 13 | 4 | Samples | Materials | (e): 2.1
560 |  |  | 07 81 00 | 2 | Shop Drawings | Shop Drawings | (e): 1.6.4; (f): G
561 |  |  | 07 81 00 | 3 | Product Data | Spray-Applied Fireproofing | bar: (f)
562 |  |  | 07 81 00 | 3 | Product Data | Protection Materials Documentation | (e): 2.3.1; (f): G
563 |  |  | 07 81 00 | 3 | Product Data | Evaluation Reports | (e): 1.4.3; (f): G
564 |  |  | 07 81 00 | 6 | Test Reports | Fire Resistance Rating | (e): 1.4.2; (f): G
565 |  |  | 07 81 00 | 6 | Test Reports | Field Tests | (e): 3.4; (f): G
566 |  |  | 07 81 00 | 7 | Certificates | Installer Qualifications | (e): 1.6.1; (f): G
567 |  |  | 07 81 00 | 7 | Certificates | Inspector Qualifications | (e): 1.6.2; (f): G
568 |  |  | 07 81 00 | 7 | Certificates | Surface Preparation Report | (e): 3.1; (f): G
569 |  |  | 07 84 00.00 22 | 2 | Shop Drawings | Firestopping System | (e): 2.1; (f): G
570 |  |  | 07 84 00.00 22 | 3 | Product Data | Firestopping Materials | (e): 2.2; (f): G
571 |  |  | 07 84 00.00 22 | 3 | Product Data | Firestopping Materials | (e): 3.1; (f): G
572 |  |  | 07 84 00.00 22 | 6 | Test Reports | Inspection Forms | (e): 3.3.1; (f): G
573 |  |  | 07 84 00.00 22 | 6 | Test Reports | Inspection Report | (e): 3.3.2; (f): G
574 |  |  | 07 84 00.00 22 | 7 | Certificates | Firestopping Inspector Qualifications | (e): 1.5.2
575 |  |  | 07 84 00.00 22 | 7 | Certificates | Firestopping Materials | (e): 2.2
576 |  |  | 07 84 00.00 22 | 7 | Certificates | Firestopping Materials | (e): 3.1
577 |  |  | 07 84 00.00 22 | 7 | Certificates | Firestopping Installer Qualifications | (e): 1.5.1
578 |  |  | 07 92 00 | 3 | Product Data | Sealants | (e): 2.1; (f): G
579 |  |  | 07 92 00 | 3 | Product Data | Primers | (e): 2.2
580 |  |  | 07 92 00 | 3 | Product Data | Bond Breakers | (e): 2.3
581 |  |  | 07 92 00 | 3 | Product Data | Backstops | (e): 2.4; (f): G
582 |  |  | 07 92 00 | 7 | Certificates | Indoor Air Quality For Interior Sealants | bar: (f)
583 |  |  | 08 01 52 | 2 | Shop Drawings | Shop Drawings | (e): 1.4; (f): G
584 |  |  | 08 01 52 | 2 | Shop Drawings | Evaluation Survey | (e): 3.1; (f): G
585 |  |  | 08 01 52 | 3 | Product Data | Hardware | (e): 2.4; (f): G
586 |  |  | 08 01 52 | 3 | Product Data | Weatherstripping | (e): 3.2.10; (f): G
587 |  |  | 08 01 52 | 3 | Product Data | Qualifications | (e): 1.4; (f): G
588 |  |  | 08 01 52 | 4 | Samples | Hardware | (e): 2.4
589 |  |  | 08 01 52 | 4 | Samples | Moldings | (e): 3.2.10
590 |  |  | 08 01 52 | 4 | Samples | Weatherstripping | (e): 3.2.10
591 |  |  | 08 01 52 | 4 | Samples | Mock-up (Repair) | bar: (f)
592 |  |  | 08 11 13 | 2 | Shop Drawings | Doors | (e): 2.1; (f): G
593 |  |  | 08 11 13 | 2 | Shop Drawings | Doors | (e): 2.1; (f): G
594 |  |  | 08 11 13 | 2 | Shop Drawings | Frames | (e): 2.4; (f): G
595 |  |  | 08 11 13 | 2 | Shop Drawings | Frames | (e): 2.4; (f): G
596 |  |  | 08 11 13 | 2 | Shop Drawings | Accessories | (e): 2.2
597 |  |  | 08 11 13 | 3 | Product Data | Doors | (e): 2.1; (f): G
598 |  |  | 08 11 13 | 3 | Product Data | Frames | (e): 2.4; (f): G
599 |  |  | 08 11 13 | 3 | Product Data | Accessories | (e): 2.2
600 |  |  | 08 14 00 | 2 | Shop Drawings | Doors | (e): 2.1; (f): G
601 |  |  | 08 14 00 | 3 | Product Data | Doors | (e): 2.1; (f): G
602 |  |  | 08 14 00 | 3 | Product Data | Accessories | (e): 2.2
603 |  |  | 08 14 00 | 3 | Product Data | Water-resistant Sealer | (e): 2.3.6
604 |  |  | 08 14 00 | 3 | Product Data | Warranty | (e): 1.5
605 |  |  | 08 14 00 | 4 | Samples | Door Finish Colors | (e): 2.3.5.2; (f): G
606 |  |  | 08 14 00 | 6 | Test Reports | Cycle-Slam | (e): 2.4
607 |  |  | 08 14 00 | 6 | Test Reports | Hinge Loading Resistance | (e): 2.4
608 |  |  | 08 14 00 | 11 | Closeout Submittals | Warranty | (e): 1.5
609 |  |  | 08 31 00 | 3 | Product Data | Access Doors And Panels | (e): 1.3; (f): G
610 |  |  | 08 31 00 | 3 | Product Data | Hardware | (e): 1.3.1; (f): G
611 |  |  | 08 31 00 | 3 | Product Data | Accessories | (e): 2.2.6; (f): G
612 |  |  | 08 31 00 | 3 | Product Data | Recycled Content | (e): 2.1
613 |  |  | 08 33 23 | 2 | Shop Drawings | Overhead Coiling Doors | (e): 2.2.1; (f): G
614 |  |  | 08 33 23 | 2 | Shop Drawings | Counterbalancing Mechanism | (e): 2.2.3; (f): G
615 |  |  | 08 33 23 | 2 | Shop Drawings | Manual Door Operators | (e): 2.2.4; (f): G
616 |  |  | 08 33 23 | 2 | Shop Drawings | Electric Door Operators | (e): 2.2.5; (f): G
617 |  |  | 08 33 23 | 2 | Shop Drawings | Bottom Bars | (e): 2.2.1.3; (f): G
618 |  |  | 08 33 23 | 2 | Shop Drawings | Guides | (e): 2.1.1.1; (f): G
619 |  |  | 08 33 23 | 2 | Shop Drawings | Mounting Brackets | (e): 2.2.3.1; (f): G
620 |  |  | 08 33 23 | 2 | Shop Drawings | Hood | (e): 2.2.2.2; (f): G
621 |  |  | 08 33 23 | 2 | Shop Drawings | Installation Drawings | (e): 2.1.1.1; (f): G
622 |  |  | 08 33 23 | 3 | Product Data | Overhead Coiling Doors | (e): 2.2.1; (f): G
623 |  |  | 08 33 23 | 3 | Product Data | Hardware | (e): 2.2.2; (f): G
624 |  |  | 08 33 23 | 3 | Product Data | Counterbalancing Mechanism | (e): 2.2.3; (f): G
625 |  |  | 08 33 23 | 3 | Product Data | Manual Door Operators | (e): 2.2.4; (f): G
626 |  |  | 08 33 23 | 3 | Product Data | Electric Door Operators | (e): 2.2.5; (f): G
627 |  |  | 08 33 23 | 3 | Product Data | Recycled content for steel curtain slats | (e): 2.2.1.1; (f): S
628 |  |  | 08 33 23 | 5 | Design Data | Overhead Coiling Doors | (e): 2.2.1; (f): G
629 |  |  | 08 33 23 | 5 | Design Data | Hardware | (e): 2.2.2; (f): G
630 |  |  | 08 33 23 | 5 | Design Data | Counterbalancing Mechanism | (e): 2.2.3; (f): G
631 |  |  | 08 33 23 | 5 | Design Data | Electric Door Operators | (e): 2.2.5; (f): G
632 |  |  | 08 33 23 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 1.3.2; (f): G
633 |  |  | 08 33 23 | 11 | Closeout Submittals | Warranty | (e): 1.3.1; (f): G
634 |  |  | 08 51 13 | 2 | Shop Drawings | Storm Windows | (e): 2.1; (f): G
635 |  |  | 08 51 13 | 3 | Product Data | Hardware | (e): 2.1.5; (f): G
636 |  |  | 08 51 13 | 3 | Product Data | Fasteners | (e): 2.1.4; (f): G
637 |  |  | 08 51 13 | 3 | Product Data | Accessories | (e): 2.1.5; (f): G
638 |  |  | 08 51 13 | 4 | Samples | Mock-Ups | (e): 1.4.2.1; (f): G
639 |  |  | 08 51 13 | 6 | Test Reports | Survey | (e): 3.2; (f): G
640 |  |  | 08 51 70 | 2 | Shop Drawings | Shop Drawings | (e): 1.5; (f): G
641 |  |  | 08 51 70 | 3 | Product Data | Hardware | (e): 2.4; (f): G
642 |  |  | 08 51 70 | 3 | Product Data | Weatherstripping | (e): 3.2.9; (f): G
643 |  |  | 08 51 70 | 3 | Product Data | Qualifications | (e): 1.5; (f): G
644 |  |  | 08 51 70 | 4 | Samples | Hardware | (e): 2.4; (f): G
645 |  |  | 08 51 70 | 4 | Samples | Weatherstripping | (e): 3.2.9; (f): G
646 |  |  | 08 51 70 | 4 | Samples | Survey | (e): 3.1.1; (f): G
647 |  |  | 08 71 00 | 2 | Shop Drawings | Hardware Schedule | (e): 1.4; (f): G
648 |  |  | 08 71 00 | 2 | Shop Drawings | Keying System | (e): 2.3.6; (f): G
649 |  |  | 08 71 00 | 3 | Product Data | Hardware Items | (e): 2.3; (f): G
650 |  |  | 08 71 00 | 8 | Manufacturer's Instructions | Installation | (e): 3.1
651 |  |  | 08 71 00 | 10 | Operation and Maintenance Data | Hardware Schedule | (e): 1.4; (f): G
652 |  |  | 08 71 00 | 11 | Closeout Submittals | Key Bitting | (e): 1.5.1
653 |  |  | 08 81 00 | 3 | Product Data | Glass | bar: (f)
654 |  |  | 08 81 00 | 3 | Product Data | Glazing Accessories | (e): 1.3; (f): G
655 |  |  | 08 81 00 | 3 | Product Data | Window Film | bar: (f)
656 |  |  | 08 81 00 | 8 | Manufacturer's Instructions | Setting and Sealing Materials | (e): 2.2
657 |  |  | 08 81 00 | 8 | Manufacturer's Instructions | Glass Setting | (e): 3.2
658 |  |  | 08 91 00 | 2 | Shop Drawings | Metal Louvers | (e): 1.4; (f): G
659 |  |  | 08 91 00 | 2 | Shop Drawings | Metal Louvers | (e): 2.2; (f): G
660 |  |  | 08 91 00 | 3 | Product Data | Metal Louvers | (e): 1.4; (f): G
661 |  |  | 08 91 00 | 3 | Product Data | Metal Louvers | (e): 2.2; (f): G
662 |  |  | 08 91 00 | 4 | Samples | Metal Louver Samples | (e): 1.5; (f): G
663 |  |  | 09 01 90.50 | 3 | Product Data | Work Plan | (e): 1.2; (f): G
664 |  |  | 09 01 90.50 | 3 | Product Data | Materials | (e): 1.2
665 |  |  | 09 01 90.50 | 3 | Product Data | Qualifications | (e): 1.4.4
666 |  |  | 09 01 90.50 | 7 | Certificates | Work Plan | (e): 1.2
667 |  |  | 09 01 90.60 | 3 | Product Data | Work Plan | (e): 1.2; (f): G
668 |  |  | 09 01 90.60 | 3 | Product Data | Chemical Paint Removers | (e): 2.1
669 |  |  | 09 01 90.60 | 3 | Product Data | Qualifications | (e): 1.4.4
670 |  |  | 09 01 90.60 | 4 | Samples | Replacement Wood Flooring
671 |  |  | 09 01 90.60 | 4 | Samples | Wood Putty
672 |  |  | 09 01 90.60 | 4 | Samples | Stain
673 |  |  | 09 01 90.60 | 7 | Certificates | Work Plan | (e): 1.2
674 |  |  | 09 22 00 | 2 | Shop Drawings | Metal Support Systems | (e): 2.1; (f): G
675 |  |  | 09 22 00 | 3 | Product Data | Metal Support Systems | (e): 2.1
676 |  |  | 09 22 00 | 3 | Product Data | Recycled Content for Metal Support Systems | bar: (f)
677 |  |  | 09 29 00 | 3 | Product Data | Cementitious Backer Units | (e): 2.1.4; (f): G
678 |  |  | 09 29 00 | 3 | Product Data | Glass Mat Water-Resistant Gypsum Tile Backing Board | (e): 2.1.3; (f): G
679 |  |  | 09 29 00 | 3 | Product Data | Water-Resistant Gypsum Backing Board | (e): 2.1.2; (f): G
680 |  |  | 09 29 00 | 3 | Product Data | Accessories | (e): 2.1.8
681 |  |  | 09 29 00 | 3 | Product Data | Gypsum Board | (e): 2.1.1; (f): G
682 |  |  | 09 29 00 | 3 | Product Data | Shaftwall Liner Panel | (e): 2.1.7; (f): G
683 |  |  | 09 29 00 | 3 | Product Data | Recycled Content for Paper Facing and Gypsum Cores | bar: (f)
684 |  |  | 09 29 00 | 3 | Product Data | VOC Content of Joint Compound | bar: (f)
685 |  |  | 09 29 00 | 7 | Certificates | Asbestos Free Materials | (e): 2.1; (f): G
686 |  |  | 09 29 00 | 7 | Certificates | Indoor Air Quality for Gypsum Board | (e): 2.1.1
687 |  |  | 09 29 00 | 8 | Manufacturer's Instructions | Safety Data Sheets | (e): 2.1
688 |  |  | 09 29 00 | 10 | Operation and Maintenance Data | Manufacturer Maintenance Instructions | (e): 2.1
689 |  |  | 09 30 10 | 3 | Product Data | Porcelain Tile | (e): 2.1.1; (f): G
690 |  |  | 09 30 10 | 3 | Product Data | Transition Strips | (e): 2.5.1; (f): G
691 |  |  | 09 30 10 | 3 | Product Data | Mortar, Grout, and Adhesive | (e): 2.3; (f): G
692 |  |  | 09 30 10 | 8 | Manufacturer's Instructions | Manufacturer's Approved Cleaning Instructions | (e): 3.8
693 |  |  | 09 51 00 | 3 | Product Data | Acoustical Units | (e): 2.2; (f): G
694 |  |  | 09 65 00 | 3 | Product Data | Resilient Flooring and Accessories | (e): 2.8; (f): G
695 |  |  | 09 65 00 | 3 | Product Data | Adhesives | (e): 2.4
696 |  |  | 09 65 00 | 3 | Product Data | Solid Vinyl Tile | (e): 2.1
697 |  |  | 09 65 00 | 3 | Product Data | Wall Base | (e): 2.2
698 |  |  | 09 65 00 | 8 | Manufacturer's Instructions | Surface Preparation | (e): 3.2; (f): G
699 |  |  | 09 65 00 | 8 | Manufacturer's Instructions | Installation | (e): 3.1; (f): G
700 |  |  | 09 65 00 | 10 | Operation and Maintenance Data | Resilient Flooring and Accessories | (e): 2.8; (f): G
701 |  |  | 09 67 23.13 | 2 | Shop Drawings | Installation Drawings | (e): 2.1; (f): G
702 |  |  | 09 67 23.13 | 4 | Samples | Hardboard Mounted Epoxy Flooring | (e): 1.5.3; (f): G
703 |  |  | 09 67 23.13 | 4 | Samples | Mockups | (e): 1.5.1; (f): G
704 |  |  | 09 67 23.13 | 5 | Design Data | Design Mix Data | (e): 1.2.3; (f): G
705 |  |  | 09 67 23.13 | 7 | Certificates | Listing of Product Installations | (e): 1.5.2
706 |  |  | 09 67 23.13 | 7 | Certificates | Referenced Standards Certificates | (e): 1.5
707 |  |  | 09 67 23.13 | 11 | Closeout Submittals | Warranty | (e): 1.6; (f): G
708 |  |  | 09 68 00 | 3 | Product Data | Carpet | (e): 2.1; (f): G
709 |  |  | 09 68 00 | 3 | Product Data | Carpet | (e): 2.3; (f): G
710 |  |  | 09 68 00 | 3 | Product Data | Carpet | (e): 2.5; (f): G
711 |  |  | 09 68 00 | 3 | Product Data | Moldings | (e): 2.8; (f): G
712 |  |  | 09 68 00 | 6 | Test Reports | Moisture and Alkalinity Tests | (e): 3.2; (f): G
713 |  |  | 09 68 00 | 8 | Manufacturer's Instructions | Surface Preparation | (e): 3.1
714 |  |  | 09 68 00 | 10 | Operation and Maintenance Data | Cleaning and Protection | (e): 3.5; (f): G
715 |  |  | 09 68 00 | 11 | Closeout Submittals | Warranty | (e): 1.5; (f): G
716 |  |  | 09 90 00 | 3 | Product Data | Coating | (e): 2.1; (f): G
717 |  |  | 09 90 00 | 3 | Product Data | Product Data Sheets | (e): 2.1
718 |  |  | 09 90 00 | 3 | Product Data | Sealant | (e): 3.3.5
719 |  |  | 09 90 00 | 8 | Manufacturer's Instructions | Application Instructions | (e): 3.4.1
720 |  |  | 09 90 00 | 8 | Manufacturer's Instructions | Mixing | (e): 2.1
721 |  |  | 09 90 00 | 10 | Operation and Maintenance Data | Coatings | (e): 2.1; (f): G
722 |  |  | 10 14 00.20 | 2 | Shop Drawings | Detail Drawings | (e): 1.4.1; (f): G
723 |  |  | 10 14 00.20 | 3 | Product Data | Installation | (e): 3.1; (f): G
724 |  |  | 10 14 00.20 | 3 | Product Data | Warranty | (e): 1.6; (f): G
725 |  |  | 10 14 00.20 | 4 | Samples | Software | (e): 1.3; (f): G
726 |  |  | 10 14 00.20 | 10 | Operation and Maintenance Data | Protection and Cleaning | (e): 3.1.1; (f): G
727 |  |  | 10 21 13 | 2 | Shop Drawings | Fabrication Drawings | (e): 2.1; (f): G
728 |  |  | 10 21 13 | 2 | Shop Drawings | Installation Drawings | (e): 3.2; (f): G
729 |  |  | 10 21 13 | 3 | Product Data | Cleaning and Maintenance Instructions | (e): 2.1; (f): G
730 |  |  | 10 21 13 | 3 | Product Data | Colors And Finishes | (e): 2.7
731 |  |  | 10 21 13 | 3 | Product Data | Anchoring Devices and Fasteners | (e): 2.2.1
732 |  |  | 10 21 13 | 3 | Product Data | Hardware and Fittings | (e): 2.2.3
733 |  |  | 10 21 13 | 3 | Product Data | Brackets | (e): 2.2.2
734 |  |  | 10 21 13 | 3 | Product Data | Door Hardware | (e): 2.2.4
735 |  |  | 10 21 13 | 3 | Product Data | Toilet Enclosures | (e): 2.3.1
736 |  |  | 10 21 13 | 3 | Product Data | Urinal Screens | (e): 2.3.2
737 |  |  | 10 21 13 | 3 | Product Data | Pilaster Shoes | (e): 2.5
738 |  |  | 10 21 13 | 3 | Product Data | Finishes | (e): 2.2.3.2; (f): G
739 |  |  | 10 21 13 | 7 | Certificates | Warranty | (e): 1.5; (f): G
740 |  |  | 10 21 13 | 10 | Operation and Maintenance Data | Plastic Identification | (e): 2.1.1; (f): G
741 |  |  | 10 26 00 | 3 | Product Data | Wall Panels | (e): 2.2; (f): G
742 |  |  | 10 26 00 | 10 | Operation and Maintenance Data | Wall Panels | (e): 2.2; (f): G
743 |  |  | 10 28 13 | 3 | Product Data | Finishes | (e): 2.1.2; (f): G
744 |  |  | 10 28 13 | 3 | Product Data | Accessory Items | (e): 2.2; (f): G
745 |  |  | 10 28 13 | 4 | Samples | Finishes | (e): 2.1.2; (f): G
746 |  |  | 10 28 13 | 4 | Samples | Accessory Items | (e): 2.2
747 |  |  | 10 44 16 | 2 | Shop Drawings | Fire Extinguishers | (e): 2.1.1; (f): G
748 |  |  | 10 44 16 | 2 | Shop Drawings | Accessories | (e): Part 2; (f): G
749 |  |  | 10 44 16 | 2 | Shop Drawings | Cabinets | (e): Part 2; (f): G
750 |  |  | 10 44 16 | 2 | Shop Drawings | Wall Brackets | (e): 2.2.2; (f): G
751 |  |  | 10 44 16 | 2 | Shop Drawings | Schedule | (e): 1.5; (f): G
752 |  |  | 10 44 16 | 3 | Product Data | Fire Extinguishers | (e): 2.1.1; (f): G
753 |  |  | 10 44 16 | 3 | Product Data | Accessories | (e): Part 2; (f): G
754 |  |  | 10 44 16 | 3 | Product Data | Cabinets | (e): Part 2; (f): G
755 |  |  | 10 44 16 | 3 | Product Data | Wall Brackets | (e): 2.2.2; (f): G
756 |  |  | 10 44 16 | 3 | Product Data | Replacement Parts List | (e): 3.2.1; (f): G
757 |  |  | 10 44 16 | 4 | Samples | Equipment Samples | (e): 1.3.1; (f): G
758 |  |  | 10 44 16 | 7 | Certificates | Fire Extinguishers Certifications | (e): 2.1.1; (f): G
759 |  |  | 10 44 16 | 7 | Certificates | Manufacturer's Warranty with Inspection Tag | (e): 1.4; (f): G
760 |  |  | 12 00 01.00 20 | 1 | Preconstruction Submittals | FF&E Schedule and Schedule Updates | (e): 3.1.1.3; (f): G
761 |  |  | 12 00 01.00 20 | 1 | Preconstruction Submittals | Contractor's Interior Designer's Qualifications | (e): 3.1.1.1; (f): G
762 |  |  | 12 00 01.00 20 | 4 | Samples | BVD FF&E Mock-Up | (e): 3.1.2.6; (f): G
763 |  |  | 12 00 01.00 20 | 4 | Samples | Final FF&E Mock-Up | (e): 3.1.2.9; (f): G
764 |  |  | 12 00 01.00 20 | 4 | Samples | Interior Finish Construction Submittals | (e): 3.1.2.13; (f): G
765 |  |  | 12 00 01.00 20 | 4 | Samples | Post Option Award FF&E Finish Submittals | (e): 3.2.2; (f): G
766 |  |  | 12 00 01.00 20 | 5 | Design Data | FF&E Basis of Design Package | (e): 3.1.2.2.2; (f): G
767 |  |  | 12 00 01.00 20 | 5 | Design Data | FF&E BVD Request for Quotation (RFQ) Package | (e): 3.1.2.5; (f): G
768 |  |  | 12 00 01.00 20 | 5 | Design Data | BVD Package | (e): 3.1.2.7; (f): G
769 |  |  | 12 00 01.00 20 | 5 | Design Data | Pre-Final FF&E Package 'Over the Shoulder' | (e): 3.1.2.10; (f): G
770 |  |  | 12 00 01.00 20 | 5 | Design Data | Pre-Final FF&E Package | (e): 3.1.2.11; (f): G
771 |  |  | 12 00 01.00 20 | 5 | Design Data | Final FF&E Package | (e): 3.1.2.9; (f): G
772 |  |  | 12 00 01.00 20 | 5 | Design Data | Final FF&E Package | (e): 3.1.2.12; (f): G
773 |  |  | 12 00 01.00 20 | 10 | Operation and Maintenance Data | Warranty and Maintenance Information | (e): 3.5.1; (f): G
774 |  |  | 12 00 01.00 20 | 11 | Closeout Submittals | Punch List(s) Submittal | (e): 3.3.2; (f): G
775 |  |  | 14 24 23 | 2 | Shop Drawings | Elevator | (e): 2.1; (f): G
776 |  |  | 14 24 23 | 2 | Shop Drawings | Elevator Components | (e): 1.2.1; (f): G
777 |  |  | 14 24 23 | 2 | Shop Drawings | Elevator Components | (e): 1.2.2; (f): G
778 |  |  | 14 24 23 | 2 | Shop Drawings | Elevator Machine | bar: (f)
779 |  |  | 14 24 23 | 2 | Shop Drawings | Elevator Controller | (e): 1.2.1; (f): G
780 |  |  | 14 24 23 | 2 | Shop Drawings | Wiring Diagrams | (e): 1.3.4; (f): G
781 |  |  | 14 24 23 | 2 | Shop Drawings | Elevator Machine Room Coordination Drawings | bar: (f)
782 |  |  | 14 24 23 | 3 | Product Data | Elevator | (e): 2.1; (f): G
783 |  |  | 14 24 23 | 3 | Product Data | Elevator Components | (e): 1.2.1; (f): G
784 |  |  | 14 24 23 | 3 | Product Data | Elevator Components | (e): 1.2.2; (f): G
785 |  |  | 14 24 23 | 3 | Product Data | Data Sheets | (e): 1.2.2; (f): G
786 |  |  | 14 24 23 | 3 | Product Data | Elevator Microprocessor Controller | (e): 2.5.2; (f): G
787 |  |  | 14 24 23 | 3 | Product Data | Auxiliary Power System | (e): 1.2.3.3; (f): G
788 |  |  | 14 24 23 | 3 | Product Data | Oil Heater | (e): 1.2.1; (f): G
789 |  |  | 14 24 23 | 3 | Product Data | Oil Cooler | (e): 1.2.1; (f): G
790 |  |  | 14 24 23 | 5 | Design Data | Heat Loads | (e): 1.2.3.2
791 |  |  | 14 24 23 | 5 | Design Data | Reaction Loads | (e): 1.2.3.1
792 |  |  | 14 24 23 | 7 | Certificates | Qualified Elevator Inspector (QEI) | (e): 3.2
793 |  |  | 14 24 23 | 7 | Certificates | Elevator Parts and Components Price Lists | bar: (f)
794 |  |  | 14 24 23 | 7 | Certificates | Warranty | (e): 1.4; (f): G
795 |  |  | 14 24 23 | 7 | Certificates | Elevator Technicians' Qualifications | bar: (f)
796 |  |  | 14 24 23 | 7 | Certificates | Endorsement Letter | (e): 1.3.1.1; (f): G
797 |  |  | 14 24 23 | 7 | Certificates | Welders' Qualifications | (e): 1.2.4; (f): G
798 |  |  | 14 24 23 | 7 | Certificates | Elevator Controller Certification | (e): 2.5.2.3; (f): G
799 |  |  | 14 24 23 | 10 | Operation and Maintenance Data | Elevator | (e): 2.1; (f): G
800 |  |  | 14 24 23 | 10 | Operation and Maintenance Data | Maintenance Control Program (MCP) | (e): 1.2.5; (f): G
801 |  |  | 14 24 23 | 10 | Operation and Maintenance Data | Software and Documentation | (e): 2.5.2.2; (f): G
802 |  |  | 21 13 13 | 1 | Preconstruction Submittals | Qualified Fire Protection Engineer (QFPE) | (e): 1.2.3; (f): G
803 |  |  | 21 13 13 | 1 | Preconstruction Submittals | Sprinkler System Designer | (e): 1.4.2.1; (f): G
804 |  |  | 21 13 13 | 1 | Preconstruction Submittals | Sprinkler System Installer | (e): 1.4.2.2; (f): G
805 |  |  | 21 13 13 | 2 | Shop Drawings | Shop Drawing | (e): 1.4.1.1; (f): G
806 |  |  | 21 13 13 | 3 | Product Data | Piping | (e): 2.2; (f): G
807 |  |  | 21 13 13 | 3 | Product Data | Fittings | (e): 2.2.1.2; (f): G
808 |  |  | 21 13 13 | 3 | Product Data | Valves | (e): 2.2.4; (f): G
809 |  |  | 21 13 13 | 3 | Product Data | Relief Valves | (e): 2.7.5; (f): G
810 |  |  | 21 13 13 | 3 | Product Data | Sprinklers | (e): 2.6; (f): G
811 |  |  | 21 13 13 | 3 | Product Data | Pipe Hangers and Supports | (e): 2.2.3; (f): G
812 |  |  | 21 13 13 | 3 | Product Data | Sprinkler Alarm Switch | (e): 2.3.1; (f): G
813 |  |  | 21 13 13 | 3 | Product Data | Valve Supervisory (Tamper) Switch | (e): 2.3.2; (f): G
814 |  |  | 21 13 13 | 3 | Product Data | Fire Department Connection | (e): 2.5; (f): G
815 |  |  | 21 13 13 | 3 | Product Data | Backflow Prevention Assembly | (e): 2.4; (f): G
816 |  |  | 21 13 13 | 3 | Product Data | Air Vent | (e): 2.7.6; (f): G
817 |  |  | 21 13 13 | 3 | Product Data | Hose Valve | (e): 2.4.1; (f): G
818 |  |  | 21 13 13 | 3 | Product Data | Nameplates | (e): 2.1.2; (f): G
819 |  |  | 21 13 13 | 5 | Design Data | Hydraulic Calculations | (e): 1.2.1.2; (f): G
820 |  |  | 21 13 13 | 6 | Test Reports | Test Procedures | (e): 3.6.1; (f): G
821 |  |  | 21 13 13 | 7 | Certificates | Verification of Compliant Installation | (e): 3.6.2.1; (f): G
822 |  |  | 21 13 13 | 7 | Certificates | Request for Government Final Test | (e): 3.6.2.2; (f): G
823 |  |  | 21 13 13 | 10 | Operation and Maintenance Data | Operating and Maintenance (O&M) Instructions | (e): 3.8; (f): G
824 |  |  | 21 13 13 | 10 | Operation and Maintenance Data | Spare Parts | (e): 1.6; (f): G
825 |  |  | 21 13 13 | 11 | Closeout Submittals | As-built drawings | (e): 3.8
826 |  |  | 21 30 00 | 1 | Preconstruction Submittals | Fire Pump Installation Related Submittals | (e): 1.3
827 |  |  | 21 30 00 | 1 | Preconstruction Submittals | Qualified Fire Protection Engineer (QFPE) | (e): 1.7.1; (f): G
828 |  |  | 21 30 00 | 2 | Shop Drawings | Installation Drawings | (e): 3.3.1; (f): G
829 |  |  | 21 30 00 | 2 | Shop Drawings | As-Built Drawings | (e): 3.10.2; (f): G
830 |  |  | 21 30 00 | 2 | Shop Drawings | Piping Layout | (e): 3.3.2; (f): G
831 |  |  | 21 30 00 | 2 | Shop Drawings | Pump Room | (e): 3.3.2; (f): G
832 |  |  | 21 30 00 | 3 | Product Data | Catalog Data | (e): 2.1; (f): G
833 |  |  | 21 30 00 | 3 | Product Data | Spare Parts | (e): 1.6
834 |  |  | 21 30 00 | 3 | Product Data | Preliminary Tests | (e): 3.8.2
835 |  |  | 21 30 00 | 3 | Product Data | Field Tests | (e): 3.8; (f): G
836 |  |  | 21 30 00 | 3 | Product Data | Manufacturer's Representative | (e): 1.7.6; (f): G
837 |  |  | 21 30 00 | 3 | Product Data | Field Training | (e): 3.10.1; (f): G
838 |  |  | 21 30 00 | 3 | Product Data | Navy Formal Inspection and Tests | (e): 3.8.3
839 |  |  | 21 30 00 | 6 | Test Reports | Preliminary Tests | (e): 3.8.2
840 |  |  | 21 30 00 | 6 | Test Reports | Navy Formal Inspection and Tests | (e): 3.8.3; (f): G
841 |  |  | 21 30 00 | 7 | Certificates | Qualified Fire Protection Engineer (QFPE) | (e): 1.7.1
842 |  |  | 21 30 00 | 7 | Certificates | Qualifications of Welders | (e): 1.7.2
843 |  |  | 21 30 00 | 7 | Certificates | Qualifications of Installer | (e): 1.7.3
844 |  |  | 21 30 00 | 7 | Certificates | Preliminary Test Certification | (e): 1.7.4
845 |  |  | 21 30 00 | 7 | Certificates | Final Test Certification | (e): 1.7.5
846 |  |  | 21 30 00 | 10 | Operation and Maintenance Data | Operating and Maintenance Instructions | (e): 3.10.1; (f): G
847 |  |  | 21 30 00 | 10 | Operation and Maintenance Data | Flow Meter | (e): 2.13
848 |  |  | 22 00 00 | 2 | Shop Drawings | Coordination Information | (e): 1.2
849 |  |  | 22 00 00 | 3 | Product Data | Pipe Materials | (e): 2.1.1; (f): G
850 |  |  | 22 00 00 | 3 | Product Data | Pipe Fittings | (e): 2.1.2; (f): G
851 |  |  | 22 00 00 | 3 | Product Data | Valves | (e): 2.3; (f): G
852 |  |  | 22 00 00 | 3 | Product Data | Valve Operating Mechanisms | (e): 2.3.1; (f): G
853 |  |  | 22 00 00 | 3 | Product Data | Backflow Preventers | (e): 2.7; (f): G
854 |  |  | 22 00 00 | 3 | Product Data | Thermostatic Mixing Valves | (e): 2.3.5; (f): G
855 |  |  | 22 00 00 | 3 | Product Data | Wall Hydrant | (e): 2.3.4; (f): G
856 |  |  | 22 00 00 | 3 | Product Data | Automatic Flow Control Valves | (e): 2.3.7; (f): G
857 |  |  | 22 00 00 | 3 | Product Data | Coffee Maker Outlet Box | (e): 2.4.1; (f): G
858 |  |  | 22 00 00 | 3 | Product Data | Flush Valve Water Closets | (e): 2.5.1; (f): G
859 |  |  | 22 00 00 | 3 | Product Data | Flush Valve Urinals | (e): 2.5.2; (f): G
860 |  |  | 22 00 00 | 3 | Product Data | Wall Hung Lavatories | (e): 2.5.4; (f): G
861 |  |  | 22 00 00 | 3 | Product Data | Countertop Lavatories | (e): 2.5.3; (f): G
862 |  |  | 22 00 00 | 3 | Product Data | General Purpose Sinks | (e): 2.5.5; (f): G
863 |  |  | 22 00 00 | 3 | Product Data | Utility Sink | (e): 2.5.6; (f): G
864 |  |  | 22 00 00 | 3 | Product Data | Three-Station Sink | (e): 2.5.7; (f): G
865 |  |  | 22 00 00 | 3 | Product Data | Mop Receptors | (e): 2.5.8; (f): G
866 |  |  | 22 00 00 | 3 | Product Data | Electric Water Coolers | (e): 2.5.9; (f): G
867 |  |  | 22 00 00 | 3 | Product Data | Emergency Eye and Face Wash | (e): 2.5.10; (f): G
868 |  |  | 22 00 00 | 3 | Product Data | Expansion Tanks | (e): 2.9; (f): G
869 |  |  | 22 00 00 | 3 | Product Data | Electric Water Heater | (e): 2.1; (f): G
870 |  |  | 22 00 00 | 3 | Product Data | Pumps | (e): 2.11; (f): G
871 |  |  | 22 00 00 | 3 | Product Data | Trap Primer Assembly | (e): 2.15.6; (f): G
872 |  |  | 22 00 00 | 3 | Product Data | Water Hammer Arresters | (e): 3.1.1.8; (f): G
873 |  |  | 22 00 00 | 3 | Product Data | Hose Bibbs | (e): 2.3.3; (f): G
874 |  |  | 22 00 00 | 3 | Product Data | Floor Drains | (e): 2.6.1; (f): G
875 |  |  | 22 00 00 | 3 | Product Data | Floor Sinks | (e): 2.6.2; (f): G
876 |  |  | 22 00 00 | 3 | Product Data | Compressed Air System | (e): 2.12; (f): G
877 |  |  | 22 00 00 | 6 | Test Reports | Tests, Flushing and Disinfection | (e): 3.7; (f): G
878 |  |  | 22 00 00 | 6 | Test Reports | Post Installation Sanitary System Survey | (e): 3.7.1.3; (f): G
879 |  |  | 22 00 00 | 10 | Operation and Maintenance Data | Fixtures | (e): 2.5; (f): G
880 |  |  | 22 00 00 | 10 | Operation and Maintenance Data | Plumbing System | (e): 3.7.1; (f): G
881 |  |  | 23 03 00.00 20 | 2 | Shop Drawings | ATFP Bracing Details | (e): 1.10.1; (f): G
882 |  |  | 23 03 00.00 20 | 3 | Product Data | ATFP Bracing Components | (e): 1.10.1; (f): G
883 |  |  | 23 05 48.00 40 | 2 | Shop Drawings | Installation Drawings | (e): 1.2; (f): G
884 |  |  | 23 05 48.00 40 | 2 | Shop Drawings | Outline Drawings | (e): 1.2; (f): G
885 |  |  | 23 05 48.00 40 | 3 | Product Data | Equipment and Performance Data | (e): 1.2; (f): G
886 |  |  | 23 05 48.00 40 | 3 | Product Data | Isolators | (e): 2.2.6; (f): G
887 |  |  | 23 05 48.00 40 | 6 | Test Reports | Type of Isolator | (e): 2.4; (f): G
888 |  |  | 23 05 48.00 40 | 6 | Test Reports | Type of Base | (e): 2.4; (f): G
889 |  |  | 23 05 48.00 40 | 6 | Test Reports | Allowable Deflection | (e): 2.4; (f): G
890 |  |  | 23 05 48.00 40 | 6 | Test Reports | Measured Deflection | (e): 2.4; (f): G
891 |  |  | 23 05 93 | 1 | Preconstruction Submittals | Records of Existing Conditions | (e): 1.3.3; (f): G
892 |  |  | 23 05 93 | 1 | Preconstruction Submittals | Independent TAB Agency and Personnel Qualifications | (e): 1.5.1; (f): G
893 |  |  | 23 05 93 | 1 | Preconstruction Submittals | TAB Design Review Report | (e): 1.5.4.2; (f): G
894 |  |  | 23 05 93 | 2 | Shop Drawings | TAB Schematic Drawings and Report Forms | (e): 1.3.3; (f): G
895 |  |  | 23 05 93 | 3 | Product Data | Equipment and Performance Data | (e): 1.3; (f): G
896 |  |  | 23 05 93 | 3 | Product Data | TAB Related HVAC Submittals | (e): 1.5.1.3; (f): G
897 |  |  | 23 05 93 | 6 | Test Reports | Completed Pre-Final DALT Report | (e): 3.2.5; (f): G
898 |  |  | 23 05 93 | 6 | Test Reports | Certified Final DALT Report | (e): 3.2.8; (f): G
899 |  |  | 23 05 93 | 6 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.5.4.4; (f): G
900 |  |  | 23 05 93 | 6 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.5.4.4; (f): G
901 |  |  | 23 05 93 | 6 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.5.4.4; (f): G
902 |  |  | 23 05 93 | 6 | Test Reports | Proportional Balancing | (e): 3.3.6.1; (f): G
903 |  |  | 23 05 93 | 6 | Test Reports | Season 1 | (e): 3.3.6.2; (f): G
904 |  |  | 23 05 93 | 6 | Test Reports | Season 2 | (e): 3.3.6.2; (f): G
905 |  |  | 23 05 93 | 7 | Certificates | Independent TAB Agency and Personnel Qualifications | (e): 1.5.1; (f): G
906 |  |  | 23 05 93 | 7 | Certificates | DALT and TAB Submittal and Work Schedule | (e): 1.5.4.1; (f): G
907 |  |  | 23 05 93 | 7 | Certificates | TAB Pre-Field Engineering Report | (e): 1.5.4.4; (f): G
908 |  |  | 23 05 93 | 7 | Certificates | Instrument Calibration Certificates | (e): 1.5.5; (f): G
909 |  |  | 23 05 93 | 7 | Certificates | DALT and TAB Procedures Summary | (e): 3.6; (f): G
910 |  |  | 23 05 93 | 7 | Certificates | Completed Pre-Final DALT Work Checklist | (e): 3.6; (f): G
911 |  |  | 23 05 93 | 7 | Certificates | Advance Notice of Pre-Final DALT Field Work | (e): 3.2.2; (f): G
912 |  |  | 23 05 93 | 7 | Certificates | Proportional Balancing | (e): 3.3.6.1; (f): G
913 |  |  | 23 05 93 | 7 | Certificates | Season 1 | (e): 3.3.6.2; (f): G
914 |  |  | 23 05 93 | 7 | Certificates | Season 2 | (e): 3.3.6.2; (f): G
915 |  |  | 23 07 00 | 2 | Shop Drawings | Coordination Information | (e): 1.3
916 |  |  | 23 07 00 | 3 | Product Data | Pipe Insulation Systems | (e): 2.3; (f): G
917 |  |  | 23 07 00 | 3 | Product Data | Pipe Insulation Systems | (e): 3.2; (f): G
918 |  |  | 23 07 00 | 3 | Product Data | Duct Insulation Systems | (e): 3.3; (f): G
919 |  |  | 23 07 00 | 3 | Product Data | Equipment Insulation Systems | (e): 3.4; (f): G
920 |  |  | 23 07 00 | 8 | Manufacturer's Instructions | Pipe Insulation Systems | (e): 2.3
921 |  |  | 23 07 00 | 8 | Manufacturer's Instructions | Pipe Insulation Systems | (e): 3.2
922 |  |  | 23 07 00 | 8 | Manufacturer's Instructions | Duct Insulation Systems | (e): 3.3
923 |  |  | 23 07 00 | 8 | Manufacturer's Instructions | Equipment Insulation Systems | (e): 3.4
924 |  |  | 23 08 00 | 6 | Test Reports | Pipe Flushing, Testing, And Water Treatment Reports | (e): 1.5; (f): G
925 |  |  | 23 08 00 | 6 | Test Reports | Completed Pre-Functional Checklists | (e): 3.3; (f): G
926 |  |  | 23 08 00 | 6 | Test Reports | Seasonal Test Report | (e): 3.12; (f): G
927 |  |  | 23 08 00 | 6 | Test Reports | Full-Load Test Report | (e): 3.13; (f): G
928 |  |  | 23 08 00 | 7 | Certificates | Certificate Of Readiness | (e): 1.6; (f): G
929 |  |  | 23 09 00.00 22 | 2 | Shop Drawings | DDC Contractor Design Drawings | (e): 3.3; (f): G
930 |  |  | 23 09 00.00 22 | 2 | Shop Drawings | Draft As-Built Drawings | (e): 3.3; (f): G
931 |  |  | 23 09 00.00 22 | 2 | Shop Drawings | Final As-Built Drawings | (e): 3.3; (f): G
932 |  |  | 23 09 00.00 22 | 3 | Product Data | Programming Software | (e): 1.8.3; (f): G
933 |  |  | 23 09 00.00 22 | 3 | Product Data | Controller Application Programs | (e): 1.8.4; (f): G
934 |  |  | 23 09 00.00 22 | 3 | Product Data | Configuration Software | (e): 1.8.1; (f): G
935 |  |  | 23 09 00.00 22 | 3 | Product Data | Controller Configuration Settings | (e): 1.8.2; (f): G
936 |  |  | 23 09 00.00 22 | 3 | Product Data | Manufacturer's Product Data | (e): 2.2; (f): G
937 |  |  | 23 09 00.00 22 | 3 | Product Data | Niagara Framework Supervisory Gateway Backups | (e): 1.8.5; (f): G
938 |  |  | 23 09 00.00 22 | 6 | Test Reports | Existing Conditions Report | (e): 3.1.1; (f): G
939 |  |  | 23 09 00.00 22 | 6 | Test Reports | Pre-Construction Quality Control (QC) Checklist | (e): 1.9.1; (f): G
940 |  |  | 23 09 00.00 22 | 6 | Test Reports | Post-Construction Quality Control (QC) Checklist | (e): 1.9.2; (f): G
941 |  |  | 23 09 00.00 22 | 6 | Test Reports | Start-Up Testing Report | (e): 3.5.2; (f): G
942 |  |  | 23 09 00.00 22 | 6 | Test Reports | Control Contractor's Performance Verification Testing Plan | (e): 3.6.5; (f): G
943 |  |  | 23 09 00.00 22 | 6 | Test Reports | Equipment Supplier's Performance Verification Testing Plan | (e): 3.6.3.1; (f): G
944 |  |  | 23 09 00.00 22 | 6 | Test Reports | Endurance Testing Results | (e): 3.6.8.3; (f): G
945 |  |  | 23 09 00.00 22 | 6 | Test Reports | Performance Verification Test Report | (e): 3.6.9; (f): G
946 |  |  | 23 09 00.00 22 | 10 | Operation and Maintenance Data | Operation and Maintenance (O&M) Instructions | (e): 3.7; (f): G
947 |  |  | 23 09 00.00 22 | 10 | Operation and Maintenance Data | Training Documentation | (e): 3.9.1; (f): G
948 |  |  | 23 09 00.00 22 | 11 | Closeout Submittals | Enclosure Keys | (e): 2.5; (f): G
949 |  |  | 23 09 00.00 22 | 11 | Closeout Submittals | Password Summary Report | (e): 3.2.7.1; (f): G
950 |  |  | 23 09 00.00 22 | 11 | Closeout Submittals | Closeout Quality Control (QC) Checklist | (e): 1.9.3; (f): G
951 |  |  | 23 21 13.00 20 | 2 | Shop Drawings | Hot water heating system | (e): 1.3.1; (f): G
952 |  |  | 23 21 13.00 20 | 3 | Product Data | Finned tube radiators and convectors | (e): 2.4.1; (f): G
953 |  |  | 23 21 13.00 20 | 3 | Product Data | Calibrated balancing valves | (e): 2.1.6.6; (f): G
954 |  |  | 23 21 13.00 20 | 3 | Product Data | Combination strainer and pump suction diffuser | (e): 2.1.10; (f): G
955 |  |  | 23 21 13.00 20 | 3 | Product Data | Pumps | (e): 2.3.1; (f): G
956 |  |  | 23 21 13.00 20 | 3 | Product Data | Expansion tanks | (e): 2.3.2; (f): G
957 |  |  | 23 21 13.00 20 | 3 | Product Data | Air separation tanks | (e): 2.3.3; (f): G
958 |  |  | 23 21 13.00 20 | 3 | Product Data | Hot water heating pipe | (e): 2.1.1; (f): G
959 |  |  | 23 21 13.00 20 | 3 | Product Data | Bypass chemical feeder | (e): 2.9.1; (f): G
960 |  |  | 23 21 13.00 20 | 6 | Test Reports | Hydrostatic test of piping system | (e): 3.4.1; (f): G
961 |  |  | 23 21 13.00 20 | 6 | Test Reports | Auxiliary equipment and accessory tests | (e): 3.4.2; (f): G
962 |  |  | 23 21 13.00 20 | 7 | Certificates | Welding procedures | (e): 1.5.2.1
963 |  |  | 23 21 13.00 20 | 7 | Certificates | Welder's qualifications | (e): 1.5.2.2
964 |  |  | 23 21 13.00 20 | 10 | Operation and Maintenance Data | Finned Tube Radiators and Convectors | (e): 2.4.1; (f): G
965 |  |  | 23 21 13.00 20 | 10 | Operation and Maintenance Data | Pumps | (e): 2.3.1; (f): G
966 |  |  | 23 21 13.00 20 | 10 | Operation and Maintenance Data | Calibrated Balancing Valves | (e): 2.1.6.6; (f): G
967 |  |  | 23 21 13.00 20 | 10 | Operation and Maintenance Data | Combination Strainer and Pump Suction Diffuser | (e): 2.1.10; (f): G
968 |  |  | 23 21 13.00 20 | 10 | Operation and Maintenance Data | Expansion tanks | (e): 2.3.2; (f): G
969 |  |  | 23 21 13.00 20 | 10 | Operation and Maintenance Data | Air separation tanks | (e): 2.3.3; (f): G
970 |  |  | 23 22 26.00 20 | 3 | Product Data | Convertors | (e): 2.3; (f): G
971 |  |  | 23 22 26.00 20 | 3 | Product Data | Condensate Return Pumping Units | (e): 2.4.1; (f): G
972 |  |  | 23 22 26.00 20 | 3 | Product Data | Valves | (e): 2.2.7; (f): G
973 |  |  | 23 22 26.00 20 | 3 | Product Data | Valve Operating Mechanism | (e): 2.2.7.7; (f): G
974 |  |  | 23 22 26.00 20 | 3 | Product Data | Steam Meters | (e): 2.2.11.1; (f): G
975 |  |  | 23 22 26.00 20 | 3 | Product Data | Traps | (e): 2.2.11.3; (f): G
976 |  |  | 23 22 26.00 20 | 3 | Product Data | Strainers | (e): 2.2.11.4; (f): G
977 |  |  | 23 22 26.00 20 | 3 | Product Data | Steam Separators | (e): 2.2.11.5; (f): G
978 |  |  | 23 22 26.00 20 | 3 | Product Data | Flash Tanks | (e): 2.2.11.8; (f): G
979 |  |  | 23 22 26.00 20 | 3 | Product Data | Expansion Joints | (e): 2.2.9; (f): G
980 |  |  | 23 22 26.00 20 | 3 | Product Data | Instrumentation | (e): 2.2.10; (f): G
981 |  |  | 23 22 26.00 20 | 6 | Test Reports | Steam Piping | (e): 2.2.1; (f): G
982 |  |  | 23 22 26.00 20 | 6 | Test Reports | Copper Tubing | (e): 2.2.8.2
983 |  |  | 23 22 26.00 20 | 6 | Test Reports | Valves | (e): 2.2.7
984 |  |  | 23 22 26.00 20 | 6 | Test Reports | Instrumentation | (e): 2.2.10
985 |  |  | 23 22 26.00 20 | 6 | Test Reports | Pipe and Pipe System | (e): 2.2; (f): G
986 |  |  | 23 22 26.00 20 | 6 | Test Reports | Convertors | (e): 2.3; (f): G
987 |  |  | 23 22 26.00 20 | 6 | Test Reports | Condensate Return Pumping Units | (e): 2.4.1; (f): G
988 |  |  | 23 22 26.00 20 | 7 | Certificates | Welding Procedure | (e): 1.4.1; (f): G
989 |  |  | 23 22 26.00 20 | 7 | Certificates | Welder's Performance Qualification Record | (e): 1.4.2; (f): G
990 |  |  | 23 22 26.00 20 | 7 | Certificates | List of Welders and Welder's Symbols | (e): 1.4.2
991 |  |  | 23 22 26.00 20 | 8 | Manufacturer's Instructions | Convertors | (e): 2.3; (f): G
992 |  |  | 23 22 26.00 20 | 8 | Manufacturer's Instructions | Condensate Return Pumping Units | (e): 2.4.1; (f): G
993 |  |  | 23 23 00 | 2 | Shop Drawings | Refrigerant Piping System | (e): 2.3; (f): G
994 |  |  | 23 23 00 | 3 | Product Data | Refrigerant Piping System | (e): 2.3; (f): G
995 |  |  | 23 23 00 | 3 | Product Data | Spare Parts | (e): 1.5.2
996 |  |  | 23 23 00 | 3 | Product Data | Refrigerant Piping Tests | (e): 3.5
997 |  |  | 23 23 00 | 3 | Product Data | Verification of Dimensions | (e): 3.1
998 |  |  | 23 23 00 | 6 | Test Reports | Refrigerant Piping Tests | (e): 3.5; (f): G
999 |  |  | 23 23 00 | 7 | Certificates | Service Organization | (e): 2.1
1000 |  |  | 23 23 00 | 10 | Operation and Maintenance Data | Maintenance | (e): 1.5; (f): G
1001 |  |  | 23 23 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.4; (f): G
1002 |  |  | 23 23 00 | 10 | Operation and Maintenance Data | Demonstrations | (e): 3.4; (f): G
1003 |  |  | 23 30 00 | 2 | Shop Drawings | Detail Drawings | (e): 1.5.4; (f): G
1004 |  |  | 23 30 00 | 3 | Product Data | Insulated Nonmetallic Flexible Duct Runouts | (e): 2.7.1.1; (f): G
1005 |  |  | 23 30 00 | 3 | Product Data | Duct Connectors | (e): 2.7.1.1; (f): G
1006 |  |  | 23 30 00 | 3 | Product Data | Duct Access Doors | (e): 2.7.2; (f): G
1007 |  |  | 23 30 00 | 3 | Product Data | Fire Dampers | (e): 2.7.3; (f): G
1008 |  |  | 23 30 00 | 3 | Product Data | Manual Balancing Dampers | (e): 2.7.4; (f): G
1009 |  |  | 23 30 00 | 3 | Product Data | Diffusers | (e): 2.7.5.1; (f): G
1010 |  |  | 23 30 00 | 3 | Product Data | Registers and Grilles | (e): 2.7.5.2; (f): G
1011 |  |  | 23 30 00 | 3 | Product Data | Centrifugal Fans | (e): 2.8.1.1; (f): G
1012 |  |  | 23 30 00 | 3 | Product Data | In-Line Centrifugal Fans | (e): 2.8.1.2; (f): G
1013 |  |  | 23 30 00 | 3 | Product Data | Air Handling Units | (e): 2.9; (f): G
1014 |  |  | 23 30 00 | 3 | Product Data | Blower-Coil Units | (e): 2.10.1; (f): G
1015 |  |  | 23 30 00 | 3 | Product Data | Energy Recovery Devices | (e): 2.11; (f): G
1016 |  |  | 23 30 00 | 3 | Product Data | Test Procedures | (e): 1.5.5
1017 |  |  | 23 30 00 | 3 | Product Data | Indoor Air Quality for Duct Sealants | (e): 2.7.1; (f): G
1018 |  |  | 23 30 00 | 6 | Test Reports | Performance Tests | (e): 3.1; (f): G
1019 |  |  | 23 30 00 | 7 | Certificates | Ozone Depleting Substances Technician Certification | (e): 1.5.3; (f): G
1020 |  |  | 23 30 00 | 8 | Manufacturer's Instructions | Manufacturer's Installation Instructions | (e): 3.2
1021 |  |  | 23 30 00 | 8 | Manufacturer's Instructions | Operation and Maintenance Training | (e): 3.12.2
1022 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.12.1; (f): G
1023 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | Fire Dampers | (e): 2.7.3; (f): G
1024 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | Manual Balancing Dampers | (e): 2.7.4; (f): G
1025 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | Centrifugal Fans | (e): 2.8.1.1; (f): G
1026 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | In-Line Centrifugal Fans | (e): 2.8.1.2; (f): G
1027 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | Air Handling Units | (e): 2.9; (f): G
1028 |  |  | 23 30 00 | 10 | Operation and Maintenance Data | Energy Recovery Devices | (e): 2.11; (f): G
1029 |  |  | 23 30 00 | 11 | Closeout Submittals | Indoor Air Quality During Construction | (e): 3.11; (f): G
1030 |  |  | 23 81 00 | 3 | Product Data | Spare Parts | (e): 3.7.1
1031 |  |  | 23 81 00 | 3 | Product Data | System Performance Tests | (e): 3.6; (f): G
1032 |  |  | 23 81 00 | 3 | Product Data | Training | (e): 3.4; (f): G
1033 |  |  | 23 81 00 | 3 | Product Data | Inventory | (e): 1.5
1034 |  |  | 23 81 00 | 3 | Product Data | Supplied Products | (e): 2.1; (f): G
1035 |  |  | 23 81 00 | 3 | Product Data | Manufacturer's Standard Catalog Data | (e): 2.2; (f): G
1036 |  |  | 23 81 00 | 6 | Test Reports | Refrigerant Tests, Charging, and Start-Up | (e): 3.5; (f): G
1037 |  |  | 23 81 00 | 6 | Test Reports | System Performance Tests | (e): 3.6; (f): G
1038 |  |  | 23 81 00 | 7 | Certificates | Service Organizations | (e): 3.7.2
1039 |  |  | 23 81 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.4; (f): G
1040 |  |  | 23 81 00 | 11 | Closeout Submittals | Ozone Depleting Substances | (e): 2.2.2.3; (f): S
1041 |  |  | 23 82 00.00 20 | 3 | Product Data | Unit Heaters | (e): 2.1; (f): G
1042 |  |  | 23 82 00.00 20 | 10 | Operation and Maintenance Data | Unit Heaters | (e): 2.1
1043 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Wireless and Wired Broadcast Communication Request | (e): 3.2.2.2; (f): G
1044 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Device Account Lock Exception Request | (e): 3.3.2; (f): G
1045 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Multiple Ethernet Connection Device Request | (e): 3.2.4.1; (f): G
1046 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Contractor Computer Cybersecurity Compliance Statements | (e): 1.9.1.6; (f): G
1047 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Contractor Temporary Network Cybersecurity Compliance Statements | (e): 1.9.6; (f): G
1048 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Cybersecurity Interconnection Schedule | (e): 1.7.2; (f): G
1049 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Proposed STIG and SRG Applicability Report | (e): 1.7.1; (f): G
1050 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Pre-Construction Control System Inventory Report | (e): 1.7.4; (f): G
1051 |  |  | 25 05 11 | 1 | Preconstruction Submittals | Contractor Personnel Certifications | (e): 1.6.1; (f): G
1052 |  |  | 25 05 11 | 2 | Shop Drawings | Network Communication, Ports, Protocols and Services Report | (e): 1.7.3; (f): G
1053 |  |  | 25 05 11 | 2 | Shop Drawings | Cybersecurity Network (Riser) Diagram | (e): 1.7.7; (f): G
1054 |  |  | 25 05 11 | 2 | Shop Drawings | System Data Flow Diagram | (e): 1.7.5; (f): G
1055 |  |  | 25 05 11 | 3 | Product Data | Control System Cybersecurity Documentation | (e): 1.7.9; (f): G
1056 |  |  | 25 05 11 | 6 | Test Reports | Wireless Communication Test Report | (e): 3.2.2.3; (f): G
1057 |  |  | 25 05 11 | 6 | Test Reports | Control System Cybersecurity Testing Procedures | (e): 3.13.1; (f): G
1058 |  |  | 25 05 11 | 6 | Test Reports | Control System Cybersecurity Testing Report | (e): 3.13.3; (f): G
1059 |  |  | 25 05 11 | 6 | Test Reports | Antivirus/Antimalware Scan Results | (e): 3.12.1; (f): G
1060 |  |  | 25 05 11 | 7 | Certificates | Software Licenses | (e): 1.8; (f): G
1061 |  |  | 25 05 11 | 11 | Closeout Submittals | Password Change Summary Report | (e): 3.4.5.5; (f): G
1062 |  |  | 25 05 11 | 11 | Closeout Submittals | Enclosure Keys | (e): 3.3.7; (f): G
1063 |  |  | 25 05 11 | 11 | Closeout Submittals | Software and Configuration Backups | (e): 1.7.6; (f): G
1064 |  |  | 25 05 11 | 11 | Closeout Submittals | Device Audit Record Upload Software | (e): 3.5.4.2; (f): G
1065 |  |  | 25 05 11 | 11 | Closeout Submittals | System Maintenance Tool Software | (e): 3.8; (f): G
1066 |  |  | 25 05 11 | 11 | Closeout Submittals | Control System Scanning Tools | (e): 3.10.2; (f): G
1067 |  |  | 25 05 11 | 11 | Closeout Submittals | STIG, SRG and Vendor Guide Compliance Result Report | (e): 1.7.8; (f): G
1068 |  |  | 25 05 11 | 11 | Closeout Submittals | Final Control System Inventory Report | (e): 1.7.4; (f): G
1069 |  |  | 25 08 10 | 6 | Test Reports | PVT Plan | (e): 3.1.1; (f): G
1070 |  |  | 25 08 10 | 6 | Test Reports | PVT Phase I Report | (e): 3.1.2.1; (f): G
1071 |  |  | 25 08 10 | 6 | Test Reports | PVT Phase II Report | (e): 3.1.2.2; (f): G
1072 |  |  | 25 08 10 | 7 | Certificates | Test Instrumentation Calibration Certificates | (e): 1.4; (f): G
1073 |  |  | 25 10 10.00 22 | 2 | Shop Drawings | UMCS Contractor Design Drawings | (e): 3.2.2; (f): G
1074 |  |  | 25 10 10.00 22 | 2 | Shop Drawings | Draft As-Built Drawings | (e): 3.2.3; (f): G
1075 |  |  | 25 10 10.00 22 | 2 | Shop Drawings | Final As-Built Drawings | (e): 3.2.3; (f): G
1076 |  |  | 25 10 10.00 22 | 3 | Product Data | Product Data Sheets | (e): 2.1.5; (f): G
1077 |  |  | 25 10 10.00 22 | 3 | Product Data | Computer Software | bar: (f)
1078 |  |  | 25 10 10.00 22 | 3 | Product Data | Enclosure Keys | bar: (f)
1079 |  |  | 25 10 10.00 22 | 5 | Design Data | UMCS IP Network Bandwidth Usage Estimate | (e): 3.2.1; (f): G
1080 |  |  | 25 10 10.00 22 | 6 | Test Reports | Pre-Construction QC Checklist | (e): 1.7; (f): G
1081 |  |  | 25 10 10.00 22 | 6 | Test Reports | Post-Construction QC Checklist | (e): 1.7; (f): G
1082 |  |  | 25 10 10.00 22 | 6 | Test Reports | Existing Conditions Report | (e): 3.1; (f): G
1083 |  |  | 25 10 10.00 22 | 6 | Test Reports | Start-Up and Start-Up Testing Report | (e): 3.4; (f): G
1084 |  |  | 25 10 10.00 22 | 6 | Test Reports | PVT Phase I Procedures | (e): 3.5.1; (f): G
1085 |  |  | 25 10 10.00 22 | 6 | Test Reports | PVT Phase I Report | (e): 3.5.2; (f): G
1086 |  |  | 25 10 10.00 22 | 6 | Test Reports | PVT Phase II Report | (e): 3.5.3; (f): G
1087 |  |  | 25 10 10.00 22 | 10 | Operation and Maintenance Data | Operation and Maintenance (O&M) Instructions | (e): 1.8; (f): G
1088 |  |  | 25 10 10.00 22 | 10 | Operation and Maintenance Data | Preventive Maintenance Work Plan | (e): 3.6.6.1; (f): G
1089 |  |  | 25 10 10.00 22 | 10 | Operation and Maintenance Data | Basic Training Documentation | (e): 3.7.1; (f): G
1090 |  |  | 25 10 10.00 22 | 10 | Operation and Maintenance Data | Advanced Training Documentation | (e): 3.7.1; (f): G
1091 |  |  | 25 10 10.00 22 | 10 | Operation and Maintenance Data | Refresher Training Documentation | (e): 3.7.1; (f): G
1092 |  |  | 25 10 10.00 22 | 11 | Closeout Submittals | Closeout QC Checklist | (e): 1.7; (f): G
1093 |  |  | 26 08 00 | 6 | Test Reports | Acceptance Tests and Inspections | (e): 3.1; (f): G
1094 |  |  | 26 08 00 | 7 | Certificates | Qualifications | (e): 1.4.1; (f): G
1095 |  |  | 26 08 00 | 7 | Certificates | Acceptance Test and Inspections Procedure | (e): 1.4.3; (f): G
1096 |  |  | 26 20 00 | 2 | Shop Drawings | Panelboards | (e): 2.13; (f): G
1097 |  |  | 26 20 00 | 2 | Shop Drawings | Transformers | (e): 2.15; (f): G
1098 |  |  | 26 20 00 | 2 | Shop Drawings | Cable Trays | (e): 2.3; (f): G
1099 |  |  | 26 20 00 | 2 | Shop Drawings | Wireways | (e): 2.27; (f): G
1100 |  |  | 26 20 00 | 3 | Product Data | Receptacles | (e): 2.12; (f): G
1101 |  |  | 26 20 00 | 3 | Product Data | Circuit Breakers | (e): 2.13.3; (f): G
1102 |  |  | 26 20 00 | 3 | Product Data | Switches | (e): 2.1; (f): G
1103 |  |  | 26 20 00 | 3 | Product Data | Transformers | (e): 2.15; (f): G
1104 |  |  | 26 20 00 | 3 | Product Data | Enclosed Circuit Breakers | (e): 2.14; (f): G
1105 |  |  | 26 20 00 | 3 | Product Data | Motor Controllers | (e): 2.17; (f): G
1106 |  |  | 26 20 00 | 3 | Product Data | Combination Motor Controllers | (e): 2.19.1; (f): G
1107 |  |  | 26 20 00 | 3 | Product Data | Manual Motor Starters | (e): 2.18; (f): G
1108 |  |  | 26 20 00 | 3 | Product Data | Secondary Bonding Busbar | (e): 2.22.3; (f): G
1109 |  |  | 26 20 00 | 3 | Product Data | Surge Protective Devices | (e): 2.28; (f): G
1110 |  |  | 26 20 00 | 3 | Product Data | Cable Trays | (e): 2.3; (f): G
1111 |  |  | 26 20 00 | 6 | Test Reports | 600-volt Wiring Test | (e): 3.5.2; (f): G
1112 |  |  | 26 20 00 | 6 | Test Reports | Grounding System Test | (e): 3.5.5; (f): G
1113 |  |  | 26 20 00 | 6 | Test Reports | Transformer Tests | (e): 3.5.3; (f): G
1114 |  |  | 26 20 00 | 6 | Test Reports | Ground-fault Receptacle Test | (e): 3.5.4; (f): G
1115 |  |  | 26 20 00 | 7 | Certificates | Fuses | (e): 2.11; (f): G
1116 |  |  | 26 20 00 | 9 | Manufacturer's Field Reports | Transformer Factory Tests | (e): 2.30.1
1117 |  |  | 26 20 00 | 10 | Operation and Maintenance Data | Electrical Systems | (e): 1.6.1; (f): G
1118 |  |  | 26 24 13 | 2 | Shop Drawings | Switchboard Drawings | (e): 1.5.2; (f): G
1119 |  |  | 26 24 13 | 3 | Product Data | Switchboard | (e): 2.2; (f): G
1120 |  |  | 26 24 13 | 6 | Test Reports | Switchboard Design Tests | (e): 2.5.2; (f): G
1121 |  |  | 26 24 13 | 6 | Test Reports | Switchboard Production Tests | (e): 2.5.3; (f): G
1122 |  |  | 26 24 13 | 6 | Test Reports | Acceptance Checks and Tests | (e): 3.5.1; (f): G
1123 |  |  | 26 24 13 | 10 | Operation and Maintenance Data | Switchboard Operation and Maintenance | (e): 1.6.1; (f): G
1124 |  |  | 26 24 13 | 11 | Closeout Submittals | Assembled Operation and Maintenance Manuals | (e): 1.6.2; (f): G
1125 |  |  | 26 24 13 | 11 | Closeout Submittals | Equipment Test Schedule | (e): 2.5.1; (f): G
1126 |  |  | 26 24 13 | 11 | Closeout Submittals | Required Settings | (e): 3.5; (f): G
1127 |  |  | 26 24 13 | 11 | Closeout Submittals | Service Entrance Available Fault Current Label | (e): 2.7; (f): G
1128 |  |  | 26 27 14.00 20 | 2 | Shop Drawings | Installation Drawings | (e): 1.4.1; (f): G
1129 |  |  | 26 27 14.00 20 | 3 | Product Data | Electricity Meters | (e): 2.1; (f): G
1130 |  |  | 26 27 14.00 20 | 3 | Product Data | Current Transformer | (e): 2.1.2; (f): G
1131 |  |  | 26 27 14.00 20 | 3 | Product Data | Communications | (e): 2.2; (f): G
1132 |  |  | 26 27 14.00 20 | 6 | Test Reports | Acceptance Checks and Tests | (e): 3.2.1; (f): G
1133 |  |  | 26 27 14.00 20 | 6 | Test Reports | System Functional Verification | (e): 3.2.2; (f): G
1134 |  |  | 26 27 14.00 20 | 6 | Test Reports | Building Meter Installation Sheet | (e): 3.2.1; (f): G
1135 |  |  | 26 27 14.00 20 | 6 | Test Reports | Meter Configuration Template | (e): 2.1.1; (f): G
1136 |  |  | 26 27 14.00 20 | 6 | Test Reports | Meter Configuration Report | (e): 3.2.1; (f): G
1137 |  |  | 26 27 14.00 20 | 10 | Operation and Maintenance Data | Electricity Meters and Accessories | (e): 1.5.1; (f): G
1138 |  |  | 26 27 14.00 20 | 11 | Closeout Submittals | System Functional Verification | (e): 3.2.2; (f): G
1139 |  |  | 26 29 23 | 2 | Shop Drawings | Schematic Diagrams | (e): 1.5.1; (f): G
1140 |  |  | 26 29 23 | 2 | Shop Drawings | Interconnecting Diagrams | (e): 1.5.2; (f): G
1141 |  |  | 26 29 23 | 2 | Shop Drawings | Installation Drawings | (e): 1.5.3; (f): G
1142 |  |  | 26 29 23 | 2 | Shop Drawings | As-Built Drawings | (e): 1.5.3; (f): G
1143 |  |  | 26 29 23 | 3 | Product Data | Adjustable Speed Drives | (e): 2.1; (f): G
1144 |  |  | 26 29 23 | 3 | Product Data | Wires and Cables | (e): 2.3
1145 |  |  | 26 29 23 | 3 | Product Data | Equipment Schedule | (e): 1.5.4
1146 |  |  | 26 29 23 | 6 | Test Reports | ASD Test | (e): 3.3.1
1147 |  |  | 26 29 23 | 6 | Test Reports | Performance Verification Tests | (e): 3.3.2
1148 |  |  | 26 29 23 | 6 | Test Reports | Endurance Test | (e): 3.3.3
1149 |  |  | 26 29 23 | 7 | Certificates | Testing Agency's Field Supervisor | (e): 3.3.1; (f): G
1150 |  |  | 26 29 23 | 8 | Manufacturer's Instructions | Installation instructions | (e): 1.5.5
1151 |  |  | 26 29 23 | 9 | Manufacturer's Field Reports | ASD Test Plan | (e): 2.5.1; (f): G
1152 |  |  | 26 29 23 | 9 | Manufacturer's Field Reports | Standard Products | (e): 1.5.6
1153 |  |  | 26 29 23 | 10 | Operation and Maintenance Data | Adjustable Speed Drives | (e): 2.1
1154 |  |  | 26 32 15 | 2 | Shop Drawings | Engine-Generator Set and Auxiliary Equipment | (e): 2.1.1; (f): G
1155 |  |  | 26 32 15 | 2 | Shop Drawings | Auxiliary Systems | (e): 1.4.9; (f): G
1156 |  |  | 26 32 15 | 2 | Shop Drawings | Detailed Drawings | (e): 1.4.8; (f): G
1157 |  |  | 26 32 15 | 2 | Shop Drawings | Acceptance | (e): 3.17; (f): G
1158 |  |  | 26 32 15 | 3 | Product Data | Engine-Generator Set Efficiencies | (e): 2.1.1; (f): G
1159 |  |  | 26 32 15 | 3 | Product Data | Emissions | (e): 2.1.1; (f): G
1160 |  |  | 26 32 15 | 3 | Product Data | Emissions | (e): 2.11; (f): G
1161 |  |  | 26 32 15 | 3 | Product Data | Filters | (e): 2.7.2; (f): G
1162 |  |  | 26 32 15 | 3 | Product Data | Special Tools | (e): 2.13; (f): G
1163 |  |  | 26 32 15 | 3 | Product Data | Special Tools | (e): 2.13; (f): G
1164 |  |  | 26 32 15 | 3 | Product Data | Remote Alarm Annunciator | (e): 1.4.9; (f): G
1165 |  |  | 26 32 15 | 3 | Product Data | Remote Alarm Annunciator | (e): 2.12.4; (f): G
1166 |  |  | 26 32 15 | 3 | Product Data | Engine-Generator Parameter Schedule | (e): 2.1.1
1167 |  |  | 26 32 15 | 3 | Product Data | Heat Exchanger | (e): 2.8.2
1168 |  |  | 26 32 15 | 3 | Product Data | Generator | (e): 2.14
1169 |  |  | 26 32 15 | 3 | Product Data | Manufacturer's Catalog | (e): 2.5
1170 |  |  | 26 32 15 | 3 | Product Data | Spare Parts | (e): 1.6.2
1171 |  |  | 26 32 15 | 3 | Product Data | Onsite Training | (e): 3.12
1172 |  |  | 26 32 15 | 3 | Product Data | Vibration-Isolation | (e): 1.4.4
1173 |  |  | 26 32 15 | 3 | Product Data | Posted Data and Instructions | (e): 3.16; (f): G
1174 |  |  | 26 32 15 | 3 | Product Data | Instructions | (e): 3.6.7.1; (f): G
1175 |  |  | 26 32 15 | 3 | Product Data | Experience | (e): 1.4.6
1176 |  |  | 26 32 15 | 3 | Product Data | Field Engineer | (e): 1.4.7
1177 |  |  | 26 32 15 | 3 | Product Data | General Installation | (e): 3.2
1178 |  |  | 26 32 15 | 3 | Product Data | Exciter | (e): 2.15
1179 |  |  | 26 32 15 | 5 | Design Data | Performance Criteria | (e): 2.14
1180 |  |  | 26 32 15 | 5 | Design Data | Sound Limitations | (e): 2.9; (f): G
1181 |  |  | 26 32 15 | 5 | Design Data | Integral Main Fuel Storage Tank | (e): 2.6.4
1182 |  |  | 26 32 15 | 5 | Design Data | Power Factor | (e): 3.6.1.2
1183 |  |  | 26 32 15 | 5 | Design Data | Heat Exchanger | (e): 2.8.2
1184 |  |  | 26 32 15 | 5 | Design Data | Time-Delay on Alarms | (e): 2.18.5
1185 |  |  | 26 32 15 | 5 | Design Data | Cooling System | (e): 2.8
1186 |  |  | 26 32 15 | 5 | Design Data | Vibration Isolation | (e): 1.4.4
1187 |  |  | 26 32 15 | 5 | Design Data | Battery Charger | (e): 2.2
1188 |  |  | 26 32 15 | 5 | Design Data | Battery Charger | (e): 2.12.3.2
1189 |  |  | 26 32 15 | 5 | Design Data | Capacity Calculations for Engine-Generator Set | (e): 2.1.1; (f): G
1190 |  |  | 26 32 15 | 5 | Design Data | Brake Mean Effective Pressure (BMEP) Calculations | (e): 2.1.1; (f): G
1191 |  |  | 26 32 15 | 5 | Design Data | Torsional Vibration Stress Analysis Computations | (e): 2.1.1; (f): G
1192 |  |  | 26 32 15 | 5 | Design Data | Capacity Calculations for Batteries | (e): 2.1.1; (f): G
1193 |  |  | 26 32 15 | 5 | Design Data | Turbocharger Load Calculations | (e): 2.1.1; (f): G
1194 |  |  | 26 32 15 | 6 | Test Reports | Performance Tests | (e): 3.6.9
1195 |  |  | 26 32 15 | 6 | Test Reports | Factory Inspection and Tests | (e): 2.25
1196 |  |  | 26 32 15 | 6 | Test Reports | Factory Tests | (e): 2.25.2
1197 |  |  | 26 32 15 | 6 | Test Reports | Onsite Inspection and Tests | (e): 3.6; (f): G
1198 |  |  | 26 32 15 | 6 | Test Reports | Acceptance Checks and Tests | (e): 3.9.2; (f): G
1199 |  |  | 26 32 15 | 6 | Test Reports | Functional Acceptance Tests | (e): 3.10.2; (f): G
1200 |  |  | 26 32 15 | 6 | Test Reports | Maintenance Procedures | (e): 3.12; (f): G
1201 |  |  | 26 32 15 | 6 | Test Reports | Operation and Maintenance Manuals | (e): 3.12; (f): G
1202 |  |  | 26 32 15 | 6 | Test Reports | Inspections | (e): 3.6.3; (f): G
1203 |  |  | 26 32 15 | 6 | Test Reports | Functional Acceptance Test Procedure | (e): 3.9.6; (f): G
1204 |  |  | 26 32 15 | 7 | Certificates | Cooling System | (e): 2.8
1205 |  |  | 26 32 15 | 7 | Certificates | Vibration Isolation | (e): 1.4.4
1206 |  |  | 26 32 15 | 7 | Certificates | Prototype Test | (e): 2.25.2
1207 |  |  | 26 32 15 | 7 | Certificates | Reliability and Durability | (e): 2.1.5
1208 |  |  | 26 32 15 | 7 | Certificates | Fuel System Certification | (e): 1.4.11; (f): G
1209 |  |  | 26 32 15 | 7 | Certificates | Start-Up Engineer | (e): 3.8; (f): G
1210 |  |  | 26 32 15 | 7 | Certificates | Instructor's Qualification Resume | (e): 3.11.1; (f): G
1211 |  |  | 26 32 15 | 7 | Certificates | Engine Emission Limits | (e): 2.1.2.1; (f): G
1212 |  |  | 26 32 15 | 7 | Certificates | Sound Limitations | (e): 2.9
1213 |  |  | 26 32 15 | 7 | Certificates | Site Visit | (e): 3.1
1214 |  |  | 26 32 15 | 7 | Certificates | Current Balance | (e): 2.14.1
1215 |  |  | 26 32 15 | 7 | Certificates | Materials and Equipment | (e): 2.4
1216 |  |  | 26 32 15 | 7 | Certificates | Factory Inspection and Tests | (e): 2.25
1217 |  |  | 26 32 15 | 7 | Certificates | Engine Tests | (e): 3.6.4; (f): G
1218 |  |  | 26 32 15 | 7 | Certificates | Generator Tests | (e): 3.6.5; (f): G
1219 |  |  | 26 32 15 | 7 | Certificates | Assembled Engine-Generator Set Tests | (e): 3.6.6; (f): G
1220 |  |  | 26 32 15 | 10 | Operation and Maintenance Data | Preliminary Assembled Operation and Maintenance Manuals | (e): 3.9.5; (f): G
1221 |  |  | 26 32 15 | 10 | Operation and Maintenance Data | Posted Data and Instructions | (e): 3.16; (f): G
1222 |  |  | 26 32 15 | 10 | Operation and Maintenance Data | Training Plan | (e): 3.11.2; (f): G
1223 |  |  | 26 41 00 | 1 | Preconstruction Submittals | Lightning Protection System Installers Documentation | (e): 1.2.3; (f): G
1224 |  |  | 26 41 00 | 2 | Shop Drawings | Overall Lightning Protection System | (e): 1.4.1.1; (f): G
1225 |  |  | 26 41 00 | 2 | Shop Drawings | Each Major Component | (e): 1.4.1.2; (f): G
1226 |  |  | 26 41 00 | 6 | Test Reports | Lightning Protection and Grounding System Test Plan | (e): 1.4.3; (f): G
1227 |  |  | 26 41 00 | 6 | Test Reports | Grounding Systems Testing | (e): 3.3.2; (f): G
1228 |  |  | 26 41 00 | 7 | Certificates | Component UL Listed and Labeled | (e): 1.4.2; (f): G
1229 |  |  | 26 41 00 | 7 | Certificates | Lightning Protection System Inspection Certificate | (e): 1.4.4; (f): G
1230 |  |  | 26 41 00 | 7 | Certificates | Roof Manufacturer's Warranty | (e): 3.1.1.1; (f): G
1231 |  |  | 26 41 00 | 7 | Certificates | UL Master Label Certification | (e): 3.3.3; (f): G
1232 |  |  | 26 51 00 | 2 | Shop Drawings | Luminaire Drawings | (e): 1.5.1; (f): G
1233 |  |  | 26 51 00 | 2 | Shop Drawings | Occupancy/Vacancy Sensor Coverage Layout | (e): 1.5.8; (f): G
1234 |  |  | 26 51 00 | 2 | Shop Drawings | Lighting Control System One-Line Diagram | (e): 1.7.2; (f): G
1235 |  |  | 26 51 00 | 2 | Shop Drawings | Sequence of Operation for Lighting Control System | (e): 2.5.1; (f): G
1236 |  |  | 26 51 00 | 3 | Product Data | Luminaires | (e): 2.2; (f): G
1237 |  |  | 26 51 00 | 3 | Product Data | Light Sources | (e): 2.3; (f): G
1238 |  |  | 26 51 00 | 3 | Product Data | LED Drivers | (e): 2.4; (f): G
1239 |  |  | 26 51 00 | 3 | Product Data | Luminaire Warranty | (e): 1.6.1; (f): G
1240 |  |  | 26 51 00 | 3 | Product Data | Lighting Controls Warranty | (e): 1.6.2; (f): G
1241 |  |  | 26 51 00 | 3 | Product Data | Local Area Controller | (e): 2.5.1.1.1; (f): G
1242 |  |  | 26 51 00 | 3 | Product Data | Lighting Control Panel | (e): 2.5.1.2.1; (f): G
1243 |  |  | 26 51 00 | 3 | Product Data | Switches | (e): 2.5.2.1; (f): G
1244 |  |  | 26 51 00 | 3 | Product Data | Digital Switch Timers | (e): 2.5.2.2; (f): G
1245 |  |  | 26 51 00 | 3 | Product Data | Wall Box Dimmers | (e): 2.5.2.3; (f): G
1246 |  |  | 26 51 00 | 3 | Product Data | Scene Wallstations | (e): 2.5.2.4; (f): G
1247 |  |  | 26 51 00 | 3 | Product Data | Occupancy/Vacancy Sensors | (e): 2.5.2.5; (f): G
1248 |  |  | 26 51 00 | 3 | Product Data | Photosensors | (e): 2.5.2.6; (f): G
1249 |  |  | 26 51 00 | 3 | Product Data | Time Clocks | (e): 2.5.2.7; (f): G
1250 |  |  | 26 51 00 | 3 | Product Data | Power Packs | (e): 2.5.2.5.5; (f): G
1251 |  |  | 26 51 00 | 3 | Product Data | Mini Inverters | (e): 2.6.4; (f): G
1252 |  |  | 26 51 00 | 3 | Product Data | Exit Signs | (e): 2.6.1; (f): G
1253 |  |  | 26 51 00 | 3 | Product Data | Emergency Drivers | (e): 2.6.3; (f): G
1254 |  |  | 26 51 00 | 5 | Design Data | Luminaire Design Data | (e): 1.5.2; (f): G
1255 |  |  | 26 51 00 | 6 | Test Reports | ANSI/IES LM-79 Test Report | (e): 1.5.3
1256 |  |  | 26 51 00 | 6 | Test Reports | ANSI/IES LM-80 Test Report | (e): 1.5.4
1257 |  |  | 26 51 00 | 6 | Test Reports | ANSI/IES TM-21 Test Report | (e): 1.5.5
1258 |  |  | 26 51 00 | 6 | Test Reports | ANSI/IES TM-30 Test Report | (e): 1.5.6
1259 |  |  | 26 51 00 | 6 | Test Reports | Occupancy/Vacancy Sensor Verification Test | (e): 3.2.1.1; (f): G
1260 |  |  | 26 51 00 | 6 | Test Reports | Photosensor Verification Test | (e): 3.2.1.1; (f): G
1261 |  |  | 26 51 00 | 7 | Certificates | LED Driver and Dimming Switch Compatibility Certificate | (e): 1.5.7; (f): G
1262 |  |  | 26 51 00 | 10 | Operation and Maintenance Data | Lighting System | (e): 1.7.1; (f): G
1263 |  |  | 26 51 00 | 10 | Operation and Maintenance Data | Lighting Control System | (e): 1.7.2; (f): G
1264 |  |  | 26 51 00 | 10 | Operation and Maintenance Data | Maintenance Staff Training Plan | (e): 3.3.2.1; (f): G
1265 |  |  | 26 51 00 | 10 | Operation and Maintenance Data | End-User Training Plan | (e): 3.3.2.2; (f): G
1266 |  |  | 27 10 00 | 2 | Shop Drawings | Telecommunications Drawings | (e): 1.6.1.1; (f): G
1267 |  |  | 27 10 00 | 2 | Shop Drawings | Telecommunications Space Drawings | (e): 1.6.1.2; (f): G
1268 |  |  | 27 10 00 | 3 | Product Data | Telecommunications Cabling | (e): 2.3; (f): G
1269 |  |  | 27 10 00 | 3 | Product Data | Patch Panels | (e): 2.4.5; (f): G
1270 |  |  | 27 10 00 | 3 | Product Data | Telecommunications Outlet/Connector Assemblies | (e): 2.5; (f): G
1271 |  |  | 27 10 00 | 3 | Product Data | Equipment Support Frame | (e): 2.4.2; (f): G
1272 |  |  | 27 10 00 | 3 | Product Data | Connector Blocks | (e): 2.4.3; (f): G
1273 |  |  | 27 10 00 | 6 | Test Reports | Telecommunications Cabling Testing | (e): 3.5.1; (f): G
1274 |  |  | 27 10 00 | 7 | Certificates | Telecommunications Contractor | (e): 1.6.2.1; (f): G
1275 |  |  | 27 10 00 | 7 | Certificates | Key Personnel | (e): 1.6.2.2; (f): G
1276 |  |  | 27 10 00 | 7 | Certificates | Manufacturer Qualifications | (e): 1.6.2.3; (f): G
1277 |  |  | 27 10 00 | 7 | Certificates | Test Plan | (e): 1.6.3; (f): G
1278 |  |  | 27 10 00 | 9 | Manufacturer's Field Reports | Factory Reel Tests | (e): 2.10.1; (f): G
1279 |  |  | 27 10 00 | 10 | Operation and Maintenance Data | Telecommunications Cabling and Pathway System | (e): 1.10.1; (f): G
1280 |  |  | 27 10 00 | 11 | Closeout Submittals | Record Documentation | (e): 1.10.2; (f): G
1281 |  |  | 27 32 50 | 2 | Shop Drawings | Nameplates | (e): 1.5.1.1.1.1; (f): G
1282 |  |  | 27 32 50 | 2 | Shop Drawings | Wiring Diagrams | (e): 1.5.1.1.1.2; (f): G
1283 |  |  | 27 32 50 | 2 | Shop Drawings | System Layout | (e): 1.5.1.1.1.3; (f): G
1284 |  |  | 27 32 50 | 2 | Shop Drawings | Identifying And Instructional Signage | (e): 1.5.1.1.1.4; (f): G
1285 |  |  | 27 32 50 | 3 | Product Data | Technical Data And Computer Software | (e): 1.5.1.1.2.1; (f): G
1286 |  |  | 27 32 50 | 3 | Product Data | Base / Master Station | (e): 2.4.1; (f): G
1287 |  |  | 27 32 50 | 3 | Product Data | Power Supply | (e): 2.4.3; (f): G
1288 |  |  | 27 32 50 | 3 | Product Data | Call Boxes | (e): 2.4.2; (f): G
1289 |  |  | 27 32 50 | 3 | Product Data | Cabling And Wiring | (e): 2.4.4; (f): G
1290 |  |  | 27 32 50 | 6 | Test Reports | Field Quality Control | (e): 1.5.1.2.1; (f): G
1291 |  |  | 27 32 50 | 6 | Test Reports | Testing Procedures | (e): 1.5.1.2.2; (f): G
1292 |  |  | 27 32 50 | 7 | Certificates | Installer | (e): 1.5.1.3.1; (f): G
1293 |  |  | 27 32 50 | 7 | Certificates | Qualified Professional Engineer (QPE) | (e): 1.5.1.3.2; (f): G
1294 |  |  | 27 32 50 | 7 | Certificates | Request For Inspection And Tests | (e): 1.5.1.3.3; (f): G
1295 |  |  | 27 32 50 | 7 | Certificates | Testing | (e): 1.5.1.3.4; (f): G
1296 |  |  | 27 32 50 | 7 | Certificates | Instructor | (e): 3.5.1; (f): G
1297 |  |  | 27 32 50 | 10 | Operation and Maintenance Data | Operation And Maintenance (O&M) Instructions | (e): 1.5.1.4.1; (f): G
1298 |  |  | 27 32 50 | 11 | Closeout Submittals | As-Built Drawings | (e): 1.5.1.4.2; (f): G
1299 |  |  | 27 32 50 | 11 | Closeout Submittals | Spare Parts | (e): 3.7.3; (f): G
1300 |  |  | 28 08 10 | 5 | Design Data | Test Plan | (e): 3.1; (f): G
1301 |  |  | 28 08 10 | 6 | Test Reports | Final Test Report | (e): 3.4; (f): G
1302 |  |  | 28 08 10 | 6 | Test Reports | Pre-Acceptance Test Certification | (e): 3.2; (f): G
1303 |  |  | 28 08 10 | 7 | Certificates | Qualifications | (e): 1.4.1
1304 |  |  | 28 10 05 | 2 | Shop Drawings | ESS Components | (e): 1.3.3.1; (f): G
1305 |  |  | 28 10 05 | 2 | Shop Drawings | Access Control System (ACS) | (e): 2.3; (f): G
1306 |  |  | 28 10 05 | 2 | Shop Drawings | Security Hardware Door Schedule | (e): 1.3.3.1; (f): G
1307 |  |  | 28 10 05 | 2 | Shop Drawings | Overall System Schematic | (e): 1.3.3.1; (f): G
1308 |  |  | 28 10 05 | 3 | Product Data | Access Control Unit | (e): 2.3.4; (f): G
1309 |  |  | 28 10 05 | 3 | Product Data | Access Control Devices | (e): 2.3.5; (f): G
1310 |  |  | 28 10 05 | 3 | Product Data | Communications Interface Devices | (e): 2.4; (f): G
1311 |  |  | 28 10 05 | 3 | Product Data | Batteries | (e): 2.5.1; (f): G
1312 |  |  | 28 10 05 | 3 | Product Data | Component Enclosure | (e): 2.7; (f): G
1313 |  |  | 28 10 05 | 5 | Design Data | Backup Battery Capacity Calculations | (e): 1.5.1; (f): G
1314 |  |  | 28 10 05 | 5 | Design Data | Error and Throughput Rates | (e): 2.3.2; (f): G
1315 |  |  | 28 10 05 | 7 | Certificates | Contractor Qualifications | (e): 1.3.4.1; (f): G
1316 |  |  | 28 10 05 | 7 | Certificates | Instructor Qualifications | (e): 1.3.4.2; (f): G
1317 |  |  | 28 10 05 | 7 | Certificates | Contact Card Readers | (e): 2.3.5.1.1; (f): G
1318 |  |  | 28 10 05 | 7 | Certificates | Contactless Card Readers | (e): 2.3.5.1.2; (f): G
1319 |  |  | 28 10 05 | 7 | Certificates | Wire And Cable | (e): 2.4.3; (f): G
1320 |  |  | 28 10 05 | 7 | Certificates | Bonding, Grounding, And Shielding | (e): 3.1.8; (f): G
1321 |  |  | 28 10 05 | 10 | Operation and Maintenance Data | ESS Components | (e): 1.3.3.1; (f): G
1322 |  |  | 28 10 05 | 10 | Operation and Maintenance Data | ESS Software, Data Package 4 | (e): 1.6; (f): G
1323 |  |  | 28 10 05 | 10 | Operation and Maintenance Data | ESS Training | (e): 3.6; (f): G
1324 |  |  | 28 10 05 | 10 | Operation and Maintenance Data | ESS Training Outline | (e): 3.6.1; (f): G
1325 |  |  | 28 10 05 | 11 | Closeout Submittals | As-Built Drawings | (e): 1.7; (f): G
1326 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Qualified Fire Protection Engineer (QFPE) | (e): 1.3.2; (f): G
1327 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Fire alarm system designer | (e): 1.8.2.1; (f): G
1328 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Supervisor | (e): 1.8.2.2; (f): G
1329 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Technician | (e): 1.8.2.3; (f): G
1330 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Installer | (e): 1.8.2.4; (f): G
1331 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Test Technician | (e): 1.8.2.5; (f): G
1332 |  |  | 28 31 76 | 1 | Preconstruction Submittals | Fire Alarm System Site-Specific Software Acknowledgement | (e): 1.7; (f): G
1333 |  |  | 28 31 76 | 2 | Shop Drawings | Nameplates | (e): 1.8.1.3; (f): G
1334 |  |  | 28 31 76 | 2 | Shop Drawings | Instructions | (e): 2.2.4; (f): G
1335 |  |  | 28 31 76 | 2 | Shop Drawings | Wiring Diagrams | (e): 1.8.1.4; (f): G
1336 |  |  | 28 31 76 | 2 | Shop Drawings | System Layout | (e): 1.8.1.5; (f): G
1337 |  |  | 28 31 76 | 2 | Shop Drawings | Notification Appliances | (e): 1.8.1.6; (f): G
1338 |  |  | 28 31 76 | 2 | Shop Drawings | Initiating devices | (e): 1.8.1.7; (f): G
1339 |  |  | 28 31 76 | 2 | Shop Drawings | Amplifiers | (e): 1.8.1.8; (f): G
1340 |  |  | 28 31 76 | 2 | Shop Drawings | Battery Power | (e): 1.8.1.9; (f): G
1341 |  |  | 28 31 76 | 2 | Shop Drawings | Voltage Drop Calculations | (e): 1.8.1.10; (f): G
1342 |  |  | 28 31 76 | 3 | Product Data | Fire Alarm and Mass Notification Control Unit (FMCU) | (e): 2.3; (f): G
1343 |  |  | 28 31 76 | 3 | Product Data | Local Operating Console (LOC) | (e): 1.4.4; (f): G
1344 |  |  | 28 31 76 | 3 | Product Data | Amplifiers | (e): 1.8.1.8; (f): G
1345 |  |  | 28 31 76 | 3 | Product Data | Tone Generators | (e): 2.5; (f): G
1346 |  |  | 28 31 76 | 3 | Product Data | Digitalized voice generators | (e): 2.5; (f): G
1347 |  |  | 28 31 76 | 3 | Product Data | LCD Annunciator | (e): 2.6.1; (f): G
1348 |  |  | 28 31 76 | 3 | Product Data | Manual Stations | (e): 2.7; (f): G
1349 |  |  | 28 31 76 | 3 | Product Data | Smoke Detectors | (e): 2.8; (f): G
1350 |  |  | 28 31 76 | 3 | Product Data | Duct Smoke Detectors | (e): 2.8.2; (f): G
1351 |  |  | 28 31 76 | 3 | Product Data | Heat Detectors | (e): 2.9; (f): G
1352 |  |  | 28 31 76 | 3 | Product Data | Addressable Interface Devices | (e): 2.1; (f): G
1353 |  |  | 28 31 76 | 3 | Product Data | Addressable Control Modules | (e): 2.11; (f): G
1354 |  |  | 28 31 76 | 3 | Product Data | Isolation Modules | (e): 2.12; (f): G
1355 |  |  | 28 31 76 | 3 | Product Data | Notification Appliances | (e): 1.8.1.6; (f): G
1356 |  |  | 28 31 76 | 3 | Product Data | Textual Display Sign Control Panel | (e): 2.13.3; (f): G
1357 |  |  | 28 31 76 | 3 | Product Data | Textual Display Signs | (e): 2.13.3; (f): G
1358 |  |  | 28 31 76 | 3 | Product Data | Batteries | (e): 2.15.1; (f): G
1359 |  |  | 28 31 76 | 3 | Product Data | Battery Chargers | (e): 2.15.2; (f): G
1360 |  |  | 28 31 76 | 3 | Product Data | Supplemental Notification Appliance Circuit Panels | (e): 2.15.1.1; (f): G
1361 |  |  | 28 31 76 | 3 | Product Data | Auxiliary Power Supply Panels | (e): 2.15.1.1; (f): G
1362 |  |  | 28 31 76 | 3 | Product Data | Surge Protective Devices | (e): 2.16; (f): G
1363 |  |  | 28 31 76 | 3 | Product Data | Alarm Wiring | (e): 2.16; (f): G
1364 |  |  | 28 31 76 | 3 | Product Data | Back Boxes and Conduit | (e): 3.3.4; (f): G
1365 |  |  | 28 31 76 | 3 | Product Data | Ceiling Bridges | (e): 3.2.9; (f): G
1366 |  |  | 28 31 76 | 3 | Product Data | Terminal Cabinets | (e): 3.3.2; (f): G
1367 |  |  | 28 31 76 | 3 | Product Data | Radio Transmitter and Interface Panels | (e): 2.19.1; (f): G
1368 |  |  | 28 31 76 | 3 | Product Data | Electromagnetic Door Holders | (e): 2.20.3; (f): G
1369 |  |  | 28 31 76 | 3 | Product Data | Document Storage Cabinet | (e): 3.12.3; (f): G
1370 |  |  | 28 31 76 | 6 | Test Reports | Test Procedures | (e): 3.8.1; (f): G
1371 |  |  | 28 31 76 | 7 | Certificates | Verification of Compliant Installation | (e): 3.8.2.1; (f): G
1372 |  |  | 28 31 76 | 7 | Certificates | Request for Government Final Test | (e): 3.8.2.2; (f): G
1373 |  |  | 28 31 76 | 10 | Operation and Maintenance Data | Operation and Maintenance (O&M) Instructions | (e): 3.1; (f): G
1374 |  |  | 28 31 76 | 10 | Operation and Maintenance Data | Instruction of Government Employees | (e): 3.11; (f): G
1375 |  |  | 28 31 76 | 11 | Closeout Submittals | As-Built Drawings | (e): 1.8.1.13
1376 |  |  | 28 31 76 | 11 | Closeout Submittals | Spare Parts | (e): 1.10.1
1377 |  |  | 31 00 00.00 22 | 1 | Preconstruction Submittals | Shoring and Sheeting Plan | (e): 3.1.1; (f): G
1378 |  |  | 31 00 00.00 22 | 1 | Preconstruction Submittals | Excavation and Trenching Plan | (e): 1.6.1; (f): G
1379 |  |  | 31 00 00.00 22 | 1 | Preconstruction Submittals | Dewatering Work Plan | (e): 1.13.2; (f): G
1380 |  |  | 31 00 00.00 22 | 1 | Preconstruction Submittals | Dewatering Work Plan | (e): 3.1.4.2; (f): G
1381 |  |  | 31 00 00.00 22 | 1 | Preconstruction Submittals | Excess Soil Disposal & Soil Sampling Plan | (e): 1.12; (f): G
1382 |  |  | 31 00 00.00 22 | 3 | Product Data | Buried Warning and Identification Tape | (e): 3.7.1; (f): G
1383 |  |  | 31 00 00.00 22 | 3 | Product Data | Geotextiles | (e): 2.6; (f): G
1384 |  |  | 31 00 00.00 22 | 6 | Test Reports | Dewatering Performance Records | (e): 3.1.4.2; (f): G
1385 |  |  | 31 00 00.00 22 | 6 | Test Reports | Select Material Test | (e): 3.10.2.2; (f): G
1386 |  |  | 31 00 00.00 22 | 6 | Test Reports | Material Test Report | (e): 3.11; (f): G
1387 |  |  | 31 00 00.00 22 | 6 | Test Reports | Density Tests | (e): 3.11; (f): G
1388 |  |  | 31 00 00.00 22 | 6 | Test Reports | Soil Sampling for Waste Characterization | (e): 1.9; (f): G
1389 |  |  | 31 00 00.00 22 | 6 | Test Reports | Fill and Backfill | (e): 3.10.2.1; (f): G
1390 |  |  | 31 00 00.00 22 | 6 | Test Reports | Borrow Materials | (e): 2.5; (f): G
1391 |  |  | 31 00 00.00 22 | 6 | Test Reports | Moisture Content Tests | (e): 3.8; (f): G
1392 |  |  | 31 21 13 | 3 | Product Data | Radon Mitigation Systems Components | (e): 2.1.2; (f): G
1393 |  |  | 31 21 13 | 6 | Test Reports | Post Mitigation Testing | (e): 3.3.2; (f): G
1394 |  |  | 31 21 13 | 7 | Certificates | Contractor Qualifications | (e): 1.8.1.1; (f): G
1395 |  |  | 31 21 13 | 7 | Certificates | Testing Laboratory Certification | (e): 1.8.2; (f): G
1396 |  |  | 31 21 13 | 7 | Certificates | Radon Mitigation System Inspection | (e): 3.3.1; (f): G
1397 |  |  | 31 21 13 | 8 | Manufacturer's Instructions | Radon Mitigation Systems Components | (e): 2.1.2
1398 |  |  | 31 21 13 | 10 | Operation and Maintenance Data | Radon Mitigation Systems | (e): 2.1; (f): G
1399 |  |  | 31 21 13 | 11 | Closeout Submittals | Radon Detector Location Log | (e): 1.6; (f): G
1400 |  |  | 31 32 11 | 1 | Preconstruction Submittals | Erosion control inspector qualifications | (e): 1.5
1401 |  |  | 31 32 11 | 3 | Product Data | Catch Basin Inlet Protection Filters | (e): 2.1; (f): G
1402 |  |  | 31 32 11 | 3 | Product Data | Compost Filter Sock | (e): 3.3.2; (f): G
1403 |  |  | 31 32 11 | 6 | Test Reports | Maintenance and Inspection Logs | (e): 3.5
1404 |  |  | 31 63 29 | 2 | Shop Drawings | Design Drawings | (e): 1.7.1; (f): G
1405 |  |  | 31 63 29 | 2 | Shop Drawings | Fabrication and Installation Drawings | (e): 1.3.1; (f): G
1406 |  |  | 31 63 29 | 3 | Product Data | Installation Plan | (e): 1.3.1; (f): G
1407 |  |  | 31 63 29 | 3 | Product Data | Casing | (e): 2.3
1408 |  |  | 31 63 29 | 5 | Design Data | Design Drawings | (e): 1.7.1; (f): G
1409 |  |  | 31 63 29 | 5 | Design Data | Cement Grout Mix Design | (e): 2.1.1.1; (f): G
1410 |  |  | 31 63 29 | 5 | Design Data | Pile Load Tests | (e): 3.3.1; (f): G
1411 |  |  | 31 63 29 | 6 | Test Reports | Pile Load Tests | (e): 3.3.1; (f): G
1412 |  |  | 31 63 29 | 6 | Test Reports | Grout Mix Proportions | (e): 2.1.1.1; (f): G
1413 |  |  | 31 63 29 | 6 | Test Reports | Grout Compressive Strength | (e): 3.3.1; (f): G
1414 |  |  | 31 63 29 | 7 | Certificates | Designer Qualifications | (e): 1.5.5; (f): G
1415 |  |  | 31 63 29 | 7 | Certificates | Installer Qualifications | (e): 1.5.6; (f): G
1416 |  |  | 31 63 29 | 7 | Certificates | Pile Materials | (e): 1.5.3; (f): G
1417 |  |  | 31 63 29 | 7 | Certificates | Field Testing Technician | (e): 3.3.3; (f): G
1418 |  |  | 31 63 29 | 11 | Closeout Submittals | As Built Data | (e): 3.4.1; (f): G
1419 |  |  | 32 01 19.61 | 3 | Product Data | Sealants | (e): 2.1; (f): G
1420 |  |  | 32 01 19.61 | 3 | Product Data | Manufacturer's Recommendations | (e): 3.4.2
1421 |  |  | 32 01 19.61 | 3 | Product Data | Application Equipment List | (e): 3.1
1422 |  |  | 32 01 19.61 | 8 | Manufacturer's Instructions | Sealants | (e): 2.1; (f): G
1423 |  |  | 32 05 33 | 1 | Preconstruction Submittals | Integrated Pest Management Plan | (e): 2.4; (f): G
1424 |  |  | 32 05 33 | 3 | Product Data | Fertilizer | (e): 2.1; (f): G
1425 |  |  | 32 05 33 | 3 | Product Data | Mulches Topdressing | (e): 2.3; (f): G
1426 |  |  | 32 05 33 | 3 | Product Data | Organic Mulch Materials | (e): 2.3.1; (f): G
1427 |  |  | 32 05 33 | 7 | Certificates | Maintenance Inspection Report | (e): 3.3.1; (f): G
1428 |  |  | 32 12 17 | 3 | Product Data | Material Batch Tickets | (e): 1.3.3; (f): G
1429 |  |  | 32 12 17 | 5 | Design Data | Mix Design | (e): 1.3.2; (f): G
1430 |  |  | 32 12 17 | 5 | Design Data | Mix Design | (e): 2.4; (f): G
1431 |  |  | 32 12 17 | 6 | Test Reports | Pavement Courses | (e): 3.5.2.1; (f): G
1432 |  |  | 32 17 23 | 1 | Preconstruction Submittals | Qualifications | (e): 1.3.2; (f): G
1433 |  |  | 32 17 23 | 3 | Product Data | Surface Preparation Equipment List | bar: (f)
1434 |  |  | 32 17 23 | 3 | Product Data | Application Equipment List | (e): 2.1.1; (f): G
1435 |  |  | 32 17 23 | 3 | Product Data | Exterior Surface Preparation | (e): 3.2
1436 |  |  | 32 17 23 | 3 | Product Data | Solventborne Paint | (e): 2.2.1; (f): G
1437 |  |  | 32 17 23 | 8 | Manufacturer's Instructions | Solventborne Paint | (e): 2.2.1; (f): G
1438 |  |  | 32 92 19 | 3 | Product Data | Wood Cellulose Fiber Mulch | (e): 2.5.3; (f): G
1439 |  |  | 32 92 19 | 3 | Product Data | Fertilizer | (e): 2.4; (f): G
1440 |  |  | 32 92 19 | 6 | Test Reports | Topsoil Composition Tests | (e): 2.2.3; (f): G
1441 |  |  | 32 92 19 | 7 | Certificates | Seed | (e): 2.1; (f): G
1442 |  |  | 33 11 00 | 1 | Preconstruction Submittals | Connections | (e): 3.1.1; (f): G
1443 |  |  | 33 11 00 | 3 | Product Data | Pipe, Fittings, Joints and Couplings | (e): 2.1.1; (f): G
1444 |  |  | 33 11 00 | 3 | Product Data | Valves | (e): 2.1.2; (f): G
1445 |  |  | 33 11 00 | 3 | Product Data | Valve Boxes | (e): 2.1.2.2; (f): G
1446 |  |  | 33 11 00 | 3 | Product Data | Pipe Restraint | (e): 2.2.1; (f): G
1447 |  |  | 33 11 00 | 3 | Product Data | Corporation Stops | (e): 2.2.3.1; (f): G
1448 |  |  | 33 11 00 | 3 | Product Data | Precast Concrete Thrust Blocks | (e): 2.2.1.2; (f): G
1449 |  |  | 33 11 00 | 3 | Product Data | Disinfection Procedures | (e): 3.2.2; (f): G
1450 |  |  | 33 11 00 | 6 | Test Reports | Bacteriological Samples | (e): 3.3.1.3; (f): G
1451 |  |  | 33 11 00 | 6 | Test Reports | Leakage Test | (e): 3.3.1.2
1452 |  |  | 33 11 00 | 6 | Test Reports | Hydrostatic Test | (e): 3.3.1.1; (f): G
1453 |  |  | 33 71 02 | 3 | Product Data | Conduit, Ducts, and Fittings | (e): 2.1; (f): G
1454 |  |  | 33 71 02 | 3 | Product Data | Duct Sealant | (e): 2.1.4; (f): G
1455 |  |  | 33 71 02 | 6 | Test Reports | Field Acceptance Checks and Tests | (e): 3.11.1; (f): G
1456 |  |  | 33 71 02 | 7 | Certificates | Cable Installer Qualifications | (e): 1.5.1; (f): G
1457 |  |  | 33 82 00 | 2 | Shop Drawings | Telecommunications Outside Plant | (e): 1.6.1.1; (f): G
1458 |  |  | 33 82 00 | 2 | Shop Drawings | Telecommunications Entrance Facility Drawings | (e): 1.6.1.2; (f): G
1459 |  |  | 33 82 00 | 3 | Product Data | Wire and Cable | (e): 2.7; (f): G
1460 |  |  | 33 82 00 | 3 | Product Data | Cable Splices, and Connectors | (e): 2.4; (f): G
1461 |  |  | 33 82 00 | 3 | Product Data | Closures | (e): 2.3; (f): G
1462 |  |  | 33 82 00 | 3 | Product Data | Building Protector Assemblies | (e): 2.2.1; (f): G
1463 |  |  | 33 82 00 | 3 | Product Data | Protector Modules | (e): 2.2.2; (f): G
1464 |  |  | 33 82 00 | 6 | Test Reports | Pre-installation Tests | (e): 3.5.1; (f): G
1465 |  |  | 33 82 00 | 6 | Test Reports | Acceptance Tests | (e): 3.5.2; (f): G
1466 |  |  | 33 82 00 | 6 | Test Reports | Outside Plant Test Plan | (e): 1.6.3; (f): G
1467 |  |  | 33 82 00 | 7 | Certificates | Telecommunications Contractor | (e): 1.6.2.1; (f): G
1468 |  |  | 33 82 00 | 7 | Certificates | Key Personnel | (e): 1.6.2.2; (f): G
1469 |  |  | 33 82 00 | 7 | Certificates | Manufacturer's Qualifications | (e): 1.6.2.3; (f): G
1470 |  |  | 33 82 00 | 8 | Manufacturer's Instructions | Building Protector Assembly Installation | (e): 2.2.1; (f): G
1471 |  |  | 33 82 00 | 8 | Manufacturer's Instructions | Cable Tensions | (e): 3.1.6.1; (f): G
1472 |  |  | 33 82 00 | 8 | Manufacturer's Instructions | Fiber Optic Splices | (e): 3.1.7.1; (f): G
1473 |  |  | 33 82 00 | 9 | Manufacturer's Field Reports | Factory Reel Test Data | (e): 2.12.1; (f): G
1474 |  |  | 33 82 00 | 10 | Operation and Maintenance Data | Telecommunications Outside Plant (OSP) | (e): 1.6.1.1; (f): G
1475 |  |  | 33 82 00 | 11 | Closeout Submittals | Record Documentation | (e): 1.8.1; (f): G
2025-10-28 15:39