# PERFORMANCE WORK STATEMENT

# FOR

# OPTIMIZED REMEDIATION CONTRACT

# AT

# SHAW AFB, SOUTH CAROLINa

# CONTRACT NUMBER: tbd

# 18 February 2026

Table of Contents

1.0	SCOPE	4

1.1	Introduction	4

1.2	Overview of ORC Scope and Requirements	4

1.2.1	Specific Scope Discussion and Limits	6

1.2.2	Preliminary Assessment/Site Inspection, Remedial Investigation or Remedial Investigation/Feasibility Study (including Supplemental Investigations), and Decision Document	6

1.2.3	Response Complete or Site Closeout	6

1.2.4	Remedial Action-Operation with Optimization including Interim RA-O (IRA-O) with Optimization	6

1.2.5	Remedial Action-Operation and Reduce Life Cycle Cost; Long Term Management and Reduce Life Cycle Cost	7

1.2.6	Remedial Action-Operation or Long-Term Management (as appropriate)	8

1.2.7	Alternate Objectives	8

1.3	Performance Requirements	11

1.3.1	Table 1: Performance Table	11

1.3.2	Additional Scope Discussion and Limits	25

2.0 APPLICABLE DOCUMENTS	28

3.0 GOVERNMENT FURNISHED INFORMATION AND PROPERTY	28

4.0 MANAGEMENT, PLANNING, AND REPORTING REQUIREMENTS	29

4.1 Project Management Plan	29

4.2 Schedule and Planning Requirements – Integrated Master Schedule	30

4.3 Milestone Payment Schedule	31

4.4 Cost and Status Reporting	34

4.5 ORC Document Repository	35

4.6 Meeting and Conference Requirements	35

4.6.1 Meeting/Teleconference Support	35

4.6.2 Public Meetings and Hearings	36

4.6.2.1 Community Involvement Plan (CIP) Update	36

4.7. Spatial Data (Map) Requirements	37

4.8 Information Security	38

4.8.1 Cybersecurity Standard Operating Procedure	38

4.9 Notification Requirements	39

4.10   Permits	39

4.10.1   Environmental Permits	39

4.10.2 Rights of Access to Non-AF Real Property	40

4.11   Photo Documentation	40

4.12   Remote and/or Austere Sites	41

4.13   Site Access	41

4.14   Worksite Activities and Coordination	41

4.14.1 Coordination of Activities	41

4.14.2  Hazardous Material, and Hazardous Waste Permitting and Reporting	41

4.14.2.1  	Regulatory Requirements	42

5.0   CHEMISTRY REQUIREMENTS	43

5.1  	Quality Assurance	43

5.2  	Laboratory Selection	44

5.3  	Analytical Data Management	44

5.4  	Record Keeping	44

5.5     PFAS Sampling and Analysis	45

6.0 	PLANS AND REPORTS	45

6.1	Quality Program Plans	45

6.1.1	Work Plans	45

6.1.2	Health and Safety Plan	45

6.1.3	Construction Quality Plan	45

6.2	Technical Plans and Reports	45

7.0  	SITE WORK	47

7.1	Conservation	47

7.2	Site Characterization and Field Investigation	47

7.3	Site Preparation	47

7.4	Demolition	48

7.5	Site Restoration	48

8.0	ENVIRONMENTAL REQUIREMENTS	48

8.1	Environmental Restoration Process Application	49

8.1.1	Conceptual Site Model Guidance	49

8.1.2	Exit Strategy	50

8.1.3	Performance and Optimization	51

8.2	Transition of Work	54

8.2.1	Table 2:  Transition of Work Table	54

8.2.2	Table 3:  Sampling Transition Table	54

8.3	Environmental Construction	58

8.3.1	Design	58

8.3.2	Inspection	58

8.3.3	Delivery and Warranty	58

8.4	Environmental Resources Program Information Management System	59

8.5	Innovative and Proven Technologies	59

8.6	Operations and Maintenance	59

8.7	Ordnance Removal and Support	60

8.8	Hazardous Waste Removal and Support	60

8.9	Study Effort Incidental to Remedy or Corrective Action	60

8.10	Five-Year Review Support	60

9.0	Performance Standards and Surveillance Activities	60

10.0	POINTS OF CONTACT	60

11.0	CONTRACTOR MANPOWER REPORTING REQUIREMENTS	60

# 1.0	SCOPE

This requirement is for environmental remediation activities at Shaw Air Force Base (AFB), South Carolina (SC).  This Performance Work Statement (PWS) defines the scope of environmental services necessary to conduct site restoration under the Optimized Remediation Contract (ORC).  The range of activities includes investigation, design, construction of remedial systems, operation and maintenance of established remedies, optimization at applicable sites, and achievement of site-specific objectives.  The Contractor shall undertake Environmental Remediation activities to achieve Performance Objectives (POs) at eighteen (18) Installation Restoration Program (IRP) sites and zero (0) Military Munitions Response Program (MMRP) sites.

NOTE:  For purposes of this ORC, the term “Government” includes the Air Force (AF) and  United States Army Corps of Engineers (USACE).  While regulators are a governmental entity, they are also a third party over whom the Air Force has no control and, as such, will be referred to as “regulators.”

## 1.1	Introduction

Shaw AFB is an active U.S. Department of Defense (DoD) installation located in northwest Sumter County, South Carolina, approximately 37 miles east of Columbia and 7 miles west of the City of Sumter along U.S. Highway 76/378. Sumter County is located in the central portion of the state and is bounded by Lee County to the north, Florence County to the east, Clarendon to the south, and Richland County to the west. The base encompasses 3,570 acres set in a mostly rural and agricultural area, although residential and commercial developments are present near the western and southeastern boundaries of the base.

Shaw AFB was activated on 30 August 1941 as one of the largest flying fields in the United States with its first task being to train cadets to fly. The first group of cadets arrived on 04 December 1941. The installation consists of airstrips, fuel depots, aviation equipment storage hangers, support buildings, residential buildings, and recreational areas.

Shaw AFB is currently home to the 20th Fighter Wing, the Air Force’s largest combat F-16 wing whose mission is to provide, project, and sustain combat-ready air forces. Shaw AFB also serves as home to Headquarters Ninth Air force and United States Air Forces Central Command whose primary mission is to project decisive air and space power for the United States Central Command and America. The 3rd Army is also located at Shaw AFB with its primary operations in the eastern portion of the base.

Remediation activities at Shaw AFB are being conducted pursuant to the National Oil and Hazardous Substances Contingency Plan (NCP), and the Resource Conservation and Recovery Act (RCRA) requirements.  Regulatory oversight is provided by the South Carolina Department of Environmental Services (SCDES).

Installation is being administered under a RCRA Corrective Action Permit dated and last renewed in 2019 with the next expiration in 2029; this document requires 1 to 2 years advanced coordination and submittal in order to be in place before the current permit expires.

## 1.2	Overview of ORC Scope and Requirements

The Contractor shall perform all the necessary environmental remediation activities needed to achieve the performance requirement described in Table 1: Performance Table, and additional scope in 1.3.2.  This PWS and enclosures listed below detail the project requirements needed to meet the AF objectives:

Enclosure 1 – Acronyms and Definitions

Enclosure 2 – Government Furnished Information (GFI)

Enclosure 2A – Administrative Record Spreadsheet

Enclosure 2B – GFI Base Documents Spreadsheet

Enclosure 2C – Site-Specific GFI

Enclosure 3 – Government Furnished Property (GFP) - Not Applicable

Enclosure 4 – Community Involvement Plan (CIP) Guidance version 4

The intent of the ORC initiative is to advance site cleanup during the Period of Performance (POP) in the most efficient and cost-effective manner, as supported by a cost-benefit analysis and exit strategy that achieves the greatest reduction in life-cycle cost (LCC).  The AF is interested in substantial reduction of long-term environmental liabilities and total LCC.  Technical approaches that are simply reduced to a minimal level of effort with no well-planned contingencies provide no assurance to the Government that the POs will be achieved without work stoppages or change orders which is not in keeping with the intent of this performance based contracting effort. The AF is required to implement remedies as necessary to enable the mission, protect human health and the environment, and comply with laws and regulations.  The goal of the ORC initiative is to ensure the AF continues to fulfill all facets of its Environmental Restoration Program (ERP) mission, by effectively and efficiently managing the program in a performance-based, results-oriented, and cost-conscious framework.

The AF requires that all sites be remediated to standards that allow for the current or reasonably anticipated future land use of the property.  Accurate documentation and reporting of contaminant removal and cost savings are critical adjuncts to optimization success.  In keeping with Defense Environmental Restoration Program (DERP) and Air Force Instruction (AFI) 32-7020, the AF defines optimization under the ORC as the reduction of contaminant mass and concentrations, reduction in LCC, or any combination of activities leading to acceleration of Response Complete (RC)/Site Closeout (SC) as a result of remedial implementation the Contractor undertakes, above and beyond what is required to maintain compliance in accordance with an approved Decision Document (DD).

The Contractor shall maintain compliance with all DDs/Records of Decision (RODs)/Proposed Plans/RCRA Permits that are currently in place until no longer required, or an alternate approach is approved.  The contractor shall conduct DD/ROD amendments or Explanation of Significant Differences (ESD) as required to implement new approach(es).

The Contractor shall function as an integral team member in support of the Air Force Civil Engineer Center (AFCEC) mission to include the sharing of information with USACE, other AFCEC Contractors, and AF personnel, in cooperation with community stakeholders, regulators, and other Government entities.

Requirements for efficient management of this contract include the achievement of the POs in the Performance Period (PP) per Table 1 and work described in Section 1.3.2 of this PWS. Requirements include timely identification and solution of impediments to successful project execution.  The Contractor shall provide all personnel, equipment, supplies, tools, materials, and other items necessary to perform the tasks defined in this PWS.  The Contractor is solely responsible for reviewing all available information and forming their independent, professional conclusions/interpretations of site conditions and requirements to achieve the POs of this contract within the PP specified in accordance with Section 3.0.  AFCEC will rely on the Contractor’s expertise in recognizing and addressing problematic issues during the execution of this contract.  The Contractor shall perform all work in accordance with federal, state, and local statutes and regulations.  The Contractor shall also comply with installation regulations.  Remedies shall conform to environmental permits, DD requirements, or other legal requirements.  The Contractor shall continue work throughout the entire duration of the POP.  The Contractor’s local office presence will be relied upon to provide rapid-response actions for field activities and on-site meetings.

### 1.2.1	Specific Scope Discussion and Limits

The scope of this contract is to perform environmental remediation services for the sites listed in Table 1 and Section 1.3.2.  The ORC Contractor shall assume contractual liability and responsibility for achieving the POs. If the selected technical approach is not working, as demonstrated by the trends in the performance model, the Contractor shall develop and implement a revised technical approach to achieve the POs, including DD amendments, if required, to implement the remedial approach.  This scope includes all known contaminants linked to the specific sites per Table 1 of the PWS (includes contaminants on, under, or sourced at/migrating from the specific sites) without regard to quantity (e.g., plume size, concentrations). See reference to Section 1.3.2 of this PWS for exclusions. The AF remains statutorily responsible for all sites listed in Table 1 and work described in Section 1.3.2.

### 1.2.2	Preliminary Assessment/Site Inspection, Remedial Investigation or Remedial Investigation/Feasibility Study (including Supplemental Investigations), and Decision Document

Table 1 of the PWS identifies Preliminary Assessment/Site Inspection (PA/SI), Remedial Investigation (RI) or RI/Feasibility Study (FS), including Supplemental Investigations, and DDs as the PO for selected sites.  The Contractor is responsible for achieving these POs as identified in Table 1 and work described in Section 1.3.2.  See PO definitions in Enclosure 1, Acronyms and Definitions.

### 1.2.3	Response Complete or Site Closeout

Table 1 of the PWS identifies RC or SC as PO for selected sites.  The Contractor is responsible for achieving these objectives as identified in Table 1 and work described in Section 1.3.2.  See PO definitions in Enclosure 1, Acronyms and Definitions.  The performance components, including the need for a performance model, are described in Section 8.1.3.

### 1.2.4	Remedial Action-Operation with Optimization including Interim RA-O (IRA-O) with Optimization

Table 1 of the PWS identifies the following POs which include optimization as follows: 1. Remedy in Place (RIP) and Remedial Action-Operation (RA-O) with Optimization, 2. DD Amendment (or Explanation of Significant Differences [ESD]) with Remedy Implementation and RA-O with Optimization, or 3. RA-O with Optimization.  The Contractor is responsible for achieving these POs as identified in Table 1: Performance Table and additional scope described in Section 1.3.2.  See PO definitions in Enclosure 1, Acronyms and Definitions.

The optimization and performance components, including the need for a performance model showing interim and final performance payment milestones, are described in Section 8.1.3. Optimization goals may include one or more of the following:

- Shorten time to RC, SC, or other DoD goals.

- Improve remedy performance and/or accelerate the progress of the remediation.

- Enhance source or plume control for engineering systems.

### 1.2.5	Remedial Action-Operation and Reduce Life Cycle Cost; Long Term Management and Reduce Life Cycle Cost

Table 1 of the PWS identifies RA-O and Reduce LCC or Long-Term Management (LTM) and Reduce LCC as the PO for selected sites.  The goal of these POs is to minimize future AF liability and cost to the greatest degree feasible.  Reduce LCC sites have achieved RIP or RC, have remedies that are effective (source control, risk mitigation, and plume stability), and have the potential for LCC reduction by optimizing some component of the existing remedy, by, for example:

- Reducing sampling frequency

- Reducing system operations

- Reducing number of wells sampled per event

- Reducing number of analytes per sampling event

The Contractor shall achieve the following objectives for each Reduce LCC site:

- Maintain compliance with all DDs and permits (currently in place or to be approved) throughout the POP.

- For RA-O sites, develop performance models showing interim and final performance payment milestones, addressing all Contaminants of Concern (COCs) and breakdown products.  Refer to Section 4.3 and Section 8.1.3.1.

- Deliver a Reduce LCC Plan, as a stand-alone plan or in the Project Management Plan (PMP), that identifies opportunities to improve cost efficiency of RA-O or LTM activities, and the planned approach for implementation.  The Reduce LCC Plan shall:

  - Provide a basis for proposed reductions in LCC throughout the POP compared to the cost of status-quo RA-O activities (those required to maintain compliance).  The planned reduction can be illustrated using a line graph (current, planned, achieved) or verbiage describing the current and planned reductions.

  - Document risk and mitigation strategies for implementing optimization activities to reduce LCC.

- Update or revise site-specific work plans, monitoring plans, and/or DDs, as appropriate.

- Deliver Reduce LCC Reports to document progress in achieving the planned reductions when those reductions are achieved.  Reduce LCC Reports may be combined with monitoring reports.  Reductions in required RA-O activities are contingent upon regulatory approval.

- Deliver an RA-O & Reduce LCC Summary and Forecasting Report two years prior to the POP end date.  The Reduce LCC Summary and Forecasting Report shall:

  - Document cost-saving activities to date and forecast remaining activities and assumptions to further reduce LCC 10 years post-POP.

Provide a realistic projection to achieve SC or RC after the POP (the Contractor shall identify which PO is the optimal endpoint).  See PO definitions in Enclosure 1, Acronyms and Definitions.

### 1.2.6	Remedial Action-Operation or Long-Term Management (as appropriate)

Table 1 of the PWS identifies RA-O or LTM in accordance with the approved RCRA Permit as the PO for selected sites.  The Contractor shall achieve the following objectives for each RA-O and LTM site:

Maintain compliance with all DDs and permits (currently in place or to be approved) throughout the PP.  Update or revise site-specific work plans, monitoring plans, and/or DDs, as appropriate.

For RA-O sites, develop performance models addressing all COCs and breakdown products.  Refer to Section 8.1.3.1, Performance Models.

- Provide a realistic projection to achieve SC or RC after the POP (the Contractor shall identify which PO is the optimal endpoint).

### 1.2.7	Alternate Objectives

This section and the subparagraphs below describe the Alternate Objective Sites and a general overview of the work associated with these sites.  Please see Table 1 and work described in Section 1.3.2 for specific elements of work required for each site with an Alternate Objective PO.  These sites have complex attributes that have, to date, inhibited progress toward the achievement of RC.  For Alternate Objective sites, as for all sites in Table 1 of the PWS where applicable, the Contractor shall maintain compliance throughout the POP of the contract with all existing regulatory requirements, including but not limited to regulations, FFAs, RCRA Permits, final or interim RODs, or other equivalent remedial DDs.  The Contractor is responsible for implementing changes to the monitoring program based on activities conducted in the Advanced Site Characterization (PWS Section 1.2.7.1), including the addition and decommissioning of wells in the monitoring well network as agreed by all parties and the addition of new delineation monitoring where new information indicates our understanding of the plumes is changed.

Based on technical review of existing site conditions/activities, the AF placed sites in the category of Alternate Objective if one or more of the following conditions exist:

Achieving RC is expected to require substantially longer than 30 years.

Achieving RC is unattainable with standard characterization and/or existing remediation technology due to technical or other limitations related to site conditions.

Achieving RC is anticipated to require advanced site characterization technologies to improve the Conceptual Site Model (CSM), determine appropriate remedial technology, and/or characterize recently regulated contaminants.

The AF will use data and information obtained during execution of this PWS to determine restoration potential and future investment strategies at Alternate Objective sites.  Each Sub-Contract Line Item Number (Sub-CLIN) for the Alternate Objective sites will only be awarded if the activities are needed to determine the future investment strategy for the site.  The decision to award each Sub-CLIN resides solely at the discretion of the AF.

The Contractor shall conduct project scoping sessions before work plan development and throughout the planning and execution of the project to meet the PO, including the Installation Point(s) of Contact (POC[s]), the AFCEC Program Manager (PM) and Remedial Project Manager (RPM), the AF technical support team, and the Contracting Officer’s Representative (COR).  Upon approval by the AF and the COR, the Contractor shall participate in scoping sessions with the regulators as appropriate.

#### 1.2.7.1	Advanced Site Characterization

Based on existing data, the AF has determined that the existing remedial approaches at the Alternative Objective sites are not achieving satisfactory remedial progress toward their intended goals.  In order for the AF to determine the best path forward for these sites, the Contractor shall conduct Advanced Site Characterization to collect data to update and refine the CSM in order to achieve the following goals:  (1) Fill data gaps; and (2) Collect data needed to: (A) Determine why existing and previous remedial actions are not effective at achieving remedial progress; (B) Determine appropriate remedial technology(ies) based on site conditions; C) Develop remediation design parameters for recommended technology(ies); and D) Determine extent and concentrations of recently regulated contaminants, if required.

Advanced Site Characterization includes one or more of the following three activities: (1) Supplemental Site Investigation (SSI), (2) Revised CSM, and (3) Groundwater Monitoring Program Update.

##### 1.2.7.1.1	Supplemental Site Investigation

The Contractor shall conduct a Supplemental Site Investigation (SSI) to collect data necessary to improve the CSM, determine appropriate remedial technology, support remediation design and construction, and/or characterize recently regulated contaminants.  The Contractor shall implement advanced characterization methods, both established approaches and state-of-science techniques consistent with AF, regulatory, Interstate Technology and Regulatory Council (ITRC), and Strategic Environmental Research and Development Program/Environmental Security Technology Certification Program (SERDP/ESTCP) guidance to attain these objectives.  Data collection includes better definition of the geology, hydrogeology, geochemistry, and/or source(s) and distribution of COCs, as required.  The Contractor shall evaluate the need for, and collect the following data where appropriate:  (1) Source Zone Delineation; (2) Source Mass/Extent,,; (3) Vertical and lateral extent of contamination, if not sufficiently defined; (4) Plume Stability; (5) Migration pathway, rates, and fluxes in 3-D; (6) Mass distribution; (7) Biogeochemical conditions and influences on contaminant degradation pathways; (8) Impact of recent and historical remedies on site conditions; and (9) Comprehensive Risk including the vapor intrusion pathway.

The SSI report shall document data collection efforts to include a risk evaluation, if appropriate.  The Contractor shall evaluate and provide recommendations regarding whether additional source control is needed or whether the plume, or portions of the plume, are amenable to natural attenuation by conducting source strength and plume stability evaluations as needed.

##### 1.2.7.1.2	Conceptual Site Model

The Contractor shall develop a revised CSM in 3-D to include establishing or updating existing fate and transport models based on existing data and data gathered during the SSI.  The CSM should cover the source area and the distal plume, to include the lateral and vertical extent of the contaminants in the context of geologic/hydrogeological parameters and the remedial actions conducted to date.

##### 1.2.7.1.3	Groundwater Monitoring Program Update

The Contractor shall evaluate the current horizontal and vertical well distribution to determine if the following can be properly evaluated:

Remedy performance in treatment areas

Hydrogeology, plume geometry, horizontal and vertical plume stability, and matrix diffusion across site

Plume migration through use of perimeter/boundary wells and sentinel wells

Based on the well network evaluation, coordinated and approved by the Government and regulators (if required), the Contractor shall optimize the monitoring well network to include adjusting sample collection frequency and the addition of new wells as appropriate.  The Contractor shall update the Basewide or Site-Specific Monitoring Plan or other equivalent document, as appropriate.

#### 1.2.7.2		Remedy Evaluation and Recommendation

Based on all existing data and data gathered during the Advanced Site Characterization, the Contractor shall evaluate the existing active and/or passive remedy(ies),,.  The Contractor shall provide recommendations to augment, modify, and/or replace the existing remedy.  The evaluation and recommendations will include a cost-benefit analysis and evaluation of the usability, expandability, and/or discontinued use of any existing infrastructure.  All remedy recommendations must include a performance model addressing all COCs and breakdown products.  Refer to Section 8.1.3.1, Performance Models.

Where necessary to evaluate the proposed technology, the Contractor shall conduct pilot-scale technology demonstrations.  The Contractor shall identify appropriate remedial technologies and target zones, design/plan, conduct, and evaluate the pilot and/or field scale technology consistent with AF, regulatory, and ITRC guidance.  The Contractor shall determine performance monitoring criteria and identify a control sub-site (current state) for comparison and to evaluate results.

In some instances, achievement of RC may not be feasible with currently available technologies within a reasonable timeframe.  If this is the case, the Contractor shall develop and evaluate alternatives for site management that will be protective of human health and the environment.  If this recommendation is made, it must include the rationale, recommended target when active remediation can cease, and a strategy for obtaining regulatory approval.

##### 1.2.7.2.1	Cost/Benefit Analysis

The Contractor shall provide a cost/benefit analysis for proposed alternatives.  Alternatives may include optimizing the remedy in the DD or other remedies with the potential for better performance.  All alternatives identified shall be evaluated against one another to determine which alternative can achieve RC in the shortest time and has the lowest overall LCC.  The cost/benefit analysis shall include:

- A focused analysis of alternative approaches, to include conceptual designs and engineering cost estimates.  The analysis shall identify the total cost of executing the optimized remedy (including the plan and reports).

- An estimate of the reduction of LCC of each alternative evaluated.

- Any risk inherent in implementing the alternative optimized remedy.

- A summary comparison of the LCC and risk of each alternative in a cost/benefit analysis that clearly states the recommended alternative.

#### 1.2.7.3	Decision Document Amendment

- Based on the results of the remedy evaluation and recommendation, it may be necessary to amend the DD to augment, modify, and/or replace the existing remedy.  If warranted, the Contractor shall update the DD.

## 1.3	Performance Requirements

### 1.3.1	Table 1: Performance Table

Table 1 presents the POs, PPs, and Performance Standards associated with all installations/sites under this ORC.  The PP specified in Table 1 starts from the Obligation Date of the first Sub-Contract Line Item Number (CLIN) for the site unless otherwise specified.  All approvals (both Government and regulator) per the Performance Standard are required in writing.  Additional scope discussion and limits can be found in Section 1.3.2.

Table 1: Performance Table

| Site | Performance Objective | Performance Period* | Performance Standard |
| --- | --- | --- | --- |
| N/A | Project Management Plan (PMP): - Draft PMP - Final PMP - Updates as necessary | Draft PMP within 60 calendar days from contract award, Final PMP within 14 calendar days of receipt of AF and USACE comments on the draft and update as necessary throughout the POP. The AF and USACE will determine when whole document PMP updates are warranted | AF and USACE approval of PMP. The PMP should be maintained with accuracy and completeness based on the current technical approach for each site, management structure, etc. |
| N/A | Integrated Master Schedule (IMS)/Milestone Payment Schedule (MPS) | Draft IMS/MPS within 60 calendar days from contract award, Final IMS/MPS within 14 calendar days of receipt of AF and USACE comments on the draft, and updates monthly throughout the POP | AF and USACE approval of IMS/MPS. |
| N/A | Basewide Quality Program Plans (QPP) for each Installation | Draft Basewide QPP within 60 calendar days from contract award and update as necessary throughout the POP | AF, USACE and regulatory approval of Basewide QPP. |
| SHAW AFB - IRP SITES |  |  |  |
| N/A | Develop and update Land Use Control Implementation Plan (LUCIP) | One (1) per year | AF, USACE and regulatory approval of Basewide LUCIP |
| All Open Sites (IRP, MMRP, PFAS, etc.) | Community Involvement Plan (CIP) and updates are required prior to the RI phase, after the DD/ROD is signed, and every five (5) years thereafter for each Installation and associated Geographically Separate Units (GSUs), per Enclosure 4. | Draft CIP or Update within 180 calendar days from Sub-CLIN award; Draft Final CIP or Update within 14 calendar days of receipt of AF comments on the draft; Final CIP or Update within 14 calendar days of approval by the AF. | AF and USACE approval of CIP. |
| CG038 (AOC O) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| CG038 (AOC O) | Alternate Objectives: - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |
| DP039 (SWMU 101, AOC 32) | LTM in accordance with the approved CMI Work Plan and RCRA Permit | Through the duration of the POP | AF, USACE, and regulatory approval of LTM documentation (e.g., Land Use Control Inspection Reports). |
| FT001 (SWMU 59) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report |
| FT001 (SWMU 59) | Alternate Objectives: - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |
| LF003 (SWMU 58) | LTM in accordance with the approved CMI Work Plan and RCRA Permit | Through the duration of the POP | AF, USACE, and regulatory approval of LTM documentation (e.g., Land Use Control Inspection Reports). |
| LF008 (SWMU 85) | LTM in accordance with the approved CMI Work Plan and RCRA Permit | Through the duration of the POP | AF, USACE, and regulatory approval of LTM documentation (e.g., Land Use Control Inspection Reports). |
| LF009 (SWMU 52) | LTM and Reduce LCC in accordance with the approved CMI Work Plan and RCRA Permit | Through the duration of the POP | AF, USACE, and regulatory approval of LTM documentation (e.g., Land Use Control Inspection Reports). |
| OT016A (SWMU 78) | RA-O in accordance with the approved CMI Work Plan, RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, Reduce LCC Summary Report, etc.). AF and USACE approval of Performance Model Evaluation Report during RA-O. |
| OT016A (SWMU 78) | Alternate Objectives: - Revised Statement of Basis/RCRA Permit Modification - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |
| OT016B (AOC F) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, Reduce LCC Summary Report, etc.). AF and USACE approval of Performance Model Evaluation Report during RA-O. |
| OT016B (AOC F) | Alternate Objectives: - Advanced Site Characterization (Focused Supplemental Site Investigation (SSI), Revised Conceptual Site Model (CSM), and Supplemental Human Health Risk Assessment) - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study plus evaluation of all Well and screen placements) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF, USACE, and regulatory approval of SSI Report, revised CSM and Risk Assessment, including all RCRA equivalents. AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |
| OT016C (AOC D) | RA-O with optimization in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| OT016D (AOC W) | Site Closeout | Seven (7) years | AF, USACE, and regulatory approval of SC documentation (e.g., Site Closeout Report and Well Abandonment Confirmation Report). |
| SD033 (SWMU 96) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| SD033 (SWMU 96) | Alternate Objectives: - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification | Seven (7) years | AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. |
| SS015 (SWMU 2) Black Hole Area – POL Yard | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| SS015 (SWMU 2) Black Hole Area – POL Yard | Alternate Objectives: - Advanced Site Characterization (Supplemental Site Investigation (SSI), Revised Conceptual Site Model (CSM), and Supplemental Human Health Risk Assessment - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan | Seven (7) years | AF, USACE, and regulatory approval of SSI Report, revised CSM and Risk Assessment, including all RCRA equivalents. AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. |
| SS035 (AOC H) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| SS035 (AOC H) | Alternate Objectives: - Advanced Site Characterization (Focused Supplemental Site Investigation (SSI), Revised Conceptual Site Model (CSM), and Supplemental Human Health Risk Assessment) - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study plus evaluation of all Well and screen placements) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF, USACE, and regulatory approval of SSI Report, revised CSM and Risk Assessment, including all RCRA equivalents. AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. |
| SS036 (AOC N) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly Operations and Maintenance [O&M] Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| SS036 (AOC N) | Alternate Objectives: - Advanced Site Characterization (Focused Supplemental Site Investigation (SSI), Revised Conceptual Site Model (CSM), and Supplemental Human Health Risk Assessment) - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study plus evaluation of all Well and screen placements) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan | Seven (7) years | AF, USACE, and regulatory approval of SSI Report, revised CSM and Risk Assessment, including all RCRA equivalents. AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. |
| ST018 (SWMU 87) | Response Complete (RC) Upon achievement of RC, continue Long Term Management (LTM) in accordance with the approved CMI Work Plan and RCRA Permit throughout the duration of the POP | Seven (7) years | AF, USACE, and regulatory approval of RC documentation (e.g., Regulator approval of, and Air Force signature on, Final Remedial Action Completion Report). AF and USACE approval of Performance Model Evaluation Report during RA-O. AF, USACE, and regulatory approval of LTM documentation (e.g., Land Use Control Inspection Reports). |
| ST018 (SWMU 87) | Vapor Intrusion Mitigation Report | Seven (7) years | AF, USACE, and regulatory approval of Vapor Intrusion Mitigation Report. |
| ST030 (AOC M) | Response Complete (RC) Upon achievement of RC, continue Long Term Management (LTM) in accordance with the approved CMI Work Plan and RCRA Permit throughout the duration of the POP | Seven (7) years | AF, USACE, and regulatory approval of RC documentation (e.g., Regulator approval of, and Air Force signature on, Final Remedial Action Completion Report). AF and USACE approval of Performance Model Evaluation Report during RA-O. AF, USACE, and regulatory approval of LTM documentation (e.g., Land Use Control Inspection Reports). |
| ST030 (AOC M) | Alternate Objectives: - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |
| SHAW AFB - DLA SITES |  |  |  |
| N/A | Basewide Quality Program Plans (QPP) for each Installation | Draft Basewide QPP within 60 calendar days from contract award and update as necessary throughout the POP | AF, USACE and regulatory approval of Basewide QPP. |
| Bldg. 1200 (SWMU 98) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly O&M Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| Bldg. 1200 (SWMU 98) | Alternate Objectives: - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |
| Bldg. 1610 & Bldg. 1612 (SWMU 99) | RA-O in accordance with the approved CMI Work Plan and RCRA Permit (includes incorporating changes based on revisions to the monitoring program) | Through the duration of the POP | AF, USACE, and regulatory approval of RA-O documentation (e.g., Annual Groundwater Monitoring Reports, Monthly O&M Reports, etc.). AF and USACE approval of Performance Model Evaluation Report. |
| Bldg. 1610 & Bldg. 1612 (SWMU 99) | Alternate Objectives: - Remedy Evaluation and Recommendation Report / Corrective Measures Study (including results of any pilot study) - Revised Statement of Basis/RCRA Permit Modification - Updated Corrective Measures Implementation Work Plan - System Decommissioning Report, if existing treatment system is not needed or operational. | Seven (7) years | AF and USACE approval of the remedy evaluation and recommended proposed remedial strategy including successful demonstration of the existing or alternate remedy (e.g., through pilot or field test) showing decreasing trends in COCs. AF, USACE, and regulatory approval of ESD or ROD Amendment (i.e., Air Force and regulatory signatures on Final ESD or ROD Amendment), including all RCRA equivalents. AF, USACE, and regulatory approval of System Decommissioning Report. |

* The Performance Period is from the date of award of the first performance Sub-CLIN.

### 1.3.2	Additional Scope Discussion and Limits

In addition to the requirements identified in Table 1, the Contractor shall be responsible for:

- Operations and Maintenance (O&M) of all remediation equipment to include all wells associated with requirements in this PWS and well abandonment with AF, USACE, and regulatory approval (if required) when the well is no longer necessary.

  - Keeping systems operating as intended throughout the contract PoP. If a system becomes non-operational, the Contractor shall submit, in writing, the plan to get the system operating again to the Installation POC within 10 days. The plan shall include the timeline for repairs.

  - For sites SS035 and SS036, evaluate performance (includes compliance sampling) of and complete reporting for the air strippers at Base drinking water wells 3, 4, and 5.

    - The Contractor shall develop an Operations Recommended Upgrades report based on the performance evaluation. Base Operations will implement any recommended changes from this report.

    - Monthly sampling and quarterly reporting of influent/effluent water at the Base drinking water wells 3, 4, and 5 is required in order to determine air stripper effectiveness or any recommended upgrades. Any sampling result at the applicable limit shall be reported immediately.

For OT016B, SS035, and SS036 replace Caustic Soda Tank at GWTP1.

- Establishing a quality control/quality assurance process to ensure documents are of an acceptable quality and do not contain typos, formatting issues, contradictory information in tables and text, etc.

- Contaminants for which there are promulgated federal, state, or local standards.

- Conducting 1,4-Dioxane investigations as described in “Interim Air Force Guidance on Sampling and Response Actions for 1,4-Dioxane at Operational and [Base Realignment and Closure] BRAC Installations,” dated 24 May 2013.  The Contractor shall present results in one Tech Memo/Report per installation documenting the analytical methods and maps depicting sampling locations within the trichloroethene (TCE) plume and sample analysis results.

  - 1,4 Dioxane Memo Steps 1 and 2 have been completed.

  - 1,4 Dioxane Compliance monitoring is required at OT016C (AOC D) and SS035 (AOC H) by SCDES.

  - 1,4 Dioxane Memo Step 3 is required at OT016C (AOC D) and SS035 (AOC H) by AF Policy/Regulations.

Manage and dispose of investigation-derived waste (IDW) media associated with PFAS in accordance with AF Guidance Memorandum “Interim Guidance on Destruction or Disposal of Materials Containing Per- and Polyfluoroalkyl Substances in the United States” dated 11 July 2023, AF Guidance Memorandum “Guidance on Incineration of Materials Containing Per- and Polyfluoroalkyl Substances” dated 14 July 2023, and Section 4.14.2 of this document. The following sites are validated PFAS sites; therefore, the Contractor shall test waste media for PFAS and dispose of it in accordance with the guidance.

- FT001P-SUB, FT006P-SUB, and FT007P-SUB.

- The Contractor shall test IDW for PFAS using EPA test method 1633 as required for waste acceptance at the following sites:

  - DP039, FT001, OT016A, OT016B, SS035, and SS036.

The contractor shall conduct PFAS sampling associated with water treatment systems GWTP1: OT016B, SS035, and SS036; and GWTP2: FT001P-SUB, FT006P-SUB, FT007P-SUB. The contractor is responsible for the O&M of the entire system, including the retro fitted portion and all media changeouts necessary. The contractor shall test influent, mid, and effluent samples for PFAS with an evaluation to determine when a media change out would be required at these sites.

Within nine months from contract award, the Contractor shall complete a one-time sampling event of all extraction wells for GWTP1- which will require development of a Sampling plan to determine the best way to grab the samples. Once the sampling has been accomplished, then a Technical Memorandum will be developed for each site with the sampling results and data gap recommendations for AF review and approval.

- Ensuring that remedial actions do not negatively impact the distribution of any other contaminants and/or emerging contaminants (e.g., PFAS, 1,4-dioxane).

- Conducting RAB-interest assessments and meetings; performing community outreach activities; and preparing CIPs or Updates as described in sections 4.6.1, 4.6.2, and Enclosure 4.

- The Contractor shall prepare and submit the RCRA Hazardous and Solid Waste Amendments (HSWA) permit renewal application.

  - The contractor will be responsible for paying any fees associated with the permit renewal or modifications, as well as issuing required public notices.

  - Two public meeting announcements are required for renewal or modification of the RCRA HSWA permit.

- Conduct Annual Basewide Well Surveys, Well Inventory and Condition Assessment. This requirement includes off-base wells.

  - Based on the annual well inspections, perform the itemized report findings to include well repairs, well redevelopments, well replacements, new well installations, and well decommissionings.

  - Include GIS files and updates for the Base maps.

  - Assist with NEPA Air force Form 813 review process, dig permits and surveys that mark treatment and utility lines.

- As required by AF/USACE at contract award, the contractor is to finalize any site ORC documents transitioned from the previous ORC contractor in any of the following versions: working copy, draft or draft final.

The Contractor shall NOT be responsible for:

- Reasonably unanticipated contaminants at sites identified in Table 1 (e.g., previously undetected mercury within a TCE plume); however, Contractors would be responsible for reasonably anticipated contaminants (e.g., vinyl chloride in a TCE plume).

- Remediation or treatment of contaminants for which there are no promulgated federal, state, or local standards or AF agreements at time of contract award unless included via modification.

- Official regulatory changes occurring after contract award, as documented in Administrative Code, laws, and regulations, e.g., decrease in residential Soil Cleanup Target Levels, Groundwater Cleanup Target Levels, etc.

- Sites not identified in Table 1.

- Sites containing radiological waste.

- Remediation of sites with unexploded ordnance (UXO), Discarded Military Munitions (DMMs), munitions constituents (MCs) present in high enough concentrations to pose an explosive hazard, and chemical warfare material (CWM).

# 2.0 APPLICABLE DOCUMENTS

The Contractor shall identify and comply with all applicable federal, state, and local statutes; Department of Defense (DoD) and AF instructions, manuals, handbooks, regulations, guidance, and policy letters (including AF policy and guidance for IRP and MMRP); Executive Orders (EOs), American Society for Testing and Materials (ASTM), American Petroleum Institute (API) Codes, National Association of Corrosions Engineers (NACE), National Fire Protection Association (NFPA), Steel Structures and Painting Counsel (SSPC), National Electrical Code (NEC), Uniform Fire Code (UFC), and International Building Code (IBC) including all changes and amendments in effect on the date of issuance of this contract.  It is the Contractor’s responsibility to identify and comply with all applicable requirements.  In addition, the Contractor shall refer to the current versions of the DoD Policy and Guidelines for Acquisitions Involving Environmental Sampling or Testing and The United States AF Construction Management Implementation Guide.

The Contractor shall identify and comply with all applicable documents for the Installations including RODs, ROD Amendments, ESDs, RCRA Permits and subsequent modifications, the Endangered Species Act, other Decision Documents, Deeds, waste management guidance, and conveyance notices.

# 3.0 GOVERNMENT FURNISHED INFORMATION AND PROPERTY

Government Furnished Information is contained in the Administrative Record (https://ar.afcec-cloud.af.mil/) or listed in Enclosure 2.  The documentation provided represents the most recent and appropriate documentation available for the Installation(s) and sites identified in this PWS. Electronic format is not guaranteed.

The Contractor shall properly account for and manage all new and existing GFP procured and utilized at the Installations as-is where-is in accordance with the Federal Acquisition Regulation (FAR).  Lists of current GFP are provided in Enclosure 3.  All Real Property installed during the contract shall be turned over to the Government consistent with procedures identified in Section 8.3.2.

The Contractor is responsible for providing all other supplies and equipment, not already installed, and not listed in Enclosure 3, that are required to achieve the POs of this contract.  All AF-owned property, including real property used for remediation purposes must be maintained by the Contractor in accordance with applicable maintenance requirements and usability for the intended purpose.  The Contractor is responsible for disposal of unneeded, unusable, or obsolete GFP as required, and transfer of remaining GFP to the Government at the end of the contract POP.  Prior to disposal of excess or unserviceable equipment listed in Enclosure 3, the Contractor shall coordinate activities with the Contracting Officer (KO) for disposition instructions.

# 4.0 MANAGEMENT, PLANNING, AND REPORTING REQUIREMENTS

The Contractor shall implement a full range of environmental remediation activities as required to meet objectives of this contract and in accordance with all applicable or relevant and appropriate federal, state, and local laws and regulations; DoD policies; and Installation-specific orders, agreements, or rules.  The Contractor shall supply all labor, equipment, and materials necessary to accomplish the work through the entire POP of the contract.  The Contractor shall perform management and planning functions, including performance measurement and fund status reporting.

The PMP, IMS, and MPS documents shall be fully integrated and consistent.  Consistency shall be maintained throughout the POP by fully implementing programmatic change control processes compliant with EC 5.2.1 (Execution of Change Control Boards) and PMP guidance. It is the Contractor’s responsibility to clearly demonstrate an applied understanding and compliance with ORC requirements, application of guidance/requirements, and consistency between the PMP, IMS, and MPS.  The Contractor shall create a single file for the IMS and MPS files and deliver them as separate files as required.

## 4.1 Project Management Plan

The Contractor shall develop and maintain a detailed PMP.  The PMP shall specify the project’s resources and tasks corresponding to the Sub-CLINs for this contract as required for the planning, execution, control, and completion of the stated POs. At a minimum, the PMP shall include the following sections:  technical approach for achieving the POs in accordance with the PWS, management approach including sub-contractor management, organization and integration of the project team, schedule management, project controls, transitional activities, risk management, quality management, health and safety management, procurement management, security management, and communications plans.  The Contractor is responsible for complying with the “Optimized Remediation Contract (ORC) Program Management Plan (PMP) Guidance” latest version, as well as standard industry practice.  Clarification on PMP content and the level of detail required to address the ORC program shall be provided by the COR.

The PMP shall demonstrate a comprehensive decomposition of each work package/PO deliverable and exhibit a clear and concise correlation between the PWS, IMS, and MPS.  The Contractor is responsible for complying with the guidance for the Development of Contract Line Item Number Structures, Integrated Master Schedules, and Milestone Payment Schedules (CLIN, IMS, and MPS Guidance) per the latest version of the “ORC PMP Guidance.”

The first draft of the PMP shall be submitted in accordance with Table 1. The Draft PMP and subsequent revisions shall be subject to AF and USACE review and approval.  The Final PMP shall be due within fourteen (14) calendar days of receipt of AF and USACE comments on the Draft versions.  The Contractor shall maintain the PMP throughout the duration of the contract utilizing dated page changes and track change deletions and insertions (electronic copies) as practicable.  Whole document PMP updates during the life of the ORC may be necessary based on the accumulation of small incremental changes or significant changes (e.g., contract requirements, technical approaches, risk and issue management, or key personnel).  The Contractor shall prepare two whole document updates during the POP of the ORC.  The AF and USACE will determine when PMP updates are warranted.

## 4.2 Schedule and Planning Requirements – Integrated Master Schedule

The Contractor shall prepare and submit an IMS in hardcopy and in electronic format (Microsoft Project, Adobe Acrobat portable document file (.pdf), and Microsoft Excel. The IMS will be finalized during development of the PMP and the Contractor shall update monthly.

The following are minimum AF requirements for the IMS:

Presents a realistic sequence and timing of all activities and documents necessary to demonstrate achievement of the PO within the PP. The IMS shall demonstrate full compliance with the PWS, including achieving POs within the required PP.

Utilizes a realistic calendar (i.e., work week of five eight-hour days, no submittals on Federal holidays, etc.), appropriate logic ties, clearly defined constraints, and identifies key points where risk mitigation/contingency actions may need to be taken.

Includes the following columns in the exact order as shown below:

Installation Name: Identify Enterprise Environmental, Safety, and Occupational Health Management Information System (EESOH-MIS) Installation Name per Table 1. The Installation name must be included in every line of every Sub-CLIN.

Site Number: Identify EESOH-MIS Site ID per Table 1 and Site Alias, if applicable. The EESOH-MIS Site ID must be included on every line of the IMS where applicable.

CLIN/Sub-CLIN: Identify CLIN and/or Sub-CLIN per Section B of the contract. The CLIN or Sub-CLIN must be included on every line of the IMS, as appropriate.

Note: Sub-CLINs for compliance activities (routine regulatory requirements to comply with binding agreements) are denoted as ####CX and Sub-CLINs for performance activities (remedial advancement or progress towards the PO) are denoted as ####AX. For example, for POs of RA-O with Optimization, the Performance Goal “A” Sub-CLINs are specifically for reporting progress in achieving the performance goal identified in the performance model (separate reports for each year). This requires a separate report identifying the most recent result for the performance indicator(s), usually a COC concentration, and how that compares with the projected value of the performance indicator in the performance model. The “C” Sub-CLINs are specifically for operating the remedy and reporting all required results, such as COC concentrations, geochemical, groundwater elevations, etc.

Task Description: Include detailed description of all activities (e.g., meetings, permitting, site access, work plans, mobilization, field work, documents, reviews, coordination with stakeholders, etc.) associated with achievement of the PO, and a clear indication of regulatory RCRA/State Program phase completions (e.g., RIP Achieved, RC Achieved, etc.) and PO achievement.

  - Activities should not be grouped together; every activity must have a separate entry. For example, the IMS must show separate activities for sample collection, sample analysis, data validation, Environmental Resources Program Information Management System (ERPIMS) upload, injections (mobilization, substrate injection, demobilization), and well installation (mobilization, drilling/well completion, demobilization).

Start and Finish Dates: Document Start date and Finish date for each required activity and document, including appropriate durations and Government and Regulatory review periods in accordance with Section 6.2 of the PWS.

- Include an obligation date, notice to proceed date, or projected award date as the first activity for each Sub-CLIN. Ensure that the obligation/notice to proceed date is in the same FY as the first line item of work.

- Include a clearly identified final field work (e.g., FINAL FIELD ACTIVITY) Start date and Finish Date for each site (i.e., indicate when the final set of field activities such as injections, groundwater sampling, or others will be complete).

Milestone Payment Amount: Include negotiated amount consistent with the approved MPS ensuring the sum of all milestone payments equals the value of the CLIN/Sub-CLIN per Section B of the contract. Include both summary and non-summary payments.

Percent Complete: Record completion status of all activities and documents as approved by the COR.

Predecessor and Successor: Define relationships and constraints associated with activities and documents.

The Contractor shall prepare and maintain the IMS in accordance with the PMP Guidance (latest version) and USACE ER 1-1-11 (Project Schedules).  The Contractor shall maintain and submit an IMS monthly in electronic format in accordance with the requirements above and include updates to progress and approved changes (e.g., Government or regulatory review periods, technical approaches, milestone payment updates, or contract requirements).  The IMSs shall be submitted electronically to the Contractor’s ORC document repository and in accordance with instructions from the COR.  The Contractor shall prepare and maintain the IMS in accordance with the PMP Guidance (latest version).

## 4.3 Milestone Payment Schedule

The Contractor shall prepare and submit an IMS, from which they will extract the information required to generate an MPS and will submit as two separate files. NOTE: The MPS is not part of the proposal. Award of the contract does not equate to final acceptance of the IMS. The IMS and MPS, including payment milestones and percentages, will be discussed and agreed upon among the Government (AF and Contracting Agent) and Contractor during the review of the initial PMP/IMS/MPS and approved by the COR.

The following are minimum AF requirements for the MPS:

Presents appropriate milestone payments considered integral and necessary to the achievement of the POs.

Ties interim and final milestone payments to performance models as described in Section 8.1.3.1 (also see Sections 1.2.4 through 1.2.5).

Includes a reasonable number of milestone payments per CLIN/Sub-CLIN based on the scope and anticipated duration to achieve CLIN/Sub-CLIN objective and/or PO.

Aligns with the CLINs/Sub-CLINs in Section B of the award document and includes the following columns:

Installation Name: Identify EESOH-MIS Installation Name per Table 1.

EESOH-MIS Site ID: Identify EESOH-MIS Site ID per Table 1 and Site Alias, if applicable.

CLIN/Sub-CLIN: Identify CLIN and/or Sub-CLIN per Section B of the contract.

Note: Sub-CLINs for compliance activities (routine regulatory requirements to comply with binding agreements) are denoted as ####CX and Sub-CLINs for performance activities (remedial advancement or progress towards the PO) are denoted as ####AX. For example, for POs of RA-O with Optimization, the Performance Goal “A” Sub-CLINs are specifically for reporting progress in achieving the performance goal identified in the performance model (separate reports for each year). This requires a separate report identifying the most recent result for the performance indicator(s), usually a COC concentration, and how that compares with the projected value of the performance indicator in the performance model. The “C” Sub-CLINs are specifically for operating the remedy and reporting all required results, such as COC concentrations, geochemical, groundwater elevations, etc.

Milestone Payment Identification Number: Include unique number assigned to each milestone payment for tracking purposes.

Milestone Payment Description: Include detailed description of definable and measurable step considered integral and necessary to the achievement of the CLIN/Sub-CLIN objective and/or PO.

Milestone Payment Amount: Include negotiated amount ensuring the sum of all milestone payments equals the value of the CLIN/Sub-CLIN per Section B of the contract.

Milestone Payment Percentage: Include percentage of the milestone payment in relation to the total CLIN/Sub-CLIN value.  The final payment milestone(s) within a CLIN/Sub-CLIN demonstrating achievement of the CLIN/Sub-CLIN objective must be a minimum of 20% of the total CLIN/Sub-CLIN value.  This may include both the AF and USACE approved and regulator approved versions. Milestones should not be front-loaded but instead be commensurate with the work completed.

Completion Date: Document completion date for each milestone payment consistent with the Finish date presented in the IMS.

Percent Complete: Identify completion status (0% or 100%) of all milestone payments as approved by the COR.

Invoice Number: Clearly indicate the invoice number associated with the milestone payment as approved by the COR for the purposes of tracking payment.  This information can be completed as invoices are prepared.

Excludes unacceptable milestone payments representing a “progress” payment or a monthly payment for level of effort expended including:

Preparation and/or submittal of documents

Site mobilization/demobilization (unless exempted by CO/KO)

Accomplishment of field activities including the following:

  - Substrate/chemical injection

  - Injection letter work plans

  - Injection summary memoranda

  - Field documentation tech memos

  - Semi-annual cap inspection tech memos

  - Quarterly and monthly LUC/LTM inspection reports

  - Quarterly discharge reports

  - Construction bond

  - Draft reports

  - Well construction logs

  - Payments of Less Than 2% of Sub-CLIN cost

Submittal of a monthly status

Management and overhead costs (e.g., program/project management, monthly reporting, etc.)

Allocation of PMP, Basewide Quality Program Plan (QPP), or other Basewide costs to specific sites

Multiple draft versions of a document before USACE/AF/Regulatory approval

Refer to the ORC PMP Guidance, Section 4.2, for more detailed information on common errors in preparation of the MPS.

The Contractor shall maintain and submit an MPS monthly, in electronic format in accordance with the requirements above and include updates to progress (e.g., Percent Complete, Invoice Number) (see Section 4.4 Cost and Status Reporting).  The MPS shall be submitted electronically to the Contractor’s ORC document repository and in accordance with instructions from the COR.  The Contractor shall prepare and maintain the MPS in accordance with the CLIN, IMS, and MPS Guidance.

Milestone payments within a CLIN/Sub-CLIN may be revised in response to changes in the approach for achievement of the CLIN/Sub-CLIN objective without a contract modification so long as the changes do not impact the total value or objective of the CLIN/Sub-CLIN.  All changes to the MPS, with the exception of tracking invoicing of completed milestone payments, must be approved by the COR.

Completion of milestones shall demonstrate payment is appropriate and warranted.  COR approval of the documentation supporting the completion of the milestone is required for payment. In general, milestones are considered complete upon approval by AF/USACE (and regulators where required).  Where regulatory approval or acceptance is required for this documentation, AF and USACE approval will occur following regulatory approval of the documentation.  Approval occurs upon final signature of documents requiring signature by the AF and/or regulators. The COR will take into consideration the appropriate approval of necessary documentation by regulators consistent with the applicable regulatory drivers of this PWS. The Contractor may propose a revision of the milestones to reflect their PMP and provide for interim milestones. Interim milestones will only be accepted if they represent significant progress toward milestone completion, and completion of these interim steps can be measured and demonstrated. Payments will be tied to the successful completion of major milestones, or an interim milestone plan approved by the Government, through the COR. To that end, all proposed interim milestones should be associated with easily demonstrated metrics tied to performance measurements (e.g., Government approval of a draft final report, Regulatory approval of a final document such as semi-annual and annual groundwater monitoring reports, Remedial Investigation reports, or Records of Decision). All milestones must have a defined means for demonstrating completion in order to facilitate certification.

Milestones must represent tangible progress toward achieving the PO.  In general, progress payments are disallowed. Progress payments include payment for interim steps needed to achieve the PO. As an example, milestones for conducting monthly landfill inspections would represent progress payments. Acceptable milestones would be a semi-annual or annual LTM Report of the results of the landfill inspections.

For milestones where regulatory approval is required and cannot be obtained, the AF and USACE will evaluate the Contractor’s supporting documents to determine if they are legally and technically acceptable to warrant payment for achieving that milestone.

The Contractor is limited to one invoice submitted to the AF/USACE per month.  The invoice must itemize the milestone payments for each CLIN/Sub-CLIN associated with the invoice.  The Contractor will not receive payment until milestones are achieved in accordance with the MPS.  The AF and USACE will not approve partial payments.

Note that AF/USACE approval of the first version of a document that will be submitted for regulatory review is a valid milestone. AF/USACE and regulatory approval of the final version of that document is also an acceptable milestone.

## 4.4 Cost and Status Reporting

The Contractor shall prepare and submit a monthly Contractor’s Progress, Status, and Management Report (CPSMR).  The CPSMR shall be used to review and evaluate the overall progress of the project, along with any existing or potential problem areas.  The report shall be prepared and submitted in an electronic format to the Contractor’s ORC document repository and/or in accordance with the CPSMR Template.  The CPSMR shall also be used to indicate whether efforts for each site are on target for meeting the PO.  The Contractor shall submit an updated IMS each month with the CPSMR.

## 4.5 ORC Document Repository

The Contractor shall maintain a document repository for all ORC documents.  The repository is intended to be a single access point repository for all ORC documentation.  It shall be accessible to stakeholders during the life of the ORC.  The Contractor shall provide notifications to AFCEC, COR, and Installation POC(s) at the time data is included in the repository.  At contract close-out, all repository documents will be transferred to DVD media and delivered to AFCEC and USACE.

The Contractor shall create and maintain a Master Document List (MDL) that includes all documents, whether the document is a deliverable or not, prepared during the course of this contract.  The Contractor shall maintain the project documents for the duration of this contract and deliver to the AF no later than 90 calendar days prior to POP expiration.

## 4.6 Meeting and Conference Requirements

### 4.6.1 Meeting/Teleconference Support

The Contractor shall participate in post-award meetings, Project Management Review (PMR) meetings, and teleconferences with the AF and USACE as necessary to achieve the POs in this PWS.  The Contractor shall coordinate meetings, provide logistical support (e.g., facilities, audio/visual), create and present materials, and lead technical discussions.

The Contractor shall also attend and/or support meetings and teleconferences to discuss technical or regulatory issues, project progress, and status with the AF and regulatory agency representatives.  Specifically, the Contractor shall host an internal kick-off meeting with the AF and USACE within fifteen (15) calendar days from contract award.  In keeping with the AF’s commitment to the regulators, the Contractor shall host a kick-off meeting with the AF and regulators within thirty (30) calendar days from contract award.  At a minimum, the following topics will be discussed at the regulatory kick-off meeting:  project schedules for field work and deliverables; achieve a mutual understanding of expected review times; identify standards, criteria, and guidance to be used during site characterization and remediation; identify potential points of compliance; identify regulatory processes and other applicable state agency programs (i.e., Water Protection, Department of Health, Air Pollution, etc.); identify site constraints and dependencies (i.e., site access, right of entry, security, ongoing site activities, topography, slope stability, etc.); and determine potential community interests.

The Contractor shall also attend and provide both technical and logistical support for annual Restoration Advisory Board (RAB) meetings and materials (if needed), quarterly Tier 1/Tier II partnering meetings and teleconferences. Monthly teleconferences with logistical support shall also be required to discuss in detail progress and any technical or management issues. RAB newsletters are required semi-annually. Also, other periodic meetings/teleconferences shall be required, as necessary.  Currently, regulatory meetings occur on a monthly basis for Shaw AFB. Weekly operational updates are sent to the state via email with upcoming activities and document under review. However, the frequency of meetings may change based on the status of the environmental restoration program.  The AF will be present for all technical and public meetings with the regulatory agencies; however, the Contractor shall coordinate the meetings, provide logistical support (e.g., facilities, audio/visual), create and present materials, and lead technical discussions.  The Contractor shall clearly identify themselves as “Contractors” in all situations involving stakeholders.  The Contractor shall prepare and submit for AF and USACE review and concurrence, any presentation materials and agendas for meetings no less than three weeks (15 working days) prior to the event.  The Contractor shall prepare minutes for all meetings attended within 14 calendar days following the event.  Travel to/from the Installation and to other continental United States (CONUS) locations for such purposes as meeting attendance, briefings, and/or presentations may be required in support of this remedial action.  These activities are considered incidental to the effort required and shall not be included for separate milestone payments.

The Contractor shall not contact any regulatory agency without prior notification and approval by the Installation POC(s).

### 4.6.2 Public Meetings and Hearings

The Contractor shall support all community involvement requirements to meet CERCLA, RCRA, and other regulatory requirements including public meetings, public notices, RAB meetings, Technical Working Groups, Community Advisory Group meetings, public comment periods, and responsiveness summary preparation.

Currently, the Shaw AFB RAB meets annually. The frequency of meetings may change based on the status of the environmental restoration program. [If the RAB becomes inactive,] the Contractor shall reassess community interest as is required every 24 months per AFI 32-7020 requirements.  The frequency of meetings may change based on the status of the environmental restoration program.  In coordination with AFCEC and the Installation POC(s), the Contractor shall coordinate and attend teleconferences as necessary with the assigned Public Affairs Officer (PAO) to ensure the PAO is fully aware of all ongoing activities, public outreach status, compliance with applicable regulations, and possible issues that might impact the AF and its public image.  The Contractor shall coordinate with the Installation POC(s) before any contact with the PAO.

Examples of types of Public Affairs requirements include the presentation of technical information and logistical support (e.g., advertising, audio-visual, handouts, report(s), recordings, verbatim transcripts, poster boards, slides, synopses, etc.) for events and/or meetings in support of the Government’s position.  All reports and other information generated under this contract shall become the property of the Government, and distribution to any other source by the Contractor is prohibited unless authorized by the COR.

The Contractor shall use staff trained in public affairs to complement the technical staff on the project.  These trained staff must attend all meetings with the public along with the appropriate technical staff.  The credentials of the trained staff must be submitted to, and be approved by, the COR in advance of any meeting with the public.  The trained staff shall demonstrate effective public communications experience and experience in building relationships with the stakeholders involved in cleanup activities or similar efforts.

The Contractor shall research, coordinate, and provide responses for short-notice internal and external requests for information such as congressional inquiries and media requests as needed by the PAO or other applicable action officers.  These inquiries require the Contractor to provide the AF factual and responsive information within 24 hours of request.

### 4.6.2.1 Community Involvement Plan (CIP) Update

The Contractor shall prepare a CIP or Update the existing CIP, in accordance with Table 1, to support the installation’s community involvement program (see Enclosure 4).  The CIP or Update shall address how the Air Force will conduct public outreach about cleanup activities and how community members can engage and participate in decision making throughout the cleanup process.  One CIP or Update is prepared for each installation.  A consolidated CIP or Update is prepared for the parent installation and any applicable Geographically Separate Units (GSU).

The Contractor is required to prepare a CIP or update the existing CIP at each installation. CIPs shall be prepared as early as possible in the CERCLA process, specifically prior to the RI phase.  CIP updates are completed after the DD/ROD is signed and every five (5) years thereafter. CIP updates also are required for Removal Actions with planning periods greater than six (6) months and removal activities lasting more than four (4) months.

## 4.7. Spatial Data (Map) Requirements

The Contractor shall NOT establish new Geographic Information Systems (GIS).

In furtherance of the environmental construction or restoration effort, the Contractor shall provide geospatial data and map(s) of Installation features (historical, existing, or planned) altered or constructed as required to achieve the POs of this contract.

The Contractor shall provide data to update the GIS and/or computer-aided design and drafting (CADD) files as required to achieve the POs of this contract.  Source data and product data remain the property of the United States Government.

The Contractor shall also ensure that GIS data is submitted in a file geodatabase that meets the current AF adaptation of Spatial Data Standards for Facilities, Infrastructure, and Environment (SDSFIE) within the AF GeoBase program.  The Contractor shall consult with each Installation POC and/or Installation Geospatial Integration Office (GIO) office to ensure CADD and GIS data is compatible with each Installation’s requirements.

All products associated with this contract that provide a map representation of the location of Installation features (historical, existing, or planned) including Installation maps, site plans, area development plans, walls-out as-built depictions, or other related overhead (plan) views of an Installation (partial or entire) must adhere to the following requirements.  (NOTE:  This requirement does not currently involve walls-in facility floor plans or interior renderings.)

All maps and associated data must comply with the latest version of SDSFIE available from the SDSFIE Web site:  https://www.sdsfieonline.org/ or contact the AFCEC GIO at AFCEC.GIO.Workflow@us.af.mil or (210) 925-4620. This data will be organized using the current version of the standard approved by the Headquarters Air Force GeoBase Office as the functional lead for Installation mapping and visualization.  The SDSFIE will determine file and feature class identification and definition, attribution, and valid domain values.  When any geospatial information collected as a result of the contract includes information identified in the Common Installation Picture or recognized Mission Data Set (MDS), the Contractor will deliver data consistent with the established requirements for the data and will ensure functionality with the receiving system.  Information must be collected at no less than 1:1200 scale.  Spatial data will meet or exceed National Map Accuracy Standards at those scales.  Metadata will be provided and will use Federal Geographic Data Committee (FGDC) Content Standards for Digital Geospatial Metadata (CSDGM) for organization.

As a requirement of this contract, the Contractor shall provide to the Government all shape files, file geodatabases, map exchange files (MXDs), and Geospatial data accumulated as a result of investigation recorded on compact discs (CDs) (FedEx for delivery on next business day) and also electronically.  Geospatial data must be delivered in a geo-referenced GIS format (feature-based file structures with one-to-one cardinality between spatial records and attribute records) which would include Environmental Systems Research Institute's (ESRI) shapefile and geodatabase formats.  All attribute data as specifically outlined in the contract must be included either in the GIS data file or as a separate table with a SDSFIE key variable that may be used to relationally join the separate table with the GIS data file.  All geospatial data must be delivered in the North American Datum 1983 (NAD83) projection, State Plane Coordinate System, using feet or metric coordinate units.  For all locations within the Restricted Area, Universal Transverse Mercator (UTM) coordinates must also be provided.  Further guidance on mapping units, coordinate systems, and projections is available from the Installation GIO.

Mapping- or Survey-Grade Global Positioning Systems (GPS) or comparable traditional survey methods will be used to collect geospatial data.  The use of mapping- or survey-grade GPS will depend on the precision requirements of the product data.  These requirements will be specified later in this PWS for all contract activities where geospatial data are involved.  In the case of contracts involving utility construction, location and attribute data will be obtained at the time of excavation.  Further information about precision requirements should be obtained from the Installation Execution Support (GeoBase) Office.

Source data and product data remain the property of the United States Government.  The Contractor shall be required to explain and demonstrate the company's process for protecting all geospatial data including, but not limited to, geometry, attributes, metadata, topologies, and relational database schemas and operations used in association with this PWS. Further information about security and non-disclosure requirements should be obtained from the Installation GIO.  Some installation map data/source/and/or product may be considered by the government to be "sensitive, but unclassified".  The intent of this clause is to prevent intentional or unintentional dissemination of "sensitive, but unclassified" information, to include unauthorized access to the source and product data by any entity wishing to do harm to the Air Force or United States Government while the data resides on the Contractor's computer network.  The Contractor is not authorized to release this information to any third party without the explicit consent of the AFCEC GIO or its involved Installation.  All source information must be returned to the Government POC or destroyed upon completion of this project.  Documentation of information destruction shall be provided to the Installation POC(s).  Special requirements for handling classified map data, if applicable, will be addressed elsewhere in this PWS.

The Contractor is required to follow Department of Homeland Security, Management Directive (MD) 11042.1 regarding Safeguarding Sensitive but Unclassified (For Official Use Only) information dated 5 January 2005.

## 4.8 Information Security

### 4.8.1 Cybersecurity Standard Operating Procedure

All information created, stored or transmitted under this contract is the property of the Government. The Contractor will remove all government information from the Contractor’s computers in accordance with Air Force and DoD policy and provide certification of removal to the KO at the end of the contract.

All subcontractors will adhere to the same cyber security standards listed above.

## 4.9 Notification Requirements

The Contractor shall notify the COR, with courtesy copies to AFCEC and Installation POC(s), of critical issues that may affect the contract performance and/or human health, safety, and the environment.  Verbal notification shall be made immediately, followed by written notification to the CO/KO with courtesy copies to AFCEC and Installation POC(s) within five (5) working days.

The types of issues that require notification include, but are not limited to, health risks, spills, Notices of Violation (NOVs) (received or anticipated), changes in critical personnel, and finding unanticipated UXO, DMMs, MCs present in high enough concentrations to pose as explosive hazard, or CWM.  Contractor shall follow the 3Rs principal of Recognize, Retreat, and Report if Munitions and Explosives of Concern (MEC) are encountered or suspect to have been encountered.

If unanticipated UXO is discovered during field activities, the Contractor shall immediately stop work, contract base security, report the discovery to the COR, AFCEC, and Installation POC(s), and implement the appropriate safety precautions. If an item is suspected to be a chemical munition (liquid filled) the contractor shall call base security who will contact Base Explosive Ordnance Disposal (EOD) to assess the item. Field activities shall not continue until clearance is received from the CO/KO.  If the Contractor anticipates working beyond the PP to achieve a final milestone due to unanticipated UXO, the Contractor shall submit a PP extension request to the CO/KO at least 60 calendar days prior to the expiration date of the Sub-CLIN.

## 4.10   Permits

The Contractor shall develop, coordinate, apply, comply with, and/or modify all federal, state, local, and other applicable environmental permits, access agreements, easements, licenses, and certificates required to achieve the POs of this contract as detailed in Sections 4.10.1 and 4.10.2.  The AF has signature authority of all easement agreements and modifications and/or renewals of new or existing permits, licenses, and certificates required under this contract.  The Contractor shall maintain a library of these documents at the Contractor’s site office as well as the corporate facility handling this contract.  The Contractor shall comply with all applicable permit conditions.

### 4.10.1   Environmental Permits

Pursuant to CERCLA (42 U.S.C. 9621(e)), no federal, state, or local permits shall be required for onsite removal or remedial actions.  The Contractor must consult with the AF prior to obtaining environmental permits for all on-site and off-site CERCLA activities.  For non-CERCLA restoration sites, the Contractor shall assist the AF to comply with all applicable permit conditions including permit modification requirements and payment of permit fees.  If the Contractor has any question whether a particular permit may or may not be required, the Contractor shall consult with the AF prior to obtaining the permit.  The Contractor shall be responsible for reviewing and responding to site-specific underground utility locating systems request tickets, or other dig permit requests, requiring the identification of subsurface appurtenances and utilities associated with the remediation systems included in this contract.  If the Contractor obtains environmental permits, it is responsible for implementing and paying for them.  Utility location ticket requests will be sent to the Contractor and the Contractor will be required to review, respond, and address all location requirements in accordance with state law and regulations.  The Contractor shall maintain all records pertaining to location requests.

### 4.10.2 Rights of Access to Non-AF Real Property

The Contractor shall prepare documents using AF-provided templates, pay the rent and associated expenses for the AF to maintain or modify existing rights of access, or to acquire new rights of access, to non-AF land which the Contractor needs to satisfy the POs of this contract.  On the AF’s behalf, the designated Installation official will negotiate and sign the documents to obtain or modify the necessary rights of access with technical assistance from the Contractor.  Based on the stated right of access needs of the Contractor, the AF will decide which type of right of access (e.g., right of entry, license, easement, lease, or fee acquisition) will be obtained.  Technical assistance expected or that may be requested by the AF from the Contractor for rights of access include description of the amount of real property on which access is being sought, provision of property surveys, title searches, and title insurance (necessary only for easements, leases for greater than 30 years, or fee acquisitions), environmental site due diligence, appraisals of fair market value, amount of expected intrusion on the property or property disturbance, cost estimates of restoring property to its original condition after access is no longer needed, and potential technical witness testimony in the event the AF must pursue involuntary condemnation through the U.S. Department of Justice in state or federal court.  Payment of associated expenses includes costs associated with providing the aforementioned technical assistance, fees for recordation of real property documents associated with acquiring the right(s) of access, costs for payment of or restoring property damage resulting from Contractor's activities on the property on which the right(s) of access were acquired, costs for obtaining "dig safe" or "utility clearance" approvals from appropriate utility and governmental entities, and costs for notifying or communicating with affected property owners regarding rights of access.

- Maintaining Right of Entry (ROE) access agreements as part of the off-base plume dynamics at Shaw AFB sites OT016, SS035, SS036.

•	 The Contractor shall support off-base land use controls (LUCs) to include annual notice letters to approximately 130 property owners, Quarterly review of property records for property transfers. Contact local drillers and SCDES Private Well Program for new well installations within area of concern. Evaluate annual sampling data to determine plume dynamics and to delineate the plume area of concern. Addition or deletion of parcels located within the plume area may vary each year using well records and produced quarterly.

•   Private parcel access agreements exist to access off base monitoring wells.  Although the ORC Contractor is not responsible for executing/maintaining the AAs they may be required to provide input to the easement process (ex., data on well locations for each parcel, maps, drawings, figures, surveys, etc.).

## 4.11   Photo Documentation

The Contractor shall prepare digital photographic documentation, as required to achieve the POs of this contract.  The Contractor shall limit photographic documentation of site(s) to building(s) under investigation, field activities, and sample locations.  Photographs containing AF personnel, mission-critical assets, or that could reveal troop movements are not permitted. Photography of any kind shall be coordinated through the COR and Installation POC.

## 4.12   Remote and/or Austere Sites

NOT APPLICABLE

## 4.13   Site Access

The Contractor shall obtain and monitor assigned security badges, Common Access Cards (CACs), and passes used by all applicable personnel for the duration of this contract.  All security badges, CACs and passes shall be returned to the Installation POC upon expiration of the badge/CAC/pass, upon completion of the project, or when possession of the badge/CAC/pass is no longer necessary (e.g., upon removal of Contractor personnel from specific projects).

Additional access or security requirements/limitations that may impact scheduling are provided below.  Advance coordination for site access is required as follows:

- OT016B, SS015, SS035 require flightline training, permissions, and/or notifications.

- DLA Sites SWMU98 and SWMU 99 require flightline training, permissions, and/or notifications.

## 4.14   Worksite Activities and Coordination

### 4.14.1 Coordination of Activities

The Contractor shall coordinate worksite activities with all applicable personnel to ensure the protection of human health and the environment; the prevention of damage to property, utilities, materials, supplies, and equipment; and the avoidance of work interruptions.  The Contractor shall provide security to work areas, if needed. The Contractor shall perform emergency response to situations arising from project activities.  The Contractor shall perform emergency repairs to facilities, systems, improvements, or utilities damaged in the course of executing the contract requirements.  The Contractor shall comply with all local, state, federal, and military law and guidance covering security activities.  The Contractor shall comply with Occupational Safety and Health Administration (OSHA) safety and health regulations and local safety office requirements.  The Contractor is required to provide the KO copies of any OSHA report(s) submitted during the duration of the contract.

### 4.14.2  Hazardous Material, and Hazardous Waste Permitting and Reporting

The Contractor shall handle all hazardous materials, and hazardous waste in accordance with applicable federal, state, local, installation and USACE requirements.  The Contractor shall provide all hazardous materials use and hazardous waste disposal documentation to AFCEC, COR and Installation POC(s), and shall register with the Hazardous Materials Pharmacy program (if available) at the installation to ensure appropriate and efficient tracking of the Contractor’s hazardous material purchases, inventories, use, and releases such as required by the Emergency Planning and Community Right-to-Know Act (EPCRA), EOs, or any Installation reporting requirements.

The Contractor shall also comply with federal, state, local, installation, and USACE requirements for any task involving the transportation of hazardous wastes, and contaminated materials to off-site treatment, storage, and/or disposal facilities.  This includes 40 Code of Federal Regulations (CFR) Parts 260 and 263, 49 CFR Parts 172, 173, 178, and 179, and all other applicable federal, state, and local transportation regulations.  The Contractor is responsible for all disposal costs of hazardous wastes.

The Contractor shall perform all work in a manner that minimizes the pollution of air, water, or land and develop contingency measures for cleanup of any spills that may occur during the performance of this Contract.  The Contractor is responsible for performing IDW characterization, management, and disposal in support of the environmental restoration project in this contract.  Waste management activities including identification, hazardous waste determination, characterization, segregation and storage, labeling and marking, preparation of transportation documents, and record keeping shall be in accordance with USEPA and Department of Transportation (DOT) regulations, state hazardous waste regulations, if applicable, and the installation RCRA permit, if applicable.  All IDW generated by the DERP is subject to the Off-Site Rule (40 CFR 300.440).  Wastes may be placed in facilities compliant with RCRA or other applicable federal or state requirements.  The Contractor is responsible for disposal costs of all IDW.

All waste media from areas with identified PFAS contamination shall be segregated, stored, and disposed of in accordance with the guidance provided in Section 1.3.

The Contractor shall write and implement waste management plans for government review and approval before initiating on-site restoration work.  The plans shall document the process for making a hazardous waste determination for IDW in accordance with 40 CFR 262.1 and procedures for managing the waste and documenting disposal.  For work involving generation and disposal of hazardous waste, the Contractor shall coordinate activities with the installation hazardous waste manager and perform waste management that complies with all generator requirements in 40 CFR Part 262.  These requirements include, but are not limited to, making hazardous waste determinations, determining generator category, obtaining USEPA ID numbers, notification of hazardous waste activity, use of the manifest system, complying with pre-transportation requirements, and maintaining records in accordance with 40 CFR 262.40 and 40 CFR 262.44.  For installations with existing hazardous waste identification numbers, coordinate waste with installation environmental staff.  Note that the installation is the waste generator and oversees and approves waste management activities.  The installation has signature authority as the generator on hazardous waste manifests prepared by the Contractor; however, Contractors may be required to sign waste characterization profiles, bills of lading for non-hazardous waste, and other DOT shipping papers.

The Contractor is required to receive a Certificate of Disposal/Destruction/or Placement for all hazardous wastes, CERCLA remediation wastes, Formerly Utilized Sites Remedial Action Program (FUSRAP) wastes, asbestos, polychlorinated biphenyls (PCB), etc. from the ultimate disposal facility.  The certificate must correlate to each shipment of waste to the facility.  The Contractor shall submit the certificates to the CO/KO for placement in the project/site file.

After IDW disposal is complete at the site, an IDW report addendum shall be prepared to describe the IDW activities at each site and included as an addendum to one of the final reports.

### 4.14.2.1  Regulatory Requirements

All activities and IDW documents required by this scope of work shall comply with, and reflect the following regulations and appropriate guidance publications, at a minimum:

- DOT, Hazardous Material Regulations, 49 CFR Subtitle B, Chapter I, Subchapters A, B, and C.

USEPA, Hazardous Waste Regulations, 40 CFR Chapter I, Subchapter I.

USEPA Regulations, 40 CFR Chapter I, Subchapter J – Superfund, Emergency Planning, and Community Right-To-Know Programs.

CERCLA, 42 USC 9601-9675.

RCRA 42 USC 6901

Other applicable federal, state, and local solid waste requirements.

- 4.15 	ORC Transition Plan

- The ORC Transition Plan is a strategic document that is initiated by the ORC Contractor two years prior to PoP end date and is delivered at least 90 days prior to the PoP end date.  The ORC Transition Plan should include but not be limited to: information regarding site statuses, the status of all operating treatments systems, contractor owned materials that will be removed and may be needed by the incoming contractor, and documents that may be in review with the regulators at the end of the PoP.  The purpose of this plan is to support a seamless transition for the incoming ORC Contractor upon the award of a follow-on ORC. This plan serves as a critical reference for the incoming Contractor when detailing transitional activities within their Project Management Plan (PMP).

# 5.0   CHEMISTRY REQUIREMENTS

The Contractor shall be responsible for the quality of all required chemistry services performed.  The Contractor shall ensure that all chemistry-related tasks are conducted in accordance with the project-specific Work Plan (WP).  Any samples that are delayed or lost by the overnight carrier or destroyed in shipping must be re-sampled within 30 days. The Contractor shall identify a Program Chemist as key personnel in the project WP.  The Program Chemist will act as a POC on all chemistry-related issues and shall be responsible for ensuring that all Data Quality Objectives (DQOs) are met.

## 5.1  	Quality Assurance

The Contractor shall develop project-specific DQOs to ensure data of adequate quality are collected to support project decisions.  DQOs shall be developed in consensus with the restoration project team and in accordance with the Uniform Federal Policy for Quality Assurance Project Plans (UFP-QAPP) and USEPA QA/G4, “Guidance on Systematic Planning Using the Data Quality Objective Process” (most recent version) and documented in the project WP.  The Contractor shall ensure that all requirements specified in the project WP are met.  If not met, the Contractor may be required to re-accomplish sampling at the Contractor’s expense.

All laboratory services shall be conducted in accordance with the approved project WP.  Samples shall not be submitted for analysis until the WP is approved.

The Contractor shall administer an AFCEC-approved performance evaluation sample program, verify and validate data, and perform corrective actions in accordance with the project WP.  See attached AFCEC guidance document, Ensuring Chemistry Data Quality – AFCEC Performance Evaluation Program.  Data validation shall be conducted on requirements presented in the WP, and performed by an independent, qualified, and experienced data validator in accordance with DoD General Data Validation Guidelines and any applicable Modules.  One hundred percent of the data shall be validated.  The level of data validation shall be project specific, a minimum of Stage 2B, documented in the project-specific WP, and approved by the COR.  The data validation standard operating procedure shall be included in the WP.  Significant deviations from project requirements discovered during data validation shall be communicated with the project chemist and COR as part of the data validation process.

A data validation report shall be prepared and shall sufficiently document the data validation procedure and provide a clear understanding of the representativeness of the data.  The results of the data validation shall be summarized in the associated technical report with supporting data validation reports included in an appendix.  A data usability assessment of the validated data shall be performed.  The results of the data usability assessment shall be included in the technical report, and shall identify the limitations of the data, and the effect qualified results have on the decisions being made for the project.

## 5.2  	Laboratory Selection

The Contractor shall select a laboratory with analytical capabilities sufficient for the methods specified in the WP and adequate throughput capacity to handle the project’s analytical workload during all field activities.  During analysis and reporting, the Contractor shall ensure that the selected laboratory is accredited under the DoD Environmental Laboratory Accreditation Program (ELAP), state, and federal requirements, including state certification where appropriate.

The Contractor may establish an on-site laboratory at the project site if determined necessary by the Contractor.  However, on-site test laboratories shall also be accredited under the DoD ELAP and meet all state and federal requirements, including state certification where appropriate.

Use if an SCDES approved laboratory is required.

## 5.3  	Analytical Data Management

The Contractor shall ensure that all hard copy and electronic data deliverables supplied by the laboratory are complete and adequate to support the quality and usability of the data.  Raw data packages shall be submitted to the Installation POC within 90 days of the completion of the sampling event. Data packages shall meet federal and state standards and include all information required to re-create the analysis, including correspondence with the laboratory regarding Quality Assurance and Quality Control (QA/QC) exceedances and documentation of corrective actions.

## 5.4  	Record Keeping

The Contractor shall create and maintain in one location written (in bound, numbered logbook) and electronic records sufficient to recreate each sampling, analytical, testing, and monitoring event, and shall make these records available to the Government upon request.  The Contractor shall maintain records of, and derived from, all activities outlined in the appropriate portion of the Quality Program Plan (QPP) supporting the generation of these sampling and analysis records.  The Contractor shall also retain written calculations using information obtained from sampling, analysis monitoring, and testing activities, to include all raw data.  All information shall be provided to the Government upon request.

All field documentation shall be recorded in bound, numbered logbooks. Field logbooks shall have numbered pages and shall include a complete record of all field activities.  If multiple field logbooks are required, each shall be numbered and specifically identified to indicate dates and sites where used.  Field documentation shall be recorded at the time of fieldwork, i.e., details may not be added after the fact.  All information required to fully recreate sampling, investigation, and remediation events shall be documented in the field logbook.  Use of field forms may augment but not replace the detail required in the field logbook.  The field logbooks are a critical part of the official project record; the Contractor shall include procedures for maintenance, review, tracking, etc. of the field logbook in the programmatic UFP-QAPP.

## 5.5     PFAS Sampling and Analysis

If PFAS sampling is required, samples shall be analyzed in accordance with DoD and AF policy. In addition, the Contractor shall follow any applicable current State or Federal guidance for PFAS sampling.

# 6.0 	PLANS AND REPORTS

All documents are to be prepared in accordance with DAFH 33-337 (Tongue & Quill).

## 6.1	Quality Program Plans

The QPP shall include the WP, the Health and Safety Plan (HSP) (as required by 29 CFR 1910.120), and the Construction Quality Plan (CQP) if required.

### 6.1.1	Work Plans

Prepare WPs to comply with DoD, AF, USACE, USEPA (epa.gov/quality), state, and local regulations and guidance.  Basewide and site-specific WPs that require sampling and analysis shall be prepared in accordance with the UFP-QAPP, using the optimized UFP-QAPP worksheets.  The optimized UFP-QAPP worksheets shall constitute the entire WP when sampling and analysis is required.  WPs shall be specified as separate payment milestones under the site-specific Sub-CLIN(s) as appropriate.

### 6.1.2	Health and Safety Plan

The Contractor shall prepare a HSP to comply with AF, USACE, OSHA, USEPA, federal/state/local health and safety regulations and guidance, including EM 385-1-1.  In accordance with EM 385-1-1, the HSP will consist of a Site Safety and Health Plan (SSHP) and Accident Prevention Plan (APP).  Utilize to the fullest extent possible any existing related HSP, tailored specifically to the current effort.  The Contractor shall maintain written certification that the approved HSP has been reviewed with all personnel that work at the project site prior to their mobilization.  The Contractor and all subcontractors are required to comply with the approved HSP (including SSHP and APP).  The Government can shut down operations due to non-compliance without cost to the Government until safety issues are resolved.

Health, Safety, and Emergency Response

The Prime Contractor shall be fully responsible for the administration of the Site-Specific Safety & Occupational Health (SOH) program for the project. General plan requirements are to include a Site-Specific Accident Prevention Plan (APP) and necessary subplans, including a Comprehensive Work Plan and a Site Safety and Health Plan (SSHP) in accordance with all local, state, and federal regulations. All documents shall be prepared in accordance with the requirements of the most recent version of the EM 385-1-1, “Safety and Occupational Health Requirements” and ER 385-1-92 Safety and Occupational Health Requirements for Hazardous, Toxic and Radioactive Waste (HTRW) Activities.

The Contractor shall utilize the services of a Certified Industrial Hygienist (CIH) or Certified Safety Professional (CSP), depending on the contamination to be impacted by investigation and cleanup activities, experienced in environmental cleanup and investigation projects to oversee the development and implementation of the health and safety program in accordance with the EM 385-1-1. This individual shall act as the Contractor Safety and Health Manager (SHM) on the project. The SHM shall review and sign all drafts, final, and revised final submittals of the SOH documents. If the information made available is insufficient to allow the Contractor to develop these documents, a description of all additional information required shall be prepared and submitted to the USACE PM. Work cannot begin until all SOH-related submittals are reviewed and accepted by the KO or the COR.

All required SOH documents shall be submitted on time for review and comments prior to the performance of any work. Comments shall be provided to the Contractor for discussion and incorporation in the succeeding version(s) of the document. The Contractor shall annotate all comments, including location of any changes. The USACE PM shall coordinate document review to ensure changes are consistent with previous versions. It is understood that at the time of the submission, there may be unknown portions of the work. The Contractor should evaluate and update the APP throughout the life of the project to ensure it is up to date and site specific. Changes, revisions, and updates to documents should be submitted to the KO or COR for acceptance. No contract work can begin without a KO or COR accepted SOH documents.

The contractor shall ensure all necessary certificates and training documentation IAW local, state, and federal regulations are attached to each document version and are valid. If site contains HTRW, additional training and certificates shall be necessary to comply with regulations per EM 385-1-1 Chapter 36 and 29 CFR 1910.120. All contractor and subcontractor certificates and training documentation must be submitted with SOH documents and any alterations shall be provided to the USACE PM or COR no later than two weeks prior to fieldwork activities.

Due to the possibility of the USACE personnel visiting the site, the Contractor shall be prepared to provide personal protective equipment (PPE), apart from air-purifying respirators and safety-toed footwear. A minimum of three (3) sets of PPE shall be present on site for the USACE use.

In the event the Contractor detects conditions that pose an immediate danger to the health and safety of personnel, or hazard to the environment, the Contractor shall stop the unsafe work being performed and report the facts to the KO or COR immediately. A written report of such incidence forwarded to the USACE PM and KO or COR is also required within seven (7) working days. The report shall be submitted using the most current form required by the EM 385-1-1.

The USACE EM 385-1-1 shall also be followed in its entirety. Should a regulatory conflict arise, the most stringent requirement shall be followed.

Key Personnel

Contractor Safety and Health Manager (SHM)

Depending on the contamination to be impacted by investigation and cleanup activities, the SHM must possess professional certification as a Certified Industrial Hygienist (CIH) or Certified Safety Professional (CSP) and have at least three years of experience implementing occupational health and safety protection requirements at environmental cleanup projects. The SHM must have in-depth knowledge of the employer’s health and safety program and have access to senior leaders within their organization structure (Chapter 36-Section 3.d of EM 385-1-1).

Site Safety and Health Officer (SSHO)

The SSHO must meet the initial, refresher, and supervisor training according to paragraph 36-3.a of the EM 385-1-1. The SSHO must also possess the training and experience outlined for a SSHO according to Chapter 2 of the EM 385-1-1. SSHOs experience required by Chapter 2 must include at least one year of experience with implementing SOH requirements on hazardous waste investigation and cleanup projects. The SSHO must have the training and experience to conduct exposure monitoring, sampling, and selecting/adjusting controls.

The Contractor must employ a minimum of one Level 1 SSHO at each project site to function as the primary SSHO. A designated Level 1 SSHO must be present at the site of work whenever work is performed. Additional or alternate SSHOs may be needed for projects with multiple sites, or shifts, or large projects. The full time Level 1 SSHO requirement may be modified to use any level SSHO or combination of levels by the USACE KO and the local Safety and Occupational Health Office (SOHO) in contract documents according to the exemptions in EM 385-1-1. Modification of the requirement must be a collaborative effort and will be based on job complexity, size, and other pertinent factors.

Task 1 Language

Accident Prevention Plan

The Contractor shall prepare and submit Draft version of a site-specific APP with a SSHP within thirty (30) calendar days of contract award. The Contractor shall address comments and submit the Final version of the APP within fifteen (15) calendar days from receipt of comments. The APP shall be prepared IAW operational and technical requirements presented in this PWS, USACE, the Occupational Safety and Health Administration (OSHA), the US EPA, and applicable federal, state, and local health and safety regulations, including the most recent USACE EM 385-1-1. The APP shall be suitable for use as a “stand alone” document. The required format of the APP is presented in EM 385-1-1.

The APP shall document project, contract, and job-specific potential hazards in the workplace, and the company policies, controls, and work practices that will be used to minimize those hazards. The APP must articulate the specific work, work process, equipment, and materials to be used, hazards pertaining to the contract work, and the control measures to be implemented The APP shall include preparation of an Activity Hazard Analysis (AHA), which shall document all definable features of work to complete the project objectives. The AHA shall include minimum requirements as outlined in the EM 385-1-1.

Site Safety and Health Plan

The SSHP shall address the safety and occupational health hazards of each phase of site operation and include the requirements and procedures for employee protection. The SSHP must specifically address the requirements to protect workers from the health hazards associated with site contamination and the specific processes that may disturb, release, and transport these contaminants during the planned investigation or remedial action activities. Changes and modification to the SSHP are permitted and must be made in writing with the concurrence of the SHM and accepted by the KO or COR. The SSHP must be developed according to 29 CFR 1910.120(b)(4) and the EM 385-1-1.

### 6.1.3	Construction Quality Plan

The Contractor shall provide a CQP to comply with AF, USACE, OSHA, USEPA, federal, state, and local quality regulations, if needed.

## 6.2	Technical Plans and Reports

The Contractor shall provide reports and various other deliverables in accordance with the most appropriate industry standard, or where applicable, any federal or state guidelines.

Technical plans and reports are required to demonstrate that POs and milestones are being met and that payment is appropriate.

Most documents must be submitted for initial AF and USACE review followed by submittal to one or more regulatory agencies.  The Contractor shall ascertain the number of copies required for delivery to all relevant parties.  Regulatory Agency review times will be based on the agency reviewing the document, complexity of the deliverable, and workload of the technical review team, including regulatory partners.  The AF is unable to commit to review times for another agency.  The Contractor shall be responsible for coordination of document review schedule with all stakeholders.  However, historical regulatory review times have averaged 30-45 calendar days for low complexity documents and 45-60 calendar days for higher complexity documents.  Please be advised that workload for those averages may not mirror workload under an ORC accelerated environment.  Therefore, Contractors should review available information and form their own independent conclusions as to the time necessary, as well as risks and appropriate mitigation and contingency measures, to achieve the PO and PP with their approach.  Legally binding documents such as reports, correspondence, No Further Action (NFA) documents, regulatory closure documents, RODs, or other decision documents shall be signed by the AF and not the Contractor.

PLEASE NOTE:  Quarterly Performance Monitoring “courtesy” Reports are emailed to SCDES solely to comply with the regulatory requirement that sample results be submitted within 30 days of receipt.  AFCEC does not expect SCDES to review and comment on these reports, and the Base RPM will assist with coordination.  Official results are submitted in the annual reports.

The Contractor shall submit all plans, reports, and other documents in, [Draft, Draft Final, and/or Final versions, as appropriate for that specific document.]  [Update document versions as required.]  Not all documents will require submittal of all versions.  The Contractor shall provide multiple versions of the following documents:

[INSTALLATION POC]: [1] soft copy and [0] CDs of all draft documents; [3] hard copies and [1] CDs of all Draft Final and Final documents.

AFCEC Program Manager: [1] soft copy and [0] CDs of all draft documents, [1] soft copies and [0] CDs of all Draft Final and Final documents.

COR: [1] soft copy and [0] CDs of all draft documents, [3] hard copies and [1] CDs of all Draft Final and Final documents.

Regulator: [1] soft copy and [2] hard copies of all draft documents, [2] hard copies and [2] CDs of all Draft Final and Final documents.

The following are the AF and USACE estimated review times.  Complex documents, Permit mods, and Decision Documents may require additional time.

| Reviewer | Document Review (for each version) | Response To Comments Review |
| --- | --- | --- |
| AF and USACE Review | 30 calendar days | 21 calendar days |
| AF, USACE, and Legal* Review | 60 calendar days |  |
| Coordination/Signature – Installation | 120 calendar days |  |
| Coordination/Signature – CZ | 90 calendar days |  |
| - Legal review required per AFI 32-7020 for: PA/SIs that result in Site Closeout, Engineering Evaluations/Cost Analysis (EE/CA), Removal Action Memoranda, FS, PP, ROD and ROD modifications, Five-Year Reviews, Remedial Action Completion Reports (RACRs), Site Closeout Reports, NPL deletion requests. See AFI 32-7020 for additional information. |  |  |

The Contractor shall upload all documents to Contractor’s ORC document repository.  The documents required for this contract shall be proposed by the Contractor and will be included in the Contractor’s IMS.

# 7.0  	SITE WORK

The Contractor shall perform site preparation, site characterization and field investigation, conservation, demolition, and site restoration as required to achieve the POs of this contract.

## 7.1	Conservation

Activities shall be planned and implemented in a manner that protects existing site utilities, structures, surface features, service operations, monitoring and other types of wells, and the general site environment.  This includes the protection of prehistoric and/or historic sites identified in the Installation Integrated Cultural Resources Management Plan; endangered/threatened wildlife species and their potential habitats; exemplary natural areas as defined in the base Integrated Natural Resources Management Plan; and trees, shrubs, and other vegetation not in the affected zone from dust damage, soil compaction, and physical contact with machines and equipment.  Work activities shall be coordinated with AFCEC, COR, and Installation POC(s) (Cultural Resources POCs, the Natural Resources POCs, and Installation Operating Support POCs) to ensure compliance with these requirements.  If appropriate, the Contractor shall conserve uncontaminated topsoil by removal, storage, or redistribution.  All reasonable measures shall be taken to minimize and suppress fugitive emissions of dust, vapors, and other site materials during site work.  All fill materials shall be non-contaminated with the proper documentation to demonstrate as such.  The Contractor shall conduct all operations and activities with the intent of reducing the amount of pollution generated.  Specific areas to be focused on are generation of solid waste, use of hazardous materials, use of ozone depleting chemicals, generation of hazardous waste, and use of energy and water.  During site work the Contractor shall plan, construct, operate, maintain, optimize, and decommission systems necessary to control storm water run-on and run-off, and transport surface water drainage to a treatment plant, discharge location, or any other appropriate destination.

## 7.2	Site Characterization and Field Investigation

The Contractor shall perform field investigation and sampling/analysis that characterizes environmental conditions, in accordance with approved DQOs, as required to achieve the POs of the site.  The Contractor shall identify specific site characterization activities proposed to achieve the POs.

## 7.3	Site Preparation

The Contractor shall perform site work as necessary to prepare sites for field activities.  Security and access controls shall be implemented to prevent unauthorized entry to sites and to protect wildlife from site exposure.  The Contractor shall survey existing utilities to determine adequacy and need for modifications to support site activities.  The Contractor shall obtain appropriate approvals and shall construct connections or new systems for electrical power, water, sewer, gas distribution, telephone, and other utilities, as required, to achieve the POs of this contract.  Additionally, the provision and cost of utility metering devices associated with implementation of existing and proposed remedies, including installation of individual meters for necessary utilities, is the responsibility of the Contractor.  The Contractor shall meter all utilities consumption on a monthly basis.  The Contractor shall not be responsible for the associated cost of utilities. Assistance with surveys that locate and mark treatment and/or utility lines, as needed.

## 7.4	Demolition

Any demolition activities shall be ancillary to other requirements.  The Contractor shall demolish facilities, systems, and other improvements as required in this contract in accordance with applicable federal, state, and local laws and regulations.  The Contractor shall conduct demolition efforts in conjunction with such activities as new environmental remedial system construction and site clearing if required to achieve the POs of this contract.  The Contractor shall perform surveys as part of demolition efforts and is responsible for providing GIS information to USACE and Installation Civil Engineering.

## 7.5	Site Restoration

The Contractor shall decontaminate equipment and facilities, decommission facilities as necessary, and fully restore the site(s) as close as possible to pre-construction conditions prior to demobilizing from the site(s).  The Contractor shall remove any temporary facilities and implement erosion control measures such as seeding, mulch, sodding, and erosion control fabrics; restore roads, structures, and utilities; and plant trees, shrubbery, grasses, and other vegetation.  The Contractor shall document and report on activities and train Government personnel to perform required maintenance, as requested.

# 8.0	ENVIRONMENTAL REQUIREMENTS

The Contractor shall perform a full range of activities to achieve the POs of this contract.  Requirements may include, but are not limited to, completion of conceptual design(s), construction, implementation, demolition, and emergency response as related to environmental engineering and construction tasks.

The Contractor shall execute environmental restoration projects in accordance with approved DQOs and applicable federal, state, and local laws and regulations.  The Contractor shall evaluate, complete, and modify designs as necessary, and plan, optimize, install, construct, test, and decommission any site as required to achieve the POs of this contract.  The Contractor shall document all activities as stated herein.

The Contractor may change the site-specific approach for attaining POs, as needed based on approval of the PM/COR, due to site conditions, regulatory changes, etc.  All changes to the site-specific PO attainment approach shall be maintained current in the PMP, IMS, and MPS.

The Contractor shall perform support such as designing, planning, programming, scoping, studying, investigating, evaluating, optimizing, and consulting on environmental engineering and construction efforts.  The Contractor shall also provide training to Government and other Contractor personnel regarding the O&M of equipment, systems, and facilities during equipment shakedown periods.  The Contractor shall perform O&M of equipment, systems, and facilities prior to approval by the Government.

The Contractor shall implement Environmental Management System (EMS) principles in accordance with Contractor requirements of AFI 32-7001 (Environmental Management), to include Green and Sustainable Remediation (GSR) techniques, to the extent practicable while ensuring protection of human health and the environment.  EMS and GSR are defined in Enclosure 1, Acronyms and Definitions.  An EMS follows the “Plan-Do-Check-Act” cycle and considers the environmental impact of investigative and remedial activities during the remedy selection process as well as operation and maintenance of the remediation activity.  The Contractor shall incorporate an EMS approach into all environmental restoration projects, evaluating activities and selecting a remedy, product, and/or service that minimizes the environmental impact from the remedy, yet provides the maximum environmental benefit to the cleanup over the entire life of the remedial project.  The Contractor shall mitigate, minimize, or otherwise manage the potential environmental impacts from all remediation activities.  Contractors working on AF Installations must complete an initial EMS awareness-level training and integrate EMS training with other required Contractor orientation and training.

## 8.1	Environmental Restoration Process Application

The Contractor shall perform all activities necessary to meet all ORC requirements.  Environmental Restoration requirements include the full range of investigation, cleanup, optimization, and LTM activities.  The Contractor shall develop and update a CSM and an exit strategy (as described in Sections 8.1.1 and 8.1.2).  The Contractor shall also provide logical approaches to improve remedy protectiveness, effectiveness, and cost efficiency and to facilitate progress towards completion of the POs.  The goals are to assess and optimize remedy performance and monitoring, to demonstrate remedy progress in accordance with approved performance models, and to take the site to its best long-term use or to closure.

This contract involves a performance-based approach, where the contracted work is performed with a focus on results.  Results are achieved by 1) The achievement of the PO in the PP in accordance with the Performance standard per Table 1, or 2) The achievement of interim milestones that demonstrate value-added progress towards the achievement of the PO.  This ORC enables the Contractor to select actions best suited to the site requirements, ensures that best management practices and best available technologies are employed, and focuses on continual improvement by applying an EMS approach.  The Contractor’s proposed approach shall be commensurate with site conditions, site status, and requirements to achieve the PO within the PP.

### 8.1.1	Conceptual Site Model Guidance

For all sites, the Contractor shall prepare or update site CSMs following DQOs.  The CSM is a comprehensive written and graphical description of all available information about site conditions that could influence remedy design, selection, or performance.  Thus, the CSM forms the basis for defining Remedial Action Objectives (RAOs) and for developing and implementing an exit strategy.  A CSM incorporates several elements, including the following:

- Three-dimensional representation of:

  - Nature and extent of contaminant (including source types and affected media)

  - Site geology

  - Site hydrogeology

  - Biological and geochemical conditions

  - Monitoring points

- Contaminant fate and transport in the environment;

- Risks, receptors, and potential receptors (under current and reasonably expected future exposure scenarios);

- Past remedial actions and locations of remedial components and monitoring points

- Historical, current, and expected future land uses; and

- Other factors relevant to the understanding of contamination at the site.

The Contractor shall develop initial or updated CSMs for all sites listed in Table 1 of this PWS and work described in Section 1.3.2.  An appropriately detailed CSM is required beginning with the remedial investigation phase for all restoration program sites and must be maintained until the end of the project life.

The Contractor shall update the CSM as new data and site knowledge are acquired.  This is crucial for assessing and optimizing remedy performance and performance monitoring programs.  New data may be obtained upon completion of remedial investigation, supplemental investigation, pilot studies, bioremediation investigations, and routine monitoring of remedy performance.  Revisions to the CSM will be included in investigation and monitoring reports, as necessary.  For more information, see USEPA Groundwater Road Map (OSWER Directive No. 9283.1-34, 2011) and Environmental Cleanup Best Management Practices: Effective Use of the Project Life Cycle Conceptual Site Model (EPA 542-F-11-011, 2011), ITRC guidance (ITRC, 2004 and 2006), and ASTM International (formerly known as American Society for Testing and Materials) standard designations E1689 (2014) and D5979 (2014).

### 8.1.2	Exit Strategy

The Contractor shall develop a stand-alone exit strategy for all Table 1 sites and work described in Section 1.3.2 where a remedy is planned or in place. Initial exit strategy development is required at the point of remedy selection for all Table 1 sites and work described in Section 1.3.2 and must be maintained until the end of the project life.  For sites where a remedy is already in place, include a new or updated exit strategy along with work planning documents.  If the exit strategy changes, the revised document must be resubmitted within 30 days.  An exit strategy for a site is the detailed plan for achieving the RAOs that have been selected as the end points.  Stated another way, the RAOs are the overall goals that must be met for the site to either achieve RC or be approved for SC or planned land use.  An exit strategy represents a formalized process for taking the site from its current state to its best long-term use or to closure (independent of duration).  The strategy represents a plan to actively manage the site and make decisions at various points that will best tailor remedial and monitoring efforts to achieve the RAOs in the most efficient and effective manner.  The strategy is best developed with consideration of stakeholder and regulatory agency concerns, resource constraints, and technical realities; it also includes well-defined means to measure and track progress.  An exit strategy is dynamic and must be updated as new data and site knowledge are acquired.  The exit strategy would need to be modified or revised if the plan for achieving the RAOs is failing. Such failure may be identified when interim milestones are not achieved, even after corrective action.  Contingent actions identified in the exit strategy decision logic would then be implemented.

A well-developed exit strategy contains six elements:

- Decision document for the RA goals

- Summary of the CSM, including a description of the future site land use

- Decision logic, flow chart, or defined sequence of remedial activities and contingency triggers

- Clearly established process to evaluate performance relative to decision parameter

- Provisions for periodic reevaluation of the project goals and RA decisions (e.g., contingency planning), and

- Means to verify cleanup following cessation of active remediation.

Because it is difficult to optimize any element of a remedial decision if the overall objectives (remediation end points) and site-specific technical constraints are not well understood, any optimization effort should begin with an evaluation of the exit strategy, which incorporates the previously listed six elements.  For more information, see ITRC guidance (ITRC, 2004 and 2006).

### 8.1.3	Performance and Optimization

#### 8.1.3.1	Performance Models

The Contractor shall develop performance models for all sites listed in Table 1: Performance Table, of this PWS and work described in Section 1.3.2 that are not currently in LTM status.  The Project Management Plan (PMP) and work planning documents shall contain the performance model.  Final performance models shall be submitted as part of the Work Plan required under PWS Section 6.1.1.  Performance models shall describe how site conditions are expected to change over time, using appropriate performance indicators, from current state through PO achievement.  The Contractor shall add all new data to the performance model and provide Performance Model Evaluation Reports which demonstrate whether the remedial response is progressing and performing consistent with the performance model.

Performance model and site management approach shall incorporate the following:

Develop and document the approach to determine remedial progress relative to the defined performance indicators, associated decision criteria, and objectives consistent with the performance model.  The documented approach is expected to facilitate decisions about optimization as well as provide a quantifiable understanding of how the response is progressing, list contingency options, and demonstrate when the objective has been reached.  An individual site may have more than one performance model (e.g., different parts of the site that are addressed by separate remedies and represented by different sets of monitoring wells).  Contingencies must be developed for performance that does not achieve interim milestones.  These contingencies must be identified in the exit strategy.  The Contractor must inform AF of any contingency being implemented and receive AF approval before implementation.

- Demonstrate an understanding of the site-specific CSM as it relates to the operation of existing systems, distribution of contaminants, and remedy effectiveness and degradation rates (see details on the definition of CSM in Section 8.1.1).  Update the CSM using DQOs as needed based on performance and monitoring data throughout the PP and implement remedy contingencies as warranted by the evolving CSM.  Submit updated CSMs subsequent to receipt of new information.

- Develop an exit strategy that identifies and implements opportunities to improve remedy protectiveness, effectiveness, and cost efficiency, and to facilitate progress toward the end goal of the exit strategy, including innovative technologies.  The goal is to accelerate contaminant reduction thereby minimizing future AF liability and cost to the greatest degree feasible.  Update the exit strategy as dictated by site progress throughout the PP.  Submit updated remediation strategies subsequent to receipt of new information.

- Develop baselines and performance models for all contaminants, including degradation products (i.e., vinyl chloride), that are regulated, that describe the historic and expected course of the remedial progress (i.e., how conditions are expected to change over time as demonstrated by appropriate performance indicators) from the current baseline state through PO achievement.

- Define the baseline state for each COC.  The baseline state is determined by using select monitoring wells that are representative of the site and with sufficient data to develop statistics-based historic concentration trends for site COCs.  A scientific approach that uses a line of best-fit (e.g., first-order decay rate) is appropriate for estimating the baseline attenuation rate.  The baseline attenuation rate, in turn, can be used to extrapolate a baseline concentration to the end of the PP.  Supporting information for the baseline concentrations shall include the rationale for the well selection and the time period used to develop the trends, justification for the selected line of best-fit, actual values used to define the trend, and extension of the line of best-fit to predict values for future years independent of future remedy implementation plans.  For additional detail on development of baselines, refer to the “ORC PMP Guidance,” Version 6, Section 2.

- Using the baseline as a starting point (above), develop a scientifically based remedial performance model for each COC.  The performance model shall be representative of the contaminant extent being addressed and include performance indicators, decision criteria, and annual and final goals achievable within the PP.  The Air Force will carefully scrutinize selected performance indicators to ensure that they demonstrate achievement of response objectives and not merely progress.  The Performance Model shall also be used to maintain or return performance of a remedy as described by the model.  The Performance Model shall indicate performance milestones that will be used to determine if the remedy is achieving the projected change in performance indicator.  Goals should be consistent with the performance model used to optimize remedial efficiency, quantify how the response is progressing, and demonstrate when the annual and final goals have been achieved.  The performance model shall show projected changes to the site performance indicator(s) based on an assumed rate of change (e.g., an estimated biodegradation rate constant).  Subsequent changes to the performance model will only be permitted at the discretion of the AF.

Performance Models will identify at least three ranges, subject to AF approval:

      - Ideal-to-acceptable performance

      - Process-improvement-and-corrective-action range requiring modifications to the remedy to return to acceptable performance, and

      - Process-failure-and-contingency action range that requires implementation of an acceptable option to the current remedy.

- The Contractor shall specify the number of consecutive data points that would trigger corrective action.

- Sites with a PO of RA-O with optimization will have payment tied to achieving performance at the interim milestone and final milestones.  This requirement applies only to sites that are in the categories defined in Sections 1.2.4 and 1.2.5.  Milestone payments are contingent upon meeting or exceeding annual performance goals in accordance with the approved performance model.

- Refer to the latest ORC PMP Guidance for additional information on the creation and use of performance models.

#### 8.1.3.2	Optimization Benefits Reporting

The Contractor shall achieve the following objectives for sites described in Section 1.2.4 and Section 1.2.5.  The Contractor shall document and submit all optimization actions implemented on an annual basis as required in the Optimization Benefits Template.  The AF defines optimization, under the ORC, as the reduction of contaminant mass and concentrations, reduction in LCC, or any combination of activities prompting acceleration to RC, as a result of remedial implementation the Contractor undertakes, above and beyond what is required to maintain compliance in accordance with an approved decision document.  The Contractor is encouraged and required to implement potential optimization opportunities at all sites where the Contractor can successfully accelerate the achievement of the PO.  This requirement will allow the AF to fulfill DoD requirement to accurately account for accelerated contaminant removal and cost savings (i.e., reduction in liability) as a result of optimization activities.

#### 8.1.3.3	Optimization Summary and Forecasting

The Contractor shall achieve the following objectives for sites described in Section 1.2.4 and Section 1.2.5.  The Contractor shall deliver one Optimization Summary and Forecasting Report two years prior to the POP end date.  The Optimization Summary and Forecasting Report shall:

- Document what remedial strategies were implemented, what remains to be implemented to achieve RC and/or SC after the ORC PP ends, and any modifications arising from performance to date.

- Identify post-POP out-year requirements associated with the probable site progression pathway to include transition of remedies, abandonment of infrastructure (e.g., piping, wells), monitoring, and maintenance through achievement of RC.

- Document a remedy-focused CSM updated with the recent monitoring data reflecting progress of the implemented remedy and supporting the expected future progress of the remedy.

- Provide a realistic schedule to achieve SC or RC after the POP (the Contractor shall identify which PO is the optimal endpoint).

## 8.2	Transition of Work

Activities will transition to this contract upon completion of the current Contractor’s field support and/or final deliverable on sites noted in the tables below.  The Contractor shall ramp-up management of this contract to ensure seamless operations of existing systems and no lapses in service.

### 8.2.1	Table 2:  Transition of Work Table

| Contract Number | Agency / Contractor / POP End | Final Expected Endpoint |
| --- | --- | --- |
| SHAW AFB |  |  |
| W912EP-16-D-0007; W912HN-20-F-1023 | USACE-SAVANNAH/ BAY WEST/ 08-18-2026 | DLA-Bldg. 1200, DLA-Bldg. 1610/1612, FT001, OT016A, OT016B, OT016C, OT016C/AOC W-T-29, SS015, SS035, SS036: RA-O CG038 , SD033, ST018, ST030: RC DP039, LF003, LF008, LF009: LTM DLA-Bldg 326: SC |
| GS-10F-181BA; W912HN24F1017 | USACE-SAVANNAH / Fourtune 4, Inc., Environmental Assessments and Consult / 23 Sep 29 | FT001P-Sub, FT006P-Sub, FT007P-Sub – GW monitoring |
| W912HN-18-D-1000 | USACE-SAVANNAH / BW#3 IXR Bldg | RA-O and O&M |
| W9128F-20-D-0050 | USACE-SAVANNAH / GWTP2 | RA-O and O&M |

### 8.2.2	Table 3:  Sampling Transition Table

| Site ID | Contract (POP End) | Final RA-O/ LTM Event under Existing Contract | Expected Date of Last Sampling Event under Existing Contract | Existing Contract Final Reports/Outcome | Next Expected Sampling Event under ORC |
| --- | --- | --- | --- | --- | --- |
| SHAW AFB |  |  |  |  |  |
| CG038 | Aug. 2026 | Quarterly GW Sampling Event | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| DP039 | Aug. 2026 | Annual GW Sampling Event | Annual in 1Q’26 | Annual monitoring Report before PoP end | Annual sampling event in 1Q’27 |
| FT001 | Aug. 2026 | Quarterly Groundwater Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| FT001P-SUB | Aug. 2026 | GWTP 2 - Monthly & Quarterly Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts to SCDES and includes monthly emails. | 4Q’26 or 1Q’27 |
| FT006P-SUB | Aug. 2026 | GWTP 2 - Monthly & Quarterly Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts to SCDES and includes monthly emails. | 4Q’26 or 1Q’27 |
| FT007P-SUB | Aug. 2026 | GWTP 2 - Monthly & Quarterly Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts to SCDES and includes monthly emails. | 4Q’26 or 1Q’27 |
| LF003 | Aug. 2026 | Annual LTM landfill cover inspection Inspections are also conducted following extreme weather event | Annual LTM site inspection in 1Q’26 | 5-year CMIPR ’25 (incudes Annual LTM (inspection) Tech memo and Groundwater monitoring) 2026 annual LTM tech memo (tech memo includes all inspections from the previous year) | 2027 Annual Inspections or extreme weather inspection |
| LF008 | Aug. 2026 | Annual LTM landfill cover inspection Inspections are also conducted following extreme weather event | Annual LTM site inspection in 1Q’26 | 5-year CMIPR ’25 (incudes Annual LTM (inspection) Tech memo and Groundwater monitoring) 2026 annual LTM tech memo (tech memo includes all inspections from the previous year) | 2027 Annual Inspections or extreme weather inspection |
| LF009 | Aug. 2026 | Annual LTM landfill cover inspection Inspections are also conducted following extreme weather event GW Sampling once/5 years (next event in 2025) | Annual LTM site inspection in 1Q’26 2025 GW Sampling | 5-year CMIPR ’25 (incudes Annual LTM (inspection) Tech memo and Groundwater monitoring) 2026 annual LTM tech memo (tech memo includes all inspections from the previous year) | 2027 Annual Inspections or extreme weather inspection |
| OT016A | Aug. 2026 | Annual GW Sampling Event | Annual Sampling in 2Q’26 | Annual report prior to end of PoP | Annual Sampling 2Q’27 |
| OT016B | Aug. 2026 | Quarterly Groundwater Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| OT016C | Aug. 2026 | Quarterly Groundwater Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| OT016D | Aug. 2026 | Annual GW Sampling Event | 2Q’26 annual sampling event. | Annual CMIPR report before end of PoP | Annual Sampling 2Q’27 |
| SD033 | Aug. 2026 | Annual GW Sampling Event | Annual Sampling in 2Q’26 | Annual report prior to end of PoP | Annual Sampling 2Q’27 |
| SS015 | Aug. 2026 | Annual GW Sampling Event | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | Annual Sampling 2Q’27 |
| SS035 | Aug. 2026 | Quarterly Groundwater Sampling Base Drinking Water Well Sampling (monthly sampling at BW#3, quarterly sampling at BW #4 & #5) | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| SS036 | Aug. 2026 | Quarterly Groundwater Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| ST018 | Aug. 2026 | Quarterly Groundwater Sampling | Performance monitoring 2Q’26 | 2Q’26 Performance monitoring report | 3Q’26 |
| ST030 | Aug. 2026 | Quarterly Groundwater Sampling | 2Q’26 (Apr-Jun) sampling event | Quarterly Rpts (3Q25 to 2Q26) 2025 Annual CMIPR (3Q’24- 2Q’25 sample events) | 4Q’26 or 1Q’27 |
| DLA – SWMU 98 | Aug. 2026 | Semi-Annual GW Monitoring | 2Q’26 semi-annual sampling event | Annual CMIPR report (includes sampling events 4Q’25 & 2Q’26) before PoP end | 4Q’26 semi-annual sampling event |
| DLA – SWMU 99 | Aug. 2026 | Semi-Annual GW Monitoring | 2Q’26 semi-annual sampling event | Annual CMIPR report (includes sampling events 4Q’25 & 2Q’26) before Pop end | 4Q’26 semi-annual sampling event |

## 8.3	Environmental Construction

The Contractor shall perform construction; restoration; and demolition of utilities, real property systems, and infrastructure in support of environmental restoration requirements as required to achieve the POs of this contract.  Construction and demolition activities shall be in conformance with applicable AF, USACE, and other federal, state, and local standards and regulations to include Installation-specific regulations.  The Contractor shall erect or install support buildings, equipment enclosures, and storage facilities for construction materials and contaminated material awaiting disposal as permitted by the Installation.

### 8.3.1	Design

A conceptual design (typically 10–30% design) for environmental projects may be provided to the Contractor for completion of the design and then construction.  This work may be provided in phases.  The Contractor is accountable for all aspects of the final design under federal, state, and applicable local laws.  All completed designs shall be signed and sealed in accordance with all applicable requirements.  The Contractor shall complete project working drawings and the various plans and schedules, including a construction schedule, and obtain submittal approvals and permits.  Working drawings and specifications shall comply with codes, laws, and the request for proposal requirements.  The working drawings shall be submitted for AF review.

The Contractor shall assist with coordinating regulatory reviews and respond to regulatory comments, shall ensure technical adequacy of the final design, and shall provide quality control of all phases of the contract.

### 8.3.2	Inspection

Upon completion of the final construction, the Contractor shall conduct a pre-final walk-through inspection and publish the pre-final inspection findings in a pre-final inspection report.

The Contractor shall conduct a final inspection and publish the findings in a final inspection report.  The inspection shall concentrate on the items identified at the pre-final inspection and recorded in the pre-final report.  The final inspection report shall (1) certify that all items of the design have been implemented and that the construction is complete; (2) include a record of “signed and sealed” as-built drawings and specifications verifying that all development standards have been met.  At the final inspection, the Contractor shall present a completed DD Form 1354, Transfer and Acceptance of Real Property to the Base Civil Engineer (BCE) or other appropriate organization for signature and approval.

### 8.3.3	Delivery and Warranty

The Contractor shall complete all inspection and commissioning requirements prior to final inspection.  The warranty shall be issued in accordance with FAR 52.246-21.  Extended warranties offered by the Contractor and its subcontractors or suppliers may be accepted at the Government’s discretion.  The Contractor shall review installed equipment and prepare a repository of equipment/systems with information such as scheduled maintenance, compatibility with existing systems, vendor sources, and warranty expiration dates for all systems installed at sites that will not achieve site closure by the end of the POP.  The Contractor shall also provide system O&M manuals and parts lists to the Government.

## 8.4	Environmental Resources Program Information Management System

The Contractor shall comply with the ERPIMS data requirements for all field-derived data/information supported by ERPIMS data structure including, but not limited to, sampling data, remediation system identification data, remediation technology performance data, relevant QA/QC data, lithology, groundwater, monitoring well location, well construction, well maintenance, and/or abandonment information.  After receipt of the contract, the Contractor shall submit an ERPIMS Data Submission Schedule within 30 calendar days of award to establish the projected framework for ERPIMS data submissions.  The Contractor shall record and enter field and laboratory data and submit this data as specified in the latest ERPIMS Data Loading Handbook (DLH) using the latest version of the ERPIMS software utility (ERPTools).  ERPIMS data submissions are required within 90 calendar days of the conclusion of each sampling event unless a written waiver or extension is obtained from the CO/KO in coordination with AFCEC Environmental Restoration Branch Chief.  The AFCEC website (address provided under separate cover) offers the latest DLH, ERPTools client software, ERPIMS policy, ERPIMS Help Desk contact info, data submission requirements, ERPTools training schedules, and more.  Data submissions shall be error-free, pass all validation checks, and fully comply with the ERPIMS DLH.  The Contractor shall ensure that any required corrections are accomplished within both the contract POP and before funds expiration.  The preferred procedure is for laboratories to use ERPTools to input/submit chemistry data for initial validation, import, and submission by the Prime Contractor.  ERPTools training is available to prime and laboratory Contractors.  All ORC milestones that include analytical sampling shall include successful ERPIMS loading of all relevant ERPIMS data elements into the production database as a minimum acceptance criterion.

## 8.5	Innovative and Proven Technologies

The Contractor shall, to the extent reasonably practical, plan, design, construct, operate, monitor, and decommission innovative environmental remediation, monitoring, and other technologies as required to achieve the POs of this contract.  The AF seeks technologies and methodologies that are innovative, sustainable, cost-effective, and will lead to accelerated closure of environmental sites.

## 8.6	Operations and Maintenance

The Contractor shall perform RA-O/O&M requirements following DQOs in accordance with Section 5.1.  The Contractor shall be responsible for the operation, maintenance, repair, replacement, installation of new wells, monitoring, optimization, and evaluation of in-place and proposed environmental systems and well network throughout their active life.  This shall include all materials required to replace any exhaustible process materials required to operate and maintain the individual processes specified in the system O&M manuals and equipment manufacturer specifications.  The Contractor shall provide system O&M manuals and parts list to the Government within 90 calendar days of system installation or modification.  The Contractor shall provide an O&M manual within 180 calendar days for systems that do not have an O&M manual, or the existing manual is deficient.  The Contractor shall be responsible for training maintenance personnel in system operations.  The Contractor shall ensure that the operation of the environmental system is optimal and effective at achieving system goals.

The Contractor shall review installed equipment and prepare databases of equipment/systems with information such as scheduled maintenance, compatibility with existing systems, vendor sources, and warranty expiration dates for all systems installed at sites that will not achieve SC by the end of the POP.  The Contractor shall maintain a complete inventory of system as-built drawings (in hardcopy and electronic) and shall update the drawings in red-line based on revisions to the systems.

## 8.7	Ordnance Removal and Support

NOT APPLICABLE

## 8.8	Hazardous Waste Removal and Support

The Contractor shall destroy, recycle, and dispose of hazardous wastes and materials and provide all hazardous materials use and hazardous waste disposal documentation to AFCEC, COR, and Installation POC(s) or designated alternate.  An AF representative will sign all hazardous waste manifests.  The Contractor shall perform associated investigative work as required.

## 8.9	Study Effort Incidental to Remedy or Corrective Action

The Contractor may engage in supplemental study work in pursuit of a remedy or corrective action.  This may include but is not limited to:  (1) performing bench-scale and pilot-scale studies of remediation technology, and (2) drafting new decision documents (e.g., ROD Amendment, ESD, RCRA Permit modification).

## 8.10	Five-Year Review Support

In accordance with AF policy, the Contractor shall support Five-Year Reviews (e.g., supplying documents to independent reviewers, attending site inspections, and participating in meetings/interviews) of all remedial actions, including non-CERCLA cleanup actions using the USEPA guidance document “Comprehensive Five-Year Review Guidance,” OSWER No 9355.7-03B-P, June 2001.  The Contractor shall also be responsible for implementing findings, recommendations, and/or deficiencies documented in a Five-Year Review which have been identified in the GFI, for any site identified in Table 1 and work described in Section 1.3.2.

# 9.0	Performance Standards and Surveillance Activities

The AF and USACE will utilize the Quality Assurance Activities to define the procedures and guidelines to evaluate the technical and quality performance of the Contractor in accordance with this PWS.  The Quality Assurance Activities ensure that the work, to include that of subcontractors and suppliers, complies with the regulatory and contractual requirements, and documents that all the various activities required to achieve completion of CLINs/Sub-CLINs and that contract requirements not associated directly with a CLIN/Sub-CLIN are being accomplished, tracked, and surveilled.

The Contractor is fully responsible for executing the work under this contract and supervising/directing the work of subcontractors. Surveillance of Contractor performance and compliance shall be completed in accordance with the PWS.  The Government’s contractual relationship and oversight responsibilities are only with the Contractor.

# 10.0	POINTS OF CONTACT

POCs will be specified upon contract award.

ITRC. (2015). Integrated DNAPL Site Characterization and Tool Selection.

SERDP/ESTCP. (2012). Matrix Diffusion Tool Kit.

USEPA. (2009). Evaluating Natural Source Zone Depletion at Sites with LNAPL.

USEPA. (2014). High Resolution Site Characterization for Groundwater Short Course, 23rd Annual NARPM Training Program.

USEPA. (2010). Best Management Practices.

USEPA. (2014). Groundwater Remedy Completion Strategy.

ITRC. (2006). Performance-Based Management.

ITRC. (2010). Use and Measurement of Mass Flux and Mass Discharge.

ITRC. (2004). Remediation Process Optimization: Identifying Opportunities for Enhanced and More Efficient Site Remediation.

ITRC. (2006). Exit Strategy–Seeing the Forest Beyond the Trees.

ITRC. (2004). Remediation Process Optimization: Identifying Opportunities for Enhanced and More Efficient Site Remediation.