## Title Page
NATIONAL ARCHIVES AND RECORDS ADMINISTRATION (NARA)
Revision History
|  | Date | Version | Author | Revision Description
|  | 2020-01-29 | 1 | Requirements & Risk Management Division (IR), Office of Information Services | Initial version
|  | 2026-02-26 | 2 | Product Delivery Division (IP), Office of the Chief Information Officer | Updated to incorporate new needs for system modernization, as well as the addition of requirements for Research Services.
Requirements Verification Traceability Matrix
(RVTM)
Agency Digital Asset Management System (ADAMS)
Version: 2.0 Final
Prepared by the NARA Product Delivery Division (IP)
02/26/2026

## Requirements
REQUIREMENTS | [8 empty] | MISC | DESIGN | DEVELOPMENT | VERIFICATION |  |  |  | DEPLOYMENT PREPARATION
Req # | Requirement Text | Type | Category | Feature | Req Priority | Status | Target Release | Source | Notes | Element | Iteration | Verification Method | Verification Test Case / Step | Verification Status | Verification Criteria | UAT Test Case | UAT Status | Validation Criteria
1 | Authorized users shall be able to upload digital special media assets and their associated metadata. | Business | N/A | Upload Assets | Must | Approved |  | ADAMS Business Case, 6/28/2019
1.1 | The solution shall provide the capability to initiate an upload in the user interface (UI). | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | To support uploading content from a desktop or laptop.
1.1.1 | The solution shall provide a UI based means to browse files/folders and select one or more object(s) for upload. | Stakeholder | Functional | Upload Assets | Must | Approved
1.1.2 | The solution shall support secure and encrypted data transfer capabilities using a NARA-approved protocol. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | For example, Secure File Transfer Protocol (SFTP), SSL/HTTPS, or others.
1.1.3 | The solution shall provide the capability for an authorized external user to upload files to the system. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | This supports the ability of authorized Moving Image and Sound reproduction vendors to upload reproduction copies of files to the ADAMS system, to eliminate the need for vendors to send hard drives to NARA and then have NARA staff upload the copies to the system. However, vendors would only have access to upload assets and would not have any access to view/search records in the system itself since ADAMS is not a public system.
1.1.3.1 | The solution shall initially place files uploaded by an external user into a segregated storage area. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | This supports the ability of NARA to perform automated security scans on the uploaded files before they are moved into the system, as well as for NARA staff to manually perform review and approval of files before adding them to the general repository.
1.1.3.2 | The solution shall allow an authorized user to move files from the segregated storage area into storage repository. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
1.2 | The solution shall provide the capability to upload a variety of content types. | Stakeholder | Functional | Upload Assets | Must | Approved
1.2.1 | The solution shall provide the capability to upload photo files. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | The minimum photo format types to be supported include: JPEG, TIFF, PNG, PSD, DNG, JPG2000, PDF, HEIF/HEIC, RAW (CR2, NEF, RW2), GIF, BMP.
1.2.1.1 | The solution shall provide the capability to identify images selected for upload which are duplicative of an image already uploaded in the system. | Stakeholder | Functional | Upload Assets | Must | Approved
1.2.1.2 | The solution shall provide a human readable notification to the user if a duplicative image was selected for upload. | Stakeholder | Functional | Upload Assets | Must | Approved
1.2.1.3 | The solution shall allow the user to override the "duplicate image" notification and proceed to commit the upload process for the selected image. | Stakeholder | Functional | Upload Assets | Must | Approved
1.2.2 | The solution shall provide the capability to upload video files. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | The minimum video format types to be supported include: Video: AVI, FLV, F4V, MPEG, MPEG-2, MPEG-4, MPG, MP4, MOV, M4V- file extension, WMV, MXF, MKV, WebM, VOB (authored DVD format), 3GP, 3G2, AVCHD, ASF, and DPX. Codecs: DivX, Apple ProRes, H.264, H.265, XviD, Ffv1 and Uncompressed video. Conservation also expects to have video files that could be Android or Mac proprietary embedded in reports and presentations.
1.2.2.1 | The solution shall provide the capability to perform text extraction of the content of an uploaded video file. | Stakeholder | Functional | Upload Assets | Should | Approved |  | Employee Communications (MC) | This may also be referred to as transcription of audiovisual files. Extracting the text of video files uploaded to the system will allow the content to be indexed and searched in order to improve discoverability of responsive files. Note that this capability only applies to corporate files, it does not apply to intermediate copies of accessioned archival records, as it would mean a duplicate copy of records already in the Catalog.
1.2.3 | The solution shall provide the capability to upload graphic image files. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | The minimum graphic image format types to be supported include: AI, INDD, PICT, PS, PDF, EPS, SWF, SVG (QXP, CDR, and PMD are nice to have).
1.2.4 | The solution shall provide the capability to upload audio files. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | The minimum audio format types to be supported include: mp3, m4A, Wav, AIFF, APE, FLAC, AC3, AAC, CAF, PCM, CD audio (CD-DA), MPEG Layer 2.
1.2.5 | The solution shall provide the capability to upload document files. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RXC (Conservation) and Heritage Science, ADAMS Business Need, 10/17/2025 | This includes files in CSV, DAT, TXT, PPT, Google Slides, and CDF files for data and data matrices.
1.2.6 | The solution shall provide the capability to upload proprietary file formats utilized by NARA's Heritage Science Research and Testing program. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RXC (Conservation) and Heritage Science, ADAMS Business Need, 10/17/2025 | NARA's Heritage Science Research and Testing program uses instruments that generate proprietary formats that store both data and instrument metadata, including FTIR, XRF and GCMS file formats. For example the GCMS file format to back up the entire method and sequence of tests run, along with the collected data is a .cmbx file- these are typically a few GB each, but just the raw data can be saved as .raw or .cdf file types from this larger format in the proprietary software for portability into other data processing programs.
1.2.7 | The solution shall provide the capability to upload additional file types identified by NARA. | Stakeholder | Functional | Upload Assets | Should | Approved |  | ADAMS Business Need, 10/17/2025 | This will support the ability to upload and ingest additional file formats that may be needed by NARA in the future.
1.3 | The solution shall provide the capability to upload the metadata associated with digital special media assets to the system. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | This includes CSV, XML, XMP, and TXT files.
1.3.1 | The solution shall provide the capability to bulk upload metadata associated with multiple digital special media assets using a CSV file for input data. | Stakeholder | Functional | Upload Assets | Must | Approved
1.3.1.1 | The solution shall provide the capability to map metadata from the uploaded CSV file to the schema used by the registry. | Stakeholder | Functional | Upload Assets | Must | Approved
1.3.2 | The solution shall provide the capability to bulk upload metadata associated with multiple digital special media assets using a XML file for input data. | Stakeholder | Functional | Upload Assets | Should | Approved
1.3.2.1 | The solution shall provide the capability to map metadata from the uploaded XML file to the schema used by the registry. | Stakeholder | Functional | Upload Assets | Should | Approved
1.3.3 | The solution shall provide the capability to bulk upload metadata associated with multiple digital special media assets using an XMP sidecar file for input data. | Stakeholder | Functional | Upload Assets | Should | Approved |  | RXC (Conservation), ADAMS Business Need, 10/17/2025 | XMP stands for Extensible Metadata Platform. It is an Adobe-developed, ISO-standard format for embedding metadata into files or storing it in separate "sidecar" files.
1.3.4 | The solution shall provide the capability to upload the metadata associated with digital special media assets using a TXT file for input data. | Stakeholder | Functional | Upload Assets | Should | Approved |  |  | For example, the ability to upload a separate transcription file in TXT format that is associated with a given video asset/file.
1.4 | The solution shall provide the capability to extract metadata embedded in a digital special media asset and use that metadata as input to the system. | Stakeholder | Functional | Upload Assets | Should | Approved
1.4.1 | The solution will provide the capability to map the extracted metadata to the schema used by the system. | Stakeholder | Functional | Upload Assets | Should | Approved
1.5 | The solution shall provide the capability for an authorized user to specify the format types supported for upload. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | To support the addition or removal of format types that may be needed in the future. An authorized user is a System Administrator or potential "superuser".
1.6 | The solution shall provide the capability for an external user to upload digital special media assets to a secure location. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | To allow external contractors to upload files without needing direct access into the system.
1.7 | The solution shall generate a checksum for each file uploaded to the system. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
1.7.1 | The solution shall display the generated checksum for each file as part of the file metadata. | Stakeholder | Functional | Upload Assets | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
1.8 | The solution shall provide the capability for an Application Administrator to delete uploaded digital special media content. | Stakeholder | Functional | Upload Assets | Must | Approved |  |  | The Application Administrator is the only user role that has permissions to delete uploaded content. Application Administrators can delete before or after approval but rarely would it be done after.
2 | Authorized users shall be able to approve digital special media assets. | Business | N/A | Approve Assets | Must | Approved |  | ADAMS Business Case, 6/28/2019 | To approve digital special media assets for acceptance into the system. Assets are not released for general use until the assets have been approved.
2.1 | When uploading digital special media assets, the system shall place the assets within a queue for approval. | Stakeholder | Functional | Approve Assets | Must | Approved |  |  | Some corporate files will require oversight to make sure files submitted for sharing with all staff are complete and appropriate (checked for quality, redundancy, metadata, etc.) Similarly, Research Services would like the ability to do rights reviews on the files coming from the lab or quality assurance on files uploaded from an external vendor before adding to the repository. This capability would address needs of both the business users as well as Corporate Records Management users.
2.1.1 | When an asset is within the queue for approval, the asset is only available to an authorized user group. | Business Rule | Constraint | Approve Assets | Must | Approved |  |  | To only allow access to assets awaiting approval in the queue to a specified user group.
2.1.2 | The solution shall send a push notification to an authorized user group when a digital special media asset is uploaded and in the approval queue. | Stakeholder | Functional | Approve Assets | Must | Approved |  |  | A push notification may be via email. This capability would address needs of both the business users as well as Corporate Records Management users.
2.2 | The solution shall provide the capability for an authorized user to approve digital special media assets awaiting approval. | Stakeholder | Functional | Approve Assets | Must | Approved |  |  | Some corporate files will require oversight to make sure files submitted for sharing with all staff are complete and appropriate before being approved (checked for quality, redundancy, metadata, etc.) Similarly, Research Services would like the ability to do rights reviews on the files coming from the lab or quality assurance on files uploaded from an external vendor before they are approved and added to the repository. This capability would address needs of both the business users as well as Corporate Records Management users.
2.2.1 | When an asset is approved, the system shall make the asset accessible to other users within the system. | Stakeholder | Functional | Approve Assets | Must | Approved |  |  | Accessible means viewable and discoverable via Search. Please note that access to files is driven by permissions (roles and groups). This capability would address needs of both the business users as well as Corporate Records Management users.
2.3 | The solution shall provide the capability to assign file names to approved content. | Stakeholder | Functional | Approve Assets | Should | Approved
2.3.1 | The solution shall provide the capability to assign an auto-generated file name to approved content. | Stakeholder | Functional | Approve Assets | Should | Approved |  |  | For example, a file would be named in the format YYYYMMDD-##-### where YYYY is year, MM is month, DD is day, ## is a sequential number to differentiate multiple jobs shots on the same day, and ### is a sequence number to keep images in chronological order.
2.3.1.1 | When a file is approved/ingested into the system, the original file name shall be saved as metadata for the file. | Business Rule | Constraint | Approve Assets | Could | Approved
2.3.2 | The solution shall provide the capability for an authorized user to manually enter a file name for approved content. | Stakeholder | Functional | Approve Assets | Should | Approved |  |  | If the system provides the capability to auto-generate file names, it must also support the ability for NARA staff to edit the file names to use their own file naming conventions. This would allow them to use record Local Identifiers in the file name or other local practices instead of an auto-generated file name.
2.4 | The solution shall provide the capability for an authorized user to reject digital special media assets awaiting approval. | Stakeholder | Functional | Approve Assets | Must | Approved
2.4.1 | When an asset is rejected, the system shall send a notification to the submitter describing the reason for the rejection. | Stakeholder | Functional | Approve Assets | Must | Approved |  |  | This capability would address needs of both the business users as well as Corporate Records Management users.
2.4.1.1 | The system shall provide the capability for an authorized user to configure the notification message received when an asset is rejected. | Stakeholder | Functional | Approve Assets | Should | Approved
3 | Authorized users shall be able to manage and store metadata for each digital special media asset. | Business | N/A | Metadata | Must | Approved |  | ADAMS Business Case, 6/28/2019 | Manage = create, read, update, and delete
3.1 | The solution shall provide the capability for an authorized user to add metadata to the record. | Stakeholder | Functional | Metadata | Must | Approved |  | APP B., Goals Reqt #15 | Metadata may be added through keying, extracting from assets, and import from properly formatted files, such as XML or a spreadsheet. For example, to add a National Archives Identifier (NAID), Local Identifier, file size, running time, tracking numbers for declassification or special access release, source element, use restrictions, and contacts for permissions. Metadata must be able to be added without compromising images. Metadata is currently added in the Adobe Lightroom Catalog using IPTC fields, metadata from the camera, and a custom keywords list. Existing metadata must be maintained and stay with the files during upload.
3.2 | The solution shall provide the capability for an authorized user to edit the metadata associated with one or more digital special media assets. | Stakeholder | Functional | Metadata | Must | Approved |  | APP B., Goals Reqt #15 | To edit the metadata of an individual asset or edit the metadata in batches.
3.3 | The solution shall provide the capability for an authorized user to add new metadata fields for a digital special media asset. | Stakeholder | Functional | Metadata | Must | Approved |  | APP B., Goals Reqt #15 | The system must provide for future additions/changes to metadata fields, such as adding more fields or complying with professional standards (e.g., metadata documenting provenance and authenticity: https://c2pa.org/).
4 | Authorized users shall be able to organize digital special media content within the system. | Business | N/A | Categorization | Must | Approved |  | ADAMS Business Case, 6/28/2019
4.1 | The solution shall provide the capability for an authorized user to group one or more digital special media assets into a folder. | Stakeholder | Functional | Categorization | Must | Approved
4.1.1 | The solution shall control access to folders of corporate digital special media assets separately from folders of archival digital special media assets. | Business Rule | Constraint | Categorization | Must | Approved |  | ADAMS Business Need, 10/17/2025 | Corporate records are those created by/within NARA itself, verus archival records that are created by other agencies/entities and accessioned into the archival holdings. Managing corporate records separately from archival records should be accomplished logically via separate folders and managed via security and access rights. The solution must allow for the separation of the storage, search, and delivery interface for the digital special media assets so that corporate and archival records are not commingled.
4.2 | The solution shall provide the capability for an authorized user to select one or more assets to create a collection. | Stakeholder | Functional | Categorization | Must | Approved |  |  | This is a virtual collection of assets.
4.3 | The solution shall provide the capability for an authorized user to update a collection. | Stakeholder | Functional | Categorization | Must | Approved |  |  | This supports adding or removing assets from the virtual collection, and it does not affect the actual asset in their original form and location in the system.
4.3.1 | A user can only update their own collections. | Business Rule | Constraint | Categorization | Should | Approved
4.4 | The solution shall provide the capability to delete a collection. | Stakeholder | Functional | Categorization | Must | Approved |  |  | This supports deleting a virtual collection, and it does not delete or affect the actual asset in their original form and location in the system.
4.4.1 | A user can only delete their own collections. | Business Rule | Constraint | Categorization | Must | Approved
5 | Authorized users shall be able to manage digital special media assets via workflows. | Business | N/A | Workflow | Must | Approved |  | ADAMS Business Case, 6/28/2019 | Manage workflows means to create/configure, edit, and delete workflows. Workflow capabilities would address needs of both the business users as well as Corporate Records Management users.
5.1 | The solution shall provide the capability for an authorized user to manage a workflow process. | Stakeholder | Functional | Workflow | Must | Approved |  |  | This includes work-in-progress. Manage workflows means to create/configure, edit, and delete workflows. This capability would address needs of both the business users as well as Corporate Records Management users.
5.1.1 | The solution shall provide the capability for an authorized user to manage separate workflows for separate user groups. | Stakeholder | Functional | Workflow | Must | Approved |  | RXC (Conservation), ADAMS Business Need, 10/17/2025 | Manage workflows means to create/configure, edit, and delete workflows.
5.2 | The solution shall provide the capability for an authorized user to define events for a workflow. | Stakeholder | Functional | Workflow | Must | Approved
5.3 | The solution shall keep an audit trail of each event within a workflow. | Stakeholder | Functional | Workflow | Must | Approved
5.4 | The solution shall keep an audit trail of all user activities in a workflow. | Stakeholder | Functional | Workflow | Must | Approved
5.5 | The solution shall provide the capability for an authorized user to define alerts for a workflow. | Stakeholder | Functional | Workflow | Should | Approved
5.5.1 | The solution shall provide the capability for an authorized user to configure when an alert is triggered. | Stakeholder | Functional | Workflow | Should | Approved
5.5.2 | The solution shall provide the capability for an authorized user to configure how often an alert is issued. | Stakeholder | Functional | Workflow | Should | Approved
5.5.3 | The solution shall provide the capability for an authorized user to configure the message displayed for an alert. | Stakeholder | Functional | Workflow | Should | Approved
5.5.4 | The solution shall provide the capability to display an alert. | Stakeholder | Functional | Workflow | Should | Approved
6 | Authorized users shall be able to manage version control for digital special media assets. | Business | N/A | Configuration Management | Must | Approved
6.1 | The solution shall provide the capability to check out a file for editing. | Stakeholder | Functional | Configuration Management | Must | Approved |  |  | This may involve editing directly within the system for a small set of file formats, but for most file formats it would likely require the user to download the file to complete the editing and then upload it back into the system in order to check it back in as a new version.
6.2 | The solution shall provide the capability to check in a file to include all changes made while the file was checked out. | Stakeholder | Functional | Configuration Management | Must | Approved
6.3 | When performing a check-in on a file, the system shall automatically create a new version of that file. | Stakeholder | Functional | Configuration Management | Must | Approved
6.4 | The system shall provide the capability to restore a file to a previous version. | Stakeholder | Functional | Configuration Management | Must | Approved
6.5 | The system shall provide the capability to display the metadata associated with each version of a file. | Stakeholder | Functional | Configuration Management | Must | Approved |  |  | This supports the ability to view the metadata for each version of a file to uniquely identify them.
7 | Authorized users shall be able to perform searches for digital special media assets within the system. | Business | N/A | Search & Retrieval | Must | Approved |  | ADAMS Business Case, 6/28/2019 | The search and delivery interface for the digital special media assets will be separated so that corporate and archival records are not commingled when searches are conducted. Permissions control what users/groups have access to search and view corporate records vs. archival records.
7.1 | The solution shall provide the capability to search on the content of digital special media assets. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  |  | This includes the ability to search and retrieve the transcribed / extracted text of video files uploaded to the system. This capability supports the needs of both the business users and Corporate Records Management users.
7.2 | The solution shall provide the capability to search on the associated metadata of digital special media assets. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  |  | This includes user-added metadata. This capability supports the needs of both the business users and Corporate Records Management users.
7.3 | The solution shall provide the capability to search on the embedded metadata of digital special media assets. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  |  | This capability supports the needs of both the business users and Corporate Records Management users.
7.4 | The solution shall provide the capability to enter criteria for a parametric (advanced) search on specific fields. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  |  | Advanced search on specified fields may include search on embedded metadata fields and user-added metadata fields. This capability supports the needs of both the business users and Corporate Records Management users.
7.5 | The solution shall provide the capability to enter criteria for a keyword search. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  |  | This includes the capability to perform an exact phrase search (e.g., if the user enters the keywords within quotation marks) and combining keywords with Boolean operators (AND, OR, NOT). This capability will support the needs of both the business users and Corporate Records Management users.
7.6 | The solution shall provide the capability to search for assets by file type. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  | ADAMS Business Need, 10/17/2025
7.7 | The solution shall provide the capability to search for assets by file name. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  | ADAMS Business Need, 10/17/2025
7.8 | The solution shall provide the capability to search for assets by folder name. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  | ADAMS Business Need, 10/17/2025
7.9 | The solution shall display a set of brief results for the assets retrieved from a search of digital special media assets. | Stakeholder | Functional | Search & Retrieval | Must | Approved
7.1 | The solution shall provide a notification to a user when no responsive results are found for a search request. | Stakeholder | Functional | Search & Retrieval | Must | Approved
7.11 | The solution shall provide the capability to filter the responsive results from a search. | Stakeholder | Functional | Search & Retrieval | Must | Approved |  |  | Adding a filter to a search result set allows the user to further refine their search and narrow down the records/files retrieved according to the specified filter criteria.
7.12 | The solution shall provide the capability to sort the responsive results from a search. | Stakeholder | Functional | Search & Retrieval | Must | Approved
7.13 | The solution shall provide the capability to save search criteria for potential reuse. | Stakeholder | Functional | Search & Retrieval | Must | Approved
7.14 | The solution shall provide the capability to render digital special media assets from the results of a search request. | Stakeholder | Functional | Search & Retrieval | Should | Approved |  |  | Render means to display or play directly within the system. The minimum common, industry-standard format types to be supported include: Video: AVI, FLV, F4V, MPEG, MPEG-2, MPEG-4, MPG, MP4, MOV, WMV, MXF, AVCHD, and ASF Audio: MP3, WAV, AAC, PCM, and MPEG Layer 2 Photo: JPEG, TIFF, PNG, PSD, DNG, HEIF/HEIC (iPhone photos), GIF, BMP, CR2 (Canon raw), NEF (Nikon raw), and RW2 (Panasonic raw) Document: CSV, TXT, PPT, Google Slides, and CDF (data & data matrices) Graphic Image: PDF Codecs: Apple ProRes, H.264, FFV1, and Uncompressed video
8 | Authorized users shall be able to export (download) digital special media assets in any format and file size from the system. | Business | N/A | Export (Download) | Must | Approved |  | ADAMS Business Case, 6/28/2019 | The export will be limited to a specified list of formats as determined by NARA.
8.1 | The solution shall provide the capability for an authorized user to select one or more digital special media assets for export. | Stakeholder | Functional | Export (Download) | Must | Approved
8.1.1 | The solution shall provide the capability to export the selected digital special media asset(s). | Stakeholder | Functional | Export (Download) | Must | Approved
8.1.1.1 | When exporting (downloading) an asset from the system, any metadata for that asset must also be included with the exported (downloaded) copy of the file. | Stakeholder | Functional | Export (Download) | Must | Approved |  | RXC (Conservation) and Heritage Science, ADAMS Business Need, 10/17/2025
8.1.2 | The solution shall provide the capability to convert one or more digital special media assets to another format during export. | Stakeholder | Functional | Export (Download) | Must | Approved |  |  | The formats available for conversion will be limited to a specified list of formats as specified by NARA. For example, the user may direct ADAMS to translate one or more raw photos to .png format, or request a .tiff file be converted to a .jpg format. The system will not retain the new file.
8.1.2.1 | When converting an asset to another format during export, the system shall retain the original format of the converted asset. | Stakeholder | Functional | Export (Download) | Must | Approved
8.1.2.2 | When converting an asset to another format during export, the solution shall provide the capability to rotate an asset prior to export. | Stakeholder | Functional | Export (Download) | Could | Approved
8.1.3 | The solution shall provide the capability to select the size of a digital special media asset during export. | Stakeholder | Functional | Export (Download) | Must | Approved |  |  | Sizing consist of the following: Video - pixel dimensions, bit rate, bit depth, compression Photo- pixel dimensions and compression, bit depth
8.1.3.1 | When resizing an asset, the system shall retain the original size of the resized asset. | Stakeholder | Functional | Export (Download) | Must | Approved
8.2 | The solution shall provide the capability to perform a bulk export of one or more selected digital special media asset(s) within the system. | Stakeholder | Functional | Export (Download) | Must | Approved |  |  | It is expected that "Select All/Deselect All" will be an available selection option.
8.3 | The solution shall provide the capability to perform a bulk export of the metadata associated with one or more digital special media asset(s) within the system. | Stakeholder | Functional | Export (Download) | Must | Approved |  |  | It is expected that "Select All/Deselect All" will be an available selection option.
9 | Authorized users shall be able to share digital special media assets. | Business | N/A | File Sharing | Must | Approved |  | ADAMS Business Case, 6/28/2019
9.1 | The solution shall provide the capability for an authorized user to select one or more digital special media assets for sharing. | Stakeholder | Functional | File Sharing | Must | Approved |  |  | For example, a single photograph or a folder containing a collection of photos. This capability should allow users the ability to create lightboxes, collections, asset groupings that can be shared with other internal users.
9.1.1 | The solution shall provide the capability for an authorized user to share the selected digital special media asset(s) with one or more internal NARA users. | Stakeholder | Functional | File Sharing | Must | Approved
9.1.2 | The solution shall provide the capability for an authorized user to share the selected digital special media asset(s) with one or more internal NARA user groups. | Stakeholder | Functional | File Sharing | Should | Approved
9.2 | The solution shall notify a user when digital special media assets are being shared with them. | Stakeholder | Functional | File Sharing | Must | Approved |  |  | For example, an email with the hyperlink to the location of the shared content.
9.3 | The solution shall enable an authorized user to view digital special media content that is shared with them. | Stakeholder | Functional | File Sharing | Must | Approved |  |  | For example, browsing a listing of shared files and folders and viewing their content directly in the system.
9.4 | The solution shall provide the capability for an authorized user to share a collection with other users via email. | Stakeholder | Functional | File Sharing | Should | Approved
10 | Authorized users shall be able to deliver digital special media assets to external users. | Business | N/A | File Delivery | Must | Approved |  |  | This supports the ability of an authorized user to create 'orders' consisting of selected files for delivery to external users. External users do not have access to ADAMS, therefore the sharing mechanism should allow an ADAMS user to share the asset with an external user without them logging into ADAMS. The solution must leverage temporary, time-sensitive URLs (e.g., cloud provider pre-signed URLs) for all shared assets. This ensures granular access control, enforces permission checks (especially when fees are involved), and prevents unauthorized, perpetual access to the digital media assets. Persistent URLs shall not be used for sharing access-controlled content. If it is on premise storage then the solution may be different and it will be based on the OEM vendor.
10.1 | The solution shall provide the capability for an authorized user to select one or more digital special media assets for delivery to an external user. | Stakeholder | Functional | File Delivery | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
10.2 | The solution shall provide the capability to share documentation about general use and specific asset-level permissions when the files are shared with an external user. | Stakeholder | Functional | File Delivery | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
10.3 | The solution shall send a notification to the requestor when shared file(s) are ready for retrieval along with the location of the file. | Stakeholder | Functional | File Sharing | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
10.4 | The solution shall provide an expiration date on files shared for delivery. | Stakeholder | Functional | File Delivery | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | NARA will determine how to set the expiration date during design and implementation.
10.4.1 | The solution shall provide the capability for an Application Administrator to configure the expiration date on files shared for delivery. | Stakeholder | Functional | File Delivery | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025
10.5 | The solution shall confirm that the external user has provided payment for the file delivery before they are granted download access. | Business Rule | Constraint | File Delivery | Must | Approved
10.6 | The solution shall provide the capability for an external user to retrieve their own requested files from the system before expiration. | Stakeholder | Functional | File Delivery | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2005
11 | Authorized users shall be able to generate standard and ad hoc reports. | Business | N/A | Reporting | Must | Approved |  | ADAMS Business Case, 6/28/2019 | Generating reports for business and records management purposes, such as, identifying records for reporting, editing, tracking, search, transfer, holds, and deletion purposes.
11.1 | The solution shall provide the capability to generate standard reports. | Stakeholder | Functional | Reporting | Must | Approved |  | APP B, Goal Reqt #11
11.1.1 | The solution shall provide the capability to generate a predefined report on digital special media files that are uploaded to the system over a given time period. | Stakeholder | Functional | Reporting | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2005 | The user should be able to specify a start date and end date for the report. The report shall include, at a minimum, the file name, file size, file type, date uploaded, the name of the user that uploaded the file, and the group (unit) of the user that uploaded the file.
11.1.2 | The solution shall provide the capability to generate a predefined report on digital special media files that were ordered by users over a given time period. | Stakeholder | Functional | Reporting | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2005 | The user should be able to specify a start date and end date for the report. This supports the ability of the user to report on files shared/delivered by a selected group (i.e., NARA unit) to satisfy orders placed by internal or external customers over that time period.
11.1.3 | The solution shall provide the capability to generate a predefined report on digital special media files ordered and delivered over time by item number, recipient, and delivering NARA unit. | Stakeholder | Functional | Reporting | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2005 | This supports the ability of a NARA unit to generate a report on orders that the unit fulfilled over a given time frame.
11.2 | The solution shall provide the capability to generate ad hoc reports. | Stakeholder | Functional | Reporting | Must | Approved |  | APP B, Goal Reqt #11
11.3 | The solution shall provide the capability to export a report. | Stakeholder | Functional | Reporting | Must | Approved
11.4 | The solution shall provide the capability to export a report in CSV format. | Stakeholder | Functional | Reporting | Must | Approved
11.5 | The solution shall provide the capability for an authorized user to restrict access to the data within standard reports by user and user role. | Stakeholder | Functional | Reporting | Must | Approved
12 | Authorized users shall be able to manage permissions and access for users via roles and groups. | Business | N/A | Account Management | Must | Approved |  |  | For example, via a dashboard or other UI-based tool for the System Administrator(s).
12.1 | The solution shall provide the capability for an Application Administrator to manage user accounts. | Stakeholder | Functional | Account Management | Must | Approved |  |  | Manage means to create/add, update, and delete. It is expected that disabling a user account would be the typical use case and deletion would be reserved for error cases.
12.1.1 | The solution shall provide the capability to create one or more user accounts. | Stakeholder | Functional | Account Management | Must | Approved
12.1.2 | The solution shall enable an Application Administrator to authorize users from multiple geographic locations to access NARA's inventory of digital special media assets. | Stakeholder | Functional | Account Management | Must | Approved |  | ADAMS Business Case, 6/28/2019 | Specific permissions for a given user will be based on the assigned user role(s) and group(s).
12.1.3 | The solution shall provide the capability to disable a user account. | Stakeholder | Functional | Account Management | Must | Approved |  |  | Disabling user accounts will be used in cases where the user left the agency or moved to a new position, and would prevent that user from accessing the system unless their account was reactivated.
12.1.3.1 | The solution shall provide the capability for an Application Administrator to document Comments related to the disabling of a user account. | Stakeholder | Functional | Account Management | Must | Approved
12.1.4 | The solution shall provide the capability to activate a user account that was previously disabled. | Stakeholder | Functional | Account Management | Must | Approved
12.1.4.1 | The solution shall provide the capability for an Application Administrator to document Comments related to the activation of a previously disabled user account. | Stakeholder | Functional | Account Management | Must | Approved
12.2 | The solution shall provide the capability to manage user roles. | Stakeholder | Functional | Account Management | Must | Approved |  |  | Manage means to create/add, update, and delete. This includes the ability to define different roles and associated permissions for users to upload files, search, select and edit file metadata, download files, deliver or share files, and delete files.
12.2.1 | The solution shall provide the capability to assign one or more roles to a user. | Stakeholder | Functional | Account Management | Must | Approved
12.2.2 | The solution shall provide the capability to manage user permissions for each user role. | Stakeholder | Functional | Account Management | Must | Approved |  |  | This includes the ability to define different roles and associated permissions for users to upload files, search, select and edit file metadata, download files, deliver or share files, and delete files.
12.2.3 | The solution shall user access according to the permissions defined for each role. | Stakeholder | Functional | Account Management | Must | Approved
12.3 | The solution shall provide the capability to manage user groups. | Stakeholder | Functional | Account Management | Must | Approved |  |  | Manage means to create/add, update, and delete.
12.3.1 | The solution shall provide the capability to manage user permissions for each user group. | Stakeholder | Functional | Account Management | Must | Approved
12.4 | The solution shall provide the capability to define access permissions to assets. | Stakeholder | Functional | Account Management | Must | Approved
12.4.1 | The solution shall provide the capability to define access permissions to assets by user account. | Stakeholder | Functional | Account Management | Must | Approved
12.4.2 | The solution shall provide the capability to define access permissions to assets by user role. | Stakeholder | Functional | Account Management | Must | Approved
12.4.3 | The solution shall provide the capability to define access permissions to assets by user group. | Stakeholder | Functional | Account Management | Must | Approved
13 | Authorized users shall be able to access online training assistance for the solution. | Business | N/A | Training | Must | Approved |  |  | This is to support help text, online manuals, and online training simulations that should be made available within the system and accessible to users NARA-wide.
14 | Authorized users shall be able to manage digital special media assets according to NARA records management standards and procedures. | Business | N/A | Records Management | Must | Approved |  | ADAMS Business Case, 6/28/2019 | The solution should be compliant with the Records Management requirements specified below, also referred to as the "IT Tiered Requirements for Records Management" that can be viewed at: https://www.archives.gov/records-mgmt/policy/frmc
14.1 | The solution shall provide the capability for agency authorized users to manage access to electronic records. | Stakeholder | Functional | Records Management - Access | Must | Approved |  | IT Tiered Requirements for Records Management
14.1.1 | The solution shall provide role-based access to individual records or groups of records. | Stakeholder | Functional | Records Management - Access | Must | Approved |  | IT Tiered Requirements for Records Management | This should include shared accounts.
14.1.2 | The solution shall provide the capability to set access restrictions on individual or groups of records. | Stakeholder | Functional | Records Management - Access | Must | Approved |  | IT Tiered Requirements for Records Management | This ensures that access to records in the system can be set according to individual, groups (organization, managers, etc.)
14.1.3 | The solution shall provide the capability for agency authorized users to access agency electronic records regardless of whether formerly associated users have changed roles or departed the organization. | Stakeholder | Functional | Records Management - Access | Must | Approved |  | IT Tiered Requirements for Records Management | This ensures that access to the records in the system is not tied to a particular user who may have created or been associated with those records, so that the records continue to be accessible after those individuals leave the agency. This includes contractors, volunteers, and interns. This also includes NARA units, offices, or organizations that have reorganized (e.g., a change in office symbols), realigned, or closed.
14.1.4 | The solution shall provide the capability for agency authorized users to access records throughout the records lifecycle. | Stakeholder | Functional | Records Management - Access | Must | Approved |  | IT Tiered Requirements for Records Management | This capability ensures continuity of access to the records for as long as required for business, Freedom of Information Act (FOIA) requests, Privacy Act requests, and investigative purposes, even if the staff associated with the creation or information in the records have left the agency.
14.2 | The solution shall provide records administration capabilities to authorized agency administrative users. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.1 | The solution shall provide authorized agency administrative users with complete visibility of the records management functionality in real or near-real time. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | Examples include visibility into individual user accounts, generating regular overall system volume and status, metrics on access restrictions, etc.
14.2.2 | The solution shall provide the capability for agency authorized users to gather system metrics on system performance. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.3 | The solution shall provide the capability to design and generate customized reports on information for which users have been granted access. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | These are reports generated specifically to support corporate records management purposes.
14.2.4 | The solution shall provide the capability for agency authorized users to manage the access rights and permission rules for users to access the electronic records. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | Manage means to create, read, update, and delete.
14.2.4.1 | The solution shall provide the capability to display trend analysis and other query results in multiple formats. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | This includes dashboards.
14.2.4.2 | The solution shall provide the capability to save trend analysis and other queries in multiple formats. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.4.3 | The solution shall provide the capability to filter report data based on the values contained in any field or column. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.4.4 | The solution shall provide the capability to sort report data based on the values contained in any field or column. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.4.5 | The solution shall provide the capability to schedule the delivery of reports to a specified list of recipients. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.4.6 | The solution shall provide the capability to save the configurations of ad hoc reports for reuse. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.5 | The solution shall provide the capability for agency authorized users to flag responsive records and manage them together as a case file. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.2.6 | The solution shall provide the capability for agency authorized users to flag content that is protected data. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | Protected data includes information that is not considered public, or that needs to be protected for any reason, such as Personally Identifiable Information (PII) or Controlled Unclassified Information (CUI).
14.2.7 | The solution shall provide the capability for agency authorized users to modify a record's status. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | For example, to update the status from Temporary to Non-Record.
14.2.8 | The solution shall provide the capability for agency authorized users to verify that electronic records and its associated metadata managed within the solution are authentic representations of the original in all properties and characteristics. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management | This requirement ensures that that there is one authentic record copy of ALL federal records and that records within the system are maintained as authentic representations of the records and exhibit all properties, characteristics, and functionality of the original records. This includes, in particular, that software updates do not render records inaccessible or inauthentic. Authenticity refers to the trustworthiness of the record as an accurate representation of the original. NARA will ensure authenticity by documenting all actions on the electronic records as informed by ISO 14721:2012, Space data and information transfer systems -- Open archival information system (OAIS) -- Reference model. This also includes capturing the checksum for uploaded files. For example, de-duping is a method used to encourage efficient data management of objects and a hash table is a well-understood method of ensuring that an object is what it is supposed to be.
14.2.9 | The solution shall provide the capability for agency authorized users to correct or amend a record. | Stakeholder | Functional | Records Management - Administration | Must | Approved |  | IT Tiered Requirements for Records Management
14.3 | The solution shall provide the capability to manage agency electronic records according to General Records Schedules (GRS), or NARA-approved Records Control Schedules (RCS), in acceptable formats, as appropriate. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | For General Records Schedules (GRS), see, https://www.archives.gov/records-mgmt/grs.html For acceptable formats, see, https://www.archives.gov/records-mgmt/policy/transfer-guidance-tables.html
14.3.1 | The solution shall maintain the integrity/authenticity of individual records (including all component parts) from records creation through its entire lifecycle to final disposition. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | From 36 CFR 1236.10 (b) "Authenticity: Controls to protect against unauthorized addition, deletion, alteration, use, and concealment."
14.3.2 | The solution shall maintain an audit trail for all actions pertaining to the record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | From 36 CFR 1236.10 (c) "Integrity: Controls, such as audit trails, to ensure records are complete and unaltered." Examples of audit controls must include access logs, alerts, errors, incident and event reporting, and regular (daily and weekly) system reporting, including recurring, user-generated reports for records management and IT stakeholders to proactively monitor the system. See also the non-functional Security & Auditing requirements included in the RVTM.
14.3.3 | The solution shall provide the capability for agency authorized users to view an audit trail of user actions on electronic records performed within the system. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.4 | The solution shall provide the capability to identify duplicate copies of a record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.5 | The solution shall provide the capability to encode and decode compressed records using NARA-accepted compression technologies used with electronic records. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Compression methods/technologies to be provided by NARA (see also NARA Transfer Guidance and 26 CFR 1236).
14.3.6 | The solution shall provide the capability to identify and calculate the records lifecycle on records individual or sets of records. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.3.6.1 | The solution shall provide the capability to use specified time-based criteria to calculate the record lifecycle of a given record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | An example of time-based criteria includes utilizing the document creation date. Can be done in a manual or automated manner.
14.3.6.2 | The solution shall provide the capability to use event-based criteria to calculate the lifecycle of a given record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.3.6.3 | The solution shall provide the capability to use as combined time and event-based criteria to calculate the lifecycle of a given record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.3.6.4 | The solution shall provide the capability to identify/flag applicable record(s) when they reach key milestone(s) in their applicable record lifecycle. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.6.5 | The solution shall provide an authorized user the capability to recalculate the record life cycle based on changes to any life-cycle criteria. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.3.6.6 | The solution shall provide an authorized user the capability to set the filing status according to the business rules associated with date change(s). | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | For example, Filing Status may be set to Open (active) or Closed (inactive). Can be done in a manual or automated manner.
14.3.6.7 | The solution shall provide the capability for agency authorized users to modify a record's filing status. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.3.7 | The solution shall provide the capability to manage multiple entries of a record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | "Multiple entries" refers to multiple copies (not necessarily multiple objects) of a record that are specifically maintained as separate copies because each copy serves an independent business interest/process.
14.3.7.1 | The solution shall provide the capability to associate and link multiple entries of a record as separate or related entities. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.7.2 | The solution shall provide the capability for each entry of a record to be associated with its own set of metadata. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.7.3 | The solution shall provide the capability to associate and link versions of records. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management | Versions refers to both current and superseded or obsolete copies of a record.
14.3.7.4 | The solution shall provide the capability to associate its own set of metadata to each version of a record. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.7.5 | The solution shall provide the capability to associate the record metadata to the record so the metadata can be accessed for display, export, etc. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.3.8 | The solution shall provide the capability for the establishment of cases and associate search results with each of the cases. | Stakeholder | Functional | Records Management - Control | Must | Approved |  | IT Tiered Requirements for Records Management
14.4 | The solution shall provide the capability to implement records schedules and associated dispositions on agency electronic records. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management | For event- and date-based schedules, disposition is based upon either the applicable NARA Records Control Schedule (RCS), or General Records Schedules (GRS).
14.4.1 | The solution shall provide the capability to implement role-based schedules and associated dispositions. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.4.2 | The solution shall provide the capability to implement event-based schedules and associated dispositions. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.4.3 | The solution shall provide the capability to implement date-based schedules and associated dispositions. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management | Can be done in a manual or automated manner.
14.4.4 | The solution shall flag a record once the retention period has been met and provide automatic notification so that disposition can be initiated by agency authorized users. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.5 | The solution shall provide the capability to set a "Grace Period" after which electronic records are assigned a records management disposition (retention) rule, which can only be changed by authorized agency administrative users. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.6 | The solution shall provide the capability for secure deletion of all eligible records according to the records schedule. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management | NIST 800-88 standard for definition of secure deletion may be referenced for additional requirements. Separation and removal capabilities of temporary records and non-records allow for destruction and deletion, while permanent records are transferred to the National Archives. Records and non-records authorized for deletion are reconciled with a disposition authority and are nonrecoverable.
17.4.6.1 | The solution shall provide the capability for authorized agency administrative users to perform bulk deletions of electronic record objects as part of scheduled dispositions or other administrative purposes. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.7 | The solution shall provide the capability to suspend retention policies (i.e., place and remove Retention Holds) for records responsive to E-Discovery orders, Freedom of Information Act (FOIA) requests, Privacy Act (PA), or other investigative purposes. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.7.1 | The solution shall provide the capability for agency authorized users to identify electronic records as being the subject of an authorized Hold action. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.7.2 | The solution shall provide the capability for agency authorized users to exempt from deletion any electronic records that are identified as being the subject of a Hold action. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.7.3 | The solution shall provide the capability for agency authorized users to remove a Hold action on electronic records and resume the disposition. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.7.4 | The solution shall provide the capability for agency authorized users to track and manage the implementation of litigation holds with associated cases. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.8 | The solution shall provide the capability to export content as a record. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.8.1 | The solution shall provide the capability to export content as a record in its native format. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.8.2 | The solution shall provide the capability to export designated records in bulk in their native formats. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.8.3 | The solution shall provide the capability to export an individual designated record in a NARA-approved format. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.8.4 | The solution shall provide the capability to export designated records in bulk in a NARA-approved format. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.9 | The solution shall provide the capability to associate an appropriate records schedule to electronic records. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.9.1 | The solution shall provide the capability to associate electronic records in the solution with an approved retention authority (records schedule). | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.9.2 | The solution shall provide the capability for agency authorized users to identify any electronic records without an associated records schedule. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.4.9.3 | The solution shall provide the capability for agency authorized users to change the records schedule associated with the electronic record(s) to a different records schedule. | Stakeholder | Functional | Records Management - Disposition | Must | Approved |  | IT Tiered Requirements for Records Management
14.5 | The solution shall provide the capability to identify a record and its record status. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management
14.5.1 | The solution shall provide the capability to auto-identify/classify an electronic object's record status. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management | This functionality is intended to provide an algorithmic framework for auto-identification of records.
14.5.1.1 | The solution shall provide the capability to auto-identify/classify an electronic object's record status using user-supplied data. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management
14.5.1.2 | The solution shall provide the capability to auto-identify/classify an electronic object's record status using the file plan. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management
14.5.1.3 | The solution shall provide the capability to auto-identify/classify an electronic object's record status using the Organizational Unit. | Stakeholder | Functional | Records Management - Identification | Should | Approved |  | IT Tiered Requirements for Records Management
14.5.1.4 | The solution shall provide the capability to auto-identify/classify an electronic object's record status using the record content. | Stakeholder | Functional | Records Management - Identification | Could | Approved |  | IT Tiered Requirements for Records Management
14.5.1.5 | The solution shall provide the capability to auto-identify/classify an electronic object's record status using the file type. | Stakeholder | Functional | Records Management - Identification | Could | Approved |  | IT Tiered Requirements for Records Management
14.5.1.6 | The solution shall provide the capability to auto-identify/classify an electronic object's record status using machine learning. | Stakeholder | Functional | Records Management - Identification | Could | Approved |  | IT Tiered Requirements for Records Management
14.5.2 | The solution shall provide the capability for a user to identify the status of a record. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management | For example, Permanent, Temporary, Transitory, Non-Record, or Personal Papers.
14.5.3 | The solution shall provide the capability for authorized users to identify vital (essential) records. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management
14.5.3.1 | The solution shall provide the capability for authorized users to identify and periodically supersede obsolete copies of vital (essential) records with copies of current vital records. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management
14.5.4 | The solution shall provide the capability to identify an ingested record to allow classification of its record status based on the applicable retention rule. | Stakeholder | Functional | Records Management - Identification | Must | Approved |  | IT Tiered Requirements for Records Management | Record status: Temporary, Permanent, Transitory, Personal Records, Non-Record
14.6 | The solution shall provide the capability for agency authorized users to identify, associate, and manage metadata for electronic records. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management
14.6.1 | The solution shall provide the capability to capture the associated metadata of an electronic record that is compliant with NARA metadata standards. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | For example, in the header of the file or in a separate file, depending on the format of the record. Electronic records created within the solution must embed metadata about the record (unique identifier, creation time-stamp, format type and version, etc.) that are compliant with NARA metadata standards.
14.6.1.1 | The solution shall provide the capability to capture the parent record series as metadata to be associated with the electronic record. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | This allows staff to specify what record series the electronic records are a part of, to facilitate the mapping of the electronic records to the appropriate NARA records schedule and the associated retention period for that record series.
14.6.1.2 | The solution shall provide the capability to capture metadata to associate individual electronic records as being part of an aggregation of related records. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | This allows staff to group individual electronic records of the same into aggregates (e.g., case files) which potentially become a different record in its own right and may need to be managed in the system as such.
14.6.1.3 | The solution shall provide the capability for agency authorized users to update the metadata for an electronic record. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management
14.6.2 | The solution shall gather and maintain metadata on records' "location," unique hash values, record status/retention requirements, access/permission data, and other metadata to support a manage-in-place strategy for records management. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | Metadata will support manage--in-place activities, de-duplication, and version control.
14.6.3 | The solution shall provide the capability to identify, associate with records, and maintain metadata specific to special file types. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | For example, multimedia, moving and still images, audio, voicemail, ownership/copyright/release data, etc.
14.6.4 | The solution shall provide the capability to identify database metadata including: Last Updated Date, Owner of the database, Last Accessed Date, and Record Formats contained in the database. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | Note: This list includes only the metadata not covered in NARA 2015-04.
14.6.5 | The solution shall provide the capability to capture metadata identified by NARA metadata standards. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | Per NARA 2015-04, the following elements should be captured provided for each file or item included in a transfer (Appendix A, Metadata Element Definitions describes the specific elements and provides examples of their appropriate use): Identifier [File Name]. The complete name of the computer file including its extension (if present). (Please see Appendix B: Recommended File and Folder Naming Conventions.); Identifier [Record ID]. The unique identifier assigned by an agency or a records management system; Title. The name given to the record; Description. A narrative description of the content of the record, including abstracts for document-like objects or content descriptions for audio or video records; Creator. The agent primarily responsible for the creation of the record; Creation Date. The date that the file met the definition of a Federal record; and Rights. Information about any rights or restrictions held in and over the record including access rights such as national security classification, or personally identifiable information, Privacy Act, or Freedom of Information Act, or usage rights relating to copyright or trademark. Agencies should provide the following metadata elements, if they apply to the record being transferred: Coverage. The geographic and temporal extent or scope of the content of the record; and Relation. The relation element should be used if a record is composed of multiple files that form a logical record, or is a necessary component of another logical record. https://www.archives.gov/records-mgmt/bulletins/2015/2015-04.html
14.6.6 | The solution shall automate the capture of records management metadata. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | Records Management functionality shall be performed in the background without user involvement to the greatest extent possible.
14.6.7 | The solution shall provide the capability for agency authorized users to create custom tags. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management
14.6.8 | The solution shall provide the capability for agency authorized users to view records within cases along with their record metadata. | Stakeholder | Functional | Records Management - Metadata | Must | Approved |  | IT Tiered Requirements for Records Management | The ability to view record metadata for records within a case includes any user-applied tags.
14.7 | The solution shall provide the capability for agency authorized users to search for electronic records within the system. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management | These are searches that specifically support the needs of Corporate Records Management, as opposed to business users.
14.7.1 | The solution shall provide the capability for agency authorized users to search for electronic records by date. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.2 | The solution shall provide the capability for agency authorized users to search for electronic records by record author. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.3 | The solution shall provide the capability for agency authorized users to search for electronic records by disposition indicators. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.4 | The solution shall provide the capability to search within a particular search results set. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.5 | The solution shall provide the capability for agency authorized users to search by author/custodian, date, and keyword simultaneously when conducting e-discovery searches. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.6 | The solution shall provide the capability for automated identification and removal of duplicates and near duplicates from a search results set. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.7 | The solution shall provide the capability for agency authorized users to search on custom tags. | Stakeholder | Functional | Records Management - Search | Must | Approved |  | IT Tiered Requirements for Records Management
14.7.8 | The solution shall provide the capability to highlight search terms in responsive records. | Stakeholder | Functional | Records Management - Search | Could | Approved |  | IT Tiered Requirements for Records Management
14.8 | The solution shall have the capability to capture electronic records. | Stakeholder | Functional | Records Management - Capture | Must | Approved |  | IT Tiered Requirements for Records Management
14.8.1 | The solution shall have the capability to capture the discrete digital asset components of the record. | Stakeholder | Functional | Records Management - Capture | Must | Approved |  | IT Tiered Requirements for Records Management
14.8.2 | The solution shall provide the capability to automatically file records upon capture without user intervention. | Stakeholder | Functional | Records Management - Capture | Must | Approved |  | IT Tiered Requirements for Records Management
14.8.2.1 | The solution shall provide the capability to designate collections of records for auto upload. | Stakeholder | Functional | Records Management - Capture | Must | Approved |  | IT Tiered Requirements for Records Management
14.8.3 | The solution shall provide the capability to upload the metadata associated with a digital asset to the system. | Stakeholder | Functional | Records Management - Capture | Must | Approved |  | IT Tiered Requirements for Records Management
14.8.4 | The solution shall support the capability to move assets from an originating system to the enterprise records repository at a frequency defined by policy. | Stakeholder | Functional | Records Management - Capture | Must | Approved |  | IT Tiered Requirements for Records Management
14.9 | The solution shall provide the capability for agency authorized users to create and implement workflows in support of NARA Corporate Records Management activities. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.1 | The solution shall provide the capability for agency authorized users to use a template to notify recipients of a litigation hold. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.2 | The solution shall provide the capability for the recipients of a litigation hold to acknowledge the receipt of the hold. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.3 | The solution shall provide the capability for logging the acknowledgment of a litigation hold by recipient. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.4 | The solution shall provide the capability for automated reminders of litigation holds with acknowledgements at a time period determined by the agency authorized user implementing the hold. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.5 | The solution shall provide the capability for agency authorized users to send a notice releasing a litigation hold to affected recipients. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.6 | The solution shall provide the capability to support artificial intelligence in review for responsiveness in eDiscovery cases. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.9.7 | The solution shall provide the capability to support redaction of responsive records in eDiscovery. | Stakeholder | Functional | Records Management - Workflow | Could | Approved |  | IT Tiered Requirements for Records Management
14.1 | The solution shall support the transfer/migration of any/all records stored and managed in the system to another storage system should future needs dictate it, and as documented in 36 CFR 1234.30, Selection and Maintenance of Electronic Records Storage Media. | Stakeholder | Functional | Records Management - Data Migration | Must | Approved |  | IT Tiered Requirements for Records Management | See: https://www.ecfr.gov/current/title-36/chapter-XII/subchapter-B/part-1236/subpart-B. Also note that the contract should specify who bears the costs of such migration (in the case of a change to contract, and contractors), as well as ensure the large amount of data contained within the system can be supported for migration.
14.10.1 | The solution shall preserve all metadata when migrating and transferring records. | Stakeholder | Functional | Records Management - Data Migration | Must | Approved |  | IT Tiered Requirements for Records Management
14.10.2 | The solution shall preserve discovery case metadata when migrating and transferring records. | Stakeholder | Functional | Records Management - Data Migration | Could | Approved |  | IT Tiered Requirements for Records Management
15 | The solution shall be 99% available, 24 hours a day, 7 days a week, with the exception of scheduled maintenance downtime. | Stakeholder | Non-Functional | Availability | Must | Approved |  |  | Please refer to the contract for the Service Level Agreements (SLAs) specified in the contract for an externally hosted solution.
15.1 | The assets in the system must be immediately available to internal users for access and use on a routine basis. | Stakeholder | Non-Functional | Availability | Must | Approved |  | RXC (Conservation) and Heritage Science, ADAMS Business Need, 10/17/2025 | This supports the ability of internal users to access files regularly/frequently without prior notice or having to retrieve them from deep storage.
16 | The solution shall be compliant with Section 508 accessibility requirements and ensure a holistic user experience for customers with disabilities and users who rely on assistive technologies. | Stakeholder | Non-Functional | Accessibility | Must | Approved |  |  | Solution must be compliant to NARA policies regarding Section 508 of the Rehabilitation Act of 1973. Compliance is being measured by successful passage of applicable WCAG 2.0 and Level AA Success Criteria for electronic content. The solution also must successfully allow for assistive technology tools, such as screen readers or other means to ensure users are conveyed all information provided by the solution in a manner which is accessible to them. Note: It is expected that open source tools for assessing compliance will be used e.g. ANDI, AXE, WAVE, NVDA, Color Contrast Checker etc. Test methods may include: automated testing using code static evaluation tools, manual testing using screen reader tools, or hybrid testing using a combination of both options.
17 | The solution shall provide the capability for backup and recovery of the system. | Stakeholder | Non-Functional | Backup & Recovery | Must | Approved |  | APP B, Goals Reqt # 14 | This includes backup and recovery of the entire solution including assets and associated metadata.
17.1 | The solution shall provide the capability to restore digital special media content from a backup. | Stakeholder | Non-Functional | Backup & Recovery | Should | Approved |  | APP B, Goals Reqt # 14
18 | The solution shall be capable of storing a minimum of 495 terabytes (TB) of digital special media content with the ability to scale on demand. | Stakeholder | Non-Functional | Capacity | Must | Approved |  |  | This will support the ingest of NARA's existing inventory of 45 TB of digital special media assets in ADAMS, as well as planned growth in 2026 as follows: - 15 TB of corporate photo and video files (Employee Communications) - 427 TB of High Quality Digital Surrogate Intermediate Video and Audio Files (Research Services) - 6 TB of conservation and preservation files (Preservation Programs and Heritage Science) - 2 TB of other graphic images
19 | The solution shall support a minimum of 51 active users using the system concurrently to perform upload, search, and file management and delivery. | Stakeholder | Non-Functional | Capacity | Must | Approved |  | ADAMS Business Need, 10/17/2025 | This includes users from the following groups: - Employee Communications (MC) = 7 users - Conservation Branch (RPXC) = 18 users - Moving Image & Sound Preservation Branch (RPXM) = 10 users - Heritage Science in the Preservation Programs Division (RPX) = 6 users - A2 Analog Records Division (RRA) = 10 users
20 | Authorized National Archives and Records Administration (NARA) users shall be able to access the solution via NARA-approved web browsers. | Stakeholder | Non-Functional | Compatibility | Must | Approved |  | APP B, Goals Reqts, #2 Access | This supports the ability of users to connect to the system using NARANet connected PCs and laptops.
20.1 | The solution shall be accessible to a user using Microsoft Edge. | Stakeholder | Non-Functional | Compatibility | Should | Approved |  | APP B, Goals Reqts, #2 Access | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
20.2 | The solution shall be accessible to a user using Google Chrome. | Stakeholder | Non-Functional | Compatibility | Must | Approved |  | APP B, Goals Reqts, #2 Access | The browser versions to be supported will be dependent upon when the system is deployed into production and the browser versions supported in the NARA baseline at that time.
20.3 | The solution shall be accessible to a user using Safari. | Stakeholder | Non-Functional | Compatibility | Should | Approved |  |  | NARA authorized browsers are those supported in standard desktop image for NARA users including Microsoft Edge and Google Chrome. It is presumed that NARA IT support may not be able to provide user support for any issues encountered if using alternative browsers such as Safari.
21 | The solution shall support Internet Protocol version 6 (IPv6). | Stakeholder | Non-Functional | Compatibility | Must | Approved |  | ADAMS Business Case, 6/28/2019
22 | The solution shall provide the capability to migrate existing digital special media assets from multiple sources into the system. | Stakeholder | Non-Functional | Data Migration | Must | Approved |  | ADAMS Business Need, 10/17/2025 | This supports the need to migrate data from the existing/legacy ADAMS system for NARA corporate records, as well as migrate 200 TB of data from on premise NetApp storage, Snap servers, and external hard drives. This capability would only be needed if we move to a cloud-based solution.
22.1 | The solution shall utilize a standardized push/upload method to the NARA network rather than building bespoke integrations for every legacy data source. | Stakeholder | Non-Functional | Data Migration | Must | Approved |  |  | For example, using a standard SFTP, secure cloud sync, or standardized physical transfer.
23 | The solution shall be a web-based, Software as a Service (SaaS) system. | Stakeholder | Non-Functional | Hosting | Should | Approved |  | Stakeholder Meeting, 9/16/25
23.1 | If the solution is a SaaS solution, the underlying data store must be hosted by NARA and the solution must be able to connect to the NARA-hosted data store. | Stakeholder | Constraint | Hosting | Should | Approved |  | Application Development and Architecture Division (IA), 2/23/2026 | NARA needs to have control of the SaaS data storage environment so that we don't lose access to any data if/when migrations are necessary. This alleviates data migration concerns, should a contract renewal result in an alternative SaaS solution.
24 | The solution shall interoperate with multimedia editing and desktop publishing applications for editing photos, videos, and graphic images. | Stakeholder | Non-Functional | Interoperability | Should | Approved |  | RXC (Conservation) and Heritage Science, ADAMS Business Need, 10/17/2025 | If possible, NARA desires ADAMS integration with the following editing software: Adobe Lightroom Catalog, Nikon Camera Control Pro 2 software, Photoshop, Adobe Acrobat, and MS Office. If a selected product cannot be integrated via an out-of-the-box plugin or API available, then files will need to be downloaded and edited offline, outside of the system.
25 | The solution shall integrate with a service to allow for the collection of payment for copies made of digital special media assets. | Stakeholder | Non-Functional | Interoperability | Should | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | This supports the recovery of fees resulting from making copies of special media archival records that are in the custody of Research Services, which are ordered by the general public. Payment must not be required for all transactions since internal copy requests (i.e., those coming from within NARA itself) must not require payment. The payment could be part of the solution itself or it could integrate with a separate payment system like Pay.gov.
26 | The solution shall meet the performance criteria for activities conducted within the system. | Stakeholder | Non-Functional | Performance | Must | Approved
26.1 | The solution shall support the upload / ingest of up to 1.2 terabytes (TB) of data in a single batch process. | Stakeholder | Non-Functional | Performance | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | For context, the average ProRes4444 file size is 129 GB, with the a larger file at the top end being DPX files of 1.5 TB. The average MP4 50mbps file size is 4.4 GB. NOTE: 1.5 TB has been included as a placeholder based on input from the business stakeholders and Systems Engineering. However, we will need input from the network team to determine if this is feasible or if they recommend a different value. We will need the technical SMEs to evaluate whether the new SaaS vendor(s) offers the feature to adjust batch size.
26.2 | The solution shall support the upload of one-to-many files totaling up to two terabytes (2 TB) per eight (8) hour working day. | Stakeholder | Non-Functional | Performance | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | This equates to a required throughput of approximately 69 megabytes per second (MB/s).
26.3 | The solution shall support the sharing of one-to-many files of up to 1 terabyte (TB) each in size, at a rate of at least two terabytes (TBs) over eight (8) hours. | Stakeholder | Non-Functional | Performance | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | This includes the ability for the user to retrieve/download the files shared with them. Cloud-based architecture is desired. This requirement may be constrained by the recipient's network speed, which is a likely bottleneck.
26.4 | The solution shall respond within 50 milliseconds after entering data in any data entry field in the user interface. | Stakeholder | Non-Functional | Performance | Should | Approved
26.5 | The solution response time for navigating between screens in the user interface shall be less than 1 second. | Stakeholder | Non-Functional | Performance | Should | Approved |  |  | When the user commits a navigation action, the target is the requested page should be fetched/loaded within 1 second; which ensures navigation performance does not hinder user performance and task flow.
26.6 | The solution response time for returning search results shall be less than 2 seconds. | Stakeholder | Non-Functional | Performance | Should | Approved
26.7 | The solution shall meet the reporting response time performance targets identified by NARA. | Stakeholder | Non-Functional | Performance | Should | Approved
26.7.1 | The solution shall generate simple reports initiated by a user and display the report directly within the user interface within 5 seconds. | Stakeholder | Non-Functional | Performance | Must | Approved |  |  | This supports the ability of end users to run more simple reports and receive the generated report directly within the user interface in a short amount of time.
26.7.2 | The solution shall generate complex reports in the background and display a confirmation within the user interface within 3 seconds of initiation of the report. | Stakeholder | Non-Functional | Performance | Must | Approved |  |  | This support having an asynchronous processing mechanism for tasks involving large file sizes. Complex reports that are run in the background reports (initiation feedback <3 seconds, with completion notification via email).
26.7.2.1 | The solution shall send an email notification to the user who initiated a complex report when the report has completed. | Stakeholder | Non-Functional | Performance | Must | Approved
27 | The solution shall be scalable to support NARA's inventory of digital special media assets and future planned growth of 248 terabytes (TB) per fiscal year. | Stakeholder | Non-Functional | Scalability | Must | Approved |  | ADAMS Business Case, 6/28/2019 | The stated growth only includes basic storage and backup costs. NARA will also need to account for several other cost drivers to be factored into the total cost of ownership (TCO) analysis, including: 1. Network Egress/Ingress costs (for data transfer in/out of the system). 2. Compute costs for processing during ingest (generating proxies, metadata extraction). 3. Storage Tiering/Access Frequency: Defining how much is 'hot' vs. 'cold' storage impacts overall pricing model significantly.
28 | The solution shall be in compliance with NARA IT Security Contractual Requirements. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  | ADAMS Business Case, 6/28/2019 | NARA IT Security Requirements are included in NARA IT Security Requirements, Version 7.4, 11/18/2023; and Security and Privacy Requirements for IT Acquisitions, Version 1.2, 12/19/2023.
28.1 | For a Software as a Service (SaaS) solution, the Cloud Service Provider (CSP) offering should be FedRAMP authorized. If the CSP SaaS offering is NOT FedRAMP authorized, it must operate on a CSP Infrastructure as a Service (IaaS) or CSP Platform as a Service (PaaS) that is FedRAMP authorized. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  | Cyber Security and Information Assurance Division (IS), 02/26/2026 | FedRAMP authorization indicates that FedRAMP has packaged essential security information from a cloud service provider that can be used by an agency to make a determination whether or not to use that service.
28.2 | The solution shall authenticate users following NARA-approved access controls. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.2.1 | The solution shall use multi-factor authentication (MFA) to authenticate authorized NARA users for access using an approved NARA identity management and authentication service. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | For example, Microsoft Entra ID used with a PIV card. This needs to be determined by NARA management to ensure the selected service aligns with agency-wide security and policy mandates for internal staff access.
28.2.2 | The solution shall authenticate external users for access using an approved identity management and authentication service. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  | RRA (Analog Records Division), ADAMS Business Need, 10/17/2025 | For example, using Login.gov to provide external users access to paid, shared files and access for external vendors who will upload intermediate copies of files. This needs to be determined by NARA management to ensure the selected service aligns with agency-wide security and policy mandates for public access.
28.2.3 | The solution shall ensure that user credentials are encrypted in transit using industry-standard protocols (TLS 1.2 or higher). | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.2.4 | Authentication requests shall utilize secure, cryptographically signed tokens for all communication between components. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | For example, JWT for tokens.
28.2.5 | The solution shall not transmit raw credentials or sensitive authentication parameters in plaintext, via URL parameters/query strings, or through unencrypted headers. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.3 | The solution shall terminate an active user session after a certain period of user inactivity. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | Terminate a user session means to log them out.
28.4 | The solution shall disable a user account after a specified duration of no user login activity. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | This will allow accounts to be automatically disabled when they have not accessed the solution after N days of no login, where "N" is a number of calendar days that can be configured by a System Administrator. Users whose user accounts which were automatically deactivated due to extended inactivity would be directed to the Help Desk or other POC to restore access if required.
28.5 | The solution shall provide the capability to terminate a user account after a specified duration of being disabled. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.6 | The solution shall maintain an audit log (history) of all activities performed in the system. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.6.1 | The solution shall provide an audit log that tracks the date, time, filename, and user that modifies a digital special media record. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | The term modify means to upload/add, update, or delete a digital special media asset. Record actions associated with disabled/terminated accounts also need to be maintained, tracked, and be auditable.
28.6.2 | The solution shall provide the capability for an authorized user to search the audit log for modifications to digital special media content. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | For example, search log entries for all changes from user XYZ in the date range 3/29/2025 thru 3/30/2025.
28.6.3 | The solution shall provide the capability for an authorized users to view an audit log of user actions performed within the system on digital special media records. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.6.4 | The solution shall provide the capability for an authorized user to perform file integrity checks. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.6.5 | The solution shall provide the capability to push/export all audit and system logs to an external Security Information and Event Management (SIEM) system. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved
28.7 | The solution shall correctly display required information, disclosures, or notifications as per NARA Directive 802 or other applicable NARA policies. | Stakeholder | Non-Functional | Security & Auditing | Must | Approved |  |  | For examples, System of Record Notification (SORN).

## StandardValues
Type | Category | Priority |  | Status | Verification Method | Verification Status | UAT Status
Business | Functional | Must | Requirements that are CRITICAL to meeting the project's objectives | Approved | Inspection | Pass | Pass
Stakeholder | Non-Functional | Should | Requirements that are critical and should be included if possible, but which can be excluded | Deferred | Analysis | Fail | Fail
System | Constraint | Could | Requirements that are part of the project's scope and add or enhance project benefits | Draft | Test | N/A | N/A
Business Rule | N/A | Would | Requirements that do not have a significant impact on project benefits or could be considered as a “would like to have” | Obsolete | Demonstration
Certification
N/A

## Column Descriptions
Column Name | Column Descriptions | Required (Y/N?)
Req # | A unique identifier for the requirement. | Yes
Requirement Text | The text of the requirement. | Yes
Type | The type of the requirement, such as "Business" or "Stakeholder". Values: Business, Stakeholder, System, Business Rule | Yes
Category | The category of the requirement, such as "Functional" or "Non-Functional". Values: Functional, Non-Functional, Constraint, N/A | Yes; Use "N/A" for Business requirements.
Feature | The high-level function, capability, feature or other grouping that has meaning for the stakeholders. | Yes
Req Priority | The priority of the stakeholder requirement as assigned by the stakeholders. Values: Must, Should, Could, Would | Yes
Status | The status of the requirement. Values: Approved, Deferred, Draft, Obsolete | Yes
Target Release | The release in which the requirement will be developed. Note that this column may be blank and hidden from view upon the initial documentation of the requirements, but should be updated during the appropriate phase of the project. | No
Source | The source of the stakeholder requirement, such as "Business Case" or "Interview". | No
Notes | Pertinent additional information about the requirement. | Yes; do not do not delete this column, just leave it empty if notes are not needed.
Element | Used to indicate mapping of design elements (e.g., subsystem or class) that are relevant to the requirement. Requirements may map to more than one design element, in which case abbreviations or IDs are preferred over names when appropriate to the project, you may use multiple columns, one per type of design entity (e.g., subsystem). | Yes; when design elements are generated for the project at least one column (tracing) is required. Use "N/A" for Business requirements.
Iteration | The iteration in which the requirements will be/is developed. | Yes, when iterations are used for the project. "N/A" for Business requirements; when the column is not needed, delete it.
Verification Method | The method used to verify the requirement. Values: Inspection, Analysis, Test, Demonstration, Certification, N/A | Yes; Use "N/A" for Business requirements.
Verification Test Case / Step | The test cases to be used by NARA to verify the requirement. | Yes; Use "N/A" for Business requirements.
Verification Status | The output or final status after performing a verification test case on a requirement. Values: Pass, Fail, N/A | Yes; Use "N/A" for Business requirements.
Verification Criteria | The attributes used to verify or determine if the system element meets the requirement and satisfies the design. | No; Use "N/A" for Business requirements; when the column is not needed, delete it.
UAT Test Case | The test case used by NARA to validate the requirement. | Yes; Use "N/A" for Business requirements.
UAT Status | The output or final status after performing a UAT test case on a requirement. Values: Pass, Fail, N/A | Yes; Use "N/A" for Business requirements.
Validation Criteria | The attributes used to validate if the stakeholder requirement meets the business need. | No; Use "N/A" for Business requirements; when the column is not needed, delete it.