STATEMENT OF WORK

FOR

P-8A Operational Flight Trainer (OFT) Projection System Upgrade

DEPARTMENT OF THE NAVY

PROGRAM EXECUTIVE OFFICE PMA290, PMA205

NAVAL AIR SYSTEMS COMMAND

PATUXENT RIVER, MD 20670

Controlled by: Department of the Navy

Controlled by: Naval Air Warfare Center Training Systems Division (NAWCTSD)

CUI Category: CTI, EXPT

Distribution/Dissemination Control: D

POC: [IPTL name, phone number, email]

Program Office – PMA 290, PMA205

(or Designated Representative)

DISTRIBUTION STATEMENT D - Distribution authorized to the Department of Defense and U.S. DoD Contractors only for CTI and export controlled 29 August 2025.  Other requests for this document shall be referred to Commanding Officer, Naval Air Systems Command, (PMA290), 47123 Buse Road, Patuxent River, MD 20670 .

WARNING - This document contains technical data whose export is restricted by the Arms Export Control Act (Title 22, U.S.C., Sec 2751, et seq.) or the Export Control Reform Act of 2018 (Title 50, U.S.C., Chapter 58, Sec. 4801-4852).  Violations of these export laws are subject to severe criminal penalties.  Disseminate in accordance with provisions of DoD Directive 5230.25.

DESTRUCTION NOTICE - For unclassified, limited distribution documents, destroy by any method that will prevent disclosure of contents or reconstruction of the document.

1.	SCOPE	6

2.	APPLICABLE DOCUMENTS	6

2.1	Government Documents	6

3.	REQUIREMENTS	9

3.1	General	9

3.1.1	Program Management	9

3.1.1.1	Work Planning and Scheduling	9

3.1.1.2	Program Planning	9

3.1.1.3	Management and Technical Integrated Product Teams (IPTs)	9

3.1.1.4	Risk Management	9

3.1.1.5	Change Management	9

3.1.2	Cyber Security	9

3.1.2.1	Vulnerability Scans	10

3.1.2.2	STIGs, SRGs, SCAP Benchmarks	10

3.1.2.3	Plan of Action and Milestones (POA&M)	10

3.1.3	RAAF Cyber Security	10

3.1.3.1	General Requirements	10

3.1.3.2	Vulnerability Scans	11

3.1.3.3	STIGs, SRGs, and SCAP Benchmarks	11

3.1.3.4	Plan of Action and Milestones (POA&M)	11

3.2	Detailed Tasks	11

3.2.1	Common Baseline Updates	11

3.2.2	OFT Visual Display System (VDS) Modification	12

3.2.3	Pre-Modification Inspection (PMI)	12

3.3	Systems Engineering Processes	12

3.3.1	Requirements Analysis	12

3.3.2	Required Documentation	13

3.3.3	Traceability	13

3.4	Software Installation	13

3.4.1	Software Product	13

3.4.2	Media and Storage Devices	13

3.4.3	Cold Start Procedure Media	14

3.4.4	Automated Processes	14

3.4.5	Cold Start Execution	14

3.5	Reviews	14

3.5.1	Dry Run Execution	14

3.5.2	Post Award Conference (PAC)	14

3.5.2.1	Post Award Conference Completion Criteria	15

3.5.3	System Requirements Technical Interchange Meeting (TIM)	15

3.5.3.1	System Requirements TIM Entry Criteria	16

3.5.3.2	System Requirements TIM Completion Criteria	16

3.5.4	Critical Design Technical Interchange Meeting (TIM)	16

3.5.4.1	Critical Design TIM Entry Criteria	17

3.5.4.2	Critical Design TIM Completion Criteria	17

3.5.5	Test Readiness Assessment (TRA)	17

3.5.5.1	TRA Entry Criteria	17

3.5.5.2	TRA Exit Criteria	18

3.5.6	Defect Review Board (DRB)	18

3.5.6.1	Government Decision of Defect Correction	18

3.5.7	Integration Test Readiness Assessment (ITRA)	18

3.5.7.1	ITRA Entry Criteria	19

3.5.7.2	ITRA Exit Criteria	19

3.6	System Test and Evaluation	19

3.6.1	Responsibility for Tests	19

3.6.2	Test, Inspection, Examination Resources and Facilities	20

3.6.3	Test Procedures	20

3.6.4	Testing Interruptions Due to Safety Concerns	20

3.6.5	Testing Suspension Due to System Defects	20

3.6.6	System Stability	20

3.6.7	Tolerance Data	20

3.6.8	Test Log	21

3.6.9	Software Changes During Government Testing	21

3.6.10	Regression Testing	21

3.6.11	T&E Discrepancy Reporting System	21

3.6.12	STR Adjudication	22

3.6.13	T&E Program Components	22

3.6.13.1	Test Readiness Assessment (TRA)	22

3.6.13.2	DT-C1 (Developmental Test #1 – Milestone C)	22

3.6.13.2.1	DT-C1 Completion Criteria	22

3.6.13.3	Integration Test Readiness Review (ITRA)	22

3.6.13.4	IT-C1 Government Final Test Phase	22

3.6.13.4.1	IT-C1 Entry Criteria	22

3.6.13.4.2	IT-C1 Completion Criteria	23

3.6.13.5	RAAF ITRA	23

3.6.13.6	RAAF On-Site Installation Verification (OSIV) Test Phase	23

3.6.13.6.1	RAAF OSIV Completion Criteria	23

3.6.13.7	Follow-on Articles (Training Devices) Acceptance Testing	23

3.6.13.8	Test Results	23

3.7	Audits	23

3.7.1	Technical Documentation (TD), Technical Manual and Engineering Drawings Validation	23

3.7.2	Physical Configuration Audit (PCA)	24

3.7.2.1	PCA Entry Criteria	24

3.7.2.2	PCA Completion Criteria	24

3.8	Integrated Logistics Support (ILS) Program	24

3.8.1	Integrated Logistics Support Verification (ILSV)	24

3.8.2	Buy Through The Prime (BTTP)	25

3.8.3	Bill of Materials (BOM) for Logistics and Supply Chain Risk Management	25

3.8.4	Excess Trainer Material Disposal	25

3.8.5	Special Tools and Test Equipment	25

3.8.6	RAAF Excess Trainer Material Disposal	26

3.8.7	RAAF Parts Categorization	26

3.8.8	Technical Publications	26

3.8.9	Item Unique Identification (IUID)	27

3.8.10	Commercial Off-The-Shelf (COTS) Documentation	27

3.8.11	Proprietary Documentation	27

3.8.12	COTS License Rights	27

3.8.13	COTS Documentation	27

3.9	Facility Requirements	28

3.9.1	Safety Requirements	28

3.9.2	RAAF Cable Colors	28

3.9.3	Electrical and Mechanical	28

3.10	Training Program	28

3.10.1	Maintenance Training	28

List of Tables:

Table 1. NAS JAX ATD	6

Table 2. NAS WHI ATD	6

Table 3. RAAF ATD   	6

| Version Number | Date | Reference | Description of Changes |
| --- | --- | --- | --- |

Statement of Work

P-8A Operational Flight Trainer (OFT) Projection System Upgrade

# SCOPE

This Statement of Work (SOW) establishes the contractor tasks for the modifications of the P-8A Aircrew Training Device (ATD) - Operational Flight Trainer (OFT) Projection System located at Jacksonville, FL Integrated Training Center (ITC); Whidbey Island, WA Fleet Training Center (FTC); and Royal Australia Air Force (RAAF) Base Edinburgh, SA ITC.

NAS JAX Devices

Table 1. NAS JAX ATD

| Device | Total QTY on site | Total QTY on OFT Tech Refresh | Applicable Devices |
| --- | --- | --- | --- |
| Operational Flight Trainer (OFT) | 10 | 10 | OFT-1, OFT-2, OFT-3, OFT-4, OFT-5 OFT-6, OFT-7, OFT-9, OFT-10, and OFT-11 |

NAS WHI Devices

Table 2. NAS WHI ATD

| Device | Total QTY on site | Total QTY on OFT Tech Refresh | Applicable Devices |
| --- | --- | --- | --- |
| Operational Flight Trainer (OFT) | 7 | 7 | OFT-12, OFT13, OFT14, OFT-15, OFT-16, OFT-19, and OFT-21 |

RAAF Base Edinburgh

Table 3. RAAF ATD

| Device | Total QTY on site | Total QTY on OFT tech Refresh | Applicable Devices |
| --- | --- | --- | --- |
| Operational Flight Trainer (OFT) | 2 | 2 | OFT-17 and OFT -18 |

# APPLICABLE DOCUMENTS

The following documents form a part of this SOW to the extent specified herein.  In the event of a conflict between documents referenced herein and the contents of this SOW, the contents of this SOW take precedence.  Nothing in this SOW, however, supersedes applicable laws and regulations, unless a specific exemption has been obtained.

## Government Documents

SPECIFICATIONS:

Naval Air Systems Command (NAVAIR), Naval Aviation Training Systems Program Office (PMA290)/Naval Air Warfare Center Training Systems Division (NAWCTSD)

| PRF 260087 | Performance Specification for Visual Display System (VDS) |
| --- | --- |

STANDARD PRACTICES:

Department of Defense (DoD):

Safety Documents

| EM 385-1-1 | Safety and Health Requirements Manual |
| --- | --- |
| Copies of the above handbooks are available at https://www.usace.army.mil/Missions/Safety-and-Occupational-Health/Safety-and-Health-Requirements-Manual/ |  |

Configuration Audit Plan

| DI-SESS-81646B | Configuration Audit Plan |
| --- | --- |
| Copies of the above handbooks are available https://quicksearch.dla.mil/qsDocDetails.aspx?ident_number=204783 |  |

National Fire Protection Association (NFPA)

| NFPA-70 | National Electric Code |
| --- | --- |
| NFPA-70E | Standard for Electrical Safety in the Workplace |
| NFPA-101 | Life Safety Code |
| Copies of latest version these document are available from http://www.nfpa.org/Catalog/ or National Fire Protection Association, 11 Tracy Drive, Avon, MA 02322 |  |

OTHER PUBLICATIONS:

Code of Federal Regulations (CFR)

| 29 CFR 1910.147 | The control of hazardous energy (lockout/tagout) |
| --- | --- |
| (Occupational Safety and Health Administration (OSHA) regulations are downloadable from https://www.osha.gov/law-regs.html) |  |

Australia and New Zealand Standards

| BDA EHS Requirements – Contractor Management – T1300 |  |
| --- | --- |
| AS/NZS 3000:2018 | Reporting, Reutilization, and Disposal (Dec 2017) |
| AS/NZS 3820:2020 | Essential safety requirements for electrical equipment dated 25 Jun 2020 |

Australia Information Security Manual (ISM)

| ISM | Control: ISM-0926; Revision: 11; Updated: Dec-24; Applicable: NC, OS, P; Essential 8: N/A Non-classified, OFFICIAL: Sensitive and PROTECTED cables are coloured neither salmon pink nor red. Control: ISM-1718; Revision: 1; Updated: Mar-23; Applicable: S; Essential 8: N/A SECRET cables are coloured salmon pink. Control: ISM-1719; Revision: 1; Updated: Mar-23; Applicable: TS; Essential 8: N/A TOP SECRET cables are coloured red. |
| --- | --- |
| Copy of the above references are available at https://www.cyber.gov.au/sites/default/files/2025-12/Information%20security%20manual%20%28December%202025%29.pdf |  |

Defense Federal Acquisition Regulations Supplement (DFARS)

| DFARS 252.225-7048 | Export-Controlled Items (June 2013) |
| --- | --- |
| DFARS 252.211-7003 | Item Unique Indentification and Valuation |
| DFARS Clauses are downloadable from http://farsite.hill.af.mil/vfdfara.htm |  |

DoD and Department of the Navy (DoN) Security and Information Assurance (IA) Instructions, Manuals, Policy Memos, and Guidance Documents

| DoDI 8510.0 | Risk Management Framework (RMF) for DoD Systems, dated 19 July 2022 |
| --- | --- |
| Copy of the above Instructions are available from https://www.esd.whs.mil/ |  |
| CNSSI 1253 | Security Categorization and Control Selection for National Security Systems, dated 29 July 2022 |
| Copy of the above Instruction is available from https://www.cnss.gov/CNSS |  |
| NIST SP 800-53 Rev 5 | Security and Privacy bookmark://acronym/Controls for Information Systems and Organizations, dated September, 2020 |
| Copy of the above Instructions are available from https://csrc.nist.gov |  |

Naval Aviation Training Systems Program Office (PMA205)

| N/A | System Engineering Plan (SEP) Version 1.0 dtd 4 Oct 2022 |
| --- | --- |

# REQUIREMENTS

## General

### Program Management

The Contractor shall

- organize, coordinate, and control the program activities to ensure compliance with the contract requirements and the timely delivery of the required product and services;

- provide the necessary program management, systems engineering, design engineering, materials, services, equipment, facilities, testing, technical, logistics, manufacturing, and clerical support for the efforts described in this SOW for the P-8A ATD - OFT Projection System listed in section 1.

#### Work Planning and Scheduling

The Contractor shall

- develop maintain an Integrated Schedule that presents the Contractor’s plans and schedules to meet the requirements of the contract showing all program milestones events, reviews, data submittals, and deliveries P-8A ATD - OFT Projection System;

- prepare the Contractor’s Progress and Status Report in accordance with (IAW) CDRL BA02.

#### Program Planning

The Contractor shall define, document, manage, and apply program planning processes in accordance with the P-8A System Engineering Plan (SEP) version 1.0.

#### Management and Technical Integrated Product Teams (IPTs)

The Contractor shall

- participate in the following IPTs throughout the project lifecycle:

- Management/ Technical IPT (biweekly);

- Technical Working Group (biweekly) focus on technical design, systems integration, planning and executing PMI, and tests to verify and validate system performance and compliance with requirements;

- include both contractor and subcontractor personnel with expertise across functional areas relevant to the respective IPT’s objectives;

- operate in a collaborative environment where communication, information sharing, and decision-making are transparent and inclusive.

#### Risk Management

The Contractor shall

- conduct risk management to systematically control the uncertainty in the project’s ability to meet cost, schedule, and performance requirements;

- provide the Government visibility into the Contractor’s tools, assessment, mitigation, and control techniques;

- update issues related to risk management and contractual execution to include critical path items, engineering, and logistics milestones.

#### Change Management

The Contractor shall

- define, document, manage, and apply a process to accomplish change management;

- use Engineering Change Proposals (ECPs) to request changes to an approved product baseline.  The Contractor shall prepare the Engineering Change Proposal (ECP) IAW the CDRL AA07.

### Cyber Security

The Contractor shall

- deliver cybersecurity compliant upgraded trainer components that satisfies the DODI 8510.01 Risk Management Framework (RMF) security control set as defined in NIST SP 800-53 and for a CNSSI 1253.  The Security Categorization is defined for this National Security System as (Confidentiality = Moderate), (Integrity = Moderate), (Availability = Low) within Enterprise Mission Assurance Support Service (eMASS) package #S-4811;

- apply the cyber testing and reporting requirements to the upgraded trainer components for NAS Jacksonville and NAS Whidbey IAW CDRL AA06 and  use the latest Navy Security Control Assessor (SCA) Risk Management Framework (RMF) and Risk Assessment Guide (RAG).

- use DoD-authorized assessment tools to perform cybersecurity testing (e.g. Assured Compliance Assessment Solution (ACAS), Defense Information Systems Agency (DISA) Security Content Automation Protocol (SCAP) Tool, Evaluate STIG, STIG Viewer, HP Fortify or substitute source code scanning tool), document, verify, and validate each applicable operating system configuration;

- develop USN A&A artifacts using the templates that are approved by the ISSO. Submit the A&A artifacts IAW CDRL AA06.

- provide a CMMC Certificate IAW the CDRL AA06.

- harden all cyber devices by applying all patches and closing all STIGs.

- Provide justification for any unclosed STIG items is required if it conflicts with system functionality, mission needs, or safety. This justification shall be included in the POA&M, which must follow the guidelines of CDRL AA06 and the latest Navy Security Control Assessor (SCA) Risk Management Framework (RMF) and Risk Assessment Guide (RAG).

#### Vulnerability Scans

The Contractor shall

- scan the upgraded trainer components with approved vulnerability scanning tools as identified by the Designated Approval Authority (DAA)/Functional Authorizing Official (FAO), Authorizing Official (AO), or Information Systems Security Manager (ISSM);

- update the vulnerability scanner with the latest signatures and scanning engines prior to the execution of each vulnerability scan;

- conduct  scans pre-IT-C1 on training devices used for software development with authorized scanning tool and provide results in an approved format to the ISSO IAW CDRL AA06.

- handle the vulnerability scans in accordance with the System’s classification level.

#### STIGs, SRGs, SCAP Benchmarks

The Contractor shall

- Cyber harden the upgraded trainer components and provide results in an approved format to the ISSO IAW CDRL AA06.

- Non-compliant STIG, SRG, and SCAP Benchmark findings shall be documented in the System POA&M on a hardware/software release basis IAW the CDRL AA06.

- Implement STIGs, SRGs, and SCAP Benchmark updates into the System as they are released IAW section 3.1.2

- provide all STIG, SRG, and SCAP Benchmark artifacts to the ISSO. The format for these artifacts must be approved by the DAA/FAO, AO, and ISSM, and must comply with the latest Navy SCA RMF and RAG. All artifacts must be handled in accordance with the system's classification level, and any non-compliant findings shall be documented in the system's POA&M..

#### Plan of Action and Milestones (POA&M)

The Contractor shall

- develop a POA&M using the approved DAA/FAO, AO, or ISSO format IAW CDRL AA06. The POA&M shall be considered a ‘living’ document and the Contractor shall update it as required it throughout the contract performance, until device acceptance;

- create the POA&M with all Not Applicable Security Controls, All Non-Compliant Security Controls, and all Non-Compliant Vulnerability Findings as identified in the Vulnerability Scans, STIGs, SRGs, SCAP Benchmarks and include all required mitigation statements IAW the latest version of the Office of the Navy Security Control Assessor (SCA), Risk Management Framework (RMF), Risk Assessment Guide (RAG).

### RAAF Cyber Security

The Contractor shall adhere to the following cybersecurity requirements to ensure the delivery of compliant and secure trainer components.

#### General Requirements

The Contractor shall deliver cybersecurity-compliant upgraded trainer components that satisfy the DODI 8510.01 Risk Management Framework (RMF) security control set as defined in NIST SP 800-53 and for a CNSSI 1253. The Security Categorization for this National Security System is defined as (Confidentiality = Moderate), (Integrity = Moderate), and (Availability = Low).

The Contractor shall apply the cyber testing and reporting requirements to trainer components in accordance with (IAW) CDRL AA08 and use the latest Navy Security Control Assessor (SCA) Risk Management Framework (RMF) and Risk Assessment Guide (RAG). The Contractor will use DoD-authorized assessment tools to perform cybersecurity testing, such as the Assured Compliance Assessment Solution (ACAS), Defense Information Systems Agency (DISA) Security Content Automation Protocol (SCAP) Tool, Evaluate-STIG, STIG Viewer, HP Fortify, or a substitute source code scanning tool. The Contractor shall document, verify, and validate each applicable operating system configuration.

The Contractor shall develop USN Assessment and Authorization (A&A) artifacts using templates approved by the Information Systems Security Officer (ISSO) and submit them IAW CDRL AA08. Furthermore, the Contractor shall provide a Cybersecurity Maturity Model Certification (CMMC) Certificate IAW CDRL AA08.

The Contractor is required to secure all cyber devices by applying all patches and closing all Security Technical Implementation Guides (STIGs). Justification for any unclosed STIG items is required. This justification shall be included in the Plan of Action & Milestones (POA&M), which must follow the guidelines of CDRL AA08 and the latest Navy SCA RMF and RAG.

#### Vulnerability Scans

The Contractor shall scan trainer components with approved vulnerability scanning tools as identified by the Designated Approval Authority (DAA)/Functional Authorizing Official (FAO), Authorizing Official (AO), or Information Systems Security Manager (ISSM). The vulnerability scanner shall be updated with the latest signatures and scanning engines prior to the execution of each scan. The Contractor will conduct scans pre-IT-C1 on training devices used for software development with an authorized scanning tool and provide results in an approved format to the ISSO IAW CDRL AA08. All vulnerability scans shall be handled in accordance with the System’s classification level.

#### STIGs, SRGs, and SCAP Benchmarks

The Contractor shall secure the upgraded trainer components and provide results in an approved format to the ISSO IAW CDRL AA08. Any non-compliant STIG, Security Requirements Guide (SRG), and SCAP Benchmark findings shall be documented in the System POA&M on a hardware/software release basis IAW CDRL AA08. The Contractor will implement STIG, SRG, and SCAP Benchmark updates into the System as they are released IAW section 3.1.2. All STIG, SRG, and SCAP Benchmark artifacts shall be provided to the ISSO. The format for these artifacts must be approved by the DAA/FAO, AO, and ISSM, and must comply with the latest Navy SCA RMF and RAG.

#### Plan of Action and Milestones (POA&M)

The Contractor shall develop a POA&M using the approved DAA/FAO, AO, or ISSO format IAW CDRL AA08. The POA&M shall be considered a ‘living’ document, and the Contractor shall update it as required throughout the entire lifecycle of the System through to device acceptance. The POA&M will be created with all Not Applicable Security Controls, all Non-Compliant Security Controls, and all non-compliant vulnerability findings as identified in the Vulnerability Scans, STIGs, SRGs, and SCAP Benchmarks. It shall include all required mitigation statements IAW the latest version of the Department of the Navy SCA RMF and RAG.

## Detailed Tasks

The Contractor shall replace, deliver, and document a new projection system for the P-8A ATD OFTs, in accordance with the Performance Specification in PRF 260087 and as specified in section 1 of this SOW.

### Common Baseline Updates

The Contractor shall

- replace the USN and RAAF OFT Projection System to common hardware baseline and software baseline to the maximum extent practical; without degrading the existing OFT performance and operational requirements;

- ensure compatibility with the existing OFT interfaces, including hardware connections and software message protocols, of the current projection system;

- procure and deliver hardware of the same form, fit and function, ensuring compatibility with cybersecurity and operational requirements, where a common hardware baseline is not practical;

- release, integrate, install, deliver, and test P-8A country-specific updates (e.g., databases, libraries, configurations, etc.) separately, as specified in this SOW and in PRF 260087.

### OFT Visual Display System (VDS) Modification

The Contractor shall

- update, integrate, test, document and deliver new Out the Window (OTW) projectors, including the removal and replacement of existing OTW projectors and associated mounting hardware with a new projection system that meets the Performance Specification for VDS in PRF 260087. All removed existing projectors and hardware shall be disposed in accordance with section 3.8.4, and 3.8.7;

- provide an automatic-alignment system and calibration process that replaces the existing systems to support the new projection system and produces a visual display system image quality that meets the Performance Specification for VDS in PRF 260087 without manual intervention;

- modify or replace OFT hardware, including but not limited to sensors, mounts, cables, blackout, lenses and blending mechanisms needed to deliver the new projection system that meets the Performance Specification for VDS in PRF 260087;

- avoid structural modifications to the trainers by excluding changes to the structure holding the OTW projectors or to the external hull of the OFT trainer;

- only have one OFT down at a time to perform this upgrade.

### Pre-Modification Inspection (PMI)

The contractor shall

- lead and perform a PMI to establish and record the premodification configuration and performance of the OFT prior to Government turn over for modifications;

- develop PMI procedures based on the baseline requirements provided by the government, including existing Aceptance Test Procedures (ATPs) and specifications, and coordinate with the Government to determine the hardware and software baseline condition;

- execute transport delay objective tests to determine light sensor hardware condition, identify if transport delay issues are hardware or software-related, and verify the transport delay tests comply with the transport delay section of the performance specification;

- execute motion objective tests to verify compliance with the motion section of the performance specification;

- record and make available to the Government all of the PMI findings that could assist determining future projection system requirements such as but not limited to: software and hardware problems, anomalies, discrepancies, deficiencies, specification/performance requirements non-conformance.

## Systems Engineering Processes

The Contractor shall

- derive and decompose the requirements for the OFT projection system solution;

- transform the requirements into a product; and

- verify and validate that the functionality of the delivered OFT projection system meets the baseline performance specification and any modification performance requirements in PRF 260087.

### Requirements Analysis

The Contractor shall

- establish system requirements for the replacement of the projection system, derive and decomposed from this SOW and in the specification requirements in PRF 260087;

- perform the system requirements analysis tasks to transform the technical requirements into a set of measurable and verifiable system requirements;

- define the functional boundary of the system in terms of behavior;

- define each function that the system is required to perform;

- define contractual implementation constraints and unavoidable solution limitation;

- analyze the interaction between systems, subsystems, and components to derive the functional requirements;

- establish system requirements for internal and external interfaces;

- identify and analyze the system requirements on the operating environment;

- verify the requirements have been allocated to hardware items and software items according to the design criteria; and

- verify the derived and decomposed requirements are testable.

### Required Documentation

The Contractor shall deliver the following USN and RAAF Aircrew CDRL’s to document integration of the OFT projection system by this SOW.

- Acceptance Test Procedures (ATPs) CDRL AA01

- Software Product Package (SPP) CDRL AA02

- Product Engineering Design Data and Associated Lists (PEDDAL) CDRL AA03 and the associated Option Selection Worksheet (OSW)

- Requirements Traceability Verification Matrix (RTVM) CDRL AA04

- RAAF SPP CDRL BB01

- RAAF Product Engineering Design Data and Associated Lists (PEDDAL) CDRL  BB02 and the associated Option Selection Worksheet (OSW)

### Traceability

The Contractor shall

- define and manage traceability between the specification requirements, product design baseline, implementation configuration items, and test procedures.

- define and provide bi-directional traceability of requirements;

- provide the Government access to the traceability tool and its database; and

- prepare Requirements Traceability Verification Matrix (RTVM)in accordance with CDRL AA04.

## Software Installation

### Software Product

The Contractor shall

- deliver all commercial software licenses, associated documentation (e.g., manuals, installation procedures), physical media, and warranty information required to meet the performance defined in this SOW and in the VDS specification requirements in PRF 260087.

- deliver the contractor owned, P-8A source funded, non-proprietary executable code and configuration information. The contractor shall deliver contractor owned, non P-8A source funded and proprietary software as licensed binary libraries and applications.

- deliver the commercial item software with the associated vendor manuals, documentation, physical media, warranty information, licenses, and installation procedures. The contractor shall transfer the commercial item software licenses to the Government at device acceptance. The commercial item software licenses shall be valid at the time of DD250 of the first article P-8A Training Devices (JAX, and AUS).

- ensure the delivered materials clearly explain to end users how they can and cannot use the software, vendor manuals, physical media, documentation, and installation procedures consistent with the license rights granted under this contract. Commercial software licenses shall be transferred to the Government upon device acceptance and remain valid for five years beyond the acceptance/RFT of the first article P-8A Training Devices;

- prepare the Software Product Package (SPP) in accordance with CDRL AA02 and BB01. The contractor shall deliver all files required to build and compile executables.

### Media and Storage Devices

The Contractor shall

- provide a complete set of software media and storage devices required to perform the SPP procedures independent of software media and storage devices used by the contractor to develop, troubleshoot or operate the training system device during Government testing. The Government will retain custody and control of the media and storage devices created or used by the Government to accomplish testing;

- provide the additional media and mass storage devices necessary for the Contractor’s internal archiving, development, testing, and other engineering and CM purposes;

- deliver the commercial and noncommercial software, databases and the build tools required to perform the SPP procedures.

### Cold Start Procedure Media

The Contractor shall

- prepare a unique set of physical media for each computational subsystem;

- prepare the physical media required to perform each subsystem SPP procedure with labeling that:

- Is formatted consistently,

- Is permanently attached to the physical media,

- Includes the media’s identifying number

- Identifies device name,

- Identifies the software item name (s),

- Idetifies the software vendor name,

- Identifies the software version number,

- Identifies the software release date,

- Identifies the security classification,

- Identifies the Contractor’s configuration management identifier (if different than media’s identifying number),

- Identifies the media piece number, for multiple piece items (e.g. Disk 1 of 3, Disk 2 of 3),

- Includes the applicable export control marking.

### Automated Processes

The Contractor shall document, control, maintain, validate, and deliver all computational automated processes (e.g., scripts, batch files, job control language, kick-start, and slipstreamed media) in the same manner as software items.

### Cold Start Execution

The Contractor shall

- execute and verify all SPP procedures prior to the Test Readiness Assessment (TRA);

- provide technical support for the Government-led execution and verification of the SPP procedures prior to the Integration Test Readiness Assessment (ITRA) in JAX, the first Follow-on Articles Acceptance Test in WHI, and RAAF ITRA in EDN.

## Reviews

The Contractor shall

- conduct and participate in conferences and reviews and ensure subcontractor participation as required;

- Prepare conference agenda, presentation material, and conference minutes for required conferences and reviews, IAW the CDRL BA01;

- Ensure presentation materials are releasable to RAAF otherwise present it in a separate forum.

### Dry Run Execution

The Contractor shall conduct a comprehensive Dry Run in preparation for each Technical Interchange Meeting (TIM), Test Readiness Assessment (TRA), and Integration Test Readiness Assessment (ITRA). The purpose of each Dry Run is to ensure all systems, procedures, and personnel are prepared, thereby minimizing risks and uncertainty during the formal event. Each Dry Run shall, at a minimum, consist of a full presentation of all relevant entry criteria and material content for the upcoming event.

### Post Award Conference (PAC)

The contractor shall conduct the PAC within 30 calendar days after contract award. The purpose of the conference shall be to establish the framework for contractor and Government interaction during the performance period of the contract.  The contractor shall present and discuss:

- Introduction and contract overview;

- discussion and clarification of specification, SOW and CDRL requirements;

- CDRL delivery schedule and status;

- subcontract limitations;

- IMS and detailed schedule with status;

- Government Furnished Equipment/Government Furnished Information needs and status;

- IPT structure, membership, and responsibilities;

- action item reporting and status;

- team contact list (names, IPT memberships, phone numbers, and email addresses);

- risks, issues and mitigation plan;

- logistics Overview: The Logistics Overview shall include, but not be limited to, the following elements:

    - long lead item and spare identification and status;

    - reliability and maintainability (R&M) engineering reporting requirements;

    - discrepancy reporting requirements;

    - operations and maintenance technical documentation;

    - commercial product license rights;

    - data rights assertions;

    - facilities and infrastructure;

    - maintenance planning;

    - training;

    - technical Manual Initial Guidance Conference TMIGC;

Prior to the PAC, establish an Integrated Development Environment (IDE) repository to serve as the central location for official CDRL deliverables, and provide the Government with access to this repository.

#### Post Award Conference Completion Criteria

The contractor shall meet the following PAC completion criteria:

- the contractor assigned Request for Action (RFAs) are closed or adjudicated by the Government, and

- the program has obtained a level of risk accepted by the Government.

### System Requirements Technical Interchange Meeting (TIM)

The System Requirements TIM assesses the system functional requirements and ensures that the required system performance is fully decomposed and is traceable to the functional baseline in PRF 260087. At the System Requirements TIM, the Contractor shall:

- identify, present, and discuss the project schedule, including the hardware, software development schedule, specifying major milestones, current status, and critical path;

- provide a complete project organizational structure;

- identify resource availability to support the schedule;

- Identify relevant Subject Matter Experts (SMEs) to be used during development and testing;

- show that the functional requirements are traceable to the allocated baseline and methodology;

- show that the explicit and derived requirements are quantified and documented;

- address the following areas:

- Hardware,

- Software,

- Logistics,

- Technical Documentation,

- Risk, Issue and Opportunities Management

- Interoperability,

- Environment, safety, and occupational health

- Configuration Management,

- Security and Cybersecurity

- Test and Evaluation

- present the results of a comprehensive risk assessment for the production, integration, and test of the requirements in this contract;

- ensure that the system modifications under review can proceed into the next project phase.

#### System Requirements TIM Entry Criteria

The Contractor shall meet the following entry criteria prior to convening System Requirements TIM:

- PAC completion criteria has been met;

- Deliver System Requirement TIM presentation materials IAW CDRL BA01;

- Delivery and acceptance (when applicable), in accordance with CDRL requirements, of the CDRL items scheduled to be delivered prior to the System Requirements TIM;

- Availability RTVM showing traceability of requirements including the requirements derived from the results of the analysis performed per para. 3.3.4;

- Project risk have been identified and mitigation plans are being executed for each risk; and

- The functional baseline is established.

#### System Requirements TIM Completion Criteria

The Contractor shall meet the following Systems Requirements TIM completion criteria:

- System Requirements TIM RFAs have been resolved and closed.

- The required technical areas have been presented.

- The Requirements analysis traceability performed per para. 3.3.4 has been accepted by the Government.

- Functional requirements, as disclosed, will satisfy the training objectives.

- System functional definition and functional decomposition is detailed enough to support detailed design.

- Processes and metrics are in place.

- Risks are known and are manageable for implementation of the functional requirements into detailed design.

- Program schedule is executable within the anticipated cost and technical risks.

- Program is properly staffed

### Critical Design Technical Interchange Meeting (TIM)

The Contractor shall

- conduct a Critical Design TIM. The Critical Design TIM is for the Contractor and Government to formally review the activities and work products generated by the Contractor during the performance of the trainer modification design stage in order to develop the product baseline, and to verify that the systems are ready to proceed into the hardware assembly, and integration phase;

- present the finalized requirements traceability from the requirements to the product baseline;

- explicit and derived requirements are quantified and documented;

- facility and infrastructure planning;

- The following items shall be topics of discussion and presentation at the Critical Design TIM:

- Modified system hardware and software design, including:

  - Computational system,

  - HW and SW Interfaces,

  - Network,

  - Software tools,

  - Open architecture, including design modularity and commonality,

- Project status: resource availability to support the schedule, current status vs. critical path

- Project problem and risk areas, recommended solutions, evaluation of alternatives, and/or mitigation plan

- Teardown, pack, and ship criteria,

- Logistics design aspects and concerns,

- IUID marking of training device equipment and Initial Support Kit,

- Parts management program status,

- Cybersecurity,

- Test and Evaluation,

    - traceability from design documentation to sub-system test requirements;

    - product baseline test procedures;

    - defined mission validation scenarios;

    - discrepancy reporting process;

    - discrepancy adjudication process;

- Safety assessment

#### Critical Design TIM Entry Criteria

The Contractor shall meet the following entry criteria prior to convening the Critical Design TIM:

- Deliver Critical Design TIM presentation materials IAW CDRL BA01.

- CDRL items scheduled to be delivered prior to the Critical Design TIM have been delivered and accepted (when applicable) IAW CDRL requirements.

- Program Risks and their respective mitigation plans are in place, being executed, and manageable for implementation of the functional requirements into a final production design.

- Trade-off analyses have been completed if applicable.

- Logistics analysis has been completed and plans have been implemented.

#### Critical Design TIM Completion Criteria

The Contractor shall meet the following production Critical Design TIM completion criteria:

- CDRL items that were part of the Critical Design TIM entry criteria have been satisfactorily discussed.

- Updated risk assessments and risk mitigation plans have been satisfactorily discussed.

- Risks and their respective mitigation plans are in place and manageable for implementation of the functional requirements into a product baseline evolution.

- Program schedule is executable within the anticipated cost and technical risks.

- Program is properly staffed.

- Critical Design TIM Request for Actions (RFAs) have been resolved and closed.

- An updated Critical Design TIM presentation incorporating feedback and changes identified during the Critical Design TIM.

- An executable schedule has been presented.

- Product baseline has been established.

### Test Readiness Assessment (TRA)

The Contractor shall

- Conduct TRA in the time between the Critical Design TIM and the beginning of DT-C1 as directed by the Government;

- Assess the readiness of the training system and the test objectives, processes, documentation and facilities;

- Present and discuss the following at TRA:

  - Status of risks;

  - Design changes since the Critical Design TIM;

  - Installation and checkout process to show the system is integrated, operational, and ready for test;

  - Program schedule;

  - CDRL status;

  - Updated RTVM;

  - Test program resources (e.g. personnel, facilities, test environment, software, tools, test assets);

  - Status of issues (if applicable);

  - All System Trouble Reports (STRs) noted from the final System Integration Test have been provided to the Government;

  - Results of Contractor-led execution of SPP procedures.

  - Detailed test schedule;

  - SPP procedure results and documentation; and

  - Cyber Security scanning results and documentation

#### TRA Entry Criteria

Prior to TRA, the contractor shall

- Deliver TRA presentation materials IAW CDRL BA01;

- Ensure all applicable CDRLs have been delivered;

- SPP procedures have been executed with results provided to the Government;

- All applicable Cyber scans have been executed with Government participation; and

- Confirm plan for testing has been established and ATPs have been accepted by the Government.

#### TRA Exit Criteria

The Contractor shall attain Government concurrence that the following TRA completion criteria have been met:

- Test Logs and ATPs have been successfully updated per Government comments;

- Baseline configuration has been verified;

- TRA RFI / RFA have been closed out; and

- The Contractor has demonstrated that the installation and checkout process for system integration has been completed and is ready for test.

### Defect Review Board (DRB)

The Contractor and Government DRB co-chairs will prepare an agenda at least 24 hours prior to the DRB and collect artifacts.

The Contractor shall

- identify a Contractor DRB co-chair;

- conduct DRB meetings at the end of each test event;

- provide Government DRB chair with agenda inputs at least 24 hours prior to DRB;

- defer to the Government as the final authority on System Trouble Report (STR) priority

- categorize all defects by impacts against an established training objective or by impact against system stability

- manage of STRs, which consists of maintaining the STR reporting system to include entering, modifying and developing STRs;

- document and send to the Government for correction all defects against GFE / GFI / GFX;

Table 4. Defect Categorization Table

| Priority | Applies if a problem could |
| --- | --- |
| 1 | Prevent the accomplishment of an essential capability Jeopardize safety, security, or other requirement designated “critical” |
| 2 | Adversely affect the accomplishment of an essential capability and no work-around solution is known |
| 3 | Adversely affect the accomplishment of an essential capability and a work-around is known Note on Priority 3 defects, workarounds are only valid if being executed by an instructor and/or system administrator. Any defect causing the student to execute a procedure differently than aircraft procedures (i.e. NATOPS/NATIPS) is a Priority-2 defect unless explicitly downgraded by the Government. |
| 4 | Result in user/operator inconvenience or annoyance but does not affect a required operational or mission-essential capability Result in inconvenience or annoyance for development or maintenance personnel but does not prevent the accomplishment of the responsibilities of those personnel |
| 5 | Any other effect |

#### Government Decision of Defect Correction

The Contractor shall

- correct all STRs as directed by the government unless otherwise adjudicated during DRB, prior to the entry into the next testing milestone;

- label STRs not selected for correction by the Government as “DRB Deferred STRs” within the Contractor’s Discrepancy Reporting System;

- disposition DRB deferred STRs as a “New STR” may be selected for correction at future DRBs

### Integration Test Readiness Assessment (ITRA)

The Contractor shall:

- Conduct an ITRA prior to commencement of USN IT-C1 and RAAF OSIV as directed by the Government;

- Present and discuss the following during ITRA:

- Installation and checkout process to show the system is integrated, operational and ready for test;

- Detailed test schedule;

- Updated requirement traceability to ATPs to verify specification requirements have been tested;

- Updated test log;

- USN DT-C1 test results, including completed ATPs & STRs;

- All applicable software versions;

- Summary of all outstanding STRs.

#### ITRA Entry Criteria

The contractor shall attain Government concurrence that the following have been satisfied as entry criteria prior to proceeding into the TRAs:

- Deliver ITRA presentation materials IAW CDRL BA01;

- Updated ATPs, to include all corrections discovered throughout previous test events, have been submitted to the Government;

- All tests procedures agreed upon by the Technical IPT have been run as evidenced by the existence of contractor test logs;

- Corrections resulting from testing have been incorporated into the baseline prior to follow-on testing;

- A complete Government-led execution of SPP procedures has been performed including documented step by step results; and

- All STRs not corrected from previous test events have been adjudicated by the Government PM.

#### ITRA Exit Criteria

The contractor shall request and receive Government concurrence that the TRA has been completed by satisfying the following completion criteria:

- Contractor test logs and records demonstrate that a complete run of the ATPs has been executed;

- The Integrated Test Team has been identified to include applicable personnel names and functions for team members involved in testing;

- Contractual CM processes have been followed, and contractor generated CM logs are available for Government review/inspection;

- Baseline configuration has been established and verified;

- Agreed plan for IT-C1 has been established and ATPs have been accepted by the Government; and

- Discrepancy reporting system’s STR database is up to date.

## System Test and Evaluation

The contractor shall

- establish a T&E program to ensure verification and validation of system performance, functionality, and compliance with the requirements of this SOW and the Performance Specification in PRF 260087;

- ensure all test components are executed IAW Government Test Plan (GTP); and

- ensure all test data is captured IAW section 3.6.13.8.

### Responsibility for Tests

The Contractor shall

- designate a Contractor Test Director (TD) to coordinate with the Government TD;

- report and document incidents (e.g. safety, facility, operations, urgent communications and findings) to the Government TD;

- lead the execution of the DT test milestones, with government participation;

- support in the IT test milestones, with the government leading execution;

- provide materials and test equipment required for execution of necessary test procedures;

- terminate testing at the request of the Government TD; and

- terminate testing when there is a concern about safety of personnel and/ or equipment.

### Test, Inspection, Examination Resources and Facilities

The Contractor shall

- furnish the inspection and equipment, and Contractor personnel to conduct testing at USN/RAAF sites, to ensure that the training system meets the requirements of this contract;

- ensure the Contractor personnel, test equipment, support equipment, spare assemblies, parts, and test logs are available for the entire test event.

### Test Procedures

The contractor shall

- develop or update applicable Acceptance Test Procedures (ATPs) to verify the Performance Specification in PRF 260087;

- develop ATP using the methods of analysis, inspection, demonstration and test to ensure thorough evaluation of the TS;

- execute and validate the ATPs prior to the start of the DT-C1 test milestone;

- prepare and deliver the ATPs IAW CDRL AA01.

### Testing Interruptions Due to Safety Concerns

The Contractor shall

- have the authority to stop testing during test events when anyone raises a safety concern;

- immediately cease testing and report safety concerns to the Government test team if a safety concern is raised during testing; and

- resume testing after requesting and receiving concurrence from the Government test team that the safety concern has been cleared.

### Testing Suspension Due to System Defects

The Contractor shall

- have the authority to suspend testing during Developmental Testing (DT) if a defect causes the system or subsystems to become unusable/untestable or inoperative in a way to prevent further reliable testing;

- use the following guidelines to determine if the test event should be suspended:

  - High Priority STR that is terminal: Does the STR preclude further testing of the trainer such that the problem requires correction prior to continuation of testing?

  - Numerous major/moderate level STRs: Does the accumulation of major STRs affect functionality in numerous areas of the trainer? Do the problems interrupt executions of the test to the point that time would be better spent evaluating trainer issues than to continue testing?

  - Excessive Total STRs: Does the total quantity of all STRs degrade trainer operation to the extent that testing or training cannot proceed uninterrupted without an excessive amount of workarounds?

  - System Stability or Maintenance events: Does the accumulation of the number of system hot starts or warm starts, or down time for maintenance preclude a continuation of the planned testing evolution?

- defer to the government for testing suspension during Integration Testing (IT)

### System Stability

The contractor shall implement a design that does not reduce system stability. The System Stability is defined as the state in which the training device can operate with minimal interruptions. Minimal interruption is defined as a training device discrepancy that can be identified and corrected within a timeframe that allows for successful completion of mission training objectives (i.e., restart (“hotstart”) subsystem, clear memory, etc.) over the remaining time allotted.

- No more than one restart per device subsystem, per event.

- No more than two device subsystem restarts per event.

- Recovery to original simulation state before failure shall not exceed 30 minutes.

- Combined recovery time throughout event shall not exceed 45 minutes.

### Tolerance Data

The contractor shall

- identify test tolerances for pass / fail criteria; and

- identify test tolerances and the source from which the specified tolerances are derived in the ATPs for each applicable criteria.

### Test Log

The Contractor shall

- prepare and maintain a log of subsystem and system discrepancies found during test events;

- begin the entries of the test log at the start of DT-C1 testing, continuing for all following test events and follow-on articles;

- record STR sign off by the Government test representative after a successful retest; and

- make the test log available to the Government upon request.

### Software Changes During Government Testing

The Contractor shall

- obtain Government authorization prior to making changes to software baselines during DT and IT events;

- maintain configuration control of software baselines used during DT, IT and Follow-on test milestones;

- provide proof to the Government that proposed software baseline changes do not display signs of regression by Contractor regression testing; and

- report any design changes that resulted from the baseline change.

### Regression Testing

The Contractor shall support the Government regression testing for verification that hardware and software configuration changes have not adversely affected the trainer functionality, as a result of the following conditions:

- when a new software load is installed;

- to verify STR corrections;

- when the trainer load/disks are rebuilt (cold start);

- when reverting to a previous baseline;

- when a hardware change has the potential to affect complex interfaces in an unpredictable way; and

when the Government needs to verify that the trainer software baseline has not been corrupted.

### T&E Discrepancy Reporting System

The Contractor shall

- document all defects as STRs from Government provided STR collection method while executing all T&E program components and regression testing to include all follow-on articles;

- provide access to their discrepancy reporting system to the Government upon request;

- provide exports as requested by the Government;

- make all STRs, both Contractor generated and Government generated, that are being tracked in its reporting system viewable and searchable from a Government Navy-Marine Corps Intranet (NMCI) computer;

- obtain final adjudication decision of all STRs from the Government DRB Chair;

- implement and utilize a discrepancy reporting system for reporting and tracking (identification, assignment, status, progress, resolution) of STRs discovered during the T&E Program Components. The discrepancy reporting system shall include at a minimum:

- STR Number

- Status (Open, Closed, No Planned Correction, Out of Scope, etc.)

- Description to include:

    - Device where defect was found

    - Subsystem where defect was found

    - Defect details including how it was found and steps to duplicate

    - Workaround

    - Location/Venue discovered (Ex. JAX, etc.)

    - SW version discovered (w/ applicable Hardware P/Ns as needed)

    - Recommendation (if needed) to include workaround in operator documentation

- Work Notes to include all status updates and DRB recommendations

- Priority Level in accordance with Table 5: Defect Categorization Table.

- ATP Section, if applicable

- Requirement the STR is linked to

- Impact to training objective

- Correction Plan (to include SW Build it will be corrected in if applicable)

- Date Identified

- Disposition (New STR, Duplicate Entry, Existing Request, Retest, etc.,). Disposition categories will be determined at Technical IPT meetings.

### STR Adjudication

The Contractor shall correct the STRs discovered in the current test phase before entering into the next test event, unless adjudicated at the DRB.

### T&E Program Components

The T&E program for the first article build shall consist of the test phases described below.

- TRA – Test Readiness Assessment

- DT-C1 (Developmental Test  –Post Milestone C)

- ITRA – Integration Test Readiness Assessment

- IT-C1 (Government Final Test Phase) (JAX)

- RAAF ITRA

- RAAF OSIV (EDN)

#### Test Readiness Assessment (TRA)

The contractor shall conduct a TRA IAW section 3.5.4

#### DT-C1 (Developmental Test #1 – Milestone C)

The combined Contractor/Government test team shall conduct DT-C1 on 1st article USN device and 1st article AUS device. The Contractor shall

- perform a complete run of the Acceptance Test Procedures (ATP) to cover the new functionality (See 3.2) and regression IAW CDRL AA01;

- lead a review of the test log at the end of each day of DT testing;

- use SMEs provided by the Government for the execution of ATPs.

##### DT-C1 Completion Criteria

The Contractor shall demonstrate that DT-C1 has been completed IAW 3.4.13.8 and by satisfying the following completion criteria:

- Cyber Security evaluation IAW section 3.1.2;

- ATPs have been executed, signed off and delivered as-run ATPs to the Government;

- Regression test series has been run after the final STRs are ready for re-test and closing documentation has been signed off by the Government test team;

- System Stability has been demonstrated as acceptable, as determined by the Government Test Director IAW with Section 3.4.6;

- CM baseline (software and hardware) has been maintained throughout test event;

- The Contractor’s Test Director and Government’s Test Director have signed off testing as complete;

- All STRs have been documented, assigned a priority and been adjudicated at DRB.

- Present documented DT-C1 results at the ITRA.

#### Integration Test Readiness Review (ITRA)

The contractor shall host a ITRA IAW section 3.5.6

#### IT-C1 Government Final Test Phase

IT-C1 will focus on the ATP runs for record and verifying DT-C1 STR corrections.  The Contractor shall

- support the IT-C1 test phase that will be conducted IAW the Government Test Plan (GTP)as discussed in the technical meetings.

##### IT-C1 Entry Criteria

Prior to entering IT-C1 the Contractor shall demonstrate the following:

- Government led execution of SPP procedures have been successfully performed to establish the final software baseline ;

- STR adjudicated for correction have been completed and software changes have been incorporated into the software product;

- Gain concurrence that the ITRA completion criteria has been successfully completed prior to entering IT-C1.

##### IT-C1 Completion Criteria

The Contractor shall demonstrate IT-C1 has been completed in accordance with 3.4.13.8 and by satisfying the following completion criteria:

- Cybersecurity verifications have been successfully performed;

- All STRs identified during testing have been corrected or adjudicated;

- Regression testing has been conducted after the final STRs are ready for test and closing documentation has been signed off by the Government test team;

- CM baseline (software and hardware) has been maintained throughout IT-C1 Test Event;

- CM discrepancies found during IT-C1 have been identified for correction or adjudication;

- The contractor’s QA representative, contractor’s test manager and the Governmnet’s IPT have signed off testing as complete.

#### RAAF ITRA

The contractor shall conduct an ITRA IAW section 3.5.6, between the completion of Critical Design TIM and prior to commencing RAAF OSIV.

#### RAAF On-Site Installation Verification (OSIV) Test Phase

RAAF OSIV will focus on the ATP runs for record.  The Contractor shall support the RAAF OSIV test phase in RAAF Base Edinburgh that will be conducted IAW the Government Test Plan (GTP) as discussed in the technical meetings.

##### RAAF OSIV Completion Criteria

The Contractor shall demonstrate RAAF OSIV has been completed IAW GTP with all results delivered IAW 3.4.13.8 and by satisfying the following completion criteria:

- Cybersecurity verifications have been successfully performed;

- All STRs identified during testing have been corrected or adjudicated;

- Regression testing has been conducted after the final STRs are ready for test and closing documentation has been signed off by the Government test team;

- CM baseline (software and hardware) has been maintained throughout RAAF OSIV Test Event;

- CM discrepancies found during RAAF OSIV have been identified for correction or adjudication;

- The contractor’s QA representative, contractor’s test manager and the Governmnet’s IPT have signed off testing as complete.

#### Follow-on Articles (Training Devices) Acceptance Testing

The Contractor shall support all regression tests for follow-on articles at each site.

#### Test Results

For all test events to include follow-on articles acceptance testing, the Contractor shall:

- record defects that comply and do not comply with the specification and requirements as STRs, IAW Section 3.4.11;

- deliver As Run ATPs and Test Inspection Report IAW CDRL AA05; and

- present through the DRB all STRs found in the current test event prior to the commencement of the next test component.

## Audits

### Technical Documentation (TD), Technical Manual and Engineering Drawings Validation

The Contractor shall

- perform validation on the Training Device (TD) , technical manuals, and Engineering Drawings prior to all documentation deliveries. This validation shall also apply to all TD and/or source data delivered under this contract, as follows:

  - Final data delivery shall be validated against the as-built training device.

  - All procedural data (i.e., operating and maintenance procedures, including checkout, alignment, removal and replacement instructions, troubleshooting, and associated scheduled (preventive) maintenance) shall be validated by actual demonstration using correctly configured system/equipment hardware.

  - Non-procedural data (including principles of operations, provisioning data, and computer-generated lists such as wiring lists) and Government-furnished source data shall be validated by comparison to engineering source data.

- Assist with Government verification.

Any deviation to the above validation requirements requires formal written approval by the Contracting Officer. The Government will not accept unvalidated data for use unless specifically authorized in writing by the Contracting Officer. Specific instructions regarding disposition of data that has not been validated will be provided as required.

### Physical Configuration Audit (PCA)

The Contractor shall

- Provide assistance in the development of a verification plan and schedule, when requested;

- support the Government led PCA after completion of IT-C1 and RAAF OSIV on first article device deliveries at NAS JAX, NAS WHI and RAAF Base Edinburgh on a date determined by the IPT;

- disconnect electrical power prior to the start of PCA;

- comply with the OSHA lockout-tagout requirements specified in 29 CFR 1910.147;

- provide the personnel, equipment, and facilities necessary to support the Government-conducted examinations;

- disassemble training system (TS) equipment to facilitate the PCA;

- reassemble TS equipment at the completion of the PCA;

- responsible for providing access to areas of the trainer not normally accessible.

- document, categorize and correct discrepancies unless otherwise adjudicated by the DRB;

- correct deficiencies recorded by the Government, or a plan for correction has been developed and approved by the Government prior to receipt and acceptance by the Government of the training devices; and

- All CDRL items scheduled to be delivered prior to PCA have been delivered and accepted IAW CDRL AA03, BB02, EA01, EA02, EA03, EA04, EB01, EB02, EB03 and EB04

The Government reserves the right to perform additional PCAs deemed necessary to determine compliance with design documentation requirements. The Government will determine the disposition of each deficiency.

#### PCA Entry Criteria

The Contractor shall gain Government concurrence to enter the PCA by demonstrating the following:

- Trainer hardware installation by the Contractor is complete including a succesful IT-C1 and RAAF OSIV events.

- PCA technical data products, CDRLs AA03, BB02, EA01, EA02, EA03, EA04, EB01, EB02, EB03 and EB04, have been made available by the Contractor to the cognizant PCA participants prior to the review.

- Current risk assessment has been provided.

#### PCA Completion Criteria

The Contractor shall submit the Configuration Audit Summary Report IAW CDRLs DA02 and  DB02.

## Integrated Logistics Support (ILS) Program

### Integrated Logistics Support Verification (ILSV)

The Contractor shall

- Participate in the Government-led ILSV, which the Government's inventory and verification of each ATD - OFT Projection system at the device sites NAS JAX, NAS WHI, and RAAF Base Edinburgh, in conjunction with the PCA;

- conduct a physical inventory of all deliverable items and equipment, including technical manuals and training documentation, drawings, tools, test and support equipment, and spare and repair parts (including those procured by the Government).

- carry out the ILSV using the Training Device Inventory Checklist/Record as a master control document for all inventoried items, with the Government witnessing and participating throughout the ILSV;

- ensure all CDRLs and data requirements are updated and delivered, including the Training Device and Inventory Checklist/Record (TD ICL/R) IAW CDRL DA03 and DB03.

### Buy Through The Prime (BTTP)

When required, a Provisioned Items Order(s) (PIO) will be used to procure a supply support package.  The Contractor shall

- order, receive, inspect, store, package, and deliver PIO initial spares concurrently with the training device(s);

- provide items that are the same as, interchangeable with, or meet the form, fit, and function requirements of the items included in the delivered TS and other deliverable hardware;

- determine and ensure that these items are manufactured and configured identically to like items of the respective device(s);

After delivery to site, the Government reserves the right to test all or a portion of the PIO(s);

- replace all failed spares and spares delivered on the PIO(s) that do not meet Form, Fit, and Function;

- replace the affected spares with new spares that match the changed trainer hardware at no additional cost to the Government, in the event the Contractor initiates hardware changes that affect Government funded spares already procured under PIO(s).

### Bill of Materials (BOM) for Logistics and Supply Chain Risk Management

The Contractor shall prepare a Bill of Materials (BOM) for Logisctics and Supply Chain Risk IAW CDRLs  (USN – CA01) and (RAAF CB01) respectively. The contractor shall procure the required materials in support of the USN and RAAF scope of work under their corresponding awarded material CLINs.

### Excess Trainer Material Disposal

The Contractor shall be responsible for the complete disposition and disposal of all excess trainer device hardware and software, including peripherals, ancillary equipment, supplies, and spares associated with the trainer. The following requirements shall apply:

- Prior to disposal of any hardware, software, peripherals, ancillary equipment, supplies, and spares, the Contractor shall inventory and prepare a list identifying all trainer items. The Government will identify all items, hardware, software, peripherals, ancillary equipment, supplies, and spares that must be excluded from disposal no later than 5 days after receipt of list from Contractor. This approved list will be returned to the Contractor.

  - the GFP legacy configuration items excluded from disposal shall be returned to the Government as soon as the contractor has analyzed current function. These items to a Government representative, located at NAS Jacksonville, FL, NAS Whidbey Island, WA as designated by the PCO;

- The Contractor shall, as part of the trainer equipment disposal task, remove all liquids including hydraulic fluids, oils, and other contaminates, using a method that complies with all federal, state, and local base regulations, including all necessary chain of custody documentation. The Contractor shall clean and sanitize all areas that liquids or contaminates were used or stored. A Government representative will be the final authorizing authority as to acceptability for the sanitized area.

- Upon completion of this disposal task, the Contractor shall provide the Government with a certificate that certifies all trainer material, hardware, software, peripherals, ancillary equipment, supplies, spares, and contaminates were disposed of in compliance with federal, state, and local base regulations.

### Special Tools and Test Equipment

The contractor shall

- utilize common tools to install and remove the projector’s system unless they are inadequate and the Government approves the use of special tools;

- utilize common tools for equipment maintenance unless they are inadequate and the Government approves the use of special tools;

- if special tools are required and approved, provide and deliver all Special Tools and Test Equipment specifically developed for use with the training devices acquired under this contract

### RAAF Excess Trainer Material Disposal

The Contractor shall be responsible for the complete disposition and disposal of all excess trainer device hardware and software, including peripherals, ancillary equipment, supplies, and spares associated with the trainer. The following requirements shall apply:

- Prior to disposal of any hardware, software, peripherals, ancillary equipment, supplies, and spares, the contractor shall inventory and prepare a list identifying all trainer items. The Government will identify all items, hardware, software, peripherals, ancillary equipment, supplies, and spares that must be excluded from disposal no later than 5 days after receipt of list from Contractor. This approved list will be returned to the contractor. The contractor shall, as part of the trainer equipment disposal task, remove all liquids including hydraulic fluids, oils, and other contaminates, using a method that complies with all federal, state, and local base regulations, including all necessary chain of custody documentation.

  - the GFP legacy configuration items excluded from disposal shall be returned to the Government as soon as the contractor has analyzed current function. These items to a Government representative, located at RAAF Edinburgh, as designated by the PCO;

- The contractor shall clean and sanitize all areas that liquids or contaminates were used or stored. A Government representative will be the final authorizing authority as to acceptability for the sanitized area.

- Upon completion of this disposal task, the contractor shall provide the Government with a certificate that certifies all trainer material, hardware, software, peripherals, ancillary equipment, supplies, spares, and contaminates were disposed of in compliance with the Commonwealth of Australia, and Australia Department of Defense regulations and policies.

### RAAF Parts Categorization

The Contractor shall

- conduct categorization of parts IAW DFARS 252.225-7048 for RAAF Aircrew Training Devices including Support Equipment to the Line Replaceable Unit level as documented in the Technical Publication (SIM, TSSD, PMS, and COTS);

- conduct categorization of parts based upon identified Line Replaceable Units and any end item that is anticipated to be exported or reimported to support removal, return to the US for repair and return to Australia;

- determine United States Munition List (USML), Commerce Control List (CCL), and Export Control Classified Number (ECCN) categorization;

- document parts categorization as part of the RAAF PCA Summary Report IAW RAAF CDRL DB02.

### Technical Publications

The Contractor shall

- develop or revise the existing Technical Manuals (TM), Training Documents (TD), and associated documentation with OFT Projection System Upgrade only, which shall consist of all documentation and drawings to operate, repair, and maintain the OFT projection system consistent with the Government’s maintenance concept as described in the TSR Requirements and defined in paragraph 3.1.1;

- deliver Technical Manuals/Engineering Drawings IAW the following CDRLs:

- USN ATD - OFT

    - Product Engineering Design Data and Associated Lists (PEDDAL) CDRL AA03 and the associated Option Selection Worksheet (OSW)

    - Product System Interface Manual (SIM) IAW CDRL EA01.

    - Planned Maintenance System (PMS) IAW CDRL EA02.

    - Training System Support Document (TSSD)  IAW CDRL EA03.

    - Commercial Off-the-Shelf (COTS) Manuals and Associated Supplemental Data IAW CDRL EA04

- RAAF ATD - OFT

- RAAF Product Engineering Design Data and Associated Lists (PEDDAL) CDRL  BB02 and the associated Option Selection Worksheet (OSW)

- System Interface Manual (SIM) IAW CDRL EB01.

- Planned Maintenance System (PMS) IAW CDRL EB02.

- Training System Support Document (TSSD)  IAW CDRL EB03.

- Commercial Off-the-Shelf (COTS) Manuals and Associated Supplemental Data IAW CDRL EB04

### Item Unique Identification (IUID)

The Contractor shall

- comply with the Defense Standardization Program (U.S. Code Title 10, Section 2451 - 2456), that requires the achievement of the highest practicable degree in the standardization of items and practices used throughout the Department of Defense (DOD);

- comply with the parts standardization program that defines the management controls to minimize the number of unique parts in the design and maximize the use of Government standard parts;

- assign an IUID to the Training System (TS) and a separate IUID to the Initial Support Kit (ISK) , and recording the IUID data into the Wide Area Workflow (WAWF) system;

- display the IUID barcodes for the TS and ISK in accordance with the marking requirements of Military Standard (MIL-STD) -130 (Series) specifications;

- document the TS IUID barcode, the ISK IUID barcode, and the drawing parts listing capturing ISK range and depth in the PEDDAL.

### Commercial Off-The-Shelf (COTS) Documentation

The Contractor shall

- provide COTS documentation in standard American English. The Government is not requiring COTS deliveries for common equipment (i.e. keyboards, mice, monitors, video cards, switches) unless that equipment requires special modifications or set up, if the COTS manual includes detailed difficult troubleshooting procedures, or if the COTS contains detailed operational procedures required for the operation of the equipment.

- Ensure that all COTS documentation conforms to contract requirements.

- Review the documentation and correct deficiencies or deviations in the manuals prior to the submission.

- Ensure that all COTS documentation contains:

    - Operation Instructions

    - Testing and Troubleshooting Procedures

    - Schematics

    - Parts Listings

    - Maintenance Pertinent Information

### Proprietary Documentation

The Contractor shall inquire with each third party COTS Original Equipment Manufacturer (OEM) about the availability of the documentation for Government use. The inability to provide this documentation or declaring this data to be proprietary, and, as such, not available to the Government, constitutes in the disqualification of the use of their equipment in the device and a rejection of the COTS submission.

### COTS License Rights

The Contractor shall

- obtain on behalf of the Government, license rights from the COTS OEM for all copyrighted or  data rights restricted COTS manuals delivered to the Government under the contract IAW CDRLs EA04 and EB04;

- affix a statement from the COTS OEM to the COTS data granting the licenses/rights to the Government to host on a Government system, reproduce, and distribute copies of any copyrighted data. Letters from the OEM or emails from the OEM granting permission to the Government the use of the copyrighted and proprietary data for the COTS delivery are considered an acceptable document;

- ensure that the letters are addressed to the Government Procuring Contracting Officer.

### COTS Documentation

The Contractor shall not, without the written approval of the Contracting Officer, incorporate any copyrighted or proprietary data in the technical data delivered under this contract. The only authorized delivery of copyrighted data is if the Contractor is the copyright owner or has obtained for the Government the license rights necessary to perfect a license or licenses in the deliverable data, and has affixed a statement of the license or licenses obtained on behalf of the Government and other persons to the data transmittal document.

## Facility Requirements

The contractor shall update OFT system heat load to the current Trainer Facility Report (TFR) IAW CDRL DA01 and DB01.

### Safety Requirements

For USN sites, the contractor’s works are subject to compliance with  EM 385-1-1, NFPA-101, NFPA-70, NFPA-70E and 29 CFR 1910 requirements.

For RAAF Facilities, the contractor works are subject to compliance with BDA EHS Requirements - Contractor Management – T1300, AS/NZS 3000:2018, and AS/NZS 3820:2020. The Contractor shall

- provide a statement of conformance for hazardous materials in the device upgrades is in compliance with Australia health and safety regulations;

- ensure system, subsystem safety to protect participants, equipment and facilities during, trainer development, integration, inspection, testing, audit events;

- meet with representatives of the Contracting Officer to discuss and develop mutual understandings relative to the administration of safety, prior to commencement of the work.

### RAAF Cable Colors

The contractor shall use designated cable colors for the projection system to be installing in RAAF facility IAW the Information Security Manual (ISM).

### Electrical and Mechanical

The Contractor shall

- verify sufficient facility provided electrical power and cooling to properly operate the TS;

- conform to the standards outlined in UFC 3-520-01 and UFC 3-580-01 when electrical and/or mechanical work is required.

## Training Program

### Maintenance Training

The contractor shall

- present a TS operator training course on the complete functionality, utilization, and operation of the device;

- conduct an over the shoulder training at the training system installation site prior to device acceptance (DD250);

- use the SIM, TSSD, PMS, COTS, and PEDDAL as the controlling documents for the training courses;

- provide a course instructor who is knowledgeable of the training system and the technical data;

- provide courses that are a combination of classroom (75 percent) and hands-on training (25 percent).