Section C - Description/Specification/Work Statement

STATEMENT OF WORK

CDC’s Resources for Improvement of Surveillance and Emergency Response (RISER)

- BACKGROUND AND NEED

The Centers for Disease Control and Prevention (CDC) is undergoing transformation under the FY2026 President’s Budget, which reforms the agency to focus on its core mission: supporting infectious disease surveillance, outbreak investigations, preparedness and response, and maintaining the Nation’s public health infrastructure.  This realignment ensures that CDC’s resources are directed toward early detection of public health threats, timely intervention, and prevention of disease escalation, ultimately strengthening the health and safety of Americans.

CDC’s public health surveillance systems form the foundation of the nation’s defense against health threats.  These systems provide vital insights into disease trends and are critical to proactively identifying and addressing public health challenges.  National and state-based surveillance platforms, supported by robust laboratory networks, enable CDC to detect risk factors, guide interventions, and prevent outbreaks from becoming epidemics or pandemics.

To support this mission, CDC’s laboratory scientists operate across 200 laboratories in the United States.  The CDC’s Resources for Improvement of Surveillance and Emergency Response (RISER) contract is designed to support two of CDC’s infectious disease-focused national Centers:

- the National Center for Immunization and Respiratory Diseases (NCIRD), and

- the National Center for Emerging and Zoonotic Infectious Diseases (NCEZID).

These Centers lead laboratory-based surveillance, deploy diagnostic assays, and conduct applied research to understand disease distribution, determinants, and burden across diverse populations.

The RISER contract builds upon the success of the CDC Influenza Reagent Resource (CDC-IRR) and its impact during responses to outbreaks such as the 2009 influenza A(H1N1) pdm09, Zika (2015), SARS-CoV-2 (2020), Mpox (2022), Ebola (2022), and the influenza A(H5N1) (2022-2025), to name a few.  In 2019, the program’s scope was expanded beyond influenza to encompass bacterial and non-influenza viral pathogens of public health significance.  This expansion enabled the rapid deployment of critical reagents and materials to public health laboratories and research partners during health emergencies.

Today, RISER will be a cornerstone of CDC’s modernized surveillance infrastructure.  It will support core agency priorities by ensuring the availability of quality reagents, supporting early detection and facilitating rapid response to domestic and international health threats, helping fulfill CDC’s mission under the President’s FY2026 vision for a stronger, more responsive public health agency.

Additional Program Participation:

While the primary scope of RISER is to support NCIRD and NCEZID, RISER may, upon CDC approval, be used to support additional CDC programs for limited-scope activities during public health emergencies or to address emerging surveillance needs.

Such participation will only occur through issued task orders, with clearly defined deliverables, cost ceilings, and timelines. Contributions from these programs may include direct funding or cost-sharing arrangements to support authorized activities.

Period of Performance Duration:

In accordance with FAR 17.204, the base and option periods for this contract are intentionally structured with varying durations. This approach allows CDC to align contract performance with program phases, fiscal year budget cycles, and operational priorities, providing the flexibility needed to meet evolving public health requirements.

II.	PROJECT OBJECTIVES

The primary core objectives of this contract are:

- to produce or acquire high-quality stocks of reference pathogens, positive controls, detection kits, genomic sequencing components, proficiency panels, and other similar types of surveillance and research reagents in direct support of CDC-developed assays and surveillance platforms;

- to ensure that these reagents, and any other materials critical to the performance of public health laboratory surveillance activities, are reliably available to CDC, its public health laboratory partners, and approved research collaborators for the characterization of circulating and novel pathogens;

- to sustain the operational capacity to rapidly scale reagent acquisition, production, and distribution in support of domestic and global public health emergencies;

- to establish and maintain secure infrastructure for real-time data exchange across contractors and with CDC, including the ability to receive and process data uploads from external partners (e.g., genomic sequencing files, proficiency panel results), and to transmit validated data to appropriate CDC programs for analysis or regulatory action;

- to enable visualization of CDC-generated analysis outputs derived from RISER-submitted laboratory data in dashboard formats, accessible through the RISER website or associated secure platforms. This includes incorporation of historical data dashboards developed by CDC, as well as future analytic summaries tied to genomic surveillance, reagent validation, and/or proficiency testing results submitted by RISER registrants. The contractor shall ensure secure integration and display functionality, in coordination with CDC-led analysis pipelines.  All software, tools, and modules used for the visualization, processing, or display of CDC-generated analysis outputs shall undergo documented validation prior to deployment, consistent with CDC’s Quality Management System (QMS) requirements and, where applicable, FDA 21 CFR Part 11 or 21 CFR Part 820 validation standards.  The contractor shall maintain validation records and make them available to CDC upon request.

The optional objectives of this contract are:

- to develop and validate scientific workflows and technology transfer protocols in support of new diagnostic assay design and platform advancement for characterization of pathogens;

- to procure and manage ancillary reagents required for the performance of CDC-developed diagnostic kits and platforms. Routine procurement of off-the-shelf commercial reagents by the contractor shall not be included in base contract operations.  Recipient laboratories are expected to source these materials independently, except when the optional task is exercised.  For selected laboratories, CDC or its designated agent may procure and maintain a small cache of emergency-use ancillary reagents for distribution.

- SCOPE OF WORK

The contractor shall produce or otherwise acquire, characterize, store, and distribute CDC-furnished pathogens and other reagents essential to the performance of CDC-developed diagnostic assays that directly support the agency’s mission of infectious disease surveillance, outbreak response, and public health infrastructure. Materials covered under this contract include live and inactivated viruses, bacteria, vector-borne pathogens, nucleic acids, antisera, proteins, cell lines, hybridomas, and monoclonal antibodies, as detailed in Appendix A – Deliverables.

To support molecular diagnostic testing efforts, the government may authorize the contractor to work with government pre-qualified subcontractors under multiple award task order mechanisms. Unless otherwise directed, task orders issued for molecular test production must comply with the quality specifications outlined in Appendix B – Quality Specifications.

RISER reagents reinforce CDC’s core mission under the FY 2026 President’s Budget by supporting early detection of infectious threats, enabling rapid outbreak response, and sustaining public health laboratory infrastructure. These reagents facilitate real-time surveillance, validation of CDC-developed assays, and uninterrupted diagnostic capacity during both routine operations and emergency deployments.

To ensure responsiveness to public health priorities, the RISER reagent catalog will be continuously updated throughout the contract period. The contractor will be responsible for maintaining a real-time inventory system that reflects current availability, emerging threats, and surveillance platform alignment.

RISER may be activated to support emergency operations initiated at the Division, Center, or CDC Emergency Operations Center (EOC) level. Activation authority may be exercised by the Contracting Officer (CO) upon written directions from authorized CDC officials at any of these levels. The contractor shall maintain readiness to scale operations consistent with the level of activation and CDC direction.

All reagents produced under this contract shall comply with the quality specifications listed in Appendix B – Quality Specifications and be manufactured in accordance with recognized national or international standards, such as International Organization for Standardization (ISO) 9001, ISO 13485 and U.S. current good manufacturing practices (cGMP), or equivalent frameworks. Detailed batch records must be retained and made available to CDC upon request. Deliverables may include Food and Drug Administration (FDA) -regulated materials such as in vitro diagnostic kits. CDC reserves the right to conduct annual site reviews to verify contractor compliance with FDA Quality Management System Regulations and 21 CFR Part 820.  CDC also reserves the right to review contractor corrective and preventive actions (CAPAs), and to conduct evaluations of contractor processes and performance related to quality management, manufacturing, testing, storage, distribution, or data integrity as necessary to ensure compliance with contract requirements.

Upon approval by CDC, RISER reagents that meet all defined quality requirements shall be made available to registered users via a secure, contractor-managed RISER website. This website must remain fully integrated with CDC’s Customer Relationship Management (CRM) system to enable order submission, track logistics, and generate required reporting. The contractor shall make all distribution-related data, including reagent-level material and shipping costs, delivery metrics, and associated customer service resolutions, available to CDC in accordance with contract-defined data delivery formats and schedules. This data shall be maintained in audit-ready systems with secure user access and formatted for regular ingestion by CDC’s CRM and analytics platforms.

To support end-to-end surveillance and public health response, the contractor shall also enable secure, real-time ingestion of laboratory-generated data from RISER registrants and surveillance partners. This includes the ability to receive genomic sequencing files, assay performance results (e.g., proficiency testing data), and post-distribution reagent validation outputs. These data shall be securely processed, logged, and made accessible to CDC programs for analysis, regulatory evaluation, or outbreak response coordination. The contractor shall establish Application Programming Interface (APIs) and/or secure web upload mechanisms for real-time submission and shall support metadata tagging, system integration, and audit trails in accordance with CDC-defined formats.

This Statement of Work is supported by task-detailed information (Appendix C - Detailed Task Descriptions (Tasks 1-12)), which include full task-level requirements, quality specifications, and deliverables.  Offerors are required to review these appendices in full when preparing proposals.

Task orders will vary in size, generally ranging from $X,XXX to approximately $X,XXX,XXX.

The government retains the authority to reallocate surge responsibilities between contractors when surge capacity limits are reached to ensure continuity of RISER operations during declared emergencies.

The period of performance for the base and each option period is defined in Section ( ). These periods are of varying lengths to meet programmatic and operational requirements and will be evaluated and priced at the time of award in accordance with FAR 17.207.

Contract Structure:

This contract is structured as a hybrid Indefinite Delivery/Indefinite Quantity (IDIQ) to provide the flexibility necessary to meet CDC’s evolving operational needs. Task orders under this contract may include:

- Firm-Fixed-Price (FFP) task orders for predictable, routine functions such as warehousing, inventory tracking, website operation, customer service, standard reporting, and procurement of a limited cache of ancillary reagents;

- Cost-Plus-Incentive-Fee (CPIF) task orders for complex, surge-related, or technically advanced tasks, including high-priority pathogen production, rapid assay development, and surge activities associated with emergency responses, where performance outcomes such as delivery time, efficiency, or quality will be incentivized;

Award-term incentives are optional government-issued extensions or pricing benefits tied to exceptional contractor performance.  Incentives may be offered based on:

- Responsiveness during public health emergencies;

- Efficient surge activation and inventory management;

- Quality control compliance and first-pass rates;

- Cross-domain coordination and minimized transition risks.

- Time-and-Materials (T&M) task orders for urgent labor-based activities, particularly in response scenarios where scope and deliverables are not yet fully defined;

- Optional award-term incentives for outstanding contractor performance in areas such as surge responsiveness, cost management, operational continuity, and mission alignment.

Award-term incentives will be applied through a formal annual performance review process led by the Contracting Officer (CO), Contracting Officer’s Representative (COR), and Subject Matter Experts (SMEs). Contractors will be evaluated against specific Key Performance Indicators (KPIs) (Appendix D – Key Performance Indicators) established in this Statement of Work, including but not limited to:

- ≥95% of orders shipped within CDC-mandated timelines;

- ≥98% first-pass Quality Control (QC) pass rates;

- Demonstrated surge activation within 10 business days of government notice;

- ≥99.95% availability for RISER IT systems;

- Timely and complete reporting (Weekly, Monthly, and Annual Reports) with <2% material error rate;

- Documented participation in cross-Domain coordination activities (e.g., PMRs, Interface Control Documents [ICDs] updates, emergency exercises).

Annual reviews will score contractor performance on each KPI using a government-approved scoring rubric. Incentives, which may include award-term extensions or pricing benefits, will be granted to contractors achieving an overall performance rating of ‘Excellent’ or higher across at least 90% of the KPIs. The government reserves the right to withhold incentives if significant deficiencies are observed or if corrective actions remain unresolved.  Repeated temperature excursions, storage failures, or other material breaches attributable to contractor negligence or non-compliance may result in reductions to performance-based payments, disqualification from award-term incentives, or other contractual remedies as determined by the government.

- DOMAIN-BASED PERFORMANCE AREAS - OVERVIEW

Offerors may propose for one or more Domains listed below.  Offerors proposing for multiple Domains must demonstrate distinct capabilities, cost structures, and organizational segregation as required.  CDC reserves the right to award Domains to combined or separate contractors.  Submissions must include:

- A complete technical proposal and cost proposal per Domain proposed;

- Acknowledgement of any interdependencies or shared infrastructure between Domains proposed; and;

- Affirmation of ability to integrate with other awardees should partial award occur.

Offerors proposing on multiple Domains must identify any shared infrastructure (e.g., facilities, data centers, personnel, logistics systems) across their submissions. Proposals must explain how infrastructure will be integrated to avoid duplicative costs and ensure operational efficiency.  The government reserves the right to adjust or disallow overhead charges if shared resources are not clearly justified or if they considered duplicative charges.  Note that each awardee is expected to designate a coordination liaison and participate in weekly integration meetings to ensure cross-Domain alignment and prevent gaps.

To ensure seamless coordination across awarded Domains, the CDC reserves the right to conduct integration reviews prior to task order execution and may designate a centralized Program Integrator to support inter-domain continuity and reduce transition risk.

Independently and not as an agent of the government, the contractor shall provide all management, labor, facilities, materials, supplies, and equipment necessary to operate and maintain the “Resources for Improvement of Surveillance and Emergency Response (RISER)” as set forth below.  Each Domain (A–D) shall include Optional Contract Line-Item Numbers (CLINs) to enable activation of surge task orders in accordance with the Surge Scaling Option described in this Statement of Work. These optional CLINs provide the government with flexibility to rapidly increase production, logistics, IT, or customer support capacity in response to emergency or high-priority operational needs, without modifying the baseline scope of core activities.

During government-directed surge activations or at the conclusion of the contract period, all Domain A–D contractors shall coordinate to ensure continuity of RISER operations. Each contractor is responsible for executing its respective surge and transition activities in alignment with CDC-approved plans, while maintaining real-time data synchronization, inventory visibility, and communication across Domains. Contractors shall participate in joint planning sessions, integration meetings, and transition reviews as required to support unified response, minimize operational disruption, and enable orderly handoff of materials, data, and systems to successor entities or other RISER awardees.

The scope of work includes these Domains, some of which may not be funded in all performance periods:

- Domain A: Core Reagent Production and Catalog Management (FFP and CPIF Eligible)

  - Reagent acquisition, characterization, Quality Assurance (QA)/ Quality Control (QC);

  - Production planning, inventory, surge capability;

  - Establishing and maintaining Standard Operating Procedures (SOPs) and batch records;

  - Operating and updating the RISER reagent catalog;

  - Conduct stability testing and shelf-life assessments for all RISER reagents produced or acquired under this contract, in accordance with CDC-approved protocols and quality specifications (Appendix B).  Stability testing applies to both routine catalog reagents and emergency response products, with results integrated into inventory management systems.

NOTE: 1) One vendor must own all aspects of SOPs, QA/QC, and production flow to ensure accountability; 2) Domain A shall focus exclusively on reagent manufacturing and catalog management.  Storage, inventory warehousing and shipping responsibilities shall reside under Domain B to ensure modularity and cost containment.

Coordination with Domain B:

All activities related to reagent storage, bulk inventory warehousing, and outbound shipping shall be performed under Domain B. The Domain A contractor shall ensure completed reagents, along with associated Certificates of Analysis (COAs) and documentation, are transferred to Domain B facilities in accordance with CDC-approved timelines and quality protocols. Coordination shall occur through documented transfer logs, shared inventory records, and participation in scheduled cross-domain meetings.

- Domain B: Facility Operations and Logistics (FFP Eligible)

  - Facility management, Select Agent registration, FDA compliance;

  - Climate-controlled storage, equipment, backup systems;

  - Domestic/international shipping logistics;

  - Compliance with International Air Transport Association/International Civil Aviation Organization Dangerous Goods Regulations (IATA) and National/International regulatory shipping requirements;

  - Management of the emergency ancillary cache.

NOTE: 1) This Domain ensures physical infrastructure and cold-chain resilience.  Procurement of ancillary reagents is not a core contract requirement and may only be exercised by the government through a separately issued task order.  Offerors shall not assume procurement of ancillary reagents as part of baseline technical or cost proposals.  If such a task order is exercised, any associated storage or distribution activities will be performed only in accordance with the scope and terms of that task order.  Core production, storage, and shipping of CDC-supplied reagents do not depend on activation of the ancillary procurement task; 2) This Domain supports repository functions including physical storage, inventory control, and shipment execution, but not manufacturing or catalog oversight.  Contractors proposing on this domain must coordinate with Domain A manufacturers to ensure real-time material handoff and traceability.  In addition, contractors shall coordinate with Domain C to ensure that all distribution, inventory, and material handoff data are captured within the integrated data systems to support decision-making, auditability, and reporting requirements across CDC programs.

Coordination with Domain A:

Domain B contractors shall receive finished reagents from Domain A in accordance with CDC timelines and shall manage all subsequent storage, inventory control, packaging, and distribution. The Domain B contractor shall confirm receipt, document storage conditions, and report any discrepancies or quality concerns back to the Domain A contractor and CDC within 24 hours.

- Domain C: Information Technology (IT) and Data Systems (T&M or FFP Eligible)

  - RISER website hosting, support and integration with CDC CRM (Microsoft Dynamics 365 or comparable CDC-approved system);

  - Cybersecurity, 508 compliance, real-time messaging;

  - Reagent status syncing, real-time data transmission or batched data transmissions (e.g., XML data feeds), IT modernization projects;

  - Development of secure data upload and validation pipelines that allow RISER users to submit surveillance results, sequencing files, and other critical data to CDC in real-time via authenticated user interfaces or APIs;

  - Serve as primary lead for Enterprise Performance Life Cycle (EPLC) compliance and reporting across all RISER IT systems.

NOTE: 1) This Domain is discrete and modular; can be bid separately by IT firms.  Offerors proposing only on Domain C must demonstrate technical capability to integrate in real-time with external RISER awardees and government systems.  Proposals must include a description of planned interface tools, coordination protocols, and past performance handling external API or secure data feed connections; 2) Support for the RISER website and CDC CRM shall be combined under this domain to maximize system integration and minimize interface risk.  For the purposes of this contract, CDC’s current CRM, which is a Microsoft Dynamics 365 platform, is considered part of the CDC CRM ecosystem and thus terms may be used interchangeably throughout the document.  References to CRM in this Statement of Work (SOW) may include Dynamics functionality unless otherwise stated.  Offerors are encouraged to demonstrate capability to manage both components as a unified service, ensuring uninterrupted data flow and system compatibility.  Orders must be submitted through the RISER website, with all order, registrant, and cost data securely ingested into the CRM back-end for processing, reconciliation, and reporting.

Domain C shall serve as the designated lead for RISER-wide IT system interoperability, including all secure data pipelines, API integration, and user authentication infrastructure.  While other Domains may interact with these systems, Domain C shall be the primary point of accountability for functionality, system uptime, and security compliance.

All contractor-managed RISER IT systems, including the website, CRM, and inventory management platforms, shall maintain a minimum operational availability of ≥99.95% (excluding scheduled maintenance). This requirement aligns with the systems’ FISMA Moderate designation and the availability criteria for Moderate-impact systems defined in FIPS 199. Contractors must implement redundancy, continuous monitoring, and failover mechanisms to ensure continuity of operations and minimize disruptions to public health response activities.

The RISER website and associated data systems shall support secure, role-based uploads of laboratory and field-generated surveillance data from domestic and international partners. This includes, but is not limited to, genomic sequencing files, proficiency testing results, field investigation datasets, and other surveillance outputs tied to RISER reagents or CDC-directed activities

All custom-developed code, configurations, and scripts for RISER IT systems (including the website, CRM, and inventory management tools) shall be maintained in a CDC-approved source code repository (e.g., GitHub Enterprise or other CDC-designated secure platform). The contractor shall provide the COR and designated CDC staff with continuous read-only access to these repositories, including full version histories. Similarly, the contractor shall provide real-time, role-based access for the COR and designated CDC staff to any bug tracking or change control systems used for managing RISER IT development activities.

All contractor-managed RISER IT systems—including the website, CRM, and inventory management platforms—shall maintain daily backups with secure off-site storage for rapid disaster recovery. Backups must be retained for at least 90 days on a rolling basis, with one full monthly archive preserved for a minimum of 12 months. Critical data (e.g., configuration files, registrant data, transaction logs, Interface Control Documents) shall be archived for the life of the contract and provided to CDC or a successor contractor during transition in accordance with the Data Governance Plan.

Data Governance Plan:
The contractor shall develop and maintain a comprehensive Data Governance Plan, submitted to the COR for approval within 90 calendar days of contract award and updated annually or upon CDC request. This plan shall explicitly integrate and reference the Data Modernization Initiative (DMI) Alignment Addendum (Deliverable #62), ensuring that all metadata standards, data-exchange schemas, and interoperability requirements described in the Addendum are incorporated within the Data Governance Plan and maintained in synchronization with its annual updates.

The plan shall include:

- Data architecture maps showing system components, interfaces, and data flows;

- Access control measures, including role-based permissions and authentication protocols;

- Designation of primary and backup data storage sites;

- Backup, archival, and disaster recovery processes;

- Digital transition protocols for data transfer to CDC or a successor contractor at contract closeout.

The contractor shall implement all measures in accordance with CDC security policies and applicable federal regulations.

Data Modernization Alignment:

All RISER data systems, interfaces, and data governance activities shall align with CDC’s Data Modernization Initiative (DMI) principles for surveillance and emergency response. The contractor shall ensure that all data architecture, metadata, and exchange protocols support CDC enterprise interoperability objectives, including but not limited to standardized schema mapping, controlled vocabularies, and data quality assurance metrics consistent with CDC’s DMI governance policies.

The contractor shall:

- Coordinate with CDC’s Data Governance Board and DMI program staff to ensure RISER data structures are interoperable with enterprise data exchange platforms;

- Implement metadata standards supporting pathogen classification, geolocation, and temporal tagging for all RISER data submissions;

- Maintain documentation of data lineage, version control, and provenance for all datasets transmitted to CDC;

- Participate in DMI-led reviews and provide technical documentation necessary for integration of RISER data into CDC’s enterprise analytics environments.

Updates to the RISER Data Governance Plan shall include a section titled “DMI Compliance and Integration” outlining how RISER data flows, APIs, and data models conform to CDC’s modernization architecture.  See also Deliverables #50 (Data Governance Plan) for integration of compliance elements and joint update requirements.

- Domain D: Customer Service and Stakeholder Support (FFP Eligible)

  - Operate the RISER customer-service hotline, email, and ticketing system; triage and route all inquiries related to registration, ordering, shipment status, and website access;

  - Perform first-line vetting of new laboratory registrations submitted through the RISER website for completeness, legitimacy, and restricted-party screening, and forward vetted records to CDC for approval;

  - Coordinate with Domain B to collect and verify shipping permits, customs documentation, and delivery confirmations prior to and after shipment;

  - Provide website and portal user support in coordination with Domain C, including account access, upload troubleshooting, and dashboard viewing issues;

  - Maintain documentation of all customer interactions and complaint records within the CDC CRM to ensure full traceability across Domains.

NOTE: This Domain may be awarded separately or bundled with Domain B. The contractor shall maintain a formal complaint-handling process compliant with FDA 21 CFR Part 820 and ISO 13485. All customer complaints or critical communications shall be documented in the CDC CRM and reported to the CDC COR and QA representatives within twenty-four (24) business hours of receipt.  Complaint logs and resolutions shall be maintained in audit-ready format and made available to CDC upon request. Domain D personnel are embedded within the workflows of Domains A–C to provide coordinated customer communication while those Domains retain operational execution authority.

Standard IT Integration Clause (Applicable to all Domains):

All IT-related tasks-including order processing, CRM synchronization, website registration, reagent status updates, and external data submission-shall follow interface control protocols established by Domain C.  Any system integration must be coordinated through Domain C to maintain cybersecurity, version control, and auditability.  Offerors shall reference this clause in lieu of restating IT dependencies within individual domain proposals.

Cross-Domain Surge Responsibilities (Applicable to Domains A-D):

The government reserves the right to issue optional task orders under any Domain (A–D) to address emergency surge scaling, continuity of operations, or transition activities. When activated, the contractor shall demonstrate the ability to scale its assigned functions: production, logistics, information systems, or customer service, by 25 to 75 percent above baseline capacity within ten (10) business days of written direction from the Contracting Officer. Each contractor shall maintain contingency procedures sufficient to enable rapid surge activation, including staffing plans, facility readiness, and data-system scalability.

Public–Private Partnership and Rapid Vendor Onboarding:
To enhance CDC’s national preparedness and ensure uninterrupted reagent supply and data continuity during public health emergencies, the contractor shall maintain capabilities to establish and support public–private partnerships under the RISER program.  The contractor(s) shall:

- Maintain and implement a Rapid Vendor Onboarding Protocol approved by CDC that enables qualification of new subcontractors, manufacturers, couriers, or technology partners within ten (10) business days of CDC direction, ensuring full compliance with applicable biosafety, QA/QC, cybersecurity, and data-governance requirements;

- Maintain a pre-vetted library of templates for Non-Disclosure Agreements (NDAs), Data-Sharing and Confidentiality Agreements, and Quality Assurance Addenda to accelerate onboarding during emergency activations;

- Provide CDC with a current list of potential industry, academic, and logistics partners capable of supporting surge production, reagent packaging, IT integration, or international distribution;

- Participate in joint exercises or CDC-led workshops, when requested, to validate readiness for partner onboarding and information-sharing;

- Document all onboarding actions, vetting results, and partner approvals in the RISER CRM or designated CDC system of record to ensure auditability;

- Ensure that all private-sector partners engaged under RISER operate under the same data-protection, confidentiality, and regulatory compliance standards required of the prime contractor.

The Rapid Vendor Onboarding Protocol shall be referenced in the contractor’s QA/QC Plan and Transition Plan and cross-linked to the Data Governance Plan to ensure consistency of quality, security, and accountability across all partner engagements.  The Rapid Vendor Onboarding Protocol (Deliverable #21) shall document the contractor’s process for qualifying new partners and shall be updated annually or whenever partner-vetting criteria or regulatory requirements change

Performance Measurement During Surge:

Contractor performance under surge activation will be evaluated against the Key Performance Indicators (KPIs) identified in Appendix D – Key Performance Indicators. At a minimum, CDC will assess:

- Timeliness of surge activation:  demonstrated scale-up of 25–75% within ten (10) business days of written direction;

- RISER IT availability:  website/CRM/inventory systems sustain ≥99.95% availability during surge;

- Logistics timeliness:  orders shipped within CDC-mandated timelines (target ≥95%); and

- Quality yield:  first-pass QC rates ≥98% where applicable to surge production. CDC may incorporate these results into award-term incentive evaluations.

Supply Chain Risk Management and Critical Material Substitution (Domain A Lead; Applicable to Domains A-B):

To ensure uninterrupted RISER operations and national readiness during public-health emergencies, the Domain A contractor shall establish and maintain a comprehensive Supply Chain Risk Management (SCRM) Plan integrated across Domains. The plan shall identify critical materials, evaluate supply-chain vulnerabilities, and define validated substitution strategies that preserve reagent quality, regulatory compliance, and delivery timelines.  The contractor(s) shall:

  - Maintain real-time visibility of all critical inputs and suppliers supporting reagent production, storage, and shipment;

  - Identify single-source or high-risk components and establish at least one qualified alternate supplier or validated substitute for each where feasible;

  - Develop documented substitution and equivalency protocols consistent with CDC’s Quality Specifications (Appendix B) and FDA 21 CFR 820 requirements;

  - Coordinate with CDC prior to implementing any critical-material substitution, providing supporting validation data, Certificates of Analysis, and impact assessments;

  - Incorporate SCRM monitoring and substitution status into the Monthly Technical Report, including supply-chain disruptions, mitigation actions, and substitutions implemented;

  - Update the SCRM Plan annually, or upon major supplier, geopolitical, or regulatory changes, and provide it to the COR for review and approval.

Domain B contractor shall support execution of the SCRM Plan within their scope of responsibility, including storage, inventory management, and shipment-related risk mitigation, and shall coordinate with the Domain A contractor and CDC on identified risks and substitution actions.  The SCRM Plan shall align with CDC’s enterprise continuity and domestic manufacturing initiatives, ensuring consistency with HHS and federal directives on supply-chain security.

Transition Responsibilities (Applicable to Domains A-D):

All Domain (A–D) contractors shall also support transition and continuity activities at the conclusion of this contract or any subsequent re-competition. Contractors shall prepare and maintain Domain-specific Partial Transition Plans describing how technical data, inventory, documentation, and government-furnished property will be securely transferred to a successor contractor or to the government. Each awardee shall participate in joint transition meetings and coordinate with CDC’s designated Integration Lead to ensure seamless hand-off of responsibilities.

Summary of Contract Tasks by Domain and Classification

| Task Section | Assigned Domain | Task Classification* |
| --- | --- | --- |
| 1. Develop Standard Operating Procedures | Domain A: Core Reagent Production and Catalog Management | Core |
| 2. Facility Requirements | Domain B: Facility Operations and Logistics | Core |
| 3. Establish, Maintain, and Operate the RISER Catalog | Domain A: Core Reagent Production and Catalog Management | Core |
| 4. Reagent Stability and Shelf-Life Management Program | Domain A: Core Reagent Production and Catalog Management | Core |
| 5. Operate and Maintain the RISER Website | Domain C: IT and Data Systems | Core |
| 6. Manage Laboratory Registration for RISER Account | Domain D: Customer Service and Stakeholder Support | Core |
| 7. Assist with Operation and Maintenance of RISER CRM | Domain C: IT and Data Systems | Core |
| 8. Receive Reagent Orders and Manage Shipping Logistics | Domain B: Facility Operations and Logistics | Core |
| 9. Shared Cost Allocation Plan Management | Domain C: IT and Data Systems | Core |
| 10. Surge Support | Domain A: Core Reagent Production and Catalog Management; Domain B: Facility Operations and Logistics; Domain C: IT and Data Systems; Domain D: Customer Service and Stakeholder Support | Optional |
| 11. Outgoing Transition to New Contractor (and Partial Domain Transitions) | Domain A: Core Reagent Production and Catalog Management; Domain B: Facility Operations and Logistics; Domain C: IT and Data Systems; Domain D: Customer Service and Stakeholder Support | Optional |
| 12. Development and Validation of Diagnostic Assay Workflows | Optional Task (Non-Domain) | Optional |

*Optional objectives shall only be exercised by the government through the issuance of a distinct task order with a defined period of performance and deliverables, and cost ceiling.  Optional tasks shall not be presumed as part of baseline scope.

TASKS TO BE PERFORMED:

The contractor shall complete the tasks within Domains outlined below in accordance with any applicable delivery dates reflected in Section XV - Deliverables / Reporting Schedule:

Offerors may propose on one or more Domains; however, award decisions may be made per Domain based on technical merit, cost realism, and performance risk.

All offerors are subject to a pre-award on-site audit by CDC or its designated representatives to verify compliance with FDA current Good Manufacturing Practice (cGMP) requirements (21 CFR Part 820), ISO 9001/13485 standards, and other applicable regulatory obligations. This audit is part of CDC’s supplier qualification process and must be successfully completed before the contract award. Offerors shall provide access to relevant facilities, quality documentation, and personnel during this pre-award audit.

Domain A: Core Reagent Production and Catalog Management

- Produce, acquire, characterize, and manage RISER reagents in alignment with CDC surveillance priorities;

- Maintain quality systems, including SOPs, QA/QC programs, stability testing, and surge readiness;

Support continuity of operations, including surge response and transition activities, as directed by CDC.

Domain B: Facility Operations and Logistics

- Provide and operate compliant facilities and infrastructure to support secure storage and distribution of RISER reagents;

- Manage domestic and international logistics, regulatory compliance, and cold-chain integrity;

- Support surge operations and transition activities within the Domain B scope.

Domain C: IT and Data Systems

- Operate and maintain RISER IT systems, including the website, data-exchange interfaces, and integration with CDC systems;

- Ensure system security, availability, and scalability to support routine operations and emergency response;

- Support continuity, surge operations, and transition of RISER IT systems as required.

Domain D: Customer Service and Stakeholder Support

- Manage laboratory registration and User Agreement (Appendix E) processing, including first-line vetting of applications submitted through the RISER website for completeness, authorized signatory, and restricted-party screening prior to CDC review and approval;

- Manage customer communications across all RISER Domains;

- Operate the RISER Help Desk during standard business hours (Monday-Friday, 8:00 a.m.–5:00 p.m. Eastern Standard Time (EST), fixed year-round regardless of daylight-savings adjustments) with the capability to escalate urgent issues outside these hours during public-health emergencies or elevated operational tempo;

- Maintain customer-service operations, complaint handling, and transition support in coordination with other Domains.

Time Calculation Standard

Unless expressly stated otherwise, all time-based requirements under this contract shall be measured in business days, defined as Monday through Friday, excluding Federal holidays.

Timeframes associated with declared public health emergencies, surge activation, or urgent public health protection measures shall be measured in calendar hours or immediate response standards as specified in the applicable task or written direction from the Government.

- DOMAIN-BASED TECHNICAL TASK DETAILS

This section provides a summary of the technical tasks associated with Domains [A–E]. Offerors are required to consult the task detailed information requirements in (Appendix C - Detailed Task Descriptions (Tasks 1-11)), for full descriptions of task-level deliverables, SOP expectations, performance standards, reporting schedules, and regulatory compliance requirements applicable to these Domains. All proposal responses must demonstrate clear understanding of, and capacity to meet, the specifications and benchmarks outlined in the referenced appendix.

In the event of multi-vendor awards across separate Domains, each contractor shall identify a dedicated liaison responsible for inter-domain coordination. Weekly integration checkpoints shall be held among awardees to reconcile task dependencies, especially between reagent production (Domain A), logistics (Domain B), and IT systems (Domain C).  For clarity in multi-award scenarios, each task below uses the phrasing “Domain [X] contractor” to reflect the lead performer responsible for that Domain.  Where multiple domains intersect, coordination requirements are noted in each task description.

Domain A: Core Reagent Production and Catalog Management

Task A.1: SOP Development

Domain A contractor shall develop SOPs for all technical functions under Domain A, including reagent receipt, handling, QA/QC, and SOP preparation related to shipping and inventory management, even though operational execution of those functions resides under Domain B. SOPs must comply with CDC quality system protocols and be approved by the COR before implementation. The government may provide examples of existing CDC-approved workflows, algorithms, templates, or reference materials, as available, to inform SOP structure and sequencing. Such materials are provided for reference only and do not relieve the contractor of responsibility for developing, validating, and maintaining contract-specific SOPs. If SOPs are transferred from CDC-developed methods, the Domain A contractor may receive assay training from CDC staff to support proper implementation.

The first set of draft SOPs must be submitted within 60 calendar days of contract award, as described in the deliverables schedule. SOP development shall continue on a rolling basis, aligned with task-specific timelines approved by the COR.

SOPs must cover all activities performed directly by the Domain A contractor or its subcontractors. Where appropriate, SOPs shall also address coordination and interface points with other Domains, such as procedures for shipment and storage (Domain B), registration workflows (Domain D), IT/data handling dependencies (Domain C), and transition continuity requirements (across all Domains) to ensure cross-Domain alignment and operational consistency across the RISER program.

The Domain A contractor shall also establish and maintain a centralized RISER SOP compendium that serves as the authoritative repository for all SOPs developed under this contract, including SOPs applicable to Domains A–D. The compendium shall reflect current COR-approved versions, identify superseded SOPs, and support audit readiness.

Task A.2: Reagent Production and QC

Domain A contractor shall acquire or produce RISER reagents listed in Appendix A – Deliverables, using qualified facilities and staff. All lots shall be tested per the specifications in Appendix B – Quality Specifications. QA and QC must be independent of production to allow rejection of non-conforming materials.

QA/QC Plan:
The contractor shall develop and maintain a comprehensive QA/QC Plan, submitted to the COR within 60 calendar days of contract award and updated annually or upon CDC request. The plan shall cover:

- QA/QC processes for reagent production, validation, and catalog management;

- Batch record documentation requirements, including retention periods and accessibility for audit;

- Reagent rejection criteria and procedures for disposition of nonconforming materials;

- Procedures for recording, investigating, and resolving customer complaints;

- Roles and responsibilities for QA/QC oversight.

Task A.3: Catalog Operations and Surge Planning

Domain A contractor shall maintain the RISER reagent catalog, including a virtual inventory tracker for display and planning purposes; physical warehousing and distribution records shall be maintained under Domain B.  The virtual inventory tracker must support real-time display of reagent status, historical batch data, and CDC-program level visibility.  The system must be auditable, regularly backed up, and interoperable with CDC data platforms.  Inventory states may include: ‘seed stock’, ‘in production’, ‘on quality hold’, ‘available for distribution’, or ‘retired’.  Terminology shall follow CDC catalog conventions.

The RISER catalog system shall align with ICDs maintained by Domain C. Any data structure changes, catalog schema updates, or API development must be coordinated with the Domain C technical lead and approved by the COR to ensure interoperability across RISER platforms. Domain A shall provide catalog updates in formats specified by Domain C to enable consistent integration with CDC’s CRM tools.

Domain A contractor shall develop an acquisition and contingency plan for surge capacity up to 75% above baseline. A comprehensive production and surge capacity plan must be submitted within 150 calendar days of contract award and updated annually or as directed by CDC.

Domain A contractor shall record and transmit per-batch production costs (labor, materials) to support CDC financial reconciliation and cost-effectiveness analysis.  Shipment history, shipment-level cost data, and delivery confirmation records shall be generated and maintained by Domain B.  Domain A shall coordinate with Domain B and Domain C to ensure that lot-level production data, shipment history, cost metadata, and catalog availability remain synchronized across RISER systems to preserve end-to-end traceability and data integrity.

Task A.4: Reagent Stability and Shelf-Life Management Program

Domain A contractor shall perform all stability testing and shelf-life management for RISER reagents in accordance with CDC-approved protocols and quality requirements.  Prior to production (or re-manufacture) of each reagent category, CDC will determine the number of kits/vials to be reserved exclusively for stability studies and the required testing cadence (e.g., initial, 3, 6, 12, 24 months), as needed. These parameters shall be documented in a Stability Testing Plan and reflected in batch planning and inventory reservations.

The contractor shall maintain automated tracking of reagent expiration dates within the RISER inventory system and shall generate monthly notifications to the CDC COR and SMEs identifying reagents scheduled to reach expiry within 60 days.  For each reagent lot approaching expiry, the contractor shall request written CDC direction regarding one of the following actions: (a) extension of the expiration date based on updated stability data; (b) redistribution of repurposing for training or non-critical use; (c) shipping of all expired material back to CDC; or (d) authorization for destruction and documentation of disposal.  No reagent shall be destroyed or have its expiration date extended without written CDC approval.

Optional Task A.5: Surge Support

Upon CDC direction, the government may activate an optional task requiring the Domain A contractor to scale reagent-production, QA/QC, and catalog management activities by 25–75 percent above baseline within ten (10) business days.

Performance during this surge activation will be measured against the KPIs in Appendix D, including timely activation within ten (10) business days, domain-relevant on-time service levels, and (as applicable) system availability of ≥99.95% and/or ≥98% first-pass QC.

Optional Task A.6: Transition Support

Upon contract completion, the contractor shall support orderly transfer of production data, batch records, QA documentation, and related technical materials to a successor contractor or to CDC, as directed.

Domain A contractor shall adopt standardized formats for vialing, labeling, product inserts, and Certificates of Analysis across all reagent’s classes unless technical justification for exception is provided.  Packaging shall support barcoding and traceability and follow CDC’s unified reagents presentation guidance.

Domain B: Facility Operations and Logistics

Task B.1: Facility Provision and Compliance

Domain B contractor shall provide and maintain dedicated laboratory and storage facilities with capabilities up to Biosafety Level (BSL)-4, including Animal Biosafety Level (ABSL) compliance. Facilities must meet requirements under the Federal Select Agent Program, USDA, FDA, and CDC biosafety standards. Domain B contractor shall submit proof of registration and inspection readiness as part of the technical proposal and maintain updated documentation throughout the contract period.

Task B.2: Secure Storage and Environmental Control

Domain B contractor shall ensure proper storage of biological materials across various temperature conditions (2–8°C, -20°C, -70°C, liquid nitrogen). Facility must include 24 hours/7-day monitoring, uninterruptible power, and backup freezers with alarm systems and security protocols including access controls and surveillance.  These storage functions apply to all RISER reagents received from Domain A production workflows.

Domain B contractor shall document and report any storage condition deviations and implement CDC-reviewed Corrective and Preventive Action (CAPA) protocols to remediate and prevent recurrence. A storage condition deviation shall be defined as any temperature or environmental condition that falls outside the CDC-approved storage range specified for the affected reagent in Appendix B – Quality Specifications, associated Stability Testing Plans, or the applicable Certificate of Analysis. The contractor shall assess the duration, magnitude, and product impact of any excursion and notify the CDC COR and QA representative in accordance with approved SOPs. CAPA initiation shall be required for excursions that result in confirmed or suspected impact to reagent quality, regulatory compliance, or distribution integrity, as determined in coordination with CDC.

Task B.3: Domestic and International Shipping

The Domain B contractor shall manage all logistics for shipping RISER reagents to domestic and international recipients. Responsibilities include shipment scheduling, packaging, cold chain management, regulatory compliance, and delivery confirmation. All shipping activities must comply with applicable laws and standards, including IATA, ICAO, U.S. Department of Transportation (DOT), and relevant import/export requirements.

The contractor shall plan and execute shipments with the objective of delivery within ninety-six (96) hours of departure, unless otherwise approved by CDC. The contractor shall implement contingency measures such as re-icing, temperature-stabilizing packaging, use of priority couriers, or in-transit cooling capacity, to preserve product integrity when extended transit durations are anticipated or encountered.

If delivery exceeds ninety-six (96) hours due to factors outside the contractor’s reasonable control (e.g., customs holds, carrier delays, weather disruptions), the contractor shall document the cause, assess potential impact to product integrity, notify the CDC COR in accordance with approved SOPs, and implement corrective or preventive measures as appropriate.

The Domain B contractor shall maintain secure, real-time tracking and confirmation systems for all shipments. The contractor shall maintain systems capable of real-time capture of shipment tracking events from courier sources.  Captured tracking data shall be transmitted or made visible to CDC and the RISER registrants within defined timeframes: within 12 hours of receipt for domestic shipments and within 24 hours of receipt for international shipments.  These intervals establish the maximum allowable delay between data capture and system transmission to the CDC CRM or RISER website.  Any delays in obtaining or uploading tracking data shall be documented in the contractor’s weekly summary report with an explanation and corrective action plan.

Shipment timing must be coordinated directly with recipient laboratories and, where applicable, any authorized intermediary consignees, freight forwarders, brokers, or clearing agents designated by the recipient or required by destination-country regulations, to ensure customs paperwork is finalized and receiving facilities are prepared. Reagents shall be delivered door-to-airport by default for international shipments, unless door-to-door delivery is pre-approved by CDC. To minimize customs-related delays or waste, the Domain B contractor shall confirm readiness for receipt and customs processing prior to dispatch, including verification of any required intermediary coordination.

All shipment tracking data, distribution cost metadata, and delivery confirmations must be captured and integrated into CDC’s CRM system, using the interface standards maintained by Domain C.  Delivery confirmations must include a timestamped receipt obtained from written confirmation from the end-user.  In absence of confirmation from end-user, the Domain B contractor shall obtain the receipt from the courier (e.g., FedEx proof of delivery).  No independent data pipelines, APIs, or endpoint modifications may be deployed without prior COR approval and Domain C coordination.

The Domain B contractor shall maintain reagent-level cost data for each shipment, including packaging, courier fees, customs charges, special handling, and internal labor. This information must be linked to the shipment record and submitted as part of the Domain B contractor’s monthly financial reports.

Domain B contractor shall ensure cost-effective shipping by obtaining and documenting no fewer than four (4) competitive quotes from qualified carriers or courier services for international or high-cost shipments (e.g., those exceeding CDC-defined thresholds). Competitive quotes shall be solicited and obtained within a reasonable planning window, not to exceed ten (10) business days from identification of the shipment requirement, unless CDC directs expedited shipment.

In instances where fewer than four quotes can reasonably be obtained within this timeframe, the contractor shall document the outreach efforts undertaken (e.g., list of vendors contacted, dates, and responses received) and submit the available quotes along with a justification memorandum in the shipment record.

Under urgent public health, surge, or CDC-directed expedited shipment scenarios, the contractor shall prioritize timely dispatch over completion of the four-quote process and shall document the justification for any deviation from standard quote procedures in the shipment record.

Quotes and any associated justification shall be retained in shipment records and made available to CDC upon request. For routine domestic shipments under pre-negotiated rate structures, the contractor shall select the lowest-cost option that meets delivery speed and cold-chain integrity requirements unless otherwise directed by CDC.

CDC reserves the right to implement a cost-sharing policy for international orders exceeding a specified threshold (e.g., $##,###), in which case recipient laboratories may be asked to absorb the difference or identify a subsidizing partner.  This measure is intended to promote equitable access while preserving overall contract affordability.

To support high-priority delivery coordination, the Domain B contractor shall assign full-time logistics specialists to be co-located at CDC Atlanta Headquarters. These individuals shall:

- Facilitate same-day or expedited shipment planning during emergency operations;

- Serve as the primary CDC liaison for shipping documentation, regulatory troubleshooting, and customs exceptions;

- Support technical integration of shipment records, tracking data, and cost fields into CDC’s CRM system, in coordination with Domain C.

Although Domain B is responsible for physical distribution, external-facing communications (e.g., status inquiries, delivery confirmations, COAs) shall be coordinated through Domain D (Customer Service and Stakeholder Support). The Domain B contractor shall ensure that shipment data is shared promptly with Domain D personnel to enable timely and accurate customer service response. Any shipment anomalies, delays, or delivery failures must be logged, reported to CDC, and included in the Domain B contractor’s incident tracking and weekly performance summaries.

Reverse Logistics and Material Disposition:

The Domain B contractor shall support reverse logistics and disposition of RISER materials when directed by CDC. This includes the retrieval, return shipment, controlled destruction, or other government-directed disposition of expired, outdated, recalled, compromised, or otherwise restricted reagents.

Upon written direction from the CDC COR or CO, the contractor shall:

- Coordinate return shipment of affected materials to CDC or other designated facilities;

- Arrange secure destruction in accordance with applicable biosafety, environmental, and regulatory standards;

- Document chain-of-custody and final disposition, including destruction certificates where applicable;

- Update inventory and CRM records to reflect disposition status;

- Notify Domain A and Domain D of any returned or destroyed materials impacting availability or customer accounts.

Optional Task B.4: Surge Support

The government may activate an optional task requiring the Domain B contractor to expand warehousing, shipping, and cold-chain operations by 25–75 percent above baseline within ten (10) business days. The contractor shall maintain contingency courier contracts, packaging stockpiles, and staffing plans for rapid surge activation.

Performance during this surge activation will be measured against the KPIs in Appendix D, including timely activation within ten (10) business days, domain-relevant on-time service levels, and (as applicable) system availability of ≥99.95% and/or ≥98% first-pass QC.

Optional Task B.5: Transition Support

Prior to contract completion, the contractor shall coordinate the physical transfer of government-owned inventory, shipping records, and facility documentation to the successor contractor under CDC supervision.

Domain C: IT and Data Systems

Task C.1: RISER Website Hosting and Operations

Domain C contractor shall host and maintain the RISER website with 99.95% uptime, secure access, Section 508 compliance and securely interface with the CDC-hosted CRM (Microsoft Dynamics 365).  The Domain C contractor shall support and maintain its data exchange, user experience, and reporting outputs in full alignment with CDC protocols. Domain C contractor is responsible for configuration, security scans, data integration with ERP, and real-time reagent availability updates.  Domain C contractor shall configure the RISER website to support secure, authenticated uploads of genomic sequencing data, assay results, and other partner-submitted data for transmission to CDC programs.  The RISER website shall also include a configurable study portal module that allows CDC to define study-specific reagent access lists and pre-set quantity limits. This module will be fully integrated within the RISER website and managed through role-based access controls, ensuring only COR or SME-approved registrants can view and order study-specific materials.

Domain C contractor shall support the secure display of CDC-generated dashboards, including public-facing registrant dashboards and internal CDC views for financial reconciliation or response planning. All dashboards must comply with Section 508 standards, maintain ≥99.5% uptime (excluding scheduled maintenance), and be hosted and integrated according to protocols maintained by Domain C. Key technical functions, security requirements, and surge-readiness expectations are detailed in Appendix Task 5. During declared emergencies, Domain C contractor shall scale website functionality, data sync frequency, and Help Desk staffing to meet surge needs. Domain C contractor is not responsible for producing analytic content, but shall ensure that dashboards, ordering workflows, and catalog availability features are reliably delivered and securely integrated with CDC systems.

The RISER website and associated CRM workflows shall support CDC-authorized administrative restoration or reactivation of canceled or closed sales orders when necessary to correct administrative error, support public health response activities, or assist registrants. The system shall preserve the original order record and maintain a complete audit trail of all status changes, including user identification, timestamp, original order state, and reason for reactivation. Reactivation shall not overwrite prior records but shall create a traceable workflow transition within the system.

The contractor shall maintain all RISER website and CRM source code, configurations, and scripts in a CDC-approved secure repository. The contractor shall provide the COR and designated CDC personnel with continuous read-only access to the repository, including version histories and change logs, throughout the period of performance.

Interface Control Document (ICD) Development and Maintenance Plan:
The contractor shall develop and maintain a comprehensive ICD Development and Maintenance Plan, submitted to the COR for review and approval within 60 calendar days of contract award. The plan shall:

- Define the process for creating, reviewing, and updating ICDs for all RISER website and associated system interfaces;

- Include security architecture diagrams for all website-related data flows;

- Specify data exchange standards, including formats, protocols, and security controls;

- Outline version control and change management procedures to ensure ICD currency and traceability;

All ICD updates shall be documented, versioned, and resubmitted for COR approval prior to implementation.

Technical Integration Plan:
The contractor shall develop and maintain a Technical Integration Plan, submitted to the COR within 90 calendar days of contract award and updated annually or upon CDC request. The plan shall detail:

- Real-time, bidirectional API architecture for data exchange between RISER systems and CDC platforms;

- Integration processes and configurations for Microsoft Dynamics 365 CRM;

- XML data exchange specifications and mapping;

- System scalability strategies to support up to a 75% increase in transactions during surge operations;

- Performance targets for API uptime (≥99.9%) and data transfer latency (≤5 seconds under normal load).

Ongoing Section 508 Compliance:
The contractor shall ensure all IT systems, platforms, and deliverables remain compliant with Section 508 accessibility standards throughout the period of performance. Compliance shall be validated through regular testing (at least annually and after any major update) using industry-standard accessibility evaluation tools and manual checks. Any identified non-compliance issues shall be remediated within 30 calendar days of detection. Documentation of testing results and remediation actions shall be submitted to the COR.

Change Control and Modernization:

The contractor shall ensure that all website development, modernization, and release activities are documented within the CDC EPLC framework, as needed.  This includes maintaining EPLC phase deliverables and reporting progress to the COR and CDC EPLC representatives.

Task C.2: CDC CRM Support

The Domain C contractor shall support the CDC-hosted CRM (Microsoft Dynamics 365). Responsibilities include entry and tracking of order and inventory data, updates to registrant accounts, and documentation and reporting consistent with CDC’s Enterprise Performance Life Cycle (EPLC) management requirements.

System Availability and Security:
The RISER CRM shall maintain ≥99.95% operational availability (excluding scheduled maintenance) to ensure uninterrupted order processing, data synchronization, and emergency response functionality. The contractor shall implement redundancy, failover mechanisms, daily backups, and continuous monitoring consistent with a FISMA Moderate designation (FIPS 199). Critical data including registrant information, transaction logs, and system configurations, shall be securely archived for the life of the contract.

Core Functional Capabilities:
The system shall:

- Log and track uploaded data tied to specific registrants, reagents, and public health response events, with secure access provided to CDC for analysis;

- Support capture, storage, and export of detailed cost data for each order, including material, packaging, labor, and shipping. These fields must be reportable in standard CDC financial dashboards and reconcilable with contractor invoices.

- Maintain historical inventory data for a minimum of the life of the contract and make prior-period inventory levels (including at least two prior fiscal years, where available) accessible to CDC-authorized users through reporting dashboards or exportable data formats within the CRM or RISER website. Historical data shall support filtering by reagent, lot number, program, geographic distribution, and time period to facilitate program analysis and forecasting.

- Support CDC-authorized administrative intervention in pending orders, including the ability for the COR, RISER Management Team, or designated CDC SMEs to modify order contents (e.g., add or remove items, adjust quantities, or annotate justification) prior to final approval.  All modifications shall be logged with user identification, timestamp, original order snapshot, and reason for change to preserve full traceability and version history within the CRM.

Cross-Domain Integration:
To ensure end-to-end data integrity and a consistent user experience, the Domain C contractor shall ensure full integration between RISER Website Operations (Task C.1) and CRM Support (Task C.2). Integration responsibilities shall include architecture alignment, interface specifications, and data flow protocols for registrant orders, shipment status, and cost metadata synchronization. These integration dependencies shall be documented and maintained in approved Interface Control Documents (ICDs).

If website and CRM functions are awarded to separate contractors, the respective awardees shall coordinate to ensure compliance with approved ICDs and CDC integration standards.

Interface Control Documents and Technical Integration Plan:
CRM-related interfaces and integrations shall be governed by the Domain C ICD Development and Maintenance Plan and Technical Integration Plan established under Task C.1. The Domain C contractor shall ensure that all CRM-specific integrations, data flows, security architecture diagrams, and API configurations are incorporated into the approved Domain C ICDs and Technical Integration Plan. No separate ICD Plan or Technical Integration Plan shall be maintained for CRM independent of the Domain C master plans.

Task C.3: Shared Allocation Plans

In addition to technical systems integration, the Domain C contractor shall also manage administrative coordination related to shared IT infrastructure costs.

The Domain C contractor shall:

- Develop and submit a Shared Cost Allocation Plan (SCAP) detailing:

  - Costs associated with shared platforms, licenses, or systems used across multiple RISER Domains or contractors;

  - Proposed allocation methods (e.g., percentage usage, transaction volume, user counts);

  - Updates to cost allocation whenever material changes occur.

The Integration Lead may request updates or validations of the SCAP for accuracy and fairness.

- Provide supporting calculations and assumptions in Excel format;

- Submit an initial SCAP within 90 days of contract award;

- Update the plan annually or as directed by the government;

- Participate in discussions and resolutions of any disputes related to shared cost allocations.

Methodology and Documentation Requirements:
The contractor shall clearly define the cost allocation methodology or methodologies used for allocating shared IT/system costs. Acceptable methods include, but are not limited to:

- Pro-rata usage based on actual consumption metrics;

- Allocation by transaction volume;

- Allocation by active user count.

The selected methodology shall be accompanied by supporting calculations and assumptions, provided in Excel format, and submitted to the COR for review and approval. The contractor shall update and resubmit these calculations whenever there is a material change in system usage, cost structure, or participating domains.

Optional Task C.4: Surge Support

When directed in writing by the Contracting Officer (CO), the Domain C contractor shall scale IT system throughput, website/CRM transaction capacity, and user-support coverage by 25–75 percent above baseline. The contractor shall maintain scalability plans for hosting, data-exchange frequency, and disaster-recovery operations.

Performance during this surge activation will be measured against the KPIs in Appendix D, including timely activation within ten (10) business days, domain-relevant on-time service levels, and (as applicable) system availability of ≥99.95% and/or ≥98% first-pass QC.

Optional Task C.5: Transition Support

At contract closeout, the contractor shall provide complete transition of source code, system configurations, security documentation, and access credentials to the successor contractor or the government.

Domain D: Customer Service and Stakeholder Support

Task D.1: Laboratory Registration and User Agreements

Domain D contractors shall manage registration of laboratories and ensure execution of User Agreements (UAs) (Appendix E) with each authorized organization. Registrations must be reviewed, tracked, and approved in coordination with the CDC COR. Registration records shall include signed UAs, approval logs, workflow status, and account status summaries. All registration and UA records shall be maintained in secure, auditable digital format, with encryption and backup protocols in place per CDC security standards.

Domain D staff shall manage the customer-facing portion of the registration and vetting process in coordination with Domain C’s website and CRM systems. Upon receipt of registration materials, the contractor shall upload all documentation into the CDC-approved Customer Relationship Management (CRM) system and verify that each submission is complete and properly signed by an authorized institutional representative or designated safety officer.

The contractor shall communicate directly with the submitting laboratory, as necessary, to resolve omissions, correct deficiencies, or clarify discrepancies. All correspondence and workflow status updates (e.g., On Hold, Approved, Active, Closed, Denied) shall be documented within the CRM system.

As part of the vetting process, the contractor shall independently verify the validity of the laboratory’s physical location and shipping address using commercially available and publicly accessible sources. Where multiple addresses are provided, the contractor shall obtain written clarification from the laboratory and document final confirmation of the approved shipping location in the CRM.

The contractor shall conduct restricted-party and export control screening of registrants and associated institutions using CDC-approved compliance screening tools or equivalent systems. Any potential matches or compliance concerns shall be flagged for CDC review prior to account activation.

Once all required information has been verified as complete and accurate, and compliance screening has been successfully completed, the contractor shall transmit the registration package to CDC for final review and approval. No account shall be activated, and no reagent orders shall be processed, prior to written CDC approval.

The contractor shall complete initial registration vetting within five (5) business days of receipt of a complete submission, excluding delays attributable to missing or deficient information from the applicant.

Customer Service and Stakeholder Support Plan:
The contractor shall develop and maintain a Customer Service and Stakeholder Support Plan, submitted to the COR within 60 calendar days of contract award and updated annually or upon CDC request. The plan shall include:

- Procedures for laboratory registration and user-agreement management, including verification of eligibility and restricted-party screening prior to CDC review;

- Procedures for triaging website and portal access issues, including escalation paths to Domain C’s technical team;

- Protocols for managing customer inquiries, including prioritization and escalation;

- Tracking and reporting of support volume, average response time, and resolution trends;

- Customer satisfaction measurement methods (e.g., feedback from RISER registrant) and integration of results into process improvements;

- Staffing levels and training requirements for customer support personnel.

Task D.2: Customer Communication and Issue Resolution

Domain D shall operate the centralized RISER customer-service function serving all Domains. The contractor shall manage hotline, email, and CRM-based ticketing for inquiries related to registration, reagent ordering, shipment status, and RISER website functionality. Routine user issues shall be resolved directly by Domain D; technical or operational issues shall be escalated to the responsible Domain (A–C) with full documentation retained in CRM.

Urgent issues, including those affecting public health response, data integrity, regulatory compliance, or shipment viability, shall be escalated within two (2) hours of identification in accordance with the escalation procedures defined in the Customer Service and Stakeholder Support Plan and applicable KPIs.

The contractor shall acknowledge and respond to customer inquiries within two (2) business days of receipt and shall resolve inquiries within five (5) business days, unless additional time is required due to factors outside the contractor’s control (e.g., pending CDC decision, external shipment delay, or registrant inaction). Any such delays and their justification shall be documented in the CRM.

Domain D must coordinate closely with Domain B for shipping logistics and import/export documentation, and with Domain C for CRM records, website alerts, and dashboard notifications. Domain A shall provide reagent-specific technical content to support responses involving reagent performance or product information.

After shipment, Domain D shall track courier and recipient confirmations, record delivery outcomes in CRM, and notify Domain B and CDC of any delivery failures requiring CAPA review. Delays or delivery failures must be logged and summarized in monthly incident and financial reports submitted to the COR, using CDC-approved formats.

Optional Task D.3: Surge Support

The government may activate an optional task requiring the Domain D contractor to scale customer-support operations by 25–75 percent above baseline within ten (10) business days. When directed, the contractor shall implement surge measures such as extended operating hours, temporary or cross-trained staffing, and prioritized handling of emergency orders. During declared public-health emergencies, surge coverage shall include expanded Help-Desk and website-support hours coordinated with Domain C to ensure seamless user assistance and system responsiveness.

Performance during this surge activation will be measured against the KPIs in Appendix D, including timely activation within ten (10) business days, domain-relevant on-time service levels, and (as applicable) system availability of ≥99.95% and/or ≥98% first-pass QC.

Optional Task D.4: Transition Support

Upon contract completion, the contractor shall assist in transferring all user-agreement records, CRM tickets, registration data, communication templates, and customer-service documentation to the successor contractor. During the transition period, Domain D shall ensure uninterrupted operation of the website and hotline until full deactivation and confirmation of successful system handoff.

- DETAILED TECHNICAL OPTIONAL REQUIREMENTS

Independently and not as an agent of the government, the contractor shall provide all management, labor, facilities, materials, supplies, and equipment necessary to complete the optional task(s) set forth below, if exercised by the government under a separately issued task order.

Optional Task A: Ancillary Reagent Procurement

#### CDC may activate this optional task to allow the contractor to procure off-the-shelf ancillary reagents or consumables in support of catalog continuity or surge readiness. These ancillary items may include extraction kits, enzymes, buffers, or other commercially available components necessary to maintain uninterrupted distribution of RISER reagents. Activation of this task does not obligate the government to a minimum purchase amount and shall be executed only via Task Order on an as-needed basis.

#### Optional Task B: Development of Improved Scientific Workflows for Diagnostic Assay Design

The goal of this optional task is to design, validate, and deliver an improved workflow or scientific process for the development of diagnostic assays to aid in the characterization of circulating and novel pathogens, and improve CDC product, material or testing processes. When activated by the government, this task may require the contractor to conduct experimental validation and support technology transfer of new assay methods to CDC programs.

If activated by the government through a separate Task Order, Optional Task B, shall be completed in accordance with the following milestones and deliverables:

- Milestone 1: Gap analysis and Proposal Development

  - The contractor shall perform a targeted gap analysis to evaluate scientific knowledge gaps and identify emerging technologies or workflows applicable to CDC-prioritized pathogens.  This shall include:

    - Literature reviews;

    - Outreach to technology developers and scientific experts;

    - Assessment of commercially available platforms or proprietary methods that may be adapted;

  - Gap analysis shall be tailored to specific workflows or scientific processes designated by the government for evaluation;

  - The contractor shall provide oral presentations or teleconference updates on progress at least twice per month, or more frequently as requested by the COR;

  - The contractor shall submit a draft technical proposal to the COR and relevant SMEs outlining the proposed workflow development plan, including:

    - Proposed assays design strategy;

    - Required resources and timeline;

    - Performance metrics and comparison parameters;

  - Work under Milestone 2 shall not begin until the COR has reviewed and approved the final version of the technical proposal.

- Milestone 2: Assay Development, Validation and Technology Transfer

  - Upon completion of Milestone 1, the contractor shall submit the gap analysis findings and proposed workflow development plan to the COR for review.  Progression to Milestone 2 shall occur only upon written authorization from the COR or Contracting Officer (CO). The government reserves the right to determine, based on the results of the gap analysis and program priorities, whether Milestone 2 will be exercised, modified, or not pursued. If authorized to proceed, the contractor shall then initiate development of the designated assay workflow. Activities may include:

    - Procurement or synthesis of critical reagents (e.g., primers, probes, enzymes, ancillary materials);

    - Design and optimization of protocol steps;

    - Testing under varying conditions to assess reproducibility and robustness;

  - The government will provide reference materials as available, including:

    - Positive and negative controls;

    - Pathogen strains required for validation;

    - Comparative data from existing assay platforms;

  - The contractor shall perform side-by-side comparison studies between the new workflow and the current CDC platform, assessing performance across metrics such as:

    - Sensitivity and specificity;

    - Time-to-result;

    - Reagent stability and usability;

    - Platform adaptability or field-deployability;

  - The contractor shall document findings in a comparative report, with detailed methodology, results, and interpretation. This report shall include:

    - Data tables and figures;

    - Trend analysis and statistical comparisons;

    - Appendices with raw data and validation protocols;

  - The contractor shall develop a draft Standard Operating Procedure (SOP) for the new workflow and provide assay training to CDC staff. Training shall include:

    - A one-week, hands-on workshop conducted at CDC’s designated laboratory facility;

    - Demonstrated execution of the assay by CDC personnel under contractor supervision;

    - Trouble shooting guidance and Q&A sessions;

  - Final deliverables under this milestone shall include:

    - A final report with all comparisons, performance summaries, and SOP(s);

    - Training records;

    - Transfer of key data, materials, and documentation to CDC.

Pending on assay development criteria, all validation data, supporting documentation, and SOPs produced under this optional task shall meet CDC Quality Management System acceptance thresholds and conform to the design-control documentation requirements specified in 21 CFR Part 820.

#### Optional Task C: Epidemiological and Data Science Support

- PLACE OF PERFORMANCE AND CONTRACT SUPPORT HOURS

Place of Performance

The primary place of performance for this contract is at the contractor’s facilities within the United States. Some tasks may require performance at CDC Headquarters in Atlanta, GA (Roybal Campus or other designated CDC facilities) for management, coordination, integration, and surge operations.

Contractors shall maintain the capability to participate in onsite meetings, Program Management Reviews, and other government-directed activities at CDC facilities with reasonable notice.

For security, regulatory, or operational purposes, specific personnel (e.g., Project Managers, IT leads, logistics specialists, emergency liaisons) may be required to be co-located at CDC’s Atlanta facilities on a full-time or as-needed basis, as directed by the COR. Any onsite work must comply with CDC facility access requirements, badging processes, and applicable health and safety protocols.

No work may be performed at CDC facilities on days when government operations are closed (e.g., federal holidays, emergency closures), unless specifically directed by the COR.

All contractor personnel requiring access to CDC networks, systems, or facilities shall complete all CDC-mandated training (e.g., cybersecurity, privacy, biosafety, ethics) within timelines specified by the government. Failure to complete training may result in access suspension and will not relieve the contractor of performance obligations.

Contract Support Hours

Contractor support shall be available during standard business hours, defined as Monday through Friday, 8:00 AM – 5:00 PM Eastern Standard Time (EST), excluding federal holidays. These hours shall remain fixed throughout the year regardless of daylight savings changes.

During declared public health emergencies or other periods of elevated activity, contractors shall provide extended support (including after hours, weekend, or 24/7 coverage) for critical functions, including but not limited to:

• IT system support for the RISER website and CRM;
• Emergency reagent production, packaging, and shipment coordination;
• Customer service for urgent ordering or registration issues;
• Data ingestion and transmission to CDC programs.

The CO will provide written directions when extended coverage is required. Contractors must ensure appropriate staffing and escalation protocols are in place to support these surge or emergency operations.

- TRAVEL

Travel may be required under this contract for purposes including:

• Attendance at Program Management Reviews (PMRs), Technical Working Group sessions, or ad hoc integration meetings at CDC Headquarters in Atlanta, GA;

• Support for surge response activities, including coordination with the CDC Emergency Operations Center or collaboration with domestic or international partner laboratories;

• Travel necessary for facility inspections, system handovers, or contractor transition activities;

• Training or technology transfer activities related to assay workflows or equipment use.

All travel shall be conducted in accordance with Federal Travel Regulations (FTR) and CDC travel approval procedures. Travel costs shall not exceed applicable Federal Travel Regulation (FTR) rates. For estimating travel costs, the contractor shall use GSA FTR Per Diem rates for domestic travel and U.S. Department of State Foreign Per Diem rates for international travel.

All travel must be preapproved in writing by the COR. Contractors shall provide their travel policies to the government for review. Travel will be reimbursed on a cost-reimbursable basis unless otherwise specified in individual task orders.

Travel planning shall include identification of personnel, justification for travel, itinerary, estimated cost, and any special equipment required. The contractor shall ensure all personnel performing on-site support at CDC facilities comply with CDC facility access requirements, including security badging, escort rules, and applicable health and safety protocols. All on-site work shall be coordinated with the COR and appropriate CDC facility security personnel.

- REPORTING REQUIREMENTS

The contractor shall submit all required reports electronically to the CO and the COR in accordance with the delivery schedules and data formats specified in Section XV. All reports, regardless of type or frequency, shall be complete, accurate, and audit-ready, with supporting documentation retained for the period specified in the contract. Reports shall be transmitted in the format specified in the Deliverables Table using a CDC-approved secure file transfer protocol. Each submission shall be reviewed internally by the contractor for quality and compliance prior to delivery to CDC.

Reports may be adjusted or supplemented at CDC’s discretion to support emergency responses, technical reviews, or compliance monitoring.

- Kickoff Meeting and Documentation.

Within fifteen (15) business days of contract award, the contractor shall coordinate an in-person or virtual kickoff meeting with the CDC COR and CO. Participants shall include CDC program SMEs, the RISER Management Team, and key contractor personnel (e.g., Project Director, Principal Investigators). Meeting objectives include confirmation of roles, deliverable schedules, communication protocols, system integration, and surge readiness due to emergency response activities.

- A proposed agenda shall be submitted five (5) days in advance;

- Detailed minutes must be submitted within ten (10) business days post-meeting and appended to the first Monthly Technical Report.

- Weekly Program Management and Coordination.

The contractor shall:

- Participate in weekly program calls with CDC to review activities, flag issues, and update task order progress;

- Submit Weekly Summary Report each Friday by 5:00PM Eastern Standard Time (EST), unless otherwise directed.  The report shall provide a concise but comprehensive overview of ongoing RISER activities and risks discussed during the weekly program calls.  At a minimum, the report shall include:

  - Communication Updates – status of major communications between contractor and CDC, including unresolved issues or needed decisions;

  - Status of Contract Deliverables – progress update for each major task or milestone with indication of on-time vs. delayed performance;

  - Testing Updates – any new, completed or ongoing assay performance, QC tests or stability testing;

  - Government-Furnished Material Updates – receipt, condition, or status changes in CDC-supplied reagents, pathogens, or equipment;

  - Inventory and Reagent Availability – status of reagents in distribution, hold, or production; including stock levels for critical materials; reagent expiration dates;

  - Order Backlog – orders pending > 9 days, with order number, destination, and reason for delay;

  - Registration and User Agreement Updates – newly submitted or pending laboratory accounts, missing information, and approval timelines;

  - Gantt Charts for Product Development – visual schedule tracking progress against development timelines;

  - Known Delays or Risk Items – identified risks with narrative explanation and proposed mitigation or corrective strategies;

  - Financial Summary – weekly burn rate per CLIN, highlighting material, labor and shipping cost trends;

  - Action Items – list of open action items, clearly identifying whether the contractor or the government is responsible for resolution, with expected due dates and status.

NOTE: The cadence of program calls may vary based on government needs.  During declared public health emergencies or periods of increased activity, calls may occur as frequently as daily.  Conversely, in periods of low activity and upon mutual agreement, weekly calls may shift to a bi-weekly cadence.

- Monthly Technical Reports.

By the 15th calendar day of each month, the contractor shall submit electronic copies of the Monthly Technical Report to both the COR and CO.  Reports must reflect work conducted during the previous month and shall include:

- Cover Page with:

  - Contract number and title;

  - Reporting period;

  - Contractor’s name and address;

  - Name(s) of person(s) who prepared the report;

  - Date of submission

- Executive Summary:

Overview of key accomplishments; summary of monthly production and shipment metrics (e.g., number of reagents manufactured, distributed, or acquired), with high-level cumulative and year-to-date totals where applicable; contract deliverable progress; emergent risks; mitigation activities; and corrective actions taken.;

- Analytical Performance Summary:

The body of the Monthly Technical Report shall present summary-level analysis and performance trends, including:

- Inventory and production trends (monthly and cumulative)

- Shipment performance and turnaround analysis (including delays > 9 days)

- Registration and customer-service performance metrics (aligned with KPIs)

- QA/QC performance and stability-testing outcomes

- Financial summary (CLIN-level expenditures and material cost trends)

- IT system performance, uptime, and dashboard operations summary

- Summary of risk posture, top-ranked risks, and cross-domain issues

- Status of integration requests and system enhancements

- Summary of government-furnished equipment status

- Summary of training conducted

- Summary of publications citing RISER materials

- Summary of any surge exercises or emergency activations (if applicable)

Narrative discussion shall emphasize trends, variances from prior months, performance against KPIs, and issues requiring CDC attention.

- Risk and Governance Annex

  - Consolidated Risk Register (detailed log)

  - Risk Heat Map

  - Technology and System Limitations Log

  - Escalated cross-domain issue summaries

Risk Register and Heat-Map Visualization:

The contractor shall maintain a consolidated Risk Register and Heat Map summarizing all open risks across Domains A-D.  The Heat Map shall:

- Categorize risks (e.g., technical, schedule, cost, regulatory, inter-domain)

- Apply a standardized color-coded scoring matrix (e.g., low = green, moderate = yellow; high = red);

- Identify likelihood, impact, mitigation status, and trend directions;

- Track historical changes (month-over-month movement in aggregate risk profile);

- Highlight newly emerging and top-ranked risks.

The Risk Register and Heat map shall be updated monthly and included as an annex to each Monthly Technical Report.  A summary of top-ranked and newly emerging risks shall be presented during each Program Management Review (PMR).

- Contractor Key Performance Indicators (KPI) Monitoring Requirement:

  - The contractor shall continuously monitor performance against all applicable Domain-specific KPIs;

  - A monthly KPI Performance Summary shall be included within the Report, identifying:

    - Each applicable KPI;

    - Actual performance for the reporting period;

    - Cumulative performance for the contract year to date;

    - Any deviations from required thresholds;

  - KPI performance data shall be supported by objective source documentation (e.g., system logs, QA records, CRM metrics, inventory reports);

- Operational Data Appendices:

The following detailed data elements shall be provided as appendices in structured or machine-readable format (e.g., XML, Excel, searchable PDF), as applicable:

- Detailed inventory logs

- Shipment-level production and distribution cost files

- Registration activity logs

- Shipment anomaly logs

- QA/QC logs and user feedback summaries

- Revised SOPs and documentation updates

- Issue tracker updates

- GFE inventory logs

NOTE: The government reserves the right to require these reports quarterly rather than monthly depending on the project phase.  The contractor and the government may mutually agree upon the format of reporting (e.g., narrative, tabular, or hybrid format), as long as it ensures clarity, completeness and ease of review.  If an optional task is activated, contractor shall submit a task-specific supplement describing activities, expenditures and deliverables associated only with the optional scope.  This shall be tracked separately from core contract reporting.

- Annual Technical Reports.

The contractor shall submit a Draft Annual Report no later than 30 calendar days prior to the end of each contract year to the COR.  CDC will provide feedback within 15 business days.  The Final Annual Report shall be submitted electronically to the COR and CO upon incorporation of CDC comments within 30 business days of receiving CDC feedback.  Each Annual Report shall:

- Summarize all major activities and achievements during the contract year;

- Include a current inventory summary and cumulative registration metrics;

- List all SOPs in effect at the time of reporting;

- Highlight changes to the reagent catalog, QA/QC processes and IT systems;

- Capture all user feedback and publications referencing RISER materials;

- Provide tabular reference to reporting months for key deliverables;

- Include a narrative comparison of current year’s performance compared to prior years;

- Provide a year-to-date performance against all applicable Baseline and Incentive KPIs (including certification by the contractor’s Program Manager or Quality Lead attesting to the accuracy of reported KPI data);

  - The Annual KPI summary shall clearly distinguish between:

    - Baseline KPI compliance status (Pass/Fail); and

    - Incentive KPI scoring percentages;

- Recommend any changes or enhancements to better meet project objectives.

E.	Final Technical Report.

No later than 30 days before the contract end date, the contractor shall submit a Draft Final Technical Report to the COR, summarizing all work conducted during the 10-year period.  CDC will provide comments within 15 business days, after which the Final Report is due within 30 business days of receiving CDC feedback.  The Final Report shall:

- Summarize performance across all domains;

- Provide a final inventory of reagents (including active, retained, expired);

- Include a cumulative summary of all SOPs, deliverables, and stakeholder engagement;

- Identify lessons learned, unresolved issues, and recommendations for future contracts;

- Confirm successful transfer of data, systems, and documentation as required.

NOTE: Delays in submission must be justified in writing to the CO.  No costs incurred after the contract end data will be reimbursed without written authorization and contract modification.

F.	Data Governance Plan

The contractor shall submit a comprehensive Data Governance Plan as part of the transition of deliverables.  This document shall include:

- Data architecture maps and metadata inventory;

- System access control protocols and decommissioning strategy;

- Interface specification references and backup data locations;

- Transition protocols for digital assets and historical logs.

The initial version is due within ninety (90) calendar days of contract award and shall be updated annually or upon CDC request. If Task 10 (Surge Support) is activated, the contractor shall ensure the Data Governance Plan reflects surge-related data flows and integration updates as applicable.

G.	Closeout Deliverables.

At the end of the contract, the contractor shall deliver the following to CDC and/or the incoming contractor (if applicable):

- Complete inventory of all RISER reagents, maintained under proper storage conditions;

- All databases and documentation supporting contract performance;

- Comprehensive listings of inventory, registrants, order logs, and archived records;

- Labeled and indexed physical files, equipment logs, and decommissioning documentation;

- Written certification that all data and property have been transferred, and no RISER-related assets remain with the incumbent.

H. 	Reporting Requirements for Optional Tasks

If Optional Task B is activated, the contractor shall:

- Submit a Gap Analysis Technical Report within 45 calendar days;

- Provide biweekly oral briefings on assay development progress;

- Submit a Final Assay Validation Report, SOPs, and training documentation upon milestone completion, and;

- Include monthly summary status and risks in the standard Monthly Status Report and quarterly progress updates.

During declared public health emergencies or urgent reagent deployment scenarios, any deviation from standard ordering or shipping procedures, including temporary modification of standard CDC approval workflows, shall occur only pursuant to written direction from the CDC Contracting Officer (CO), COR, or other authorized CDC official. Such deviations must be documented with CDC-approved justification.  The contractor shall:

- Maintain an emergency override log capturing the requester, justification, CDC approver, data-time of action, and reagent affected;

- Transmit this log to the COR in the next scheduled Monthly Technical Report or within 5 business days for high-impact deployments;

- Retain this log as part of the formal RISER audit record for no less than 5 years.

- INCIDENT RESPONSE AND CORRECTIVE ACTION FOR MATERIAL STORAGE

The contractor shall:

- Immediately quarantine any government-furnished materials affected by environmental excursions or facility failures;

- Notify the CO and COR of any incident affecting material storage conditions within twenty-four (24) hours of discovery;

- Submit a preliminary written incident report within five (5) business days, detailing:

  - Date, time, and duration of the incident;

  - Temperature logs and monitoring records;

  - Lot numbers, quantities, and types of affected materials;

  - Immediate actions taken;

  - Preliminary root cause analysis;

- Develop and submit a CAPA plan within ten (10) business days, which shall include:

  - Root cause determination;

  - Corrective measures and timelines not exceeding thirty (30) calendar days unless otherwise authorized by the COR;

  - Preventive steps to avoid recurrence;

CDC reserves the right to review, approve and verify completion of the CAPA plan.  Contractor shall submit biweekly updates on CAPA status until closure is achieved.

- Maintain an incident log accessible to CDC upon request.

Repeated incidents or failure to comply with these requirements may result in:

- Financial offsets;

- Withholding performance-based payments;

- Contract modification or termination for cause.

In addition to incidents occurring within contractor-controlled storage environments, this section also applies to materials that are compromised during shipment due to courier delays, customs holds, or field handling issues. For shipment-related material failures, including those identified by recipient laboratories upon delivery, contractors shall follow the notification, documentation, and quarantine protocols described in Appendix C – Task 8, Section 4: Documentation and Order Recordkeeping. Returned materials suspected of being compromised shall be segregated from active inventory, and any viability testing results reported by the recipient shall be conveyed to CDC immediately to assess the need for replacement shipments or additional investigation.

- GOVERNMENT FURNISHED MATERIALS

Upon contract award and approval of the contractor’s SOPs governing the secure receipt, storage, tracking, and reporting of biological materials, the government shall initiate the transfer of all RISER-related pathogens, reagents, and reference materials from the incumbent CDC-IRR contractor’s facility to the new contractor’s designated storage site.

The initial RISER inventory to be furnished by the government is estimated to include:

- Over 300,000 vials containing viruses, bacteria, antigens,  antisera, cell lines, monoclonal antibodies, plasmids, and other genetic materials; and

- Over 65,000 Reverse Transcription Polymerase Chain Reaction (RT-PCR) typing kits and reagent panels supporting CDC-developed surveillance platforms.

The contractor shall receive, document, and store all government-furnished materials in accordance with approved biosafety protocols and regulatory requirements (e.g., Select Agent, FDA, IATA). Inventory must be logged upon arrival into the RISER catalog and made available to CDC via secure, audit-ready digital systems.

The contractor shall notify the Contracting Officer (CO) and Contracting Officer’s Representative (COR) in writing within five (5) business days if any issues, discrepancies, or delays are encountered during the transfer of government-furnished materials from the incumbent contractor. Notification shall include a description of the issue, potential impacts on material integrity or chain-of-custody and proposed corrective measures.

The government reserves the right to audit receipt and integration activities during and after the transfer.

- INSURANCE REQUIREMENTS

The contractor shall maintain, at its own expense, insurance coverage of the types and minimum amounts specified below for the entire period of performance, including all option periods:

- Commercial General Liability Insurance: Minimum $1,000,000 per occurrence and $2,000,000 aggregate.

- Property Insurance: Sufficient to cover loss or damage to contractor-owned or leased facilities, equipment, and materials used in performance of this contract.

- Errors and Omissions (Professional Liability) Insurance: Minimum $1,000,000 per claim.

Where permissible under applicable law, insurance policies shall name the United States government as an additional insured.

Proof of Coverage: The contractor shall provide Certificates of Insurance to the Contracting Officer and Contracting Officer’s Representative within 30 calendar days of contract award, annually thereafter, and upon request. Certificates shall clearly identify the coverage types, limits, effective dates, and any additional insured designations. Failure to maintain required coverage may be grounds for termination for default.

- DATA OWNERSHIP AND RETENTION CLAUSE

All data, logs, reports, and records generated under this contract are the property of the United States government.  The contractor shall retain such records for a minimum of five (5) years after contract completion or longer if required by applicable law or regulation.  Upon request, the contractor shall promptly provide copies of all such records to the government in a format specified by the COR.

Any software, source code, scripts, configurations, system integrations, dashboards, workflows, or other custom-developed technical artifacts created or modified specifically for the RISER program under this contract shall be delivered to the government with rights consistent with FAR 52.227-14 (Rights in Data – General) and any other applicable contract clauses. The contractor shall provide sufficient documentation, configuration metadata, and access credentials to ensure continuity of operations and transition to CDC or a successor contractor.

Nothing in this clause shall be construed to transfer ownership of contractor-developed proprietary tools, pre-existing software, or intellectual property developed independently of this contract, except to the extent such materials are modified or funded under this contract.

- MULTI-VENDOR COORDINATION AND INTEGRATION

All SOPs, dashboards, and reports shall use CDC-approved standardized formats to ensure interoperability and seamless integration across all RISER domains and vendors.

  - Purpose:

In the event that multiple contract awards are issued under the RISER program, effective coordination and integration among contractors are essential to maintain continuity of operations for global reagent production, storage, distribution, catalog management, and emergency response support.  The requirements in this section apply to all contractors performing work under the RISER Statement of Work.

  - Government Designation of Integration Lead:

- The government reserves the right to designate an Integration Lead for RISER.  This may be:

  - A government representative; or

  - One of the awarded contractors designated as Lead Systems Integrator (LSI).

- The Integration Lead shall:

  - Coordinate technical, logistical, and administrative activities across all RISER contractors;

  - Oversee alignment of deliverables and ensure interoperability between systems, processes, and data flows;

  - Facilitate joint planning and reporting to the government COR and CO

In the event the government designates an Integration Lead, the Integration Lead shall have the authority to:

- Recommend modifications to technical approaches, schedules, or deliverables where necessary to achieve cross-vendor integration;

- Identify and propose resolutions for inter-vendor conflicts;

- Request joint impact assessments from all affected contractors when changes are proposed.

The Integration Lead shall not have contractual authority to:

- Issue task orders or obligate funding;

- Modify contract terms or pricing.

All final decisions affecting contractual obligations remain the responsibility of the government CO.

  - Contractor Cooperation Requirement:

All RISER contractors shall:

- Cooperate fully with the government, the Integration Lead, and other RISER contractors;

- Share relevant technical, operational, and schedule information necessary to ensure seamless integration of RISER tasks and deliverables;

- Participate in joint planning, risk management, and emergency response exercises as required by the government;

- Adhere to RISER-established processes and protocols for communication, data exchange, and problem resolution.

Data Sharing Requirements:

Contractors shall share data necessary for performance of cross-domain tasks in accordance with CDC-approved security, confidentiality, and data-governance protocols. Data sharing shall be categorized as follows:

- Mandatory Shared Data (Government and applicable RISER awardees)

The following data elements shall be shared with the government and, where operationally required, other RISER awardees to ensure seamless integration and continuity of operations:

  - Inventory levels and availability status for reagent handoffs;

  - Production schedule milestones required for downstream logistics planning;

  - Interface specifications necessary for system interoperability;

  - Status updates for emergency response coordination.

- Restricted Data (Government-Only, not shared with other contractors)

The following categories of data shall be provided  to the government but shall not be shared with other RISER awardees unless explicitly authorized in writing by the Contracting Officer:

  - Contractor cost or pricing data beyond government reporting requirements;

  - Proprietary internal process documentation not required for integration;

  - Internal quality management documentation unless specifically requested by the government.

The government reserves the right to direct additional data sharing as needed for program oversight.

  - Integrated Master Schedule:

RISER contractors shall jointly develop and maintain a government-approved Integrated Master Schedule that:

- Identifies all program tasks, milestones, and interdependencies across contractors, including:

  - Reagent manufacturing and packaging timelines;

  - Logistics and distribution milestones;

  - Website/CRM development and updates;

  - Emergency response activation timelines.

- Reflects critical paths, resource constraints, and schedule risks impacting RISER operations;

- Is updated monthly or as otherwise directed by the government.

  - Interface Control Documentation:

RISER contractors shall jointly develop and maintain ICDs that define:

- Data formats, security protocols, and exchange frequencies for:

  - Reagent inventory management systems;

  - Order processing and CRM data flows;

  - Shipment tracking and logistics data;

  - Unburdened reagent and distribution costs.

- Technical standards to ensure interoperability of RISER systems;

- Responsibilities for data creation, sharing, and consumption between contractors.

ICDs shall be:

- Submitted to the government for approval;

- Updated as necessary to reflect changes in RISER operations, systems, or requirements.

Contractors shall jointly develop security architecture diagrams identifying logical separations, access controls, and role-based permissions in all shared IT platforms.  Diagrams shall be included as part of ICDs.

  - Joint Meetings:

All RISER contractors shall participate in the following joint meetings unless otherwise directed:

- Weekly Technical Working Group Meetings

  - Purpose: Coordinate technical activities including reagent production planning, website/CRM development, and logistical integration.

- Monthly Program Management Reviews (PMRs)

  - Purpose:  Review overall RISER performance, risk status, deliverables, and inter-vendor dependencies.

- Quarterly Executive-Level Reviews

  - Purpose: Discuss strategic program goals, significant risks or barriers, and upcoming operational priorities (e.g., emergency preparedness)

Contractors shall:

- Provide agendas in advance of meetings;

- Record and submit meeting minutes documenting discussions, action items, responsible parties, and deadlines.

Participation in any emergency preparedness exercises (e.g., mock surge drills or tabletop simulations) shall occur only if formally directed by the CDC through written COR notification or, where such participation requires modification of contract scope or funding, through written direction from the Contracting Officer (CO).

  - Shared Tools and Platforms:

RISER contractors shall utilize government-approved tools for:

- Document sharing and management (e.g., CDC SharePoint);

- Issue and task tracking (e.g., Jira, or other CDC-approved systems);

- Collaborative development and knowledge management (e.g., Confluence or other CDC-approved systems).

Contractors shall comply with all security, privacy, and access controls established for RISER program operations.

Contractors shall coordinate with the Integration Lead and government regarding cost allocation for shared Informational Technology systems, licenses, or collaborative tools used under the RISER program. Contractors shall:

- Identify any anticipated shared system costs in proposals and during task order negotiations;

- Avoid duplicative software licenses or hosting costs;

- Document the proportional usage basis for allocating shared system costs if costs are split among multiple contractors.

The government reserves the right to review and approve shared cost allocations and disallow duplicative charges.

The Integration Lead shall administer collaboration platforms and approve configuration changes.  Contractors shall not independently modify shared tool architecture without prior Integration and government approval.

  - Joint Risk and Issue Management:

RISER contractors shall maintain a consolidated RISER Program Risk and Issue Log that captures:

- Technical risks affecting cross-vendor integration;

- Operational risks related to reagent inventory, logistics disruptions, emergency response, and system interoperability;

- Mitigation plans assigned owners and timelines for resolution.

Cross-vendor risks or issues shall be jointly reviewed and addressed during scheduled PMRs and Technical Working Group meetings.

In the event of cross-domain risk or system conflict, CDC will serve as the final adjudicating authority.  CDC may also designate a RISER Coordinating contractor to facilitate documentation, technical validation, and inter-vendor consensus during remediation.

  - Joint Change Control Board:

Contractors shall participate in a Joint Change Control Board (JCCB) for RISER. The JCCB shall:

- Review proposed changes to interfaces, shared systems, or processes affecting more than one Domain;

- Require submission of impact assessments including:

  - Technical impacts;

  - Schedule implications;

  - Cost estimates.

- Develop recommendations for government approval.

No contractor shall implement cross-domain changes without government written approval unless explicitly authorized for emergency actions.

  - Intellectual Property Protection:

Contractors shall retain ownership of proprietary tools, software, or processes developed outside the RISER contract, except where deliverables are funded entirely under this contract. For any custom development funded under the RISER program:

- All deliveries, including software source code, documentation, and configurations, shall be provided to the government with unlimited rights;

- Contractors shall not impose restrictions on other RISER awardees’ use of government-funded deliverables necessary for program continuity.

Contractors shall ensure that confidential business information is not disclosed to other RISER awardees without prior written government authorization.

  - Dispute Resolution Process:

In the event of a dispute between RISER contractors concerning task assignments, data sharing, technical integration, or operational coordination, the following escalation process shall apply:

- Contractors shall first attempt to resolve disputes collaboratively;

- If unresolved within five (5) business days, the matter shall be escalated to the government COR and CO for resolution;

- The CO’s decision shall be final.

During declared public health emergencies, disputes that may impact operational readiness shall be escalated to the CO within one business day.

  - Standardized Reporting:

All RISER contractors shall submit reports in government approved formats to:

- Enable consolidation of information across all RISER work streams;

- Support consistent reporting of:

  - Inventory levels;

  - Distribution performance metrics;

  - Website/CRM performance data;

  - Emergency response readiness.

- Facilitate government oversight and program decision-making.

  - Surge Cost Management and Emergency Participation:

All RISER contractors shall:

- Support surge production and logistics activities during public health emergencies as directed by the government.;

- Provide estimates of incremental costs associated with surge activities promptly upon government request;

- Not refuse participation in emergency operations solely based on cost concerns without first submitting justification to the CO for review.

The government may authorize equitable adjustments or cost-sharing mechanisms for extraordinary surge costs exceeding baseline funding levels.  If contractors cannot agree on cost allocation for shared systems or licenses, the matter shall be escalated to the CO for final determination.

  - Personnel Conflicts of Interest:

RISER contractors shall:

- Ensure personnel hired from another RISER prime contractor or major subcontractor are screened for potential conflicts of interest;

- Prevent transfer of proprietary, business-sensitive, or confidential information between contractors without government consent;

- Promptly disclose any proposed hires that could create conflicts of interest for government review and approval.

  - Shared Performance Metrics and Accountability:

For performance metrics impacted by multiple contractors, the government shall:

- Designate a primary contractor responsible for reporting and achieving each metric;

- Require collaborative root cause analysis where failures result from shared responsibilities;

- Reserve the right to apportion performance incentives or penalties based on contributions to metric outcomes across contractors.

  - Partial Domain Transition Planning:

In the event of a transition affecting only one Domain:

- Remaining RISER contractors shall cooperate in transferring relevant data, systems, and interfaces to the successor contractor;

- Transition plans shall include:

  - Joint meetings with incoming contractor staff;

  - Data mapping and system interface walkthroughs;

  - Handover of documentation relevant to cross-domain processes.

The government may direct additional support from contractors not affected by the transition to ensure continuity.

All contractors shall submit draft partial transition plans for their respective Domains within 180 days of contract award.  Plans shall be updated annually or upon significant operational changes.

  - Emergency Communication Command Structure:

During declared public health emergencies, the government may designate an Emergency Operations Lead EOL who shall:

- Act as the single point of contact for operational coordination across all contractors;

- Provide interim operational direction necessary to protect public health, subject to the limits of existing contract scope and available funding, and subject to subsequent review and ratification by the CO.

In emergency situations requiring immediate action, the EOL may issue written interim operational direction.  Contractors shall comply with such direction to the extent consistent with existing contract scope and funding.  Only the CO possesses the legal authority to obligate funds, modify task orders, or authorize equitable adjustments.

Any EOL directive that may result in work beyond established funding ceilings or outside existing task order scope shall:

- Be documented in writing by the EOL within 24 hours;

- Be submitted to the CO for review and potential ratification; and

- Not be deemed binding with respect to funding or scope modification unless and until ratified by the CO.

The contractor shall not bear financial risk for costs reasonably incurred under EOL emergency direction that is subsequently ratified by the CO. If ratification is not granted, resolution shall occur in accordance with applicable contract clauses governing changes and disputes.

  - Surge Reallocation Authority:

In the event of a public health emergency or other surge activation, the government reserves the unilateral right to reassign, redistribute, or supplement task responsibilities across RISER domains or contractors if it determines that a contractor has reached its maximum operating or surge capacity. Such reassignments shall be made through written notification from the CO and may include:

- Issuing supplemental task orders to another contractor within the same Domain;

- Shifting surge-related work to another qualified Domain contractor;

- Reducing task scope temporarily for the saturated contractor to relieve performance burden.

This authority applies only during government-declared emergencies or surge activation and does not alter the base performance obligations outside of such events.

Domain Leadership and Vendor Coordination in Multi-Award Scenarios

To accommodate the hybrid acquisition structure of RISER and promote effective performance across multiple awardees, the following guidance clarifies domain leadership, inter-domain integration responsibilities, and CDC's coordination expectations under a multi-vendor model.

1. Domain Leadership Roles: Each Domain (A through D) may be awarded to a separate contractor. For all task execution, the contractor assigned to a specific domain shall be considered the "Domain Lead Contractor" for that area. The Domain Lead Contractor is accountable for the execution, quality assurance, documentation, and reporting of tasks within that Domain.

Domain Leadership and Vendor Coordination in Multi-Award Scenarios

| Domain | Title | Core Scope | Lead Contractor Responsibilities* |
| --- | --- | --- | --- |
| A | Core Reagent Production and Catalog Management | SOPs; QA/QC; batch manufacturing; stability and shelf-life program; catalog operations; surge planning | Reagent formulation/production; lot tracking and QA records; catalog maintenance and updates; transfer of finished lots and COAs to Domain B; maintain surge production readiness and support transition tasks as directed. |
| B | Facility Operations and Logistics | Qualified facilities (BSL-1 to BSL-4); secure storage and climate control; cold-chain shipping; domestic/international logistics and regulatory compliance | Secure storage and inventory custody; packaging and temperature-controlled distribution; courier/customs coordination and delivery verification; maintain surge shipping capability; support transition logistics as directed. |
| C | IT and Data Systems | Website, CRM, APIs, ICDs/SCAP; data governance and dashboard support; security and uptime | Host and operate website/CRM; manage integrations and ICDs/SCAP; ensure DMI-aligned data exchange; maintain 99.95% availability targets; enable emergency data routing and support transition of data/assets as directed. |
| D | Customer Service and Stakeholder Support | Registration and UA processing; help desk; customer communications; complaint handling; surge coverage | Vet laboratories and process User Agreements; operate hotline/email and CRM ticketing; coordinate shipment status communications with Domain B and portal support with Domain C; extend hours and staff during surge; support orderly transition of customer-service records |

*Surge Support and Outgoing Transition are exercised as optional tasks across Domains A-D (Tasks 10-11).

2. CDC Integration Lead and Oversight: CDC will designate an Integration Lead to facilitate communication across Domains and ensure continuity where tasks require data or operational handoffs between vendors.  The Integration Lead may be the COR or another CDC-designated official, as determined by the government.  This Integration Lead will:

- Review ICDs;

- Coordinate joint meetings and root cause analyses;

- Resolve cross-vendor data integrity or operational issues.

3. Cross-Domain Coordination Requirements: Some RISER functions are inherently shared across Domains. Contractors must:

- Participate in joint planning sessions;

- Maintain system compatibility (e.g., APIs between Domains A, B, C, and D);

- Use standardized formats for SOPs, dashboards, and reports.

If all Domains are awarded to a single contractor, the government may consolidate Cross-Domain coordination activities and deliverables under that contractor’s integrated program management structure.

- DELIVERY SCHEDULE

Applicability of Cross-Domain Deliverables:

The Deliverables Table below includes both Domain-specific and Cross-Domain deliverables. Cross-Domain deliverables (e.g., joint risk logs, integration meeting minutes, or other multi-vendor coordination reports) apply only when more than one contractor is awarded under the RISER program.

In the event that a single offeror is awarded all Domains (A–D), the government may, at its discretion, waive or consolidate such Cross-Domain deliverables into a single integrated deliverable or into standard Monthly Technical Reports. The Contracting Officer (CO) will identify any waived or consolidated deliverables at the time of award or through written modification.

Regardless of award configuration, the contractor remains responsible for maintaining internal records that demonstrate equivalent coordination, integration, and quality management consistent with the intent of each deliverable.

| RISER Contract Delivery Schedule |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Cross-Domain Deliverables |  |  |  |  |  |  |
| Item # | Domain / Task | Description | Deliverable Detail | Quantity / Format | Delivery Date | Delivery To |
| 1 | All Domains / Startup | Kickoff meeting Agenda and Minutes | Agenda and post-meeting minutes confirming roles, deliverables, communication protocols, and emergency readiness | 1 electronic copy / Word | Agenda – 5 days before meeting; Minutes – within 10 business days following the kickoff meeting | CO / COR / RISER Management Team |
| 2 | All Domains / Startup | Certificates of Insurance | Proof of active Commercial General Liability, property, and Errors & Omissions coverage naming U.S. Gov as additional insured (where permissible) | 1 electronic copy / PDF | Within 30 calendar days of award; annually or upon CO request | CO and COR |
| 3 | All Domains / Transition (Task 11*) | Draft Partial Transition Plans (for each Domain) | Preliminary cross-Domain transition strategies including personnel, data, and inventory handoff plans with a preliminary Data Governance outline | 1 electronic copy / Word and XML | Within 180 calendar days of contract award; updated annually or upon operational changes | COR, SMEs, RISER Management Team |
| 4 | All Domains / Transition (Task 11*) | Final Transition Plans (comprehensive plan integrating all Domains) | CDC-approved comprehensive transition plan that integrates all Domain A-D plans into one coordinated schedule, defining roles, timelines, and handoff procedures for program-wide continuity | 1 electronic copy / Word and XML | At least 18 months prior to contract expiration | COR |
| 5 | All Domains / Transition (Task 11*) | Updated Partial Transition Plans | Annual updates to Domain-specific transition strategies reflecting organizational or operational changes | 1 electronic copy / Word and XML | Annually or upon major change | COR |
| 6 | All Domains / Reporting | Weekly Summary Report | Summary of program status, risks, deliverables and key metrics | 1 electronic copy / searchable PDF | By 5:00PM EST each Friday | COR and RISER Management Team |
| 7 | All Domains / Reporting | Weekly Data Reports | Reagent and shipment snapshot aligned with weekly call cadence | 1 electronic copy / XML | By 5:00PM EST each Friday | COR, SMEs, and RISER Management Team |
| 8 | All Domains / Reporting | Monthly Technical Report | Narrative and quantitative update on tasks, inventory, risks, QA/QC metrics, and cross-Domain performance including dashboard and system logs | 1 electronic copy / searchable PDF and XML | By the 15th calendar day of each month | COR, SMEs, and RISER Management Team |
| 9 | All Domains / Reporting | Risk and Issue Log | Rolling register of identified risks and mitigation status; full log available on request | 1 electronic copy / Word and XML | Included in each Monthly Technical Report; full log upon request | COR, SMEs, and RISER Management Team |
| 10 | All Domains / Reporting | Risk Register Heat Map | Graphical summary of risk likelihood, impact, trend, and mitigation status, annexed to Monthly Technical Report and presented at PMRs | 1 electronic copy / Excel or searchable PDF | Monthly with Technical Report; summarized at PMRs | COR and RISER Management Team |
| 11 | All Domains / Reporting | Technology and System Limitations Log | Summary of architectural or programming constraints affecting performance and interoperability | 1 electronic copy / Word and XML | Included in each Monthly Technical Report; full log upon request | COR, SMEs, and RISER Management Team |
| 12 | All Domains / Reporting | Annual Technical Report – Draft | Year-end summary of contract performance for CDC review | 1 electronic copy / searchable PDF and XML | 30 calendar days before end of each contract year | COR and RISER Management Team |
| 13 | All Domains / Reporting | Annual Technical Report – Final | Final version of Annual Report after CDC comment resolution. | 1 electronic copy / searchable PDF and XML | Within 30 business days after receiving CDC feedback | CO, COR, SMEs, and RISER Management Team |
| 14 | All Domains / Closeout | Final Technical Report – Draft | Summary of all contract activities and lessons learned for CDC review. | 1 electronic copy / searchable PDF and XML | 30 calendar days before contract end date | COR and RISER Management Team |
| 15 | All Domains / Closeout | Final Technical Report | Approved summary of contract performance across all Domains. | 1 electronic copy / searchable PDF and XML | Within 30 business days after receiving CDC feedback | CO, COR, SMEs, and RISER Management Team |
| 16 | All Domains / Risk & Compliance | Corrective and Preventive Action (CAPA) Plan | Post-incident root-cause and preventive-action plan with bi-weekly status updates until closure. | 1 electronic copy / searchable PDF | Within 10 business days of incident; updates bi-weekly until resolved | CO, COR, SMEs and RISER Management Team |
| 17 | All Domains / Risk & Compliance | Emergency Override Log | Documentation of CDC-approved SOP deviations during emergencies with justifications and approvals | 1 electronic copy / Word and XML | With Monthly Report or within 5 business days of action | CO and COR |
| 18 | All Domains / Joint Vendor Coordination | Minutes from Joint Vendor meetings (Program Management Reviews and Technical Working Groups) | Meeting minutes documenting cross-contractor discussions, action items and deadlines | 1 electronic copy / Word | Within 5 business days after meeting | COR and RISER Management Team |
| 19 | All Domains / Joint Vendor Coordination | Joint Risk and Issue Log (Integrated) | Cross-contractor log tracking multi-vendor risks and inter-Domain dependencies. | 1 electronic copy / Word and XML | Updated monthly or as requested | COR, RISER Management Team, Integration Lead |
| 20 | All Domains / Joint Vendor Coordination | Joint Change Control Board Impact Assessments | Impact analysis for proposed cross-Domain changes submitted through Joint Change Control Board | 1 electronic copy / Word | As needed per change proposal | COR and Joint Change Control Board |
| 21 | All Domains / Surge & Transition | Rapid Vendor Onboarding Protocol | Comprehensive, CDC-approved procedure describing how new subcontractors, manufacturers, couriers, or technology partners will be qualified and activated within 10 business days of CDC direction during surge or transition operations. The protocol shall include templates for NDAs, Data-Sharing Agreements, Quality Assurance Addenda, and vetting checklists. | 1 electronic copy / Word (+ supporting forms in PDF or XML) | Initial submission within 90 calendar days of award; annual updates or as requested by CDC | CO, COR, RISER Management Team, and SMEs |
| 22 | All Domains / Post-Emergency After-Action Report | Post-Emergency After-Action Report | Written after-action report submitted following deactivation of a public health emergency task order. The report shall summarize activities conducted under emergency authority, inventory reconciliation, remaining emergency stock levels, lessons learned, operational challenges, mitigation strategies, recommendations for future response optimization, and any deviations from standard processes. Supporting production logs, shipping records, QC summaries, and deviation documentation shall be included | 1 electronic copy / Word (+ supporting forms in PDF or XML) | Initial submission within 30 calendar days following deactivation of the applicable emergency task order; | COR and RISER Management Team |
| 23 | All Domains / Final Transition Report | Final Transition Report | Comprehensive report submitted upon completion of the transition period summarizing completed transition activities, timeline adherence, inventory transfer logs, system handoff records, documentation of data and material disposition, unresolved issues (if any), and recommendations for future RISER transitions. | 1 electronic copy / Word (+ supporting forms in PDF or XML) | Within 30 calendar days following completion of Task 11 | COR and SMEs |
| Domain A: Core Reagent Production and Catalog Management |  |  |  |  |  |  |
| 24 | Domain A / Task A.1 | Draft Standard Operating Procedures (SOPs) | Initial SOPs covering all technical and operational activities (production, QA/QC, shipping, inventory). Must include cross-Domain interface points | 1 electronic copy / Word | Within 60 calendar days of contract award | COR and SMEs |
| 25 | Domain A / Task A.1 | Final Standard Operating Procedures (SOPs) | COR-approved SOPs replacing drafts; compliant with CDC QMS, ISO 13485, and 21 CFR Part 820 | 1 electronic copy / searchable PDF | Within 120 calendar days of contract award | COR, RISER Management Team, and SMEs |
| 26 | Domain A / Task A.2 | Quality Assurance and Quality Control (QA/QC) Plan | Plan detailing QA/QC processes, batch-record retention, reagent rejection criteria, and customer-complaint procedures | 1 electronic copy / searchable PDF | Within 60 calendar days of contract award | CO, COR, RISER Management Team, and SMEs |
| 27 | Domain A / Task A.2 | Supply Chain Risk Management Plan | Comprehensive plan identifying critical materials, single-source suppliers, alternate sourcing and substitution protocols, and risk-mitigation strategies to ensure continuity of reagent production and distribution. Plan shall include supplier qualification criteria, equivalency validation procedures, and annual update requirements. | 1 electronic copy / Word and XML (optional appendices) | Initial submission within 120 calendar days of award; updated annually or upon significant supplier or regulatory change | COR, RISER Management Team, and SMEs |
| 28 | Domain A / Task A.3 | Production and Inventory Management Plans | Dual plans defining reagent production timelines, acquisition strategies, and supply-chain risk management | 1 electronic copy / Word and XML | Within 150 calendar days of contract award; updated annually or as directed | COR, RISER Management Team, and SMEs |
| 29 | Domain A / Task A.4 | Stability Testing Plan | Comprehensive plan detailing reagent stability-testing cadence, protocols, pass/fail criteria, and data retention requirements | 1 electronic copy / Word or XML | Initial plan within 30 calendar days of each performance period start; updated annually | COR, RISER Management Team, and SMEs |
| 30 | Domain A / Task A.4 | Stability Testing Reports | Reports summarizing test results, expiry reagents, and CAPA actions; cross-referenced to lot numbers and inventory records | 1 electronic copy / Word or XML (+ raw data XML) | Quarterly or within 10 business days following completion of testing cycle | COR, RISER Management Team, and SMEs |
| 31 | Domain A / Task A.4 | Expiration Forecast Report | Monthly list of reagents reaching expiry within 60 days with CDC-approved disposition instructions | 1 electronic copy / XML | Monthly (embedded in the Technical Report) | COR, RISER Management Team, and SMEs |
| 32 | Domain A / Task A.2 + A.3 | Production Batch Records | Complete batch records for all reagents produced, including QA/QC results and CDC approvals | 1 electronic copy / Word and XML | Prior to contract completion and upon CDC request | COR and SMEs |
| 33 | Domain A / Task A.4 (Coordinated with Domain C)** | External Data Upload Integration Validation Logs | Verification logs documenting successful transmission, format validation, and receipt acknowledgment of stability-testing results and reagent-validation datasets in CDC-approved formats. Logs shall identify transmission method, date/time of submission, CDC recipient, and any subsequent corrections or updates. | 1 electronic copy / Word and XML | With Quarterly Stability Reports or upon system update | COR and Domain C Lead |
| 34 | Domain A / Task A.5 (Task 10 Ref.*) | Surge Capacity Plan (Production Focus) | Domain A-specific contingency procedures for scaling production and QA/QC 25–75 % above baseline within 10 business days of CDC direction. Include a KPI Mapping Matrix that identifies which Appendix D KPIs apply during surge and where the metrics will be reported. | 1 electronic copy / searchable PDF | Within 90 calendar days of contract award; update annually or after activation | CO, COR, RISER Management Team, and SMEs |
| 35 | Domain A / Task A.6 (Task 11 Ref.*) | Transition Support Records | Documentation of production-date handoff, batch records, and QA archives transferred to successor contractor during transition | 1 electronic copy / Word and XML | Upon transition task activation or contract closeout | COR, RISER Management Team, and SMEs |
| Domain B: Facility Operations and Logistics |  |  |  |  |  |  |
| 36 | Domain B / Task B.1 | Facility Provision and Compliance Documentation | Proof of facility registration and inspection readiness (Select Agent Program, USDA, FDA, and CDC biosafety standards). Includes accreditation and inspection readiness evidence | 1 electronic copy / PDF | With technical proposal and maintained throughout contract period | CO, COR, and SMEs |
| 37 | Domain B / Task B.2 | Facility Environmental Control Records | Temperature mapping and validation records for all storage zones; includes emergency power verification and CAPA for any failures | 1 electronic copy / Word and XML | Submitted annually or upon COR request | COR and RISER Management Team |
| 38 | Domain B / Task B.2 | CAPA Documentation for Storage Deviations | Root-cause and corrective actions for temperature excursions or facility incidents | 1 electronic copy / Word and XML | Submitted annually or upon COR request | COR and RISER Management Team |
| 39 | Domain B / Task B.3 | Shipping and Logistics SOPs | CDC-approved standard procedures for domestic and international shipping, including documentation, cold-chain integrity, and customs compliance | 1 electronic copy / PDF | Within 60 calendar days of award; update annually or upon CDC request | COR, RISER Management Team, and SMEs |
| 40 | Domain B / Task B.3 | Shipping Authorization and Tracking Records | Shipment-level records linking CDC COR authorization, tracking data, and delivery confirmations (domestic within 12 hours, international within 24 hours) | 1 electronic copy/ XML | Track for each shipment and summary must be included in Weekly and Monthly Reports | COR and RISER Management Team |
| 41 | Domain B / Task B.3 | Returned / Compromised Reagents Protocol Report | Documentation of reagents returned due to suspected compromise (cold-chain breach or customs delay) with test results and resolution | 1 electronic copy / Word and XML | Within 5 business days of event or in next Monthly Technical Report | COR, RISER Management Team, and SMEs |
| 42 | Domain B / Task B.3 | Shipment Incident Log | Cumulative log of shipment delays, customs issues, cold-chain failures, and mitigations | 1 electronic copy / XML | Updated continuously; summary in Monthly Technical Report | COR, RISER Management Team, and SMEs |
| 43 | Domain B / Task B.3 (Coordinated with Domain C)** | Shipment Data Integration Validation Logs | Evidence of successful data sync between shipping systems and CDC CRM via approved ICDs | 1 electronic copy / XML or Word | With Monthly Technical Report or upon system change | COR and Domain C Lead |
| 44 | Domain B / Task B.3 | Quality Assurance and Quality Control (QA/QC) Plan | Quality Assurance and Quality Control Plan governing storage, cold-chain management, packaging validation, shipment verification, incident reporting, CAPA procedures, and logistics-related quality controls. | 1 electronic copy / searchable PDF | Within 60 calendar days of contract award | CO, COR, RISER Management Team, and SMEs |
| 45 | Domain B / Task B.4 (Task 10 Ref.*) | Surge Shipping SOP and Logistics Surge Plan | Written SOP and plan for scaling warehousing and shipping operations up to 75% above baseline within 10 business days; includes mock drill if directed. Include a KPI Mapping Matrix that identifies which Appendix D KPIs apply during surge and where the metrics will be reported. | 1 electronic copy / searchable PDF | SOP and Plan within 180 calendar days of award; drill annually (if requested) | CO, COR, RISER Management Team, and SMEs |
| 46 | Domain B / Task B.5 (Task 11 Ref.*) | Facility and Inventory Transfer Records | Final records documenting physical transfer of inventory, permits, and facility documentation to successor contractor | 1 electronic copy / Word and XML | Upon transition task activation or contract closeout | COR, RISER Management Team, and SMEs |
| Domain C: IT and Data Systems |  |  |  |  |  |  |
| 47 | Domain C / Task C.1 (ref. Task C.2***) | Interface Control Documents Development and Maintenance Plan | Comprehensive plan governing creation, review, and version control of Interface Control Documents (ICDs) for RISER IT systems (i.e., website and CRM); includes security architecture diagrams, APIs, and security boundaries | 1 electronic copy / searchable PDF | Within 60 calendar days of contract award | COR and RISER Management Team |
| 48 | Domain C / Task C.1 (ref. Task C.2***) | Technical Integration Plan | Plan detailing real-time bidirectional API architecture, Microsoft Dynamics 365 CRM integration, XML exchange specs, and scalability/performance targets | 1 electronic copy / searchable PDF | Initial submission within 90 calendar days of award; updated annually or upon CDC request | CO, COR, RISER Management Team |
| 49 | Domain C / Task C.1 (ref. Task C.2***) | Shared Cost Allocation Plan | Allocation of shared hosting, license, and platform costs; includes methodology and supporting Excel calculations | 1 electronic copy / Word and XML | Initial plan due within 90 calendar days of award; updated annually or upon significant change | COR |
| 50 | Domain C / Task C.1 | Data Governance Plan (Domain C Lead) | Defines data architecture, access controls, backup sites, archival processes, and digital transition protocols; includes DMI Compliance and Integration section | 1 electronic copy / Word and PDF | Within 90 calendar days of award; updated annually or upon CDC request | CO and COR |
| 51 | Domain C / Task C.1 (ref. Task C.2***) | Security Architecture Diagrams | Logical and physical system boundary diagrams showing data flows, access controls, and vendor separation; submitted with ICDs | 1 electronic copy / Word and PDF | With ICD; updated as needed | COR and RISER Management Team |
| 52 | Domain C / Task C.1 | Section 508 Accessibility Testing and Remediation Reports | Documentation of annual and post-update Section 508 testing, results, and remediation actions; includes VPAT updates | 1 electronic copy / Word and PDF | Annually and within 30 days after any major update | COR and CDC Information Security Team |
| 53 | Domain C / Task C.1 | Website Security Scan Summary Report | Monthly summary of weekly automated vulnerability scans, penetration tests, and remediations | 1 electronic copy / Word and PDF | Monthly with Technical Report | COR and CDC Information Security Team |
| 54 | Domain C / Task C.1 | Dashboard Maintenance Log | Summary of uptime, user activity, accessibility issues, and dashboard changes (embedded in MTR) | 1 electronic copy / Word and XML | Included in Monthly Technical Report | COR, and SMEs |
| 55 | Domain C, Task C.1 | Bug and Change Control Logs | Cumulative log of reported issues and system changes with status and resolution dates | 1 electronic copy / Word and XML | Updated monthly; summary in Monthly Technical Report | COR, RISER Management Team, and SMEs |
| 56 | Domain C, Task C.1 | Source Code Repository Access Verification | Documentation confirming COR and designated CDC personnel maintain continuous read-only access to RISER source code repositories, including version histories and audit logs | 1 electronic copy / Word and PDF | Within 60 calendar days of award; maintained throughout contract; verified quarterly | COR, and SMEs |
| 57 | Domain C / Task C.2 | CRM Configuration Documentation | Current configuration records, custom entities, and security roles for RISER CRM | 1 electronic copy / Word and XML | Within 90 calendar days of award; update with major changes | COR and CDC IT Services Offices |
| 58 | Domain C / Task C.2 | System Backup and Disaster-Recovery Verification Reports | Proof of daily backups and disaster-recovery tests for RISER website and CRM systems | 1 electronic copy / PDF and XML | Monthly or as requested by CDC | COR and CDC Information Security Team |
| 59 | Domain C / Task C.2 | Annual Security Self-Assessment and POA&M Update | Annual security package submission including PIA, POA&M, and remediation actions | 1 electronic copy / Word and PDF | Annually | COR and CDC Information Security Team |
| 60 | Domain C / Task C.2 (Coordinated with Domain D)*** | IT Help Desk Metrics and System Support Performance Summary | Statistics on IT-related support tickets associated with the RISER website, CRM functionality, dashboards, interfaces/APIs, data synchronization, access/authentication issues, and other technical defects. Metrics shall include ticket volume, categories, response times, resolution times, reopen rates, and root-cause trends. | 1 electronic copy / Word or XML | Monthly with Technical Report | COR and RISER Management Team |
| 61 | Domain C / Task C.2 | CRM and IT Support Operations Plan | Plan describing CRM administration procedures, technical support workflows, system ticket triage processes, escalation paths for technical defects, coordination with Domain D customer service operations, and performance monitoring for system-related support activities. | 1 electronic copy / Word and PDF | Within 90 calendar days of award | COR and RISER Management Team |
| 62 | Domain C / Task C.3 (DMI Alignment) | Data Modernization Initiative Alignment Documentation Addendum | Addendum to SCAP or Data Governance Plan showing changes required for CDC Data Modernization Initiative compliance | 1 electronic copy / Word and PDF | With annual plan updates or upon CDC request | COR and CDC DMI Program Office |
| 63 | Domain C / Task C.5 (Task 11 Ref.*) | IT System Transition Package | Delivery of source code, configuration metadata, and system access credentials to CDC or successor contractor | 1 electronic copy / Word and XML (+secure repository handoff) | Upon transition activation or contract closeout | COR and CDC IT Services Office |
| Domain D: Customer Service and Stakeholder Support |  |  |  |  |  |  |
| 64 | Domain D / Task D.1 | Customer Service and Stakeholder Support Plan | Written plan detailing registration and User Agreement management, inquiry handling procedures, escalation protocols, customer-satisfaction tracking, and staffing requirements | 1 electronic copy / Word and PDF | Within 60 calendar days of contract award; updated annually or upon CDC request | COR and RISER Management Team |
| 65 | Domain D / Task D.1 | Registration Records and User Agreements Database | Secure, auditable electronic and physical records for all laboratory registrants and executed User Agreements. | 1 electronic copy / Word or XML | Maintained throughout contract; provided to CDC upon request or at closeout | COR, RISER Management Team |
| 66 | Domain D / Task D.1 (Coordinated with Domain C)** | Quarterly Account Audit and Verification Summary | Audit results confirming accuracy of registrant information, biosafety levels, and active status; includes corrective actions taken. | 1 electronic copy / Word or XML | Quarterly within 15 calendar days after period closes | COR, RISER Management Team |
| 67 | Domain D / Task D.2 (Coordinated with Domains B and C)** | Customer Inquiry and Resolution Log | Log of all customer inquiries and resolutions recorded in CDC CRM; includes metrics on response time and resolution status. | 1 electronic copy / Word or XML | Updated continuously; summary included in Monthly Technical Report | COR and RISER Management Team |
| 68 | Domain D / Task D.2 (Coordinated with Domains B and C)** | Customer Complaint Records and Follow-up Summary | Records of complaints linked to shipments or reagents and documented resolutions actions per FDA 21 CFR Part 820 and ISO 13485 | 1 electronic copy / Word or XML | Included in Monthly Technical Reports and available upon CDC request | COR, RISER Management Team and SMEs |
| 69 | Domain D / Task D.2 | Customer Service Help Desk Metrics and Performance Report | Monthly summary of customer-facing Help Desk performance, including registration/UA support, order inquiries, shipment-status inquiries, documentation requests (e.g., donation letters/import permits), escalation timeliness, response times, resolution rates, and after-hours support activity. | 1 electronic copy / Word or XML | Monthly with Technical Report | COR and RISER Management Team |
| 70 | Domain D Task D.3 (Task 10 Ref.*) | Surge Customer-Support Plan and Extended Coverage SOPs | Procedures for scaling customer support operations 25-75% above baseline within ten (10) business days; includes extended Help-Desk and website-support hours coordination with Domain C. Include a KPI Mapping Matrix that identifies which Appendix D KPIs apply during surge and where the metrics will be reported. | 1 electronic copy / Word and PDF | Within 90 calendar days of award; updated annually or after activation | CO and COR |
| 71 | Domain D / Task D.4 (Task 11 Ref.*) | Customer-Service Transition Records | Documentation of CRM tickets, registration data, communication templates, and customer-service procedures transferred to successor contractor; ensures continuity of website and hotline operations until deactivation. | 1 electronic copy / Word and XML | Upon transition activation or contract closeout | COR and RISER Management Team |
| Optional Task 12: Development and Validation of Diagnostic Assay Workflows |  |  |  |  |  |  |
| 72 | Non-Domain | Gap Analysis Technical Report (Milestone 1) | Report identifying workflow gaps and proposing new assay development plan with supporting literature review and platform assessment. | 1 electronic copy / Word | Within 45 calendar days of Task Order activation | COR and SMEs |
| 73 | Non-Domain | Oral progress Updates / Telebriefings | Biweekly oral presentations or slide decks summarizing assay development progress and scientific findings | Summary notes / Slide Decks (Electronic) | Biweekly or as requested by COR during Task Order period | COR and SMEs |
| 74 | Non-Domain | Final Assay Validation Report (Milestone 2) | Comprehensive report including comparative data, performance metrics, statistical analysis, and validation results; includes SOP(s) and training records. | 1 electronic copy / Word and searchable PDF (+ appendices) | Within 30 calendar days of validation completion | COR and SMEs |
| 75 | Non-Domain | Final SOP(s) for Assay Workflow | COR-approved Standard Operating Procedure(s) for validated assay workflow aligned with CDC QMS and 21 CFR 820 | 1 electronic copy / Word | With Final Assay Validation Report | COR and SMEs |
| 76 | Non-Domain | CDC Assay Training Records | Documentation of hands-on training provided to CDC staff (agenda, attendance, evaluations) supporting technology transfer. | 1 electronic copy / Word | Within 10 business days of training completion | COR and SMEs |

*    Optional Task; Deliverable required if the government activates the corresponding Task Order.

**  Requires coordination with other Domains for data-exchange validation or reporting integration.

***Requires coordination between Tasks C.1 and C.2 or with Domain D.

- LIABILITY AND INDEMNIFICATION

The contractor shall be liable for any loss, damage, or destruction of government-furnished or government-owned material, reagents, biological specimens, or products stored, processed, or handled under this contract, when such loss, damage, or destruction is due to the contractor’s negligence, failure to follow approved SOPs, inadequate facility controls, or non-compliance with contract requirements.

The contractor shall:

- Maintain commercial general liability insurance and property insurance sufficient to cover the replacement value of stored materials;

- Promptly (within 24 hours) notify the CO and COR of any incident causing material loss or damage;

- Promptly (within 24 hours of becoming aware) notify the CO and COR of any suspected misuse, unauthorized redistribution, regulatory non-compliance, export-control concern, diversion, or other improper use of RISER materials by a registrant or third party, including any violation of applicable User Agreement terms. The contractor shall cooperate fully with CDC in any resulting investigation and shall take immediate action as directed by CDC, including suspension of shipment or account access if required;

- Submit a full incident report including root cause analysis and a proposed CAPA plan.

In addition:

- The contractor shall indemnify and hold harmless the United States government from any third-party claims, damages, fines, or penalties arising from loss, damage, or contamination of materials due to the contractor’s actions or omissions;

- The contractor’s liability for loss of government-owned materials shall not be limited to the value of the contract unless otherwise specified by law.

The government reserves the right to recover the replacement cost of lost or damaged materials and any direct costs associated with regulatory filings, recalls, or replacement production attributable to the contractor’s failure to comply with contractor requirements.

Limitation of Liability and Consequential Damages

Contractor’s liability under this contract shall extend to all direct costs incurred by the government due to loss, damage, or compromise of government-furnished materials, including costs of replacement materials, regulatory filings, corrective actions, and associated operational disruptions.  Contractor shall not be liable for consequential or indirect damages except where such damage arises from gross negligence, willful misconduct, or material breach of this contract.

Insurance Coverage

The contractor shall maintain, at a minimum, the following insurance coverage throughout the period of performance:

- Commercial General Liability Insurance with coverage limits of not less than $1,000,000 per occurrence;

- Property Insurance sufficient to cover the full replacement value of government-furnished materials stored or managed by the contractor;

- Errors and Omissions Insurance with coverage limits of at least $1,000,000 per claim.

The contractor shall provide certificates of insurance to the CO and COR annually and upon request.  All insurance policies shall name the United States government as an additional insured where permissible under applicable law.

- ADDITIONAL REQUIREMENTS

Information Security and Privacy

[ENTER TEXT HERE]

Human Subjects Protections in Research

[ENTER TEXT HERE]

Paperwork Reduction Act (PRA)

[ENTER TEXT HERE]

Section 508 Compliance

Part A – Provision

Reference HHSAR 352.239-73[8] Electronic Information and [Communication] Technology

Accessibility Notice.

(Deviation)

(a) Any offeror responding to this solicitation must comply with established HHS Information and

Communication Technology (ICT) accessibility standards. Information about Section 508 is available

at https://www.hhs.gov/web/section-508/index.html.

(b) The Section 508 accessibility standards applicable to this solicitation are stated in the clause at 352.239-79 Information and Communication Technology Accessibility. In order to facilitate the Government’s determination whether proposed ICT supplies, products, platforms, information, and documentation meet applicable Section 508 accessibility standards, offerors must submit an appropriate HHS Section 508 Accessibility Conformance Checklist (see https://www.hhs.gov/web/section-508/accessibility-checklists/index.html) or an Accessibility Conformance Report (ACR) (based on the Voluntary Product Accessibility Template (VPAT) see https://www.itic.org/policy/accessibility/vpat), in accordance with the completion instructions. The purpose of the checklists and conformance reports are to assist HHS acquisition and program officials in determining whether proposed ICT supplies, products, platforms, information, and documentation conform to applicable Section 508 accessibility standards. Checklists and ACRs evaluate—in detail—whether the ICT conforms to specific Section 508 accessibility standards and identifies remediation efforts needed to address conformance issues.

(c) If an offeror claims its supplies or services meet applicable Section 508 accessibility standards, and it is later determined by the Government, i.e., after award of a contract or order, that supplies, products, platforms, information, documentation, or services support delivered do not conform to the described accessibility standards, remediation of the supplies, products, platforms, information, documentation, or services support to the level of conformance specified in the contract will be the responsibility of the Contractor at its expense.

(d) In order to facilitate the Government's determination whether proposed ICT supplies meet applicable Section 508 accessibility standards, offerors must submit an Accessibility Conformance Report, in accordance with its completion instructions and tailored to the requirements in the solicitation. The purpose of the Report is to assist HHS acquisition and program officials in determining whether proposed ICT supplies conform to applicable Section 508 accessibility standards. The template allows offerors or developers to self-evaluate their supplies and document, in detail, whether they conform to a specific Section 508 accessibility standard, and any underway remediation efforts addressing conformance issues. Instructions for preparing the Template are available at https://www.section508.gov/.

(e) Additionally, offerors must provide enough information to assist the Government in determining that the ICT services conform to Section 508 accessibility standards, including any underway remediation efforts addressing conformance issues.

(f) Respondents to this solicitation must identify any inability to conform to Section 508 requirements. If an offeror claims its supplies or services meet applicable Section 508 accessibility standards, and it is later determined by the Government, i.e., after award of a contract or order, that supplies or services delivered do not conform to the described accessibility standards, remediation of the supplies or services to the level of conformance specified in the contract will be the responsibility of the Contractor at its expense.

(g) Items delivered as electronic content must be accessible to HHS acceptance criteria. Checklist for various formats are available at http://508.hhs.gov/. Materials, other than items incidental to contract management, that are final items for delivery should be accompanied by the appropriate checklist, except upon approval of the Contracting Officer or Contracting Officer’s Representative.

Part B - Clause

HHSAR 352.239-74[9] Electronic, Information, and Communication Technology Accessibility.

(Deviation)

(a) Pursuant to Section 508 of the Rehabilitation Act of 1973 (29 U.S.C. 794d), as amended by the Workforce Investment Act of 1998, all information and communication technology (ICT) supplies, products, platforms, information, documentation, and services, or support developed, acquired, maintained or delivered under this contract or order must comply with the Revised 508 Standards, which are located at 36 C.F.R. 1194.1 and Appendices A, B, and C, and are available at https://www.access-board.gov/ict/. Information about Section 508 is available at https://www.hhs.gov/web/section-508/index.html.

(b) Additional Section 508 accessibility standards applicable to this contract or order are identified as follows:

205 WCAG 2.0 Level A & AA Success Criteria

302 Functional Performance Criteria

502 Inoperability with Assistive Technology

503 Applications

504 Authoring Tools

602 Support Documentation

603 Support Services

If it is determined by the Government that ICT supplies, products, platforms, information, documentation, and services support provided by the Contractor do not conform to the described accessibility standards in the contract, remediation of the supplies, products, platforms, information, documentation, or services support to the level of conformance specified in the contract will be the responsibility of the Contractor at its own expense.

(c) In the event of a modification(s) to this contract or order, which adds new ICT supplies or services or revises the type of, or specifications for, supplies, products, platforms, information, documentation, or services support, the Contracting Officer shall require that the Contractor submit a completed HHS Section 508 Accessibility Conformance Checklist (see https://www.hhs.gov/web/section-508/accessibility-checklists/index.html) or an Accessibility Conformance Report (ACR) (based on the Voluntary Product Accessibility Template (VPAT) see https://www.itic.org/policy/accessibility/vpat), and any other additional information necessary to assist the Government in determining that the ICT supplies or services conform to Section 508 accessibility standards. If it is determined by the Government that ICT supplies, products, platforms, information, documentation, and services support provided by the Contractor do not conform to the described accessibility standards in the contract, remediation of the supplies, products, platforms, information, documentation, or services support to the level of conformance specified in the contract will be the responsibility of the Contractor at its own expense.

(d) If this is an Indefinite-Delivery type contract, a Blanket Purchase Agreement or a Basic Ordering Agreement, the task/delivery order requests that include ICT supplies, products, platforms, information, documentation, or services support will define the specifications and accessibility standards for the order. In those cases, the Contractor shall be required to provide a completed HHS Section 508 Accessibility Conformance Checklist (see https://www.hhs.gov/web/section-508/accessibility-checklists/index.html) or an ACR (based on the VPAT see https://www.itic.org/policy/accessibility/vpat), and any other additional information necessary to assist the Government in determining that the ICT supplies, products, platforms, information, documentation, or services support conform to Section 508 accessibility standards. If it is determined by the Government that ICT supplies and services provided by the Contractor do not conform to the described accessibility standards in the provided documentation, remediation of the supplies, products, platforms, information, documentation, or services support to the level of conformance specified in the contract will be the responsibility of the Contractor at its own expense.

(e) The contractor shall identify to the Contracting Officer any perceived exception or exemption to Section 508 requirements for review by the agency Section 508 Program.

Printing

[ENTER TEXT HERE]

[ENTER TITLE OF OTHER CLEARANCE REQUIRED]

[ENTER TEXT HERE]

- DEFINITIONS

The following definitions apply throughout this Statement of Work and all associated appendices and task orders.  Where terms overlap with federal acquisition regulations or CDC enterprise policy, the regulatory definition prevails:

| Term | Definition |
| --- | --- |
| Integration Lead | The government-designated individual or contractor (Lead Systems Integrator – LSI) responsible for facilitating technical and operational coordination across all RISER Domains (A-D). The Integration lead oversees interface alignment, joint risk tracking, and cross-vendor communication but has no authority to modify contract scope or obligate funds |
| Emergency Operations Lead (EOL) | A CDC official designated during declared public-health emergencies to provide interim operational direction to RISER contractors when necessary to protect public health. EOL direction shall be limited to operational coordination within existing contract scope and available funding and shall be documented in writing. Any direction that may result in work beyond established task order scope or funding ceilings must be submitted to the Contracting Officer (CO) for review and potential ratification. Only the CO possesses the legal authority to obligate additional funds, modify task orders, or authorize equitable adjustments. |
| Partial Transition Plan | A domain-specific plan, prepared by each contractor within 180 days of award and updated annually, describing how data, inventory, systems, and responsibilities will transfer to a successor contractor or to CDC for that Domain. Partial Transition Plans collectively support the Final Transition Plan under Task 11. |
| Surge Activation / Surge Support | A government-directed operational escalation, initiated by written notice from the CO, requiring contractors to scale production, logistics, IT, or customer-service capacity by 25-75% above baseline within ten (10) business days. Surge activation remains within optional CLINs and continues until CDC issues written de-activation. |
| Rapid Vendor Onboarding Protocol | CDC-approved procedure enabling qualification of new subcontractors, manufacturers, or logistics partners within ten (10) business days during surge or transition operations, ensuring full compliance with biosafety, QA/QC, and data-governance requirements. |
| Cross-Domain Continuity Plan | The integrated plan that consolidates all Domain-specific Partial Transition Plans and defines cross-Domain data, system, and material hand-off procedures to ensure uninterrupted RISER operations. |
| Data Modernization Initiative (DMI) Alignment | Compliance with CDC’s enterprise standards for interoperable, metadata-driven data exchange, including schema mapping, controlled vocabularies, and quality metrics consistent with CDC Data Modernization Initiative governance policies. |
| Corrective and Preventive Action (CAPA) | A documented process for identifying, analyzing, correcting, and preventing non-conformances affecting reagent quality, facility operations, or data integrity, consistent with FDA 21 CFR 820 requirements. |
| Business day | Business day means Monday through Friday, excluding Federal holidays. |
| Emergency Response Timeframe | Emergency response timeframe means calendar hours measured from the time of written direction under a declared public health emergency. |

- ACRONYMS

| Acronym | Full Term |
| --- | --- |
| AAALAC | Association for Assessment and Accreditation of Laboratory Animal Care |
| ABSL | Animal Biosafety Level |
| APHIS | Animal And Plant Health Inspection Service |
| API | Application Programming Interface |
| BCP | Business Continuity Plan |
| BMBL | Biosafety and Microbiological and Biomedical Laboratories |
| BSL | Biosafety Level |
| CAPA | Corrective and Preventive Action |
| CDC | Centers for Disease Control and Prevention |
| CLIN | Contract Line-Item Number |
| CO | Contracting Officer |
| COA | Certificate of Analysis |
| COI | Conflict-of-interest |
| COR | Contracting Officer’s Representative |
| CPIF | Cost-Plus-Incentive-Fee |
| CRM | Customer Relationship Management |
| CSPO | Cyber Security Program Office |
| cGMP | current Good Manufacturing Practice |
| DMI | Data Modernization Initiative |
| DOT | Department of Transportation |
| EOC | Emergency Operations Center |
| EOL | Emergency Operations Lead |
| EPLC | Enterprise Performance Life Cycle |
| ERP | Enterprise Resource Planning |
| EST | Eastern Standard Time |
| FDA | Food and Drug Administration |
| FFP | Firm-Fixed-Price |
| FOIA | Freedom of Information Act |
| FSAP | Federal Select Agent Program |
| GFE | Government-Furnished Equipment |
| HEPA | High-Efficiency Particulate Air |
| HHS | U.S. Department of Health and Human Services |
| HR | Human Resources |
| IACUC | Institutional Animal Care and Use Committee |
| IATA | International Air Transport Association |
| ICAO | International Civil Aviation Organization |
| ICD | Interface Control Document |
| IDIQ | Indefinite Delivery/Indefinite Quantity |
| IMS | Incident Management System |
| IRR | Influenza Reagent Resource |
| ISO | International Organization for Standardization |
| IT | Information Technology |
| JCCB | Joint Change Control Board |
| KPI | Key Performance Indicators |
| LSI | Lead Systems Integrator |
| MFA | Multi-factor authentication |
| NCIRD | National Center for Immunization and Respiratory Diseases |
| NCEZID | National Center for Emerging and Zoonotic Infectious Diseases |
| NIC | National Influenza Center |
| NIH | National Institutes of Health |
| OSHA | Occupational Safety and Health Administration |
| PIA | Privacy Impact Assessment |
| PMR | Program Management Review |
| POA&M | Plan of Action and Milestones |
| POP | Period of Performance |
| PPE | Personal Protective Equipment |
| QA | Quality Assurance |
| QC | Quality Control |
| QMS | Quality Management System |
| QMSR | Quality Management System Regulation |
| RISER | Resources for Improvement of Surveillance and Emergency Response |
| RCA | Root Cause Analysis |
| RT-PCR | Reverse Transcription Polymerase Chain Reaction |
| RUO | Research-Use-Only |
| SCAP | Shared Cost Allocation Plan |
| SCRM | Supply Chain Risk Management |
| SFTP | Secure File Transfer Protocol |
| SME | Subject Matter Expert |
| SMTA | Standard Material Transfer Agreement |
| SOP | Standard Operating Procedure |
| SOW | Statement of Work |
| T&M | Time and Materials |
| UA | User Agreement |
| USDA | United States Department of Agriculture |
| VPAT | Voluntary Product Accessibility Template |
| XML | Extensible Markup Language |
| 21 CFR 820 | Title 21 of the Code of Federal Regulations Part 820 (FDA Quality Management System Regulation) |

- POINT OF CONTACT INFORMATION:

Contracting Officer’s Representative:

Vic Veguilla

404-639-0424

Dhu3@cdc.gov

Contracting Officer:

- EVALUATION FACTORS:

To ensure technical merit, operational capacity, and risk mitigation, the government will evaluate proposals based on the following multi-phase criteria. Offerors may submit responses for one or more Domains but must address all evaluation components for each Domain proposed.

Phase I: Pre-award Systems Integration and Data Security Validation:   The offeror shall demonstrate its ability to establish secure, bidirectional, and real-time data exchange between the RISER website, CDC enterprise systems (e.g., CRM, ERP), and other RISER awardees.

- Participate in a pre-award test to validate secure transmission and receipt of reagent order requests, shipment data, registration records, and cost information via XML or CDC-defined formats;

- Demonstrate integrity, security, and traceability of transmitted data;

- Identify protocols for audit trails, failover, and encryption measures to protect sensitive information.

Phase II: Technical Approach: Offerors will be evaluated based on their understanding of Domain-specific requirements, proposed methodologies, innovation, and ability to execute under the hybrid IDIQ contract structure. Submissions must address the following:

  - Technical Understanding and Methodology:

- Clear articulation of each proposed Domain’s purpose and deliverables;

- Description of methods and processes for achieving performance goals;

- Integration strategy with other RISER awardees to ensure end-to-end compatibility;

- Offeror’s proposed strategy for coordination with other Domain awardees to ensure continuity and eliminate interface gaps will be evaluated for realism and feasibility

  - Program Management and Communication:

- Demonstrated project management practices, staffing strategy, and communication protocols with CDC;

- Ability to support weekly and emergency cadence program calls, timely reporting, and accurate financial and inventory summaries.

  - Personnel Qualifications:

- Experience and qualifications of key personnel (e.g., Project Director, Principal Investigators, IT leads, shipping coordinators);

- Description of strategies to recruit, train, and retain qualified scientific and technical staff.

  - Innovation and Optional Task Capabilities:

- Prior experience with developing, validating, and transferring scientific workflows and assay development processes;

- Capability to lead experimental validation efforts and conduct technology transfer as outlined in the Optional Technical Requirements.

  - Risk Mitigation and Contingency Planning:

Offerors must briefly outline mitigation strategies for the following potential challenges to demonstrate their understanding of the magnitude, inter-domain dependencies, and operational scope of the project.

- Supply-chain disruption: Plans for multi-vendor sourcing, advance stocking of critical materials, qualified alternate supplies, and pre-approved substitution workflows to maintain reagent production and QA/QC continuity;

- Surge demand: Procedures for scaling production and logistics 25-75 percent above baseline, including cross-training of staff, activation of secondary facilities, and prioritized scheduling under CDC direction;

- Labor shortages or workforce interruptions: Staffing continuity plans, remote-work protocols (where permissible), use of temporary or standby personnel, and retention strategies for key technical staff;

- IT or data-system outages: Redundant hosting, disaster-recovery plans, and failover mechanisms for RISER website, CRM, and inventory systems consistent with FISMA-moderate controls; procedures for maintaining data integrity during temporary loss of CDC connectivity;

- International shipping or regulatory delays: Pre-cleared courier networks, advance customs documentation, cold-chain monitoring, and environmental-contingency measures (e.g., re-icing, rerouting) to preserve material integrity during extended transit;

- Multi-vendor communication and coordination failures: Mechanisms to ensure continuous, transparent communication among RISER domain contractors including use of shared collaboration tools (e.g., CDC SharePoint, Jira), participation in weekly integration meetings, adherence to Interface Control Documents (ICDs), and escalation protocols to resolve cross-domain data or operational conflicts within defined timelines.

Offerors may identify additional risks unique to their proposed domain(s) and shall describe the governance, escalation, and communication mechanisms they will employ to coordinate risk response with CDC.

  - Alignment with CDC Mission and RISER Objectives:

Evaluate the extent to which the offeror’s proposal demonstrates:

- Understanding of CDC’s surveillance and emergency response goals;

- Commitment to RISER’s core priorities: early threat detection, assay support, rapid reagent deployment, and seamless stakeholder interaction.

  - Data Systems and Interoperability Readiness (Especially for Domain C)

Assess the offeror’s ability to:

- Build and maintain real-time, bidirectional APIs;

- Support CRM (Microsoft Dynamics 365) integration, system scalability, and XML data exchange;

- Ensure system uptime, Section 508 compliance, and user authentication protocols.

  - QA/QC Program

Offeror should provide:

- A detailed QA/QC plan for reagent production, validation and catalog management;

- Procedures for batch record documentation, reagent rejection, and customer complaints

  - Emergency Surge Capability

Offeror should describe their capacity to:

- Rapidly scale up operations by 25-75% above baseline in response to emergency task orders;

- Prioritize critical reagents or pathogens and support CDC EOC operations.

  - Cost Realism and Resource Allocation

While not traditionally part of the technical evaluation, offerors shall justify proposed resource allocations for each Domain and identify any shared infrastructure, facilities, personnel, or systems supporting multiple Domains. Proposals shall provide staffing levels and associated costs sufficient to demonstrate cost realism, avoid duplication, and support modular Domain performance.

Proposals will be evaluated for infrastructure efficiency and cost integration. Offerors proposing multiple Domains must clearly demonstrate how shared resources support cost-effectiveness and operational integration across Domains. Failure to distinguish overlapping costs or to adequately explain shared resource allocations may impact the realism or acceptability of the proposed pricing. Duplicative or unsupported charges may be rejected.

  - Prior Experience with Similar-Sized Contracts

Offerors shall describe prior experience managing contracts of similar scope, magnitude, and complexity to RISER.  Proposals will be evaluated on:

- The scale of past projects, including contract value, volume of reagents managed, and number of stakeholders served;

- Experience handling high-volume surge requirements or emergency response;

- Successful integration of multi-domain technical tasks under hybrid contract structures;

- Ability to operate secure IT systems integrated with federal platforms;

- Past performance outcomes and client references relevant to large-scale laboratory reagent production, logistics, or data systems management.

  - Program Coordination Role (Optional)

Offerors may propose to serve as a RISER Coordinating Contractor to provide operational and administrative support to CDC in facilitating cross-domain integration, risk management coordination, and multi-vendor alignment. This role shall operate under the direction of the CDC-designated Integration Lead and shall not supersede government authority.

Proposals should clearly describe how the offeror will support CDC in convening stakeholders, documenting integration activities, managing joint risk logs, ensuring cross-domain SOP consistency, and aligning systems across Domains A, B, C, and D. Offerors must outline any associated administrative costs for this coordination role within their business proposal.

CDC will evaluate these proposals based on the offeror’s demonstrated capacity for cross-functional program management, systems integration experience, prior leadership in multi-vendor environments, and feasibility of the proposed coordination structure and cost.

FAR, HHSAR clauses:

1. General Provisions

- FAR 52.252-2: Clauses Incorporated by Reference

- FAR 52.202-1: Definitions

- FAR 52.204-13: System for Award Management Maintenance

2. Contract Type (IDIQ)

- FAR 52.216-22: Indefinite Quantity

- FAR 52.216-18: Ordering

- FAR 52.216-19: Order Limitations

- FAR 52.216-1: Type of Contract

- FAR 52.217-9: Option to Extend the Term of the Contract

3. Performance & Inspection

- FAR 52.246-4: Inspection of Services – Fixed Price

- FAR 52.246-6: Inspection – Time-and-Materials and Labor-Hour (if used)

- FAR 52.212-4: Contract Terms and Conditions – Commercial Items

4. Data Rights, Confidentiality, and Security

- FAR 52.227-14: Rights in Data – General

- FAR 52.239-1: Privacy or Security Safeguards

- HHSAR 352.224-70: Privacy Act

- HHSAR 352.239-70: Standards for Security of IT Systems

- HHSAR 352.239-71: Information Security Program Requirements

- FAR 52.204-25: Prohibition on Contracting for Certain Telecom and Video Surveillance

5. Reporting, Deliverables, and Government Oversight

- FAR 52.242-15: Stop-Work Order

- FAR 52.242-17: Government Delay of Work

- HHSAR 352.242-70: Key Personnel

- HHSAR 352.242-71: Administrative Contracting Officer

- HHSAR 352.242-73: Withholding of Contract Payments

6. Subcontracting and Multi-Vendor Coordination

- FAR 52.244-2: Subcontracts

- FAR 52.244-6: Subcontracts for Commercial Items

- HHSAR 352.231-70: Salary Rate Limitation (if applicable to subcontractors)

7. International Activities / Shipping

- FAR 52.247-34: FOB Destination

- FAR 52.247-35: F.O.B. Destination, Within Consignee’s Premises

- HHSAR 352.270-2: Indian Preference (if applicable)

- Custom Export/Import Provisions (CDC internal clauses or referenced agency supplements)

8. Optional Tasks and R&D Provisions

- FAR 52.227-11: Patent Rights – Ownership by the Contractor (if R&D is funded)

- FAR 52.234-1: Industrial Resources Developed Under Defense Production Act (if activated during emergencies)