PERFORMANCE WORK STATEMENT (PWS)

Compliance-Lab Support Services BPA, DPW Environmental Division

9 March 2026

Part 1

General Information

1.   General:   This is a non-personal service(s) contract under which the personnel rendering the service(s) are not subject, either by the contract’s terms or by the manner of its administration, to the supervision and control usually prevailing in relationships between the Government and its employees.  The Government will neither supervise contractor employees nor control the method by which the contractor performs the required tasks.  Such Contractor employees shall be accountable solely to the Contractor who, in turn, is responsible to the Government.  Under no circumstances will the Government assign tasks to, or prepare work schedules for, individual contractor employees.  It shall be the responsibility of the Contractor to manage its employees.  The Contractor shall guard against any actions that are of the nature of personal services or give the perception of personal services.  If the Contractor believes that any actions constitute or are perceived to constitute personal services, it shall be the Contractor's responsibility to notify the Contracting Officer (KO) immediately.

1.1   Description of Services/Introduction:   This is a non-personal service(s) contract to provide environmental compliance, surveys, assessment, consultant services, inspections, trainings,  advisory and lab services.

1.2   Background:   The requirements for hazardous materials/hazardous waste, spill prevention, air emissions, noise, storm water, tanks, oil water separators, contaminants, permits, environmental awareness and training of environmental-related media are stipulated in various host nation waste laws, acts, regulations and US-Army standards.  The applicable acts/laws/regulations in its current version include but are not limited to:

- Army in Europe Environmental Quality Program (AER 200-1)

- Environmental Guidance for Military Exercises (AER 200-2)

- Environmental Management (AER 200-100)

- Environmental Final Governing Standards Germany (FGS)

- Closed Substance Cycle Waste Management Act (Kreislaufwirtschaftsgesetz - KrWG)

- German Federal Water Act (Wasserhaushaltsgesetz –WHG)

- Ordinance on Hazardous Substances (Gefahrstoffverordnung - GefStoffV)

- Federal Soil Protection Law and Ordinance Contaminated Sites (Bundesbodenschutz-Gesetz und Bundes-Bodenschutz- und Altlastenverordnung - BBodSchV)

- Landfill Ordinance (Verordnung über Deponien und Langzeitlager – Deponieverordnung - DepV)

- Federal Emission Protection Law (Bundes-Immissionsschutz-Gesetz - BImSchG)

- Ordinance on the record keeping for the disposal of wastes (Verordnung über die Nachweisführung bei der Entsorgung von Abfällen (Nachweisverordnung - NachwV)

- Ordinance on Systems for Handling Substances Hazardous to Water (Verordnung über Anlagen zum Umgang mit wassergefährdenden Stoffen - AwSV)

- Waste Water Ordinance (Abwasserverordnung - AbwV)

- Old Wood Ordinance (Altholzverordnung - AltholzV)

- Waste Oil Ordinance (Altölverordnung - AltölV)

- Act on the distribution, the return and the environmentally compatible disposal of batteries and accumulators  (Gesetz über das Inverkehrbringen, die Rücknahme und die umweltverträgliche Entsorgung von Batterien und Akkumulatoren (Batteriegesetz - BattG))

- Act on the distribution, the return and the environmentally compatible disposal of electrical and electronic equipment (Gesetz über das Inverkehrbringen, die Rücknahme und die umweltverträgliche Entsorgung von Elektro- und Elektronikgeräten (Elektro- und Elektronikgerätegesetz - ElektroG))

- Technical Rules for Hazardous Substances (Technische Regeln für Gefahrstoffe - TRGS)

- Communications of the Federal/State Working Group on Waste (Mitteilungen der Bund/Länder-Arbeitsgemeinschaft Abfall (LAGA)

- Applicable DIN-Regulations

1.3   Scope:   The Contractor shall provide and is responsible for, personnel, equipment, all labor equipment, supplies, transportation, tools, materials, supervision, and all support costs necessary to perform services as described in the PWS and associated contract documents, except for those items specified in Part 3 Government Property and Services.  The Contractor shall perform to the standards and acceptable quality levels identified in this PWS and associated contract documents.

1.4   Objectives:   The objective of this project includes (applicable for all FGS Compliance Chapters), but not limited to:

- Provide management plan update e.g. Hazardous Waste Management Plan, Asbestos Management Plan, Spill Prevention Control and Reporting Management Plan, Cultural Resources Management Plan, Lead Based Paint Management Plan, Potable Water Plan, Storm Water Pollution Prevention Plan

- Provide inspections/site visits (Compliance assessment inspections and reporting e.g. according to AwSV § 47, tanks (AST/UST, commissioning, decommissioning, TUEV certifications), HWSA/HWAP, storm water, drainage Sumps, WOT, pre-inspections EPAS, explosion protection, Operating Instruction, historic research, ground water wells, soil gas wells, De-Commissioning of Ground Water Wells/ Soil Gas Wells, Rain Water Retention Basin Inspection, Hardstand Inspection, SWPP Site Inspection,  Safety Cabinet Inspection

- Develop, update and provide trainings in-person/virtual/field exercises e.g. Building Contaminants Training, Hazardous Waste Training, Environmental Officer Basic Training, Environmental Officer Refresher Training, Spill Response Training & Field Exercise

- Provide documentations e.g. facility documentations according to AwSV § 43, Operational Manuals, Operating Instructions e.g. according to AwSV § 44, HWSA etc., Booklets i.e. Recycling Booklets, Water Conservation Booklets etc., Flyers/Trifolds, Explosion Protection Documents

- Advisory and consultant services and recommendations for corrective action (Compliance assessment report, contact with authorities, translation service, Hazardous Substance Compliance Program Support, EQCC (update unit distribution list, support slide preparation, prepare meeting minutes), Support environmental awareness events, EPAS (track findings, support external EPAS visits, prepare communication material), Garrisons conduct internal, Follow up to an internal EPAS, Hazard communication program)

- Provide support with Host Nation permits (Determine Host Nation permits requirements, Meeting with Regulatory Agency, Site visits and Research, Permit Application Implementation Plan,  Permit Renewal Package, Hydraulic Calculation)

- Surveys e.g. Mapping Survey, Geospatial Data Update, Database Update, As-built Survey of storm drainage system, Field verification survey, Back-Flow Prevention Survey

- Air Emission inventory update

- Parts Cleaner Services

- Lab services

- Finalizing Deliverables/Printing

1.5   General Information

1.5.1   Quality Control Plan (QCP):   The Contractor shall develop and maintain a QCP to ensure services are performed in accordance with (IAW) this PWS.  The Contractor shall develop and implement procedures to identify, prevent, and ensure non-recurrence of defective services.  The Contractor's QCP is the means by which it assures that the work provided complies with the requirements of the contract.  The Contractor’s Proposed QCP shall be submitted to the Contracting Officer (KO) through the Contracting Officer’s Representative (COR) for review (Deliverable#01).

1.5.1.1   The Government will review and either notify the Contractor in writing of acceptance of the plan or return their comments to the Contractor within twenty (20) days.  If the Government has provided comments, the Contractor shall then have twenty (20) to submit a Final QCP.  After receipt of the Final QCP, the Contractor may receive the Contracting Officer’s acceptance in writing.  Any proposed changes to the accepted QCP are required to be resubmitted for acceptance by the Contracting Officer no later than twenty (20) prior to the anticipated change and before implementation by the Contractor.  The timeline noted above will apply for review and acceptance for proposed changes.  At a minimum, the QCP must include and answer the following to be acceptable:

a. A chart showing the organizational structure and lines of authority, the names, qualifications, duties, responsibilities, and classification of each member of the Contractor's Quality Control Team.

b. How will the Contractor monitor work to ensure that performance complies with all deliverables (etc. timelines, deadlines, and goals)?

c. How will the Contractor monitor work to ensure that performance complies with all specifications and requirements of the contract, including clauses?

d. How will the Contractor monitor and ensure staff qualifications remain current and valid including DOCPER processes/approvals throughout contract performance?

e. How will the Contractor ensure all keys issued will remain controlled items (Paragraph 1.7 Key Control)?

f. How will the Contractor inventory and track maintenance of all Government Provided Equipment / Materials?

g. How will the Contractor identify, investigate, and correct any non-conforming performance and prevent similar deficiencies in the future?

h. How will the Contractor file and save all Quality Control related documents for the life of the contract plus 5 years?

1.5.1.1   Optional addendum to the QCP:   Reserved.

1.5.1.2   Potential Issues:   The Contractor shall inform the COR of issues or potential issues that might affect the performance within 24 hours between 0700 and 1700 hour of identifying those issues.  Verbal reports shall be followed-up by written reports (Deliverable#02).

1.5.2   Quality Assurance:   The Government will evaluate the Contractor’s performance under this contract in accordance with the Quality Assurance Surveillance Plan (QASP).  This plan is primarily focused on what the Government must do to ensure that the Contractor has performed in accordance with the performance standards.  It defines how the performance standards will be applied, the frequency of surveillance, and the acceptable quality levels (performance thresholds).

1.5.3   Recognized Holidays:   The following provides information on recognized holidays for the purpose of the PWS.  If submittal of any documentation (e.g. deliverables, submittals, etc.) deadlines fall on a holiday, the closest work day prior to the holiday will apply as the deadline for submittal.

1.5.3.1   U.S. Holidays:   Work shall not be performed on U.S. holidays occurring during the normal workweek unless otherwise directed by the Contracting Officer.  When a U.S holiday occurs on a Saturday or a Sunday, the holiday is observed on the preceding Friday or following Monday, respectively

New Year’s Day January 1st			M. L. King Memorial Day 3rd Monday in January

Presidents Day 3rd Monday in February		Memorial Day last Monday in May

Juneteenth Day June 19th				Independence Day July 4th

Labor Day 1st Monday in September		Columbus Day 2nd Monday in October

Veteran’s Day November 11th			Thanksgiving Day 4th Thursday in November

Christmas Day December 25th

1.5.3.2   Host Nation Holidays:   Work shall not be performed on local Host Nation holidays occurring during the normal workweek unless otherwise directed by the Contracting Officer.

The German national and local holidays include but are not limited to:

New Year’s Day January 1st 			Three Kings Day January 6th

Good Friday Varies				Easter Monday Varies

Labor Day May 1st				Ascension Day Varies

Whit Monday Varies				Corpus Christ Varies

Day of German Unity October 3rd			All Saint Day November 1st

Christmas December 25th				2nd Christmas 26th

1.5.4   Operating Hours:   The Government facility office hours, facility operating hours, and the Contractor support hour requirements often coincide, however, they may differ. Please refer to the following.

1.5.4.1   Government Facility Office Hours:   The Government facility office hours are 0700 to 1700, Monday through Friday except U.S. Holidays identified in paragraph 1.5.3.1/1.5.3.2 above or when the Government facility is closed due to local or national emergencies, administrative closings, or similar Government directed facility closings.

1.5.4.2   Government Facility Operating Hours:   The Government facility operating hours occur between the hours of 0700 to 1700, Monday through Saturday.  The Government facility is open for operations during the recognized U.S. Holidays identified in paragraph 1.5.3.1/1.5.3.2 above.  The Government facility may close due to local or national emergencies, administrative closings, or similar Government directed facility closings and will be communicated by the KO to the Contractor.

1.5.4.3   Contractor Support Hours:   The Contractor shall provide support between the hours of 0700 to 1700, Monday through Friday, except U.S. and host nation holidays identified in paragraph 1.5.3.1/1.5.3.2 above or when the Government facility is closed due to local or national emergencies, administrative closings, or similar Government directed facility closings.  The Contractor shall maintain an adequate workforce at all times for the uninterrupted performance of all tasks defined within this PWS when the Government facility is not closed for the above reasons.  When hiring personnel, the Contractor shall keep in mind that the stability and continuity of the workforce is essential.

1.5.5   Contractor Work Plan:   The Contractor shall prepare and maintain a Work Plan.  The plan, as a minimum, shall identify regularly scheduled work (to include location, work to be completed, timeline, etc.), including a health and safety plan for activities associated with the sampling and analysis of items described in  paragraph 5.3.  The Contractor’s proposed Draft of Work Plan shall be submitted to the Contracting Officer via the COR for review within twenty (20) days after date of contract award.  The Government will review and either accept or return their comments to the Contractor within ten (10) days).  The Contractor shall then have three (3) days) to submit a Final Work Plan (Deliverable#03). Any proposed change to the accepted Final Work Plan is required to be resubmitted via the COR for review and acceptance by the Contracting Officer at a minimum thirty (30) days prior to implementation.  The timeline noted above shall apply for review and acceptance for proposed changes.

1.5.6   Training Holidays:   USAREUR has historically granted military personnel training holidays as compensation for time that they spent in field training.  These are typically combined with regular holiday leave schedules (for example, Christmas half days or day on day off schedules).  Training holidays may affect access to military operated facilities.  If scheduled work or access to facilities is required, coordination with occupants will be necessary or the work in affected facilities shall be rescheduled after the training holiday.  However, announced training holidays or exodus of military personnel may provide the Contractor with an opportunity for unrestricted access to facilities and areas.  The Contractor shall take full advantage of such opportunities by planning maintenance or actions that are better accomplished when such areas are vacant.

1.5.7   Place of Performance:   The work to be performed under this contract will be performed throughout the United States Army Garrison (USAG) Stuttgart:

- Kelley Barracks

- Patch Barracks

- Panzer Kaserne

- Stuttgart Army Airfield (SAAF)

- Robinson Barracks

- Kornwestheim Golf Course

- Training Area Boeblingen

- Warehouse (Weilimdorf)

1.6   Security Requirements:   The following information is provided on security related matters.

1.6.1   Security Program:   Reserved.

1.6.2   Personnel Security Clearance Requirements:   Reserved.

1.6.3   Installation Access:   Access to U.S. installations and controlled areas is limited to personnel who meet security criteria and are authorized by Host Nation law to work in that country.  Failure to submit required information/data and obtain required documentation or clearances in accordance with Army in Europe (AE) Regulation 190-16 (AE Reg 190-16) Installation Access Control or (AE) Regulation 604-1 for Germany specific contracts, will be grounds for denying access to U.S. installations and controlled areas.  The Contractor shall ensure that any subcontractors used in performance of this contract complies with these requirements and that all employees, of both the Contractor and any subcontractor utilized by the Contractor, are made aware of and comply with these requirements.  Should anything in this paragraph conflict with AE Reg 190-16 or (AE) Regulation 604-1, the regulation takes precedent.

The Contractor shall be aware of and comply with the requirements associated with Installation Access Control.  The Government is not liable for any costs associated with performance delays due solely to a firm’s failure to comply with Installation Access Control System (IACS) processing requirements.

The contractor shall provide at least three (3) persons that have to obtain installation passes with sign-in privileges, as they are responsible for escorting and supervising subcontractors and occasional on-site prime contractor employees while on the U.S. installation.

The Contractor shall return installation passes to the issuing IACS office when the contract is completed or when a Contractor employee no longer requires access.

1.6.3.1   Installation Pass Log:   In addition, the Contractor shall provide the Contracting Officer, via the COR, an Initial Installation Pass Log within twenty (20) days after contract award (Deliverable # 04).  The log must contain at a minimum the following information of each employee: First Name, Last name, Installation Pass number and Expiring Date of Installation Pass.  The log shall be updated as employees are added or removed.  The Updated Installation Pass Log shall be current and available at any time upon request by the Government and submitted to the COR within five (5) days after any changes to the log (Deliverable # 04).

1.6.3.2   The Contractor shall collect the installation access passes the same day employment of an individual has expired or has been terminated and shall return them to the issuing office within three (3) days (Deliverable # 05).

1.6.3.3   Upon termination or cancellation of this contract, the Contractor shall collect all outstanding installation access passes and return them to the issuing office within three (3) days (Deliverable # 05).

1.6.3.4   Common Access Cards (CAC):   The Contractor shall provide the following information: Last, First Middle Name, Cadency Name, Personal identifier (e.g. Social Security Number, Federal Identification Number, or Tax Identification Number), date of birth, primary email address (this email address will be used to contact the individual), digital copy of ID (Personalausweis), digital copy of police certificate of good conduct (PGCC) to the COR with 15 calendar days after award (unless circumstances require otherwise and as directed by the Contracting Officer) (Deliverable #06).  The Contractor shall ensure safeguarding of Personally Identifiable Information (PII) and comply with requirements under 1.22.5. The Contractor shall submit the Trust Associate Sponsorship System (TASS) application request to the COR as required.  CACs are Government property and must be accounted for.

The contractor and all subcontractor employees will be issued a CAC only if duties involve one of the following: (1) Both physical access to a DoD facility and access, via logon, to DoD networks on-site or remotely; (2) Remote access, via logon, to a DoD network using DoD-approved remote access procedures; or (3) Physical access to multiple DoD facilities or multiple non-DoD federally controlled facilities on behalf of the DoD on a recurring basis for a period of 6 months or more.

1.6.3.4.1   The Contractor shall provide a CAC log within the first 30 calendar days after contract award and within five (5) days after changes have been made (Deliverable #A.07) (unless circumstances require otherwise and as directed by the Contracting Officer). The COR will provide format and content for the log during the post award meeting.  Note - CACs are Government property and must be accounted for.

1.6.4   Background Checks:   Army in Europe (AE) Regulation 604-1 provides guidance pertaining to background checks for U.S. and Host Nation Contractors.

1.6.4.1   U.S. Citizen:   Contractors that work with or teach youth under the age of 18 years are subject to local and stateside background checks.  The Requiring Activities Security Manager through COR will determine the extent of background checks required.  The Contractor employee may begin performance of the contract after receiving a favorable local background check.  The Contractor agrees to replace the employee should results of the stateside background check, if required, be unfavorable as determined by the Requiring Activities Security Manager.  The Contractor’s replacement of the employee with the unfavorable background check shall be within a timeframe provided by the Requiring Activities Security Manager.  The Contractor shall also replace employees whose background check, during their tenure of employment, renders them with an unfavorable local or stateside background check, as determined by the Requiring Activities Security Manager.  The Contractor shall forward a copy to the KO via the COR and the Requiring Activities Security Manager of each favorable background check within thirty (30) days of receipt by the Contractor, identifying such with the appropriate contract number (Deliverable # 08).  The Contractor shall forward a copy to the KO via the COR and the Requiring Activities Security Manager of each unfavorable background check within three (3) days of receipt by the Contractor, identifying such with the appropriate contract number (Deliverable # 09).  When the Government awards a non-personal services contract directly to an individual, the failure of the individual to provide a favorable background check would be grounds for termination.

1.6.4.2   Local Nationals and Third Country Nationals:   Local national and third country national Contractors that work with or teach youths under the age of 18 years are subject to background checks as determined by the Requiring Activities Security Manager.  As a minimum prior to beginning performance, Contractors employing local national and third country nationals shall furnish the KO via the COR and the Requiring Activity Manager a Police Good Conduct Certificate - PGCC (Polizeiliches Führungszeugnis), issued within the previous four months, no later than thirty (30) days after contract award (Deliverable # 09).  Forwarding correspondence from the Contractors shall identify the associated contract number.  The Requiring Activity Manager will determine the favorability of the Police Good Conduct Certificate - PGCC (Polizeiliches Führungszeugnis) and notify the Contractor.  The Contractor shall forward a copy of unfavorable Police Good Conduct Certificate - PGCC (Polizeiliches Führungszeugnis) to the KO via the COR and the Requiring Activity Manager within three (3) days of receipt, identifying such with the appropriate contract number (Deliverable # 09).  Local nationals and third country nationals agree to the same employee termination provisions as stated for U.S. Citizens (see paragraph 1.9.5.1 above, in particular, same requirements to replace the employee (and within timeframe noted) when results of background check are unfavorable).  IAW AER604-1, all on-site Contractors, regardless of nationality, must be living in the Host Nation for a minimum of one year.  Proof of residency must be provided.

1.6.5   Physical Security:   The Contractor shall safeguard all Government equipment, information, and property provided for Contractor use. At the close of each work period, Government facilities, equipment, and materials shall be secured IAW the Army Physical Security Program (AR 190-13).

1.6.6   Operations Security (OPSEC) Requirements:   Contractor personnel shall adhere to facility security policies and restrictions.  The Contractor shall immediately report suspicious activities to security personnel.

1.7   Key Control:   The Contractor shall establish and implement methods of making sure all keys issued to the Contractor by the Government are not lost or misplaced and are not used by unauthorized persons.  NOTE: All references to keys include key cards.  No keys issued to the Contractor by the Government shall be duplicated.  The Contractor shall develop procedures covering key control that shall be included in the Quality Control Plan.  Such procedures shall include turn-in of any issued keys by personnel who no longer require access to locked areas.  The Contractor shall immediately report any incidents of lost or duplicate keys to the Contracting Officer.  In the event keys, other than master keys, are lost or duplicated, the Contractor shall, upon direction of the Contracting Officer, re-key or replace the affected lock or locks; however, the Government, at its option, may replace the affected lock or locks or perform re-keying.  When the replacement of locks or re-keying is performed by the Government, the total cost of re-keying or the replacement of the lock or locks shall be deducted from payment due to the Contractor.  In the event a master key is lost or duplicated, all locks and keys for that system shall be replaced by the Government and the total cost deducted from the payment due to the Contractor.  The Contractor shall prohibit the use of Government issued keys by any persons other than the Contractor’s employees.  The Contractor shall prohibit the opening of locked areas by Contractor employees to permit entrance of persons other than Contractor employees engaged in the performance of assigned work in those areas, or personnel authorized entrance by the Contracting Officer.  The Contractor shall establish and implement methods of ensuring that all lock combinations are not revealed to unauthorized persons.  The Contractor shall ensure that lock combinations are changed when personnel having access to the combinations no longer have a need to know such combinations.  These procedures shall be included in the Quality Control Plan.

1.8   Post Award Conference/Periodic Progress Meetings:   The Contractor shall attend any post award conference convened by the contracting activity or contract administration office in accordance with FAR Subpart 42.5.  The Contracting Officer, COR, and other Government personnel, as appropriate, may meet periodically with the Contractor to review the Contractor's performance.  At these meetings the Contracting Officer will apprise the Contractor of how the Government views the Contractor's performance and the Contractor shall apprise the Government of problems, if any, being experienced.  Appropriate action shall be taken to resolve outstanding issues.  These meetings shall be at no additional cost to the Government. The Kick-off meeting will be in person the progress meetings can be held virtual (MS Teams).

1.8.1   The Contractor shall attend, participate in, and furnish input to scheduled and unscheduled meetings, conferences, and briefings that relate to the functions and services herein as required by the Government to provide effective communication and impart necessary information.  The Contract Manager or designated representative shall attend meetings as requested by the Government.  Meeting attendees shall at times include Contractor managerial, supervisory, and other personnel knowledgeable of the subject matter. Meetings may start or end outside of regular duty hours.

1.9   Contracting Officer’s Representative (COR):   Refer to Part 2 of this PWS for the definition of a COR.  As determined by the Contracting Officer, a COR will be appointed and identified by letter of designation, a copy of which will be provided to the Contractor by the Contracting Officer.  The designation letter states the responsibilities and limitations of the COR, especially with regard to changes in cost or price, estimates, or changes in delivery dates.  The COR is not authorized to change any of the terms and conditions of the resulting order.  The COR monitors all technical aspects of the contract and assists in contract administration.  The COR is not authorized to obligate the Government.  If the work is not written in the contract, the COR is not authorized to request new work.  The COR is authorized to perform the following functions: assure that the Contractor performs the technical requirements of the contract, perform inspections necessary in connection with contract performance, maintain written and oral communications with the Contractor concerning technical aspects of the contract, issue written interpretations of technical requirements, including Government drawings, designs, specifications, monitor Contractor's performance and notifies both the Contracting Officer and Contractor of any deficiencies, coordinate availability of Government property, and coordinate site entry of Contractor personnel.

1.10   Key Personnel:   The following personnel are considered key personnel by the Government:

- Program Manager (PM)

- Alternate Program Manager (APM)

1.10.1   The Contractor shall provide a Program/Contract Manager, Quality Control Manager, etc. who shall be responsible for the performance of the work.  The name of this person and an Alternate Program/Contract Manager, who shall act for the Contractor when the Manager is absent, shall be provided in writing to the KO no later than five (5) days after contract award  (Deliverable # 10). The Contract Manager and Alternate Contract Manager shall have full authority to act for the Contractor on all contract matters relating to daily operation of this contract.  The Contract Manager or Alternate Contract Manager shall be available between the hours of 0700 to 1700, Monday through Friday.  The Contractor shall notify the KO and COR in the event of a transition (replacing or removal) of key personnel working under this contract.  The Government reserves the right to review the qualifications of any Contractor personnel proposed to replace existing personnel and accept/reject the individual based on its judgement that the individual can perform similarly as the transitioned personnel.

1.10.2   Qualifications for all key personnel listed below:

a. Program Manager and Alternate Program Manager:   The PM and APM shall speak fluently the German language.  In addition the PM and APM shall meet English level 3 (Good working knowledge (refer to attachment 2 ‘English Language Fluency Clarification’). The Program Manager must demonstrate a minimum of four (4) years’ experience, within the past 10 years as a contractor working on US Army contracts.

b. Quality Control Manager (QCM):   The Quality Control Manager must demonstrate a minimum of four (4) years’ experience, within the past 10, working as a Quality Control Manager.  The QCM shall be able read and write at English Language Fluency level 3 (refer to attachment 2 ‘English Language Fluency Clarification’).

c. Personnel Qualifications:   All contractor personnel must demonstrate a minimum of two (2) years’ experience with a bachelor’s degree or other special qualifications required to perform work.  Contractor personnel performing this work shall meet English level 3 (Good working knowledge).

1.10.3   All Contractor personnel performing services shall submit the applicable German training certificates (Deliverable # 11) to the COR no later than ten (10) days after contract award to demonstrate their competency to perform the required work.

1.10.4   Special Qualifications:   Personnel who are adequately qualified with valid certifications to perform requested tasks and inspection in accordance with applicable federal and/or state and/or other legislation and ordinances (see Chapter 1.2)

1.10.4.1   Hazardous Material / Hazardous Waste:   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| EPAS Assessors | As Required | - A minimum of four (4) years’ experience or further special qualifications to perform work. - Additional a minimum of two (2) years’ experience with Hazardous Material / Hazardous Waste, within the past five (5) years - A minimum of two (2) years’ experience with TRGS 510 - A minimum of two (2) years’ experience with TRGS 520 - A mininmum o ftwo ( 2) years’s experience with waste management | - Bachelor’s degree or further special qualifications required to perform work - Trained in TRGS 510 - Trained in TRGS 520 - Waste management officer (Abfallbeauftragter) - Current Training as a waste management offocier(Abfallbeauftragter |
| Hazardous Material/Hazardous Waste Training Instructor | As required | - A minimum of two (2) years’ experience with Ordinance on Hazardous Substances (Gefahrstoff-verordnung - GefStoffV) - A minimum of two (2) years’ experience with waste management | - Trained in Ordinance on Hazardous Substances (Gefahrstoffverordnung - GefStoffV) - Waste management officer (Abfallbeauftragter) - Current Training as a waste management officer (Abfallbeauftragter) |

1.10.4.2   Building Contaminants:   Personnel must demonstrate a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| Building Contaminants #1 | As Required | - A minimum of four (4) years’ experience or further special qualifications required to perform work. - Two (2) years’ experience with building contaminants, within the past five (5) years | - Bachelor of Science e.g. chemistry, environmental science - Other special qualifications as required to perform work |
| Building Contaminants #2 | As Required | - A minimum of two (2) years’ experience with TRGS 519 | - Trained and certified in TRGS 519 |
| Building Contaminants #3 | As Required | - A minimum of two (2) years’ experience with building contaminants | - Building contaminants expert |

1.10.4.3   Petroleum Oil and Lubricants (POL):   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| POL #1 | As Required | - A minimum of four (4) years’ experience or further special qualifications required to perform work. - Two (2) years’ experience with POL within the past five (5) years | - Bachelor of science - Other special qualifications required to perform work |
| POL #2 | As Required | - A minimum of two (2) years’ experience with contaminated sites, within the past five (5) | - Technical expert for contaminated sites Altlastensachver-ständiger according to § 18 BBodSchG und § 36 GewO auf den Sachgebieten 1 bis 5). |

1.10.4.4   Spill Prevention and Response Planning:   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| Spill Prevention/Response | As Required | - A minimum of four (4) years’ experience or further special qualifications required to perform work. - Two (2) years’ experience with Spill Prevention and Response Planning within the past five (5) years | - Bachelor of science - Other special qualifications required to perform work |

1.10.4.5   Historical and Cultural Resources:   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| Historical/Cultural Resource | As Required | - A minimum of four (4) years’ experience or further special qualifications required to perform work. - Two (2) years’ experience with Historical and Cultural Resources within the past five (5) years | - Bachelor of science - Other special qualifications required to perform work |

1.10.4.5   Air Emissions:   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| Air Emissions #1 | As Required | - A minimum of four (4) years’ experience or further special qualifications | - Bachelor’s degree in engineering or further special qualifications required to perform work |
| Air Emissions #2 | 1 | - Two (2) years’ experience with German emission control laws BImSchG and BImSchV | - Emission control officer (Immissionsschutzbeauftragter) - Current Training as an Emission control officer (Immissionsschutzbeauftragter) |

1.10.4.6   Clean Water/Waste Water:   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| Water #1 | As Required | - A minimum of four (4) years’ experience or further special qualifications required to perform work. - Two (2) years’ experience with clean water/ wastewater within the past five (5) years | - Bachelor of science - Other special qualifications required to perform work |
| Water #2 | 1 | - A minimum of two (2) years’ experience with clean water act permit management and assessments. | - Bachelor in hydrogeology, geo-ecology or adequate degree |
| Water #3 | As Required | - A minimum of four (4) years’ experience with the technical inspection of AwSV | - Certified company (Fachfirma) according to AwSV § 45 + 62 |
| Water #4 | 1 | - A minimum of four (4) years’ experience with the technical inspection of AwSV | - A certified expert required by legal specification according to AwSV §47 |
| Water #5 | 1 | - A minimum of two (2) years’ experience with service equipment cleaners’ machines and proper disposal of used liquids | - Certified expert to service equipment cleaners’ machines and proper disposal of used liquids |
| Water #6 | 1 | - A minimum of two (2) years’ experience as a water protection officer (Gewässerschutzbeauftragter) | - Water protection officer (Gewässerschutzbeauftragter) - Current Training as Water protection officer (Gewässerschutzbeauftragter) |

1.10.4.7   Advisory Service:   The Contractor shall provide a minimum of:

| Title | # of Personnel | Experience | Education |
| --- | --- | --- | --- |
| Advisory #1 | As Required | - A minimum of four (4) years’ experience or further special qualifications required to perform work. - Two (2) years’ experience with requested task within the past five (5) years | - Bachelor of science in the required task - Other special qualifications required to perform work |
| Advisory #2 | As Required | - A minimum of two (2) years’ with contacting and corresponding with appropriate authorities (paragraph 1.2) |  |
| Advisory #3 | 1 | - A minimum of two (2) years’ experience with Geospatial Data, Current US Army software ArcGIS Desktop 10.4.1 or ArcGIS Pro 2.7 within the past five (5) years | - Trained and experienced in Geospatial Data, Current US Army software ArcGIS Desktop 10.4.1 or ArcGIS Pro 2.7 |
| Advisory #4 | As Required | - A minimum of two (2) years’ experience with within the past five (5) years in handling Hazardous Materials and Hazardous Waste | - Very good knowledge in handling Hazardous Materials and Hazardous Waste |
| Advisory #5 | As Required | - A minimum of two (2) years’ experience with within the past five (5) years with OSHA regulations (Hazcom and Hazwoper), AR 200-1, AER 200-1 and the GFGS, Technical Rules for Hazardous Substances (TRGS 520) certification, Spill Prevention and Response requirements | - Trained with OSHA regulations (Hazcom and Hazwoper trainings), AR 200-1, AER 200-1 and the GFGS. - Fluent English and German language skills are required in speaking and writing. |
| Advisory #6 | 1 | - A minimum of two (2) years’ experience within the past five (5) years in professional translating officinal correspondence from English to German as well as from German to English. LEVEL 5 as a Professional Translator/ Interpreter or Equivalent | - Trained in translating officinal correspondence from English to German as well as from German to English. LEVEL 5 Professional Translator/ Interpreter or Equivalent |

1.11   Identification of Contractor Employees:   All Contractor personnel attending meetings, answering Government telephones, and working in other situations where their Contractor status is not obvious to third parties must identify themselves as such to avoid creating an impression in the minds of members of the public that they are Government officials.  The Contractor shall ensure that all documents or reports produced by Contractors are suitably marked as Contractor products or that Contractor participation is appropriately disclosed.

1.12   Contractor workspace (staging site, on-site office, desk or work area, etc.):   shall contain a sign signifying the space is occupied by Contractor employee(s) to ensure that Government employees and the public know that they are not Government employees.  Workspace sign location shall be coordinated with the COR. Contractor employees shall identify themselves by name and company affiliation when answering the telephone, presenting briefings, conducting or attending meetings, and seminars.  All Contractor correspondence (written, facsimile, and email display) shall include their company name.  Requirements for Contractor vehicles is addressed under Part 4 paragraph 4.4.

1.12.1   Contractor Identification Badges:   Contractor personnel shall be easily identifiable through the display of badges.  The Contractor (to include subcontractors) shall provide each of their employees an easily readable identification badge.  The badge must include the employee’s name, the contractor’s company name, the functional area of assignment, and a recent color photograph of the employee.  Companies with U.S. Government contracts will require their employees to wear these badges visibly when performing work at Government workplaces unless this would be impractical because of mission or safety considerations.  The Contractor shall collect all ID Badges upon completion of the contract or termination of employee.  A listing of issued ID cards shall be furnished to the Contracting Officer prior to the contract performance date and updated as needed to reflect Contractor personnel changes (Deliverable #11a).

1.13   Contractor Travel:   The Contractor may be required to travel to the places of performance during the performance of this contract to attend meetings and to perform the tasks described in Part 5.  The Contractor shall provide the personnel with sufficient capability to independently travel between USAG Stuttgart installations.  Upon government request, the contractor shall be prepared to travel to meeting locations with host nation stakeholders and authorities such as the county offices in Stuttgart, Esslingen, Boeblingen and Ludwigsburg with no extra costs to the Government.  All mobilization will be defined at call level and covered under the mobilization task.

1.14   Other Direct Costs (ODCs):   Reserved.

1.15   Data Rights:   The Government has unlimited rights to all documents and materials produced under this contract.  All documents and materials, to include the source codes of software, produced under this contract shall be Government owned and are the property of the Government with all rights and privileges of ownership and copyright belonging exclusively to the Government.  These documents and materials may not be used or sold by the Contractor without written permission from the Contracting Officer.  All materials supplied to the Government shall be the sole property of the Government and may not be used for any other purpose.  This right does not abrogate any other Government rights.

1.16   Non-Disclosure Requirements:   Performance under this contract may require the Contractor to access data and information proprietary to a Government agency, another Government Contractor, or of such nature that its dissemination or use other than as specified in this work statement would be adverse to the interests of the Government or others.  The Contractor and Contractor personnel, shall not divulge or release data or information developed, or obtained under performance of this PWS, except to authorized Government personnel or upon written approval of the Contracting Officer.  The Contractor shall not use, disclose, or reproduce proprietary data, which bears a restrictive legend, other than as specified in this PWS.  All documentation showing individual names or other personal information shall be controlled and protected under the provisions of the Privacy Act of 1974, Public Law 93-579, 5 United States Code (U.S.C.) Section 552a.

1.17 The use of propaganda violates DoD Commercial Use of Imagery Guidelines stated at http://www.defenseimagery.mil/products/dodimagery/commercialuse.html  The Contractor shall not cite any information (e.g., contract information, pictures, locations, etc.) obtained through this contract on any marketing tools to include its company website.

1.18   Non-Disclosure Statements:   Reserved.

1.19   Organizational Conflict of Interest (OCI):   Contractor and subcontractor personnel performing work under this contract may receive, have access to or participate in the development of proprietary or source selection information (e.g., cost or pricing information, budget information or analyses, specifications or work statements, etc.) or perform evaluation services which may create a current or subsequent OCI as defined in FAR Subpart 9.5.  The Contractor shall notify the Contracting Officer immediately whenever it becomes aware that such access or participation may result in any actual or potential OCI and shall promptly submit a plan to the Contracting Officer to avoid or mitigate any such OCI (Deliverable #12).  The Contractor’s OCI Mitigation Plan will be determined to be acceptable solely at the discretion of the Contracting Officer.  In the event the Contracting Officer unilaterally determines that any such OCI cannot be satisfactorily avoided or mitigated, the Contracting Officer may affect other remedies as he or she deems necessary, including prohibiting the Contractor from participation in subsequent contracted requirements which may be affected by the OCI.

1.20   Phase In /Phase Out Period:   Reserved.

1.21   Safety:   Reserved.

1.21.1   Host Nation Safety Laws and Regulations:   Reserved.

1.22   Environmental Compliance:   The following provides information on Environmental Compliance.

1.22.1   Environmental Compliance Plan and Program:   Reserved.

1.23   Required Training:   The following provides information on training requirements.

1.23.1   Anti-Terrorism (AT) Level I Training:   All Contractor employees, including subcontractor employees, who are employed under the contract, shall complete AT Level I Training within thirty (30) days (Deliverable # 11) after contract start date or effective date of incorporation of this requirement into the contract, whichever applies, or thirty (30) days after employment of new personnel.  Contractor personnel traveling overseas shall complete area of responsibility (AOR) specific AT awareness training for U.S. based Contractor employees and associated subcontractor employees.  The Contractor shall submit certificates of completion (Deliverable # 13) for each affected Contractor employee and subcontractor employee to the COR (or to the KO, if a COR is not assigned) within ten (10) days after completion of this training by all employees and subcontractor personnel.  AT Level I awareness training is available at https://jkodirect.jten.mil.  Contractor personnel shall complete refresher training every twelve (12) months except AOR specific AT Level I training which shall be completed as required by local AT policies (Deliverable #13).

1.23.2    OPSEC Training:   All Contractor employees, including subcontractors, shall complete Level I OPSEC training within twenty (20) days of employment under this contract.  Verification of the training shall be provided to the COR within ten (10) days after completion of the training. OPSEC Level I training is available at http://www.cdse.edu/catalog/elearning/GS130.html.  Contractor personnel must complete refresher training every 12 months.  Verification of the training shall be provided to the COR within ten (10) days after completion of the training (Deliverable # 14).

If training cannot be conducted on the website, the Contractor shall coordinate with the COR, who will contact the local OPSEC Officer at their assigned location for classroom training.  Contractor personnel completing training in the classroom will receive a certificate or the training attendance roster signed by the OPSEC Officer.  Verification of the training shall be provided to the COR within ten (10) days after completion of the training.

1.23.3   iWATCH Training:   The Contractor and all associated subcontractors shall brief all employees on the local iWATCH program (training standards provided by the requiring activity ATO).  This locally developed training will be used to inform employees of the types of behavior to watch for and instruct employees to report suspicious activity to the COR.  This training shall be completed within twenty (20) days after the contract is awarded and within twenty (20) days after new employees commence contract performance. Verification of the training shall be provided to the COR within ten (10) days after completion of the training (Deliverable#15). Training slides found on the Army OneSource we site: http://www.myarmyonesource.com/familyprogramsandservices/iwatchprogram/default.aspx.

1.23.4   Information Assurance (IA) Training

1.23.4.1   Personally Identifiable Information (PII):   Reserved.

1.23.5   Threat Awareness Reporting Program:   Per AR 381-12, Threat Awareness and Reporting Program (TARP), contractor employees must receive annual TARP training by a CI agent or other trainer as specified in 2-4b.

1.24   Authorization to Perform Services in Germany

1.24.1   Contractors performing services in the Federal Republic of Germany (FRG) shall comply with German law.  The Contractor shall determine whether performance requires registration with German authorities or authorization to do business in Germany and, if so, shall comply with all requirements.  Whether or not registration or authorization to do business is required, the Contractor shall determine what documents or authorization its employees and any subcontractor employees must possess to work in Germany.  The Contractor shall ensure affirmatively that its employees and subcontractor employees possess such documents or authorizations.

1.24.2   Contractor employees who: (a) are not nationals of Germany or other European Union countries; (b) are not members of the force, the civilian component or their dependents; or c) do not have assimilated status under Articles 71, 72, or 73 of the Supplementary Agreement to the NATO SOFA shall possess work and residence permits.

1.24.3   By acceptance of and performance under this contract, the Contractor affirms that it has complied with the requirements above.  Compliance with this requirement and German law is a material contract requirement.  Noncompliance by the Contractor or subcontractor at any tier shall be grounds for issuing a negative past performance evaluation and terminating this contract for default.

1.25   Notice to Proceed:   Reserved.

1.26   Electromagnetic Compatibility Directive:   The Contractor certifies that all electrical and electronic equipment and appliances furnished are in compliance with the Electromagnetic Compatibility Directive 2014/30/EU.  For radio transmitting and telecommunication devices furnished in the Federal Republic of Germany, the Contractor certifies that all such items have been approved by the Bundesamt fuer Zulassungen.  Any penalties for noncompliance imposed by the Government of the European country where the equipment or appliances are delivered or product liability claims caused by interference generated by furnished appliances or equipment are solely the responsibility of the Contractor.

1.27   Government Property and Services:   Reserved.

1.28   Conventional Forces Europe (CFE) Treaty Verification Inspection:   Contractor-owned or controlled structures and containers located on U.S. Government installations are subject to short-notice inspections by CFE treaty inspection teams.  The Government will endeavor to provide the Contractor as much notice as possible in the event of such inspections.  The contractor shall provide access to such structures and containers at the request of the Government.  The Contractor shall report such inspections to the KO through the COR in writing within ten (10) calendar days of completion of the inspection.  Contractor-owned or controlled structures and/or containers on U.S. installations may have to be inspected to comply with the CFE treaty even if Contractor personnel are unavailable to provide access.  Any costs borne by the Contractor or any impact on contract performance as a result of the inspection will be a matter of negotiation between the Contractor and the KO.

PART 2

DEFINITIONS & ACRONYMS

2.  Definitions and Acronyms

2.1   Definitions:   Although not inclusive of every term used within this PWS, the following provides a list of definitions used throughout this PWS and commonly used in the acquisition field.

Contracting Officer – means a person with authority to enter into, administer, and or terminate contracts, and make related determinations and findings on behalf of the Government.  Note: The only individual who can legally bind the Government.

Contracting Officer's Representative (COR) – As defined in DFARS 202.101, means an individual designated and authorized in writing by the Contracting Officer to perform specific technical or administrative functions.  Department of Defense Instruction (DoDI) 5000.72, Part II Definitions states the following when defining a COR:  “Defined in subpart 202.101 of Reference (f).  Any individual delegated responsibilities pursuant to subpart 1.602-2 of Reference (e), regardless of local terminology, must be certified in accordance with this instruction.  For example, local terminology can be COR, contracting officer’s technical representative, technical point of contact, technical representative, alternate COR, administrative COR, assistant COR, line item manager, task order manager, quality assurance personnel, quality assurance evaluator, or COR management.”  In addition, Army Regulation 70-13, Chapter 2, paragraph 2-2g, states, in part, the following when providing support personnel to assist the COR, “…These other surveillance support personnel may serve as on-site representatives of the COR in performance of actual contract surveillance if they meet all COR requirements and have been appointed by the Contracting Officer as alternate CORs.”

Contractor – means a supplier or vendor awarded a contract to provide specific supplies or service to the Government.  The term used in this contract refers to the prime.

Contractor-acquired property – means property acquired, fabricated, or otherwise provided by the Contractor for performing a contract, and to which the Government has title.

Day – means, unless otherwise specified, a calendar day.

Defective Service – means service output that does not meet the standard of performance associated with the Performance Work Statement.

Deliverable – means anything that can be physically delivered, but may include non-manufactured things such as meeting minutes or reports.

Government-furnished property – means property furnished to the contractor the Government and subsequently furnished to the Contractor for performance of a contract. Government-furnished property includes, but is not limited to, spares and property furnished for repair, maintenance, overhaul, or modification. Government-furnished property also includes Contractor-acquired property if the Contractor-acquired property is a deliverable under a cost contract when accepted by the Government for continued use under the contract.

Government property – means all property owned or leased by the Government.  Government property includes both Government-furnished property and Contractor-acquired property. Government property includes material, equipment, special tooling, special test equipment, and real property. Government property does not include intellectual property and software.

Property Administrator – means an authorized representative of the Contracting Officer appointed in accordance with agency procedures, responsible for administering the contract requirements and obligations relating to Government property in the possession of a Contractor.

High Level Objective (HLO) – means a key overarching result-based objective for a project necessary to achieve the project’s vision. HLOs are similar to Level 2 in a Work Breakdown Structure.  Each HLO may contain several statements to flesh out the areas necessary to meet the objective.

Physical Security – means that part of security concerned with physical measures designed to safeguard personnel; to prevent unauthorized access to equipment, installations, material, and documents; and to safeguard against espionage, sabotage, damage, and theft.

Quality Assurance – (or Government contract quality assurance) means the various functions, including, inspection, performed by the Government to determine whether a Contractor has fulfilled the contract obligations pertaining to quality and quantity.

Quality Assurance Surveillance Plan (QASP) – means the key Government-developed surveillance process document, and is applied to Performance-Based Service Contracting (PBSC).  The QASP is used for managing Contractor performance assessment by ensuring that systematic quality assurance methods validate that Contractor quality control efforts are timely, effective, and are delivering the results specified in the contract or task order.  The QASP directly corresponds to the performance objectives and standards (i.e., quality, quantity, timeliness) specified in the Performance Work Statement (PWS).  It provides specific details on how the Government will survey, observe, test, sample, evaluate, and document Contractor performance results to determine if the Contractor has met the required standards for each objective in the PWS.  The QASP, with very few if any exceptions, is an internal to Government document.

Quality Control – means all necessary measures taken by the Contractor to assure that the quality of an end product or service shall meet contract requirements.

Statement – means the specific results-based activities required to satisfy HLOs.  A statement contains a result, the context of the statement, and the required action(s). Statements focus on “what” is to be accomplished; however they are not prescriptive in describing “how” the outcome is to be achieved. Each HLO may have several statements to flesh out the areas necessary to meet the objective. Statements are similar to Level 3 in a Work Breakdown Structure.

Subcontractor – means one that enters into a contract with a prime Contractor.  The Government does not have privity of contract with the subcontractor.

Work Day – The number of hours per day the Contractor provides services in accordance with the contract.

Work Week – Monday through Friday, unless otherwise specified.

2.2   Acronyms:  Although not inclusive of every term used within this PWS, the following provides a list of acronyms used throughout this PWS or commonly used in the acquisition field.

ACOR			Alternate Contracting Officer's Representative

AER 			Army in Europe REgulation

AFARS			Army Federal Acquisition Regulation Supplement

AHA			Activity	Hazard Analysis

AOR			Area of Responsibility

AR			Army Regulation

AST			Above Ground Storage Tank

AT			Anti-terrorism

ATCTS			Army Training Certification Tracking System

AQL			Acceptable Quality Level

AwSV			Ordinance on Systems for Handling Substances Hazardous to Water

CAC			Common Access Card

CSE			Contractor Support Element (CSE)

CCE			Contracting Center of Excellence

CFE 			Conventional Forces Europe

CFR			Code of Federal Regulations

CONUS			Continental United States (excludes Alaska and Hawaii)

COR			Contracting Officer’s Representative

COTS			Commercial-Off-the-Shelf

CWA			Clean Water Act

DA			Department of the Army

DD250			Department of Defense Form 250 (Receiving Report)

DD254			Department of Defense Contract Security Requirement List

DFARS			Defense Federal Acquisition Regulation Supplement

DMDC			Defense Manpower Data Center

DoD			Department of Defense

DPW			Department of Public Works

DFARS			Defense Federal Acquisition Regulation Supplement

ED			Environmental Division

EPAS 			Environmental Performance Assessment System

FAR			Federal Acquisition Regulation

FGS			Final Governing Standards

FRG			Federal Republic of Germany

GFP			Government Furnished Property

HLO			High Level Objective

HIPAA			Health Insurance Portability and Accountability Act of 1996

HM			Hazardous Material

HN			Host Nation

HQDA			Headquarters Department of the Army

HW			Hazardous Waste

HWAP			Hazardous Waste Accumulation Point

HWSA			Hazardous Waste Storage Area

HWMP			Hazardous Waste Management Plan

IA			Information Awareness

IAC			Installation Access Control

IACO			Installation Access Control Office

ID			Identification

IGCE			Independent Government Cost Estimate

IT			Information Technology

JTR			Joint Travel Regulation

JPAS			Joint Personnel Adjudication System

KO			Contracting Officer

KrWG			Closed Substance Cycle Waste Management Act (Kreislaufwirtschaftsgesetz)

LNSP			Local national Screening Program

NachwV			Verordnung über die Nachweisführung von Abfällen (Nachweisverordnung)

NISPOM			National Industrial Security Program Operating Manual

NTP			Notice to proceed

OCI			Organizational Conflict of Interest

OCONUS		Outside Continental United States (includes Alaska and Hawaii)

ODC 			Other Direct Costs

OPSEC			Operations Security

OSHA			Occupation Safety and Health Administration

NATO			North Atlantic Treaty Organization

PII			Personally Identifiable Information

PIPO			Phase In/Phase Out

POC			Point of Contact

PPE			Personal Protective Equipment

PRS			Performance Requirements Summary

PWS			Performance Work Statement

QA			Quality Assurance

QAP			Quality Assurance Program

QASP			Quality Assurance Surveillance Plan

QC			Quality Control

QCP			Quality Control Program

RA			Requiring Activity

RCO			Regional Contracting Office

SAAR			System Authorization Access Request

SCI			Sensitive Compartmented Information

SDWA			Safe Drinking Water Act

SDS			Safety Data Sheets

SIGE			Safety and Health Protection Plan

TE			Technical Exhibit

TO			Task Order

TPOC			Technical Point of Contact

TRGS 510		Technical Rules for the storage of Hazardous Substances in mobile containers

TRGS 520		Technical Rules for the storage of Hazardous Substances in stationary containers

UOM 			Unit of Measurement

USAG			United State Army Garrison

UST			Underground Storage Tank USAREUR		U.S. Army Europe

SOFA			Status of Forces Agreement

SWPPP			Storm Water Pollution Prevention Plan

WHG			German Federal Water Act (Wasserhaushaltsgesetz)

WOT			Waste Oil Tank

PART 3

GOVERNMENT PROPERTY (GP) AND SERVICES

3.  Government Property and Services

3.1   Services:   The Government will provide the Contractor with an account and access required for all databases and systems required to complete tasks in this PWS, including SDSFIE Online, the DISDI Portal, and Army Installation Geospatial Platform.  The Government will provide support to assist with coordination between the contractor and Garrison point of contacts for sampling events.

3.2   Facilities:   The Government will provide desk space for the Contractor to provide the support outlined in the PWS.

3.3   Utilities:   Reserved.

3.4   Equipment:   The Government will provide computers, desks, chairs, working space, office supplies, standard office software (MS Office, Windows) and access to enterprise geospatial tools and datasets, as needed.  Scanner, copy machine, large plotter are made available within the building.  The contractor will most often be working on Government computers and network systems.  All desktop hardware, operating systems and software provided by the Government are incidental to the performance of this contract

3.5   Special Tooling and Test Equipment:   Reserved.

3.6   Materials:   The Government will provide:  The Garrsion Hazardous Waste Management Plan, Spill Prevention and Resposnse Plan, Maps, Floor plans, Standard Operating Procedures (SOPs), Policies, etc. necessary to perfrom the services described in the PWS.

3.7   Training:   The Government will provide the following training: AT Level 1 Awareness, OPSEC, iWATCH and and IA training.

3.8   Common Access Cards (CAC):   The Government will provide Common Access Cards (CAC) via the Trusted Associate Sponsorship System (TASS) (Web site https://www.dmdc.osd.mil/tass/).

PART 4

CONTRACTOR FURNISHED ITEMS AND SERVICES

4.   Contractor Furnished Property and Services

4.1   General:   The Contractor shall furnish all personnel, equipment, supplies, transportation, tools, materials, supervision, and other items necessary to perform services as described in the PWS and associated contract documents, except for those items specified in Part 3 Government Property and Services.

4.2   Secret Facility Clearance:   Reserved.

4.3   Materials:   The Contractor shall provide Personal Protective Equipment (PPE), technical equipment, transportation, supplies and materials needed in the performance of this contract.

4.4   Vehicles and Equipment:   The Contractor shall provide all necessary vehicles (no GSA vehicles provided to Contractor for use on this contract) and equipment to perform the work described in this PWS.  All Contractor provided vehicles and equipment shall present a neat, professional appearance.  Contractor's vehicles and equipment used in the performance of this contract shall meet all local and Host Nation traffic, safety, and environmental requirements.  Vehicles and equipment found to be unsafe shall be removed from the installation and replaced.  The Contractor shall not use any Government-owned tools, materials, or parts to maintain Contractor vehicles and equipment without prior written approval of the KO.  The COR may inspect the Contractor’s vehicles and equipment at any time.

The contractor shall provide a company notebook for each on-site employee including the most current ESRI ArcGIS software in order for personnel to work independently should government network access be interrupted.

The contractor shall provide any additional equipment such as external hard drives, internet/Wi-Fi stick, GPS mapping tools etc. required to perform services described in the PWS.

4.5  Background Checks):   The Contractor shall provide Background Checks in accordance with this PWS and as determined by the Government.

PART 5

SPECIFIC TASKS

5.1   Basic Services:   The Contractor shall furnish all labor, materials, tools, supplies, services, equipment, project management, permits, contract/procurement administration, etc. necessary to perform all work in accordance with the PWS.  The Contractor shall conduct all work in accordance pertinent state, local, and federal regulations along with approved work plans.

The contractor on-site personnel is required to use government phones or business cell phones for all business related communication and be available for services during normal business hours of the environmental office.  Knowledge of U.S. Army organization, mission, structure and function at the Garrison level will be required to perform these tasks.

This performance work statement (PWS) solicits services for providing environmental compliance support to meet regulatory standards within the Directorate of Public Works (DPW), Environmental Division (ED) established by the Final Governing Standards (FGS) for Germany, a combination of U.S. and German regulations.  Along with the FGS, all work performed must follow applicable host nation laws, acts, and regulations throughout the USAG Stuttgart.

The Contractor shall provide support through management of environmental compliance services for the following FGS requirements:

- Hazardous materials/hazardous waste

- Spill prevention

- Air emissions

- Noise

- Storm water

- Tanks

- Oil water

- Separators

- ContaminantsPermits

- Environmental awareness and training

The Contractor shall perform:

- scheduling/coordination

- provide equipment/materials

- oversight of management measures for inspections

- site visits

- training events

- samplings

- lab services

- other efforts that will be discussed further in detail

The Contractor shall coordinate site access as appropriate including scheduling with Range Control or with the COR for appropriate POCs depending on the facility.  In the event the Contractor is having challenges in certain areas, the Contractor must notify the COR with two (2) hours.

5.2   Specific Tasks

5.2.1   Project Management:   This element includes direct management of the project, as well as the support for administrative functions needed for successful project management.  The project manager is expected to focus on managing the performance of the TO including: technical and financial performance, interacting with the ED project team

- financial tracking

- communicating with team members

- preparing management reports

- attending management meetings

- organizing of a regular status meeting in TEAMS, one meeting per month and when necessary

- coordinating contract issues with the project teams providing required project support functions

5.2.1.1   The Contractor must document any necessary meetings via meeting minutes and submit a copy to the COR for review within five (5) days (Deliverable #16), electronically via email.  Thereafter, if the COR does not respond within five (5) days, the meeting minutes become final.

5.2.1.2   The Contractor will submit a brief quarterly progress report and submit a copy to the COR within five (5) days (Deliverable # 17), electronically via email.  Quarterly progress report shall detail, at a minimum, what has been accomplished during the period since last reporting, what is expected to be accomplished during the next month, schedule (including dates for deliverables), and costs incurred during the month. The schedule shall include dates for deliverables and the sequence of tasks needed to reach the objectives for this PWS.

5.2.1.3   The contractor must submit all deliverables according to specifications detailed in Technical Exhibit B.

5.2.2   Advisory Services:   Upon government request, the Contractor shall provide advisory service through their expertise. This includes but is not limited to preparation, and coordination of various site visits, inspections, and training events upon government request.  Support efforts shall include all FGS chapters, especially the following environmental compliance topics:

- hazardous materials/hazardous waste

- recycling

- spill prevention

- air emissions

- noise

- drinking/waste/storm water

- tanks

- oil water separators

- contaminants

- samplings

- permits

- environmental awareness

- historic research

- training

5.2.2.0.1   The Contractor shall provide professional recommendations based upon site visit results, visual assessments/inspections or document research. Recommendations shall include measures needed to remediate an area of potential concern or provide corrective action measures.

5.2.2.0.2   Advisory services includes:

- Professional recommendations based upon site visits

- Visual assessments/inspections

- Additional work needed to remediate an area of potential concern or provide corrective action

- Submission of a report

5.2.2.0.3   Contractor reports must clearly evaluate the site condition concerning the maintenance and storage of hazardous materials/waste, tanks, salt silos, OWS, retention/infiltration basins and other facilities on USAG Stuttgart in reference to corresponding German and State Regulations and local authorities.  The contractor must evaluate impacts to the environment where environmental requirement thresholds are exceeded or where there are potential failures of compliance requirements.  The contractor must provide a report that includes recommendations for further action with photo documentation if requested by the COR.

5.2.2.1   Hazardous Substance Compliance Program Support:   The Contractor shall provide hazardous substance (HS) compliance and management support to ensure the Garrison is following all applicable GFGS and U.S. Army Regulations, including U.S. Army Regulation 200-1 (AR 200-1) and U.S. Army in Europe Regulation 200-1 (AER200-1).

5.2.2.2   Support Environmental Awareness Events:   The Contractor shall provide support for environmental awareness events within USAG Stuttgart installations.  Events include Earth Day, American Recycle Day, Safety Day, and school activities.

5.2.2.3   EPAS (track findings, support external EPAS visits, prepare communication material):   USAG Stuttgart conducts internal Environmental Performance Assessment System (EPAS) inspections annually, except every third year, when as an external EPAS audit is conducted. Internal EPAS inspections are typically conducted between May and August.  In support of this requirement, the Contractor shall provide a quality review of the Garrison’s environmental management program while referencing Army standard protocols.  This shall include historical document reviews and site visits at locations at various locations within USAG Stuttgart to evaluate their compliance status.  Before external EPAS audits, the Contractor shall prepare all units, organizations, and tenants by conducting courtesy inspections.  The Contractor shall assess environmental compliance in all media areas and document discrepancies both on the audit template and in photographs.

5.2.2.3.1   Follow-up to an internal EPAS:   As a follow up to an internal EPAS inspection, the Contractor shall support in the development of potential corrective actions measures for findings made during an inspection.  The Contractor shall assist in ranking the risk level of the findings from low to high and shall provide and maintain this information within associated database.  The Contractor shall, on a weekly basis, update the database and inform ED TPOC of progress made on corrections.  The Contractor shall prepare corrective action status reports describing the progress in a standard format provided by the Garrison that allows the Garrison Commander to monitor compliance trends and progress.  The Contractor shall follow up on findings via email/phone call on a monthly basis with unit/tenant to close out findings.  Documentation on follow-up and correspondence on findings shall be provided to ED chief on a monthly basis.

5.2.2.4   Advisory Service for Compliance:   The Contractor shall provide expertise and consultant services for environmental related topics. Upon Government request, the Contractor shall facilitate compliance assessment.

5.2.2.4.1   The Contractor shall provide a yearly completion report by the end of each contract POP.  The Contractor shall provide a draft of the completion report within fifteen (15) days prior to POP end (Deliverable #18).  Upon Government provided comments, the Contractor shall then have three (3) days to submit a final electronic copy to the COR (The deliverable can be ordered by the Government in English and in German otherwise in English or in German

5.2.2.5   Compliance Assessment Report:   The Contractor shall prepare a compliance assessment report identifying deficiencies and recommended corrective actions per site assessment of each location.  Corrective action recommendations should have enough detail to support a design or work order (e.g., “increase containment capacity to X gallons/liters” or “install leak detection equipment suitable for [one or more specific substances]”).  Deficiencies should include a ranking system based on severity and likelihood of an incident occurring.

5.2.2.5.1   The Contractor shall provide a draft report within three (3) months.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy to the COR ( The deliverable can be ordered by the Government in English and in German (Deliverable #19) otherwise in English or in German (Deliverable #20).

5.2.3   Management Plans:   The Contractor shall update existing management plans regarding requirements outlined in German Final Governing Standards (GFGS) (reference potential list of examples below).  Support efforts shall include, but are not limited to, provided examples.  Upon Government request, the Contractor shall provide management plans in English and/or in German.

5.2.3.1   The Contractor shall update existing management plans.

5.2.3.1.1   The Contractor shall provide a draft report within five (5) months, electronically, via email in word and pdf file to the COR.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy and hardcopies as required to the COR meeting.  The deliverable can be ordered by the Government in English and in German (Deliverable #21) otherwise in English or in German (Deliverable #22).

5.2.3.2   Services under this task include, but are not limited to the following:

- Update contact information, such as: POC, address, telephone, and emergency numbers, building numbers, signature blocks

- Changes to operation locations, list of facilities, spreadsheets or similar

- Add or remove operating locations, facilities, units etc.

- Changes to maps included in the plan

- Contractor shall review and use information provided from Compliance Assessment to update report

- Review of the Government requested sections for consistency with host nation legal requirements, GFGS and current best practices

- Update all maps and geospatial data layers associated with the plan

- Develop new content to include chapters, sections, appendices

- If necessary, field verify current information contained in plan

5.2.4   Training:   The Contractor shall provide training on behalf of USAG Stuttgart Environmental Division.  The training shall be in accordance with current laws and regulations.  The training will be a MS PowerPoint presentation or other format as clarified by COR.  The Contractor shall prepare attendance rosters for each training class and provide the rosters to the Environmental Division (ED) after completion of training.  Upon Government provided comments, the training shall be in English and/or in German.  The Contractor shall reach out to participants and, in coordination with ED, establish training schedule.

5.2.4.1   Develop Training:   Upon government request, the Contractor shall develop training as an MS PowerPoint presentation or other format clarified by COR, regarding environmental related topics. Topic will be determined upon Government request.

5.2.4.1.1   The Contractor shall provide a draft developed training within six (6) months, electronically, via email as MS PowerPoint and pdf file to the COR.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy and one hardcopy to the.  The deliverable can be ordered by the Government in English and in German (Deliverable #23) otherwise in English or in German (Deliverable #24).

5.2.4.2   Update Training:   The Contractor shall update existing training as an MS PowerPoint presentation or other format as clarified by COR.  Topic to be determined upon Government request.  The Contractor shall provide a draft update within three (3) months, electronically, via email as MS PowerPoint and pdf file to the COR.

5.2.4.2.1   Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy to the COR The deliverable can be ordered by the Government in English and in German (Deliverable #25) otherwise in English or in German (Deliverable #26).

5.2.4.3   Online Seminar:   The Contractor shall provide online training live, on a website that is accessible through a government computer (i. e. Microsoft Teams).  The Contractor shall provide a conference call dial- in phone number to provide the opportunity for communication to the speaker and the audience.

5.2.4.3.1   The Contractor shall provide online seminar within three (3) months.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #27) otherwise in English or in German (Deliverable #28).

5.2.4.4   In-Person Training:   The Contractor shall provide in-person training at one of the USAG Stuttgart installations.  The Contractor shall provide all necessary equipment such as projector and laptop to conduct the training.

5.2.4.4.1   The Contractor shall provide in-person-training within three (3) months.

5.2.4.4.2   The deliverable can be ordered by the Government in English and in German (Deliverable #29) otherwise in English or in German (Deliverable #30).

5.2.4.5   Field Exercise:   Along with training, the Contractor shall include a field exercise.  A field exercise usually will take about 2-3 hours.  The Contractor shall provide all necessary materials and equipment to demonstrate practical implementation of training topics.

5.2.4.5.1   The Contractor shall provide field exercise within three (3) months . The deliverable can be ordered by the Government in English and in German (Deliverable #31) otherwise in English or in German (Deliverable #32).

5.2.4.6   Provide training material for students:   Upon Government request, the Contractor shall provide an electronic and/or hardcopy handout to each student.

5.2.4.6.1   The Contractor shall provide a draft for the training material for students within three (3) months.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #33) otherwise in English or in German (Deliverable #34).

5.2.4.7   Training Exam:   Upon Government request, the Contractor shall provide an electronic and/or hardcopy training exam for the students.  The Contractor shall work with COR to determine exam length and questions types.

5.2.4.7.1   The Contractor shall provide draft exam within three (3) months.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final electronic copy to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #35) otherwise in English or in German (Deliverable #36).

5.2.4.8   Training Certification:   At the end of the training, the Contractor shall prepare training certificates for each of the participants in English and/or German as well as provide photos to document training session, upon Government request.  The Contractor shall provide a template of the certificate in advance.

5.2.4.8.1   The Contractor will sign the certificates and provide photos, in electronic form, to COR and ED technical POC (TPOC) within three (3) days after the training is completed.  Upon Government provided comments, the Contractor shall then have three (3) days to submit a final electronic copy to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #37) otherwise in English or in German (Deliverable #38).

5.2.4.8   Training Examples:

5.2.4.8.1   Building Contaminants Training:   The training shall include topics of building contaminants awareness (subject to change in accordance with IMCOM/EO training requirements): Asbestos Fibers, Artificial Mineral Fibers, Polychlorinated Biphenyls (PCB), Polycyclic Aromatic Hydrocarbons (PAH), Pentachlorophenol (PCP), Heavy metals (Lead in paint, etc.), Wood Preservatives (Lindan, DDT etc.), Insulation materials containing, HBCD, Lead Based Paint Awareness, Radon or other to be defined topics.

5.2.4.8.2   Hazardous Material/ Hazardous Waste Awareness Training:   The Contractor shall provide hazardous material/ hazardous waste awareness training to the organizations and units.  In accordance with AER200-1, employees that use hazardous materials must be properly trained.  Training must address chemicals exposure to workers in the performance of their official duties, associated hazards, method of labeling chemicals, and associated documentation, safety data sheets (SDSs), audits and Inspections.  Documentation of the training and content provided will be annotated on the periodic inspection report for that location.

5.2.4.8.3   Environmental Officer Basic Training) – (Priced at BPA level):   The Contractor shall provide 24-hour basic EO classroom training for five (5) up to ten (10) students. A final exam with a minimum passing grade of 70% shall be developed. The Government, in electronic format, will provide existing EO basic training slides and the exam questions. Training will include a two (2) hour site visit with the students during the training organized by Contractor.

5.2.4.8.3.1   The presentation shall include the following topics (subject to changes according IMCOM/EO training requirements): Introduction, Hazardous Substances, Globally Harmonized System of Classification and Labelling of Chemicals (GHS), Safety Data Sheet, Controlling Hazards, Storage and Segregation of HM, Managing Hazardous Waste, Medical Waste Management, Solid Waste and Recycling, Transportation, Spill Response, Storm Water Pollution Prevention, Audit Inspections.

5.2.4.8.4   Environmental Officer Refresher Training– (Priced at BPA level):   The Contractor shall provide 8-hour refresher EO classroom training for five (5) up to ten (10) students. A final exam with a minimum passing grade of 70% shall be developed. The Government will provide existing EO basic training slides and the exam questions. The presentation shall include the following topics (subject to changes according IMCOM/EO training requirements): Introduction, Hazardous Substances, Globally Harmonized System of Classification and Labelling of Chemicals (GHS), Safety Data Sheet, Controlling Hazards, Storage and Segregation of HM, Managing Hazardous Waste, Medical Waste Management, Solid Waste and Recycling, Transportation, Spill Response, Storm Water Pollution Prevention, Audit Inspections.

5.2.4.8.5   Spill Response Training & Field Exercise:   Installations will provide necessary training and spill response drills to ensure the effectiveness of personnel and equipment according to current regulations. The presentation will include the following topics (subject to changes according IMCOM/EO-Training requirements): USAG Stuttgart Spill Prevention and Response Plan, The Red Plan, Personal Protective Equipment, Safety Data Sheets, Spill Equipment, Spill Response Procedures, Spill Prevention, Oil-Water Separators.

5.2.4.8.5.1   During the presentation, the Contractor shall present examples of different spill response equipment such as booms, mats, pillows, and absorbents for universal, oil-only and chemical spills.  The Contractor shall also present examples of different personal protective equipment (PPE) such as chemical resistant goggles, gloves and apron.

5.2.5   Inspections:   Prior to inspections, the Contractor shall coordinate with COR and ED TPOC to determine inspection template/inspection report to be used and inspection schedule. Upon Government request, the Contractor shall coordinate and schedule inspections with associated units.  The Contractor shall provide all inspection and working documents in English and/or German.  Per inspection, if repair work identified, the Contractor shall document and provide an inspection report/site visit report with corrective actions.

5.2.5.1   Inspection:   Upon Government request, the Contractor shall conduct an inspection in accordance with current environmental requirements/regulations.

5.2.5.1.1   The Contractor shall provide the inspection report within fifteen (15) days after the inspection is completed.  Upon Government provided comments, the Contractor shall then have five (5) days to submit a final electronic copy to the COR  The deliverable can be ordered by the Government in English and in German (Deliverable #39) otherwise in English or in German (Deliverable #40).

5.2.5.2   Technical Inspection (qualified specialist):   Upon Government request, the Contractor shall conduct a technical inspection by a qualified specialist (qualifizierte Fachkraft, Fachfima) in accordance with current environmental requirements/regulations.

5.2.5.2.1   The Contractor shall provide the inspection report by a qualified specialist within fifteen (15) days after the inspection is completed.  Upon Government provided comments, the Contractor shall then have five (5) days to submit a final electronic copy to the COR The deliverable can be ordered by the Government in English and in German (Deliverable #41) otherwise in English or in German (Deliverable # 42).

5.2.5.3   Technical Certification Inspection (certified expert i.e. TÜV Sachverständiger):   Upon Government request, the Contractor shall conduct a technical inspection by a certified expert (Sachverständiger) in accordance with current environmental requirements/regulations.

5.2.5.3.1   The Contractor shall provide the technical inspection report by a certified expert within fifteen (15) days after the inspection is completed.  Upon Government provided comments, the Contractor shall then have five (5) days to submit a final electronic copy to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #43) otherwise in English or in German (Deliverable #44).

5.2.5.4   Re-Inspection:   Upon Government request, the Contractor shall conduct a re-inspection in accordance with current environmental requirements/regulations.  Inspection report shall document findings and necessary corrective action measures.

5.2.5.4.1   The Contractor shall provide the re-inspection report within fifteen (15) days after the inspection is completed.  Upon Government provided comments, the Contractor shall then have five (5) days to submit a final electronic copy to the COR. The deliverable can be ordered by the Government in English and in German (Deliverable #45) otherwise in English or in German (Deliverable #46).

5.2.5.5   Site Visit:   Upon Government request, the Contractor shall perform a site visit to review or/and confirm data.

5.2.5.5.1   The Contractor shall provide the site-visit report within fifteen (15) days after the inspection is completed.  Upon Government provided comments, the Contractor shall then have five (5) days to submit a final electronic copy to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #47) otherwise in English or in German (Deliverable #48).

Examples (FFP at BPA Level)

- Tanks –AST/UST

- Inspection/Testing of Tanks – AST/UST

The Contractor shall inspect a tank by a certified specialist (Fachfirma) according AwSV. ED TPOC must approve inspection report template before the first inspection.

The following services shall be done:

- Functional and operational control of the leak detection devices.

- Functional testing of the optical and acoustical alarm system.

- Functional testing of the limit indicator device.

- Functional testing of the fill level control.

- Tightness and functional control of all connection pipes.

- Visual evaluation of the catchment basin (floor) sealing.

- Visual control of all pipes and fittings.

- Control / Filling of compressed gas cylinders.

- Functional testing of the ventilation.

- Cleaning of the filling port and respective sieve on demand.

- Evaluation of the tank manhole condition, control of condensed water.

- Control of proper labeling and required documents

- Preparation of inspection report for each tank facility including photo documentation

- Commissioning of a Tank– AST/UST

The Contractor shall commission a tank by a certified specialist (Fachfirma). A certified expert (i.e. TÜV Sachverstaendiger) must approve the commissioning of a tank. Contractor shall provide the commissioning certificate to the Government.

- Decommissioning a Tank– AST/UST

The Contractor shall decommission a tank by a certified specialist (Fachfirma). A certified expert (i.e. TÜV Sachverstaendiger) must approve the decommissioning of a tank. Contractor shall provide the decommissioning certificate to the Government.

- Inspection of Hazardous Waste Storage Area (HWSA)/Hazardous Waste Accumulation Points (HWAP) (5.2.5.2)

The Contractor shall inspect Hazardous Waste Storage Area (HWSA) and the Hazardous Waste Accumulation Points (HWAP) upon request. HWSA/HWAP are shall be inspected for malfunctions and deterioration, operator errors, and discharges that may be causing, or may lead to, a release of HW constituents to the environment or threat to human health but not limited to.

An inspection point is defined as a place where hazardous substances are stored.

Units vary in size and therefore categorized by inspection points:

- 1 inspection point

- 2 inspection points

- 3 inspection points

Inspection should take no longer than two (2) hours (1 - 2 inspection points 30-45 min; 3- inspection points 45-60 min;).

Location of inspection consists of a working area occupied by a unit, which can include multiple buildings, annexes, sheds and other storage items, including compressed gas cages or portable tanks. For purposes of this task, a “unit” may consist of no more than 5 inspection points, e.g. 1 main building, 2 hazardous material storage areas, 1 compressed gas storage cage and 1 hazardous waste accumulation point.

Upon Government request, the following parameters shall be inspected and rated and documented with photos:

- Condition of the concrete grounds (cracks, damages)

- Condition and content of the drainage sump

- Condition of the roofing (water tightness, damages)

- Condition of fences and meshing, view protection

- Functionality of access gates

- Container labeling.

- Containers closed properly.

- High liquid level or overflow of container.

- Container structurally intact.

- Wheels, if present, properly braked/chocked

- Containers located so as to minimize potential for puncture or release.

- CAA pad, if present, free of chips, cracks, &etc.

- Check the date of initial accumulation to ensure sufficient time for on-site accumulation.

- Secondary containments and their condition

The inspection includes on request the following:

- Contractor shall coordinate and schedule inspection with specific unit POC

- Inspect in accordance with inspection checklist provided

- Update the ENV Management Excel Sheet

- Verify and Update Garrison Environmental Officer Information (Tab B)

- Verify Inspection Tracking (Tab C)

- Verify Equipment Inventory List (Tab D)

- Verify Hazardous Waste Inventory (Tab E)

- Verify and Update Hazardous Material (HM), Inventory/Authorized User List (AUL) (Tab F)

- Provide work specific, on the spot training to pertaining Environmental Officer during inspections.

The Contractor shall verify all information provided within each tab/column of the ENV Management Sheet and embedded Master HM Inventory/AUL list by unit POC. If POC does not provide adequate information, the Contractor shall make a conservative estimate determined from inspection and note in the inventory and the inspection report that unit did not provide operational details.

Each unit is responsible for providing all Safety Data Sheets (SDS).  If identified that SDS are missing the Contractor shall note on the inspection checklist.   In addition, if no inventory list is present, the Contractor shall initiate one, which will include all materials present.  Upon initiation, the Contractor shall show the EO how to complete the inventory sheets so that they can continue to keep current.

III.  Site Visits at HM/HW locations

The Contractor shall conduct site visits at hazardous material (HM)/hazardous waste (HW) locations including hazardous material storage areas, receiving locations, transportation procedures, HWAP, HWSA, tanks, salt silos and other facilities. The Government, in electronic format, will provide list of locations upon request. The Contractor shall assess each location for compliance.

- Inspection of HWSA Drainage Sumps)

The Contractor shall inspect a HWSA-drainage sump. The Contractor shall provide results in an inspection sheet/log, template available from ED TPOC.

- Storm Water Inspection

The Contractor shall maintain proper controls of non-point sources by performing visual inspections of existing water retention/infiltration basins along with associated outfall locations. The Government, in electronic format, will provide basin and outfall locations and an inspection checklist upon request.

- AwSV Facility Inspection

The Contractor shall perform AwSV inspection by a certified expert (Sachverständiger) conform to AwSV requirements (AwSV § 47). The Contractor shall inspect the facility to ensure compliance with AwSV regulations. As part of the inspection, the Contractor will include proper certification, which also includes a report. The facility can include 1 – 5 tanks, 1 HWAP, 1 HWSA or 1 Salt Silo

The AwSV inspections include, but not limited to, HWAP/HWSA, tanks, and salt silos.

- Rainwater Retention Basin Inspection

The Contractor shall perform an inspection of a rainwater retention basin throughout the Garrison, maintain and track an inspection log and provide inspection reports after the inspection. The Government will provide the format and content.

- Hardstand Inspection

The Contractor shall inspect areas within the USAG Stuttgart footprint for potential hazard of water endangering substances released. This includes inspecting areas, such as: wash racks, gas stations, parking areas for tactical vehicles, outside maintenance areas at motor pools, or other areas where water endangering substances might be released into the environment. The Contractor shall develop an inspection sheet, approved by the USAG Stuttgart COR. Inspections shall include visual observations and a report recommending corrective action measures. The report shall also state location conditions (unit/activity, location, usage, surface material (e.g. concrete, asphalt, bone stones), curbs, possible releases to environment like sewer, storm water inlets, etc.) and current site conditions. Deficiencies shall be addressed with recommendations for fixing the deficiencies. To determine extent of deficiencies it might be necessary to measure out the area (length, square meters).  Photo documentation shall be included in the report.

- SWPP Site Inspection

The Contractor shall coordinate, obtain access, and inspect hazardous material and waste accumulation points.  Document findings and any changes observed in order to update the current USAG Stuttgart Storm Water Pollution Prevention Plan (SWPPP).

Each inspection includes the following:

- Inspect hazardous waste accumulation point (HWAP) facilities, wash racks, gas stations, motor pools, etc.

- Recommend implementation of SWPPP and BMP in the plan.

- Review and update if necessary Best Management Practices (BMP)

- Include updated maps of the installations. All drawings must be compatible with USAREUR Spatial Data Standards (SDS), formerly known as the Tri-Service Spatial Data Standards, as well as all applicable Federal Geographic Data Committee (FGDC) standards.

SWPPP should review and update the following elements:

- Site and activity description, including a site map

- Identification of potential pollutant sources

- Description of controls to reduce pollutants

- Maintenance/inspection procedures

- Records of inspections and follow-up maintenance of BMPs

- SWPPP amendments

- SWPPP certification

- Reassess the selection of erosion and sediment control BMPs at each site

Reassess good housekeeping BMPs that’s should be used at each site

5.2.6   Surveys:   Upon request, the Contractor shall provide or update a survey.  Survey documentation will be in English and/or German.

5.2.6.1   Mapping Survey:   The Contractor shall perform a field survey mapping throughout required area within USAG Stuttgart.  Obtained data shall be incorporated into appropriate GIS layers to comply with the most current version of the DOD geospatial data standards.  The GIS layer(s) shall contain all required attributes in accordance with (IAW) the Quality Assurance Plan (QAP) of the respective Spatial Data Standards for Facilities, Infrastructure, and Environment (SDSFIE) feature class.  Survey results shall be submitted as ArcGIS geodatabase in the current software version used at ED office.

5.2.6.1.1   The Contractor shall provide a draft mapping survey and a report within six (6) months.  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final mapping survey and the report to the COR.  The deliverable can be ordered by the Government in English and in German (Deliverable #49) otherwise in English or in German (Deliverable #50).

5.2.6.2   Geospatial Data Update:   The Contractor shall perform a data evaluation to determine accuracy of both spatial and attribute data.  Updated and verified data shall be submitted to ED TPOC in conjunction with survey submittal.  The ED TPOC’s geodatabase shall be updated in current software version used at ED office.  It is the intention of the ED TPOC to eventually update the database to meet SDSFIE 4.0 formatting requirements.  Therefore, any geographic data collected will also be recorded in a simple Microsoft Excel format, where all aspects of SDSFIE 4.0 data can also be stored for future use in an updated database (e.g. Stormwater Feature Class information cannot be saved in the existing ED TPOC database, but it is desired to have this information when the upgrade is made).  Existing CAD/GIS data will be provided to the Contractor upon request.

5.2.6.2.1   The Contractor shall provide a draft of the Geospatial Data Update within six (6) months. Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final to the COR. The deliverable can be ordered by the Government in English and in German (Deliverable #51) otherwise in English or in German (Deliverable #52).

5.2.6.3   Database Update:   The Contractor shall update existing MS Access database with the results obtained during field survey.  All data shall be categorized regarding Army location (ARLOC), facility number or installation depending on the type and extent of the survey.  Technical data shall be inserted in tables and made available for data queries.  The Contractor shall develop database reports to be exported in word or pdf format in order to extract required information.  Sorting and filtering of data shall be made available.  The Contractor shall verify that the updated database works on a USAG ED TPOC workstation.

The Contractor shall provide a draft of the database update within six (6) months).  Upon Government provided comments, the Contractor shall then have ten (10) days to submit a final database update date to the COR .  The deliverable can be ordered by the Government in English and in German (Deliverable #53) otherwise in English or in German (Deliverable #54).

5.2.6.3.1   Survey Task Examples

- As-built Survey of Storm Water Drainage System )

The Contractor shall perform an as-built survey of storm water drainage throughout required area within USAG Stuttgart to include lines, inlets, and manholes. Data shall be incorporated into appropriate GIS layers to comply with the most current version of the DOD spatial data standards. Survey results will be incorporated into a map illustrating storm water drainage system that depicts the following:

- All open ditches, percolation pipes and other elements of the storm water drainage system, including elevation and storm water flow direction in those elements

- Outfalls and an associated geographic coordinates

- Structural dimensions for infiltration or retention basin

- Include all receiving waters

- Field Verification Survey

The Contractor shall perform field verification survey of existing data available at the ED office. Data shall be verified for accuracy, location, and technical parameters. This includes, but is not limited to:

- Tanks, oil water separators, groundwater monitoring wells

- Generators, air emission sources, hazardous waste collection points

- Historic sites and structures, hard stands, soil sampling points

- Back-Flow Prevention Survey

The Contractor shall conduct a Cross Connection Control/Backflow Prevention Device Survey (CCC/BFPD) addressing cross-connection and backflow prevention requirements specific to the protection of potable water systems at USAG Stuttgart. The CCC/BFPD survey satisfies the requirement to develop and maintain a cross-connection control and backflow prevention program referenced in GFGS, DIN 1717, Chapter 2 of Army Regulation (AR) 200-1, and Chapter 12 of AR 40-5. The Contractor shall conduct a survey to identify all backflow prevention devices within identified installation, IAW respective German standards for hazardous class 1 thru 5.

5.2.7   Technical Environmental Services

5.2.7.1   Air Emission Inventory Update:   The Contractor shall update USAG Stuttgart Air Emission Inventory.  The update shall be a review and evaluation of pre-existing documents.  It requires site visits, inspections, and an update to regulatory requirements.

5.2.7.1.1   The Contractor shall provide updated air emission inventory within three (3) months after NTP. The deliverable is in English  (Deliverable #55).

5.2.7.2   Safety Cabinet Inspection:   The Contractor shall coordinate, obtain access, and inspect safety cabinets used for storage of hazardous materials.  Safety cabinet inspection shall be carried out and approved in accordance with §4 Para. 3 of the Workplace Ordinance (Arbeitsstättenverordnung).  Safety cabinet used for storing hazardous substances shall comply with TRGS 510 and GefSoffV requirements.  Documentation is required in German, provided in electronic version and/or hardcopy ten (10) days after completion (Deliverable #56).

5.2.7.1   Parts Cleaner Services:   The Contractor shall provide equipment and fluid replacement services to support units/activities performing vehicle maintenance, in accordance with KrWG regulation (Closed Substance Cycle Waste Management Act).  The Contractor shall inspect the parts cleaner and replace cleaning solution on a regular basis.  The contractor is for the disposal of the waste generated.

5.2.7.1.1   Currently the maximum tank capacity of the M100 is 60L and min 30L and for Model 112 Max capacity is 80L and min 40L.

5.2.7.1.2   The Government is only renting these machines, which means when services will no longer be needed the contractor will have to remove the machines.

5.2.7.1.3   Upon request, the Government will provide a list of parts cleaners/models locations.

5.2.7.1.4   The Contractor shall provide the parts cleaner services within one (1) month after NTP with documentation in German provided ten (10) days after completion (Deliverable #57).

5.2.7.4   Hardcopy/Printing Services:   The Contractor shall provide printing services to finalize deliverables required under specific tasks. For each deliverable, the Government will specify quantity and quality according to the specifications.  Upon request, the Contractor shall provide the hard copy products within ten (10) days (Deliverable #58).

5.2.7.5   Documentation:   Upon Government request, the Contractor shall provide or update documentation in English and/or in German.  For example a facility documentation, operation manuel, operating instructions, booklets, flyers or others.  The draft and the final versions shall be provided in electronic version and/or hardcopy.  For any updates, the Government will supply a current copy.  The deliverable can be ordered by the Government in English and in German (Deliverable #59) otherwise in English or in German (Deliverable #60).

5.2.7.6   Permits:   Upon Government request, the Contractor shall support in the update or renewal of a permit.  The Contractor shall provide the requested permit renewal package/ document within three (3) months upon request.  Associated documents will be in English and/or German (Deliverable #61).

5.2.7.7   Spill Supplies:   The Contractor shall provide spill supplies upon to properly response to spill incidents.  Spill supplies will include but not limited  to: emergency mobile spill kits, Absobents sandbags, eye wash stations, secondary containments etc.  Upon request, the Contractor shall provide requested spill supplies within  four (4) weeks  (Deliverable #62).

5.3   Lab Services

5.3.1   Storm Water Sampling:   The Contractor shall conduct storm water sampling, analysis, and reporting.  Proper coordination required for access to sampling locations and sampling shall be completed between the working hours of 0700-1700.

5.3.1.0.1   The Contractor shall coordinate, obtain access, appropriate bottles, and collect storm water sampling in accordance with qualified sample method (qualifizierte Stichprobe) or grab sampling within USAG Stuttgart Garrison Footprint.  Sampling shall be conducted by a certified technical person and follow all German standards (BBodSchV, DIN, etc.) and proper Chain of Custody.

5.3.1.0.2   For each sampling event, document the following:

- Visual observations of each area, obstructions of water flow, water contamination (foam etc.)

- Discharge location identification

- Date and time of sample collection

- Weather conditions at time of sampling

- Name and title of sampler

- Sampling method used

- Water temperature in situ

- Parameters tested

- Test detection limits

- Name of analytical testing laboratory

- Date of testing

5.3.1.1   Lab Analysis:   The samples shall be provided to a lab within 1-2 business days. Refer to Attachment 06 - Storm Water Sampling Parameters.  The Contractor shall provide lab analysis results within ten (10) business days, electronically via email to COR (Deliverable #63).

5.3.1.2   Storm Water Reporting:   The Contractor shall compile storm water results from Panzer Hotel, Panzer Elementary & High School and update the previous year’s Final Storm Water Investigation Report for Panzer Kaserne, which will be provided by COR as well as sampling locations necessary (reference Attachment 04 & 05 for sampling locations).  From the date in which the last sample is collected, the Contractor shall provide a draft report in English and German to COR within thirty (30) calendar days, electronically via email to COR will review and either notify the Contractor in writing of acceptance or return their comments to the Contractor within ten (10) business days.  Whether or not the COR has provided comments, the Contractor shall then have five (5) days to address and/or submit the final report, electronically via email (Deliverable #64).

5.3.2   Drinking Water Sampling:   The Contractor shall coordinate, obtain access, certified personnel, collect appropriate bottles from a certified lab, and collect a drinking water sample from a continuous use cold-water faucet within the USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  Sample collection can take place within army family housing (AFH), BOQs, community water stations (CWS), community facilities, ready buildings, schools, or UPH.  Do not sample from:

Abandoned buildings

Faucets with aerators or strainers, unless the aerator or strainer is removed before sampling

Faucets with water filter or “water purifiers”

Leaky faucets that allow water to run outside of the faucet

Hot water faucets

Hoses (garden hose, slop-sink hose)

Fire hydrants

5.3.2.0.1   If the faucet has an aerator or strainer, remove it first.  Using an alcohol flame, carefully flame the inside of the faucet.  Flaming the faucet is optional, but highly recommended.  Allow the cold water tap to run to waste for 3-5 minutes.  This is to allow collection of a water sample from the main water distribution system.  In low-use areas (vacant housing units or outdoor spigots), allow the water to run for 5 minutes.  After collection, water samples will be stored appropriately and transported to the laboratory for analysis within stagnation period.

5.3.2.1   Bromate Sampling:   The Contractor shall collect bromate samples to be analyzed by a certified lab.

5.3.2.1.1   FGS C3.3.2.6.1.1 Disinfectant/Disinfection Byproducts (DDBP) Requirements:   Systems using ozone for disinfection or oxidation are required to take at least one sample per month from the distribution system for each treatment plant in the system using ozone under normal operating conditions.  Systems may reduce monitoring from monthly to once per quarter if the system demonstrates that the yearly average raw water bromide concentration is <0.05mg/L based upon monthly measurements for one year.

5.3.2.1.2   Noncompliance is based on a yearly running monthly average of samples, computed quarterly, that exceeds the MCL of 0.010 mg/L.

5.3.2.2   Chloride & Fluoride Sampling:   The Contractor shall sample for free available chlorine and fluoride to be analyzed by a certified lab.

5.3.2.2.1   For fluoride, if sample results are above 1.5mg/L, the Government will then request the Contractor to conduct repeat sampling on an as needed basis.

5.3.2.2.2   For chlorine, if residual values are below 0.03mg/L, the Government will then request the Contractor to conduct repeat sampling on an as needed basis.

5.3.2.3   Chlorite Sampling:   The Contractor shall conduct chlorite sampling to be analyzed by a certified lab.

5.3.2.3.1   If the average concentration of sample results are above 1.0 mg/L, the Government will then request the Contractor to conduct repeat sampling on an as needed basis.

5.3.2.3.2   FGS C3.3.2.6.1.1 Disinfectant/Disinfection Byproducts (DDBP) Requirements:

The maximum residual disinfectant level (MRDL) of 1.0 mg/L for chlorite shall be met in drinking water.  Noncompliance for chlorite exists if the average concentration of any three-sample set (i.e., one monthly sample set from within the distribution system) exceeds the MCL 1.0 mg/L.

5.3.2.4   Lead in Drinking Water Sampling:   The Contractor shall coordinate, obtain access, appropriate certified personnel, collect appropriate bottles from a certified lab, and collect drinking water samples from a continuous use cold-water faucet within the USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  The Contractor shall complete sampling within five (5) business days upon Government request.  The Contractor shall ensure the 250-mL sample containers are kept sealed between the time of preparation by the laboratory and the collection of the sample.  Collect samples before a facility/ housing unit opens and any water is used.  Do not run any drinking water outlets or flush toilets elsewhere in the facility before collecting samples.

5.3.2.4.1   There will be a series of three bottles taken:

5.3.2.4.1.1   First draw sample collection. Place the first draw labeled sample container under the faucet. Do not allow the sample container to touch the faucet. Open the faucet as you would if you were filling a glass or a pot for cooking (e.g., fully open faucet). Collect water immediately after opening the faucet without allowing any water to go to waste. Cap and seal the container.

5.3.2.4.1.2   30-second flush-sample collection. Next, fully open the faucet and allow the water to flow to waste for 30 seconds. After 30 seconds, while the water is still flowing, place the 30-second flush-labeled sample container under the faucet and collect a sample. Cap and seal the container.

5.3.2.4.1.3   2-minute flush-sample collection. Finally, fully open the faucet again and allow the water to flow to waste for 2 minutes. After 2 minutes, while the water is still flowing, place the 2-minute flush-labeled sample container under the faucet and collect a sample. Cap and seal the container.

5.3.2.5   Legionella Sampling:   The Contractor shall coordinate, obtain access, appropriate certified personnel, collect appropriate bottles from a certified lab, and collect a drinking water sample from a continuous use cold-water faucet within the USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  The Contractor shall complete sampling within five (5) business days upon Government request.  Samples (250 mL) will be collected in accordance with Zweck b) of DIN EN ISO 19458, DVGW Technische Regel W 551, DVGW Information Paper Nr. 74, and the recommendation of the German Environment Agency.  The water temperature at the time of sample collection and the maximum water temperature that is reached at each sample location will be measured and documented.  Samples must be transported as quickly as possible to the laboratory, preferably within 24 hours, but no later than 48 hours.  The samples need to be kept cool (5°C ±3°C) and protected from light at all times during transport.

5.3.3   Waste Water Sampling:   The Contractor shall coordinate, access, and obtain appropriate personnel/equipment/bottles from the lab to collect samples of potential waste water from basins, ASTs, USTs or drainage systems and provide a report with recommendations based on the analysis results within the USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  The Contractor shall complete sampling within five (5) business days upon Government request.  The Contractor shall provide lab analysis results within ten (10) business days, electronically via email to COR (Deliverable #63).

5.3.4   Additional Water Sampling:   Per Government request, the Contractor shall coordinate, obtain access, appropriate certified personnel, collect appropriate bottles from a certified lab, and collect a water sample within USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  The Contractor shall complete sampling within five (5) business days upon Government request.  After collection, water samples will be stored appropriately and transported to the laboratory for analysis within stagnation period.

5.3.5   Water Analysis:   All analyses of the samples must be done by a laboratory, which has a valid accreditation (see 1.10.4 Special Qualifications).  Parameters will be determined based upon requirements by USAG Stuttgart.  Reference Attachment 08 –Lab Analysis Parameters.  The Contractor shall provide lab analysis results within ten (10) business days to COR, electronically via email (Deliverable #63)

5.3.6   Building Materials Sampling, Analysis & Reporting:   The Contractor shall provide sampling, analysis and reporting services for building materials as required below:

5.3.6.1   Building Material Sample collection from a wall tile, wall plaster, insulation materials, wooden floors.

5.3.6.1.1   The Contractor shall coordinate, access, obtain appropriate equipment/certified personnel necessary to conduct the sampling and collect building material sample from wall tile, wall plaster, insulation materials, or wooden floors on an as needed basis within USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  Sampling shall be conducted by a certified technical person for hazardous material handling which includes, but not limited to; asbestos, PCB, lead based paint etc. and follow all German guidelines such as TRGS 519.  The Contractor shall complete sampling within five (5) business days upon Government request.  The sampling area must be refilled and rebuilt to the previous condition as necessary.

5.3.6.2   Building Material Sample Collection by drill through floor cores.

5.3.6.2.1   The Contractor shall coordinate, access, obtain appropriate equipment/certified personnel necessary to conduct the sampling and collect building material samples by drilling through floor cores on an as needed basis within USAG Stuttgart Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  Sampling shall be conducted by a certified technical person for hazardous material handling which includes, but not limited to; asbestos, PCB, lead based paint etc. and follow all German guidelines such as TRGS 519.  The Contractor shall complete sampling within five (5) business days upon Government request.  The sampling area must be refilled and rebuilt to the previous condition as necessary.

5.3.6.3   Building Material Sample Collection from an existing pile.

5.3.6.3.1   The Contractor shall coordinate, access, obtain appropriate equipment/certified personnel necessary to conduct the sampling and collect building material sample from an existing pile on an as needed basis within USAG Stuttgart Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  Sampling shall be conducted by a certified technical person for hazardous material handling which includes, but not limited to; asbestos, PCB, lead based paint etc. and follow all German guidelines such as TRGS 519. The Contractor shall complete sampling within five (5) business days upon Government request.  The sampling area must be refilled and rebuilt to the previous condition as necessary.

5.3.6.4   Building Material Sample Collection Reporting.

5.3.6.4.1   For building material sample collection, the Contractor shall produce small report (max. 5 pages) to include work conducted, lab results, discussion of results, further investigation requirements, disposal requirements, location map, colored photographs, and sampling and analytical protocols shall be provided fifteen (15) business days after lab results are returned.  Reports shall be provided electronically in both English and German (Deliverable #65).

5.3.6.5   Building Materials Analysis.

5.3.6.5.1   All analyses of the samples must be processed by a laboratory with valid accreditation (see 1.13 Special Qualifications).  Parameters will be determined based upon requirements by USAG Stuttgart.  Reference Attachment 08 –Lab Analysis.

5.3.7   Radon Sampling, Analysis, Reporting.

5.3.7.1   Upon request, the Contractor shall provide radon sampling with analysis and reporting.  The Contractor shall provide lab analysis results and a report within twenty (20) business days after lab results are returned to COR, electronically via email in English and German  (Deliverable #66).

5.3.8   Emergency Services

5.3.8.1   Emergency Services – Water & Soil Sampling:   The Contractor shall be available for emergency sampling per Government request, within the next business day.  The Contractor shall coordinate, obtain access, necessary certified personnel/equipment/bottles for water/soil collection, and sampling protocol shall be prepared for each sample within the USAG Stuttgart Garrison Footprint (refer to Attachment 09 – USAG Stuttgart Footprint).  Soil sampling would consist of grab samples. Parameters will be determined based upon requirements by USAG Stuttgart.  Reference Attachment 08 –Lab Analysis Parameters.

5.3.8.2   Emergency Services – Analysis 24 hours:   The Contractor shall provide a service for expedited analysis within 24 hours upon Government request, sent electronically via email to the COR.  If expedited service is possible given the requested parameter the Contractor shall coordinate, obtain access, necessary equipment/bottles for water collection, and sampling protocol shall be prepared for each sample within the USAG Stuttgart Garrison Footprint (Deliverable #67).  Reference Attachment 08 –Lab Analysis Parameters.

5.3.8.3   Emergency Services – Analysis 36 hours:   The Contractor shall provide a service for expedited analysis within 36 hours upon Government request, sent electronically via email to the COR.  If expedited service is possible given the requested parameter the Contractor shall coordinate, obtain access, necessary equipment/bottles for water collection, and sampling protocol shall be prepared for each sample within the USAG Stuttgart Garrison Footprint (Deliverable #68).  Reference Attachment 08 –Lab Analysis Parameters.

5.4   System for Award Management (SAM) Service Contract Report (SCR):   The Contractor shall report ALL Contractor labor hours (including subcontractor labor hours) required for performance of services provided under this contract f via a secure data collection site.  The Contractor is required to completely fill in all required data fields through the following web address: www.SAM.gov.  Reporting inputs will be for the labor executed during the period of performance during each Government FY, which runs from October 1 through September 30.  While inputs may be reported any time during the FY, all data shall be reported no later than October 31 of each calendar year.  Contractors may direct questions to the help desk by clicking “View Assistance for SAM.gov” which is located at the top of the SAM.gov website.  From there, you can the select “Contact Our Service Desk” which will allow you to contact SAM.gov directly.  If contract period of performance ends prior to September 30, the Contractor has 30 calendar days from end date of the contract to complete the SAM SCR requirement.

Steps for Submitting a Service Contract Report (SCR)

- Go to www.sam.gov and log in.

- Select Entity Registrations and then select Service Contract Reporting.

- SAM displays your entities which have service contracts and meet the reporting criteria. Select View by entity to see the service contracts for each entity.

- Next, select Add for the service contract against which you want to create a Service Contract Report. Each service contract which meets the FAR Subpart 4.1703 reporting thresholds is displayed.

- You will be taken to the Complete Service Contract Report page. SAM displays the contract details and allows you to report. You are required to enter the following information:

- Total Amount Invoiced: Total dollar amount invoiced for services performed during the previous Government fiscal year under the contract (this amount should include the prime and any subcontract amount).

- Prime Contractor Hours Expended: Prime contractor direct labor hours expended on the services performed during the previous Government fiscal year. The amount you enter is automatically divided by 2,080 hours to calculate a Full Time Employee (FTE) equivalent, displayed under the Prime Contractor Hours Expended as Prime Contractor FTEs.

- Report any required Tier 1 subcontractor information by selecting the Add Tier 1 Subcontract Information button.

- When you are ready to submit the report, select Submit. This saves your report and returns you to the Select Service Contract page where you can create other SCRs or edit an existing SCR.

Steps for Editing a Submitted Report

- Follow steps 1-4 above. Any previously submitted SCR will have a View/Edit button instead of an Add button.

- Select View/Edit. You will be able to view the current SCR, edit available fields, and resubmit the record. You can also delete previously entered information altogether.

STD:  All information provided by the Contractor shall be accurate, complete, and not exceed suspense dates noted in corresponding paragraph above.

AQL: 100% Compliant

(Deliverable #69).

PART 6

APPLICABLE PUBLICATIONS

6.   Applicable Publications (Current Editions):   The following publications, manuals, regulations, etc. are mentioned in this PWS and are listed below.

6.1.1	Department Of Defense Contract Security Classification Specification (DD Form 254)

6.1.2	Department of Defense Security Agreement (DD Form 441)

6.1.3	National Industrial Security Program Operating Manual (DoD 5220.22-M)

6.1.4	Installation Access Control (AE Reg 190-16)

6.1.5	The Army Physical Security Program (AR 190-13)

6.1.6	Contractor Identification (AE Reg 27-715)

6.1.7	U.S. Army Corps of Engineers Safety and Health Requirements Manual (EM 385-1-1)

6.1.8	Information Assurance Workforce Improvement Program (DoD 8570-M)

6.1.9	Information Assurance Training Certification and Workforce Management Directive (DoDD 8570.01)

6.1.10	Information Assurance (AR 25-2)

6.1.11	Electromagnetic Compatibility Directive (2004/108/EC)

6.1.12	Policies and Procedures for Property Accountability (AR 735-5)

6.1.13	Final Governing Standards for Germany, February 2010, revised September 2020

PART 7

ATTACHMENT AND TECHNICAL EXHIBIT LISTING

7.   Attachment List

7.1   Technical Exhibit A – Deliverables Schedule

7.2   Technical Exhibit B – Performance Requirements Summary

7.3   Attachment 1 – Estimated Workload Data

7.4   Attachment 2 – English Language Fluency Clarification

7.5   Attachment 3 – Laboratory Analysis Parameters List

TECHNICAL EXHIBIT A

DELIVERABLE SCHEDULE

| Deliverable | Frequency | # of Copies | Medium/Format | Submit To |
| --- | --- | --- | --- | --- |
| 01. Quality Control Plan (paragraph 1.5.1) | Once within twenty (20) days after contract award and no later than twenty (20) days prior to any anticipated changes. | One each to the KO | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 02. Potential Issues (paragraph 1.5.1.2) | If potential issues identified, within five (5) days a written report is required. | One each to the COR. | Electronic delivery via email in English | To the COR |
| 03. Final Contractor Work Plan (paragraph 1.5.5) | Draft: Once within twenty (20) days after contract award and no later than twenty (20) days prior to any anticipated changes. Final: Once within twenty (20) days after contract award and no later than twenty (20) days prior to any anticipated changes. | One each to the COR. | Electronic delivery via email in English | To the COR |
| 04. Installation Pass Log (paragraph 1.6.3.1) | Within twenty (20) days after contract award and within five (5) days after any changes. | One each to the COR. | Electronic delivery via email in English | To the COR |
| 05. Installation passes (paragraph 1.6.3.1 - 1.6.3.3) | Within three (3) days after employment expiration, contract termination or cancellation. | n/a | Original passes in English | To the COR |
| 06 personal information for CAC (paragraph 1.6.3.4) | Once within 15 days after contract award. | One each to the Contracting Officer and Contracting Officer’s Representative | Electronic delivery via email using Adobe PDF | To the Contracting Officer through the Contracting Officer’s Representative (COR) |
| 07 CAC log (paragraph 1.6.3.4.1) | Once within 30 days after contract award and within 5 days after changes have been made. | One each to the Contracting Officer and Contracting Officer’s Representative | Electronic delivery via email using Adobe PDF | To the Contracting Officer through the Contracting Officer’s Representative (COR) |
| 08. Background Check (LNSP, Police Good Conduct Certificate (Polizeiliches Fuehrungszeugnis)) (paragraph 1.6.4.1, 1.6.4.2) | Within thirty (30) days after contract award | One each to the COR. | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 09. Unfavorable background check (LNSP, Police Good Conduct Certificate (Polizeiliches Fuehrungszeugnis)) (paragraph 1.6.4.1, 1.6.4.2) | Within three (3) days | One each to the COR. | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 10. Names of Contract Manager and Alternate Contract Manager (paragraph 1.10) | Within five (5) days | One each to the KO | In writing via email in English. | To the KO |
| 11. Personnel Performing Services Certificates (paragraph 1.10.3) | Within ten (10) days after contract award | One each to the COR. | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 11a Contractor Identification Badges (paragraph 1.12.1) | Prior to the contract performance date and updated as needed | One each to the KO and COR. | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 12. Plan to avoid or mitigate OCI (paragraph 1.19) | Within ten (10) days after notice of the OCI | One each to the COR. | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 13. AT Level I Training Certificate (paragraph 1.23.1) | Key personnel and on-site Contractor employees, including subcontractor employees shall complete AT Level I Training within thirty (30) days after contract award and after 12 months each year. The certificate of completion shall be provided within ten (10) days after completion of the training. | One each to the COR. | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 14. OPSEC Training Certificate (paragraph 1.23.2) | Key personnel and on-site Contractor employees, including subcontractor employees shall complete the training within twenty (20) days after contract award and after 12 months each year. Verification of the training shall be provided within ten (10) days after completion of the training. | One digital copy | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 15. iWATCH Training Certificate (paragraph 1.23.3) | One time, key personnel and on-site Contractor employees, including subcontractor employees twenty (20) days after contract award and within twenty (20) days after new employees commence contract performance | One digital copy | Electronic delivery via email as pdf file in English | To the KO through the COR |
| 16. Meeting Minutes (paragraph 5.2.1.1) | Within five (5) days. | One digital copy | Electronic delivery via email as pdf file in English | To the COR |
| 17. Quarterly Progress Reports (paragraph 5.2.1.2) | Within five (5) days. | One digital copy | Electronic delivery via email as pdf file in English | To the COR |
| 18. Yearly Completion Report (paragraph 5.2.2.4.1) | Draft: Within fifteen (15) days prior to POP end Final: Within three (3) days upon receiving Government comments | One digital copy | Electronic delivery via email as word and pdf file in English and German | To the COR |
| 19. Compliance Assessment Report (paragraph 5.2.2.5.1) | Draft: Within three (3) months Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery via email as word and pdf file in English and German | To the COR |
| 20. Compliance Assessment Report (paragraph 5.2.2.5.1) | Draft: Within three (3) months Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery via email as word and pdf file in English or German | To the COR |
| 21. Update Management Plan (paragraph 5.2.3.1.1) | Draft Within five (5) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy in each language | Electronic delivery via email as word, pdf file in English and German | To the COR |
| 22. Update Management Plan (paragraph 5.2.3.1.1) | Draft Within five (5) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy in each language | Electronic delivery via email as word, pdf file in English or German | To the COR |
| 23. Develop Training (paragraph 5.2.4.1.1) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery via email as MS Power Point and pdf file in English and German | To the COR |
| 24. Develop Training (paragraph 5.2.4.1.1) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery via email as MS Power Point and pdf file in English or German | To the COR |
| 25. Updated Training (paragraph 5.2.4.2.1) | Draft: Within three (3) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy | Electronic delivery via email as MS Power Point and pdf file in English and German | To the COR |
| 26. Updated Training (paragraph 5.2.4.2.1) | Draft: Within three (3) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy | Electronic delivery via email as MS Power Point and pdf file in English or German | To the COR |
| 27. Online Seminar (paragraph 5.2.4.3.1) | Within three (3) months | One training session | Online seminar in English and German | To the COR |
| 28. Online Seminar (paragraph 5.2.4.3.1) | Within three (3) months | One training session | Online seminar n English or German | To the COR |
| 29. In-Person Training (paragraph 5.2.4.4.2) | Within three (3) months upon request | One training session | In-Person Training in English and German | To the COR |
| 30. In-Person Training (paragraph 5.2.4.4.2) | Within three (3) months upon request | One training session | In-Person Training in English or German | To the COR |
| 31. Field Exercise (paragraph 5.2.4.5.1) | Within three (3) months upon request | One field exercise | Field Exercise in English and German | To the COR |
| 32. Field Exercise (paragraph 5.2.4.5.1) | Within three (3) months upon request | One field exercise | Field Exercise in English or German | To the COR |
| 33. Training Material for Students (paragraph 5.2.4.6.1) | Draft : Within three (3) months upon request Final: Final: Within ten (10) days upon receiving Government comments | One digital copy One hardcopy in each language | Electronic delivery via email as word, pdf file and one hardcopy in English and German | To the COR |
| 34. Training Material for Students (paragraph 5.2.4.6.1) | Draft : Within three (3) months upon request Final: Final: Within ten (10) days upon receiving Government comments | One digital copy One hardcopy in each language | Electronic delivery via email as word, pdf file and one hardcopy in English or German | To the COR |
| 35. Training Exam (paragraph 5.2.4.7.1) | Draft : Within three (3) months upon request Final: Final: Within ten (10) days upon receiving Government comments | One digital copy One hardcopy in each language | Electronic delivery via email as word, pdf file and one hardcopy in English and German | To the COR |
| 36. Training Exam (paragraph 5.2.4.7.1) | Draft : Within three (3) months upon request Final: Final: Within ten (10) days upon receiving Government comments | One digital copy One hardcopy in each language | Electronic delivery via email as word, pdf file and one hardcopy in English or German | To the COR |
| 37. Training Certification (paragraph 5.2.4.8.1) | Draft: Within three (3) days after the training is completed Final: Final: three (3) days upon receiving Government comments | One digital copy One hardcopy in each language | Electronic delivery via email as word, pdf file and one hardcopy in English and German | To the COR |
| 38. Training Certification (paragraph 5.2.4.8.1) | Draft: Within three (3) days after the training is completed Final: Within three (3) days upon receiving Government comments | One digital copy One hardcopy in each language | Electronic delivery via email as word, pdf file and one hardcopy in English or German | To the COR |
| 39. Inspection Report (paragraph 5.2.5.1.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments | One digital copy | Electronic delivery via email pdf file in English and German | To the COR |
| 40. Inspection Report (paragraph 5.2.5.1.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments | One digital copy | Electronic delivery via email pdf file in English or German | To the COR |
| 41. Technical Inspection Report (paragraph 5.2.5.2.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments. | One digital copy | Electronic delivery via email pdf file in English and German | To the COR |
| 42. Technical Inspection Report (paragraph 5.2.5.2.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments. | One digital copy | Electronic delivery via email pdf file in English or German | To the COR |
| 43. Technical Certification Inspection Report (paragraph 5.2.5.3.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments. | One digital copy | Electronic delivery via email pdf file in English and German | To the COR |
| 44. Technical Certification Inspection Report (paragraph 5.2.5.3.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments. | One digital copy | Electronic delivery via email pdf file in English or German | To the COR |
| 45. Re-Inspection Report (paragraph 5.2.5.4.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments | One digital copy | Electronic delivery via email pdf file in English and German | To the COR |
| 46. Re-Inspection Report (paragraph 5.2.5.4.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments | One digital copy | Electronic delivery via email pdf file in English or German | To the COR |
| 47. Site Visit Report (paragraph 5.2.5.5.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments | One digital copy | Electronic delivery via email pdf file in English and German | To the COR |
| 48. Site Visit Report (paragraph 5.2.5.5.1) | Draft: Within fifteen (15) days after inspection. Final: Within five (5) days upon receiving Government comments | One digital copy | Electronic delivery via email pdf file in English or German | To the COR |
| 49. Mapping Survey and Report (paragraph 5.2.6.1.1) | Draft: Within three (3) Draft : Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | ArcGIS geodatabase in the current software version used at ED office in English and/ German | To the COR |
| 50. Mapping Survey and Report (paragraph 5.2.6.1.1) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | ArcGIS geodatabase in the current software version used at ED office in English or German | To the COR |
| 51. Geospatial Data Update (paragraph 5.2.6.2.1) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | ArcGIS geodatabase in the current software version used at ED office in English and German | To the COR |
| 52. Geospatial Data Update (paragraph 5.2.6.2.1) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery Current software version used at ED office and Excel file in English or German | To the COR |
| 53. Database Update (paragraph 5.2.6.3) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery Current software version used at ED office in English and German | To the COR |
| 54. Database Update (paragraph 5.2.6.3) | Draft: Within six (6) months upon request Final: Within ten (10) days upon receiving Government comments | One digital copy | Electronic delivery Current software version used at ED office in English or German | To the COR |
| 55. Air Emission Inventory Update (paragraph 5.2.7.1) | Within three (3) months upon receiving Government comments | One digital copy | Electronic delivery via email word and pdf file in English | To the COR |
| 56. Safety Cabinet Inspection, including documentation (paragraph 5.2.7.2) | Within ten (10) days after completion | One digital copy | Electronic delivery via email in German | To the COR |
| 57. Parts Cleaner Service including documentation (paragraph 5.2.7.1.4) | Within one (1) month upon request with documentation provided ten (10) days after completion | One digital copy | Electronic delivery via email in German | To the COR |
| 58. Hard Copy / Printing service (paragraph 5.2.7.4) | Within ten (10) days upon request | One hardcopy | As requested | To the COR |
| 59. Provide or update Documentation (paragraph 5.2.7.5) | Draft: Within three (3) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy | Electronic delivery via email as word and pdf file in English and German | To the COR |
| 60. Provide or update Documentation (paragraph 5.2.7.5) | Draft: Within three (3) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy | Electronic delivery via email as word and pdf file in English or German | To the COR |
| 61. Permit Renewal Package (paragraph 5.2.7.6) | Draft: Within three (3) months upon request Final: Within ten (10) days upon receiving Government comments. | One digital copy | Electronic delivery via email as word and pdf file in English and German | To the COR |
| 62. Spill supplies (paragraph 5.2.7.7) | provide spill supplies upon request within four (4) weeks | NA | As requested | To the COR |
| 63. Lab Analysis Results (paragraph 5.3.1.1; 5.3.3.,; 5.3.5) | Lab analysis results within ten (10) business days | One digital copy | Electronic delivery via email as pdf file | To the COR |
| 64. Storm Water Reporting (paragraph 5.3.1.2) | Draft-report within thirty (30) calendar days after last sample Final: Within ten (10) days upon receiving Government comments. | One digital copy | Electronic delivery via email as word and pdf file in English and German | To the COR |
| 65.Building Materials Sample Analysis + Reporting (paragraph 5.3.6.4.1) | report within fifteen (15) business days after lab results are returned | One digital copy | Electronic delivery via email as word and pdf file in English and German | To the COR |
| 66. Radon Sampling Reporting (paragraph 5.3.7.1) | Analysis results with a report within fifteen (15) business days after lab results are returned | One digital copy | Electronic delivery via email as pdf file in English & German | To the COR |
| 67. Emergency Services – Lab Analysis, 24hrs (paragraph 5.3.8.2) | Within twenty-four (24) hours from when sampling was conducted. | One digital copy | Electronic delivery via email as pdf file | To the COR |
| 68. Emergency Services – Lab Analysis, 36hrs (paragraph 5.3.8.3) | Within thirty-six (36) hours from when sampling was conducted. | One digital copy | Electronic delivery via email as pdf file | To the COR |
| 69. SCR Reporting (paragraph 5.4) | One time, no later than Oct 31 of each year | One digital copy | Electronic delivery via system of record | Verification sent to the COR |

TECHNICAL EXHIBIT B

PERFORMANCE REQUIREMENTS SUMMARY

| Performance Objective (The Service required—usually a shall statement) | #### Standard, PWS | Performance Threshold (This is the maximum error rate. It could possibly be “Zero deviation from standard”) |
| --- | --- | --- |
| Quality Control Plan (QCP) | 1.5.1 | Zero deviation from standard |
| Contractor Work Plan | 1.5.5 | Zero deviation from standard |
| Installation Passes Log | 1.6.3.1 | Zero deviation from standard |
| Anti-Terrorism (AT) Level I Training | 1.23.1 | Zero deviation from standard |
| OPSEC Training | 1.23.2 | Zero deviation from standard |
| iWATCH Training | 1.23.3 | Zero deviation from standard |
| Project Management - Meeting Minutes | 5.2.1 | Zero deviation from standard |
| Advisory Service for Compliance, yearly completion report | 5.2.2.4 | Zero deviation from standard |
| Compliance Assessment Report | 5.2.2.5 | Zero deviation from standard |
| Management Plans, update | 5.2.3 | Zero deviation from standard |
| Site Visit | 5.2.3.3 | Zero deviation from standard |
| Develop Training | 5.2.4.1 | Zero deviation from standard |
| Update Training | 5.2.4.2 | Zero deviation from standard |
| Online Seminar | 5.2.4.3 | Zero deviation from standard |
| In-Person Training | 5.2.4.4 | Zero deviation from standard |
| Field Exercise | 5.2.4.5 | Zero deviation from standard |
| Provide training material | 5.2.4.6 | Zero deviation from standard |
| Training Exam | 5.2.4.7 | Zero deviation from standard |
| Training Certification | 5.2.4.8 | Zero deviation from standard |
| Inspection | 5.2.5.1 | Zero deviation from standard |
| Technical Inspection | 5.2.5.2 | Zero deviation from standard |
| Technical Certification Inspection | 5.2.5.3 | Zero deviation from standard |
| Re-Inspection | 5.2.5.4 | Zero deviation from standard |
| Site Visit | 5.2.5.5 | Zero deviation from standard |
| Mapping Survey | 5.2.6.1 | Zero deviation from standard |
| Geospatial Data Update | 5.2.6.2 | Zero deviation from standard |
| Database Update | 5.2.6.3 | Zero deviation from standard |
| Air Emission Inventory Update | 5.2.7.1 | Zero deviation from standard |
| Safety Cabinet Inspection | 5.2.7.2 | Zero deviation from standard |
| PWS: 5.2.7.3 Parts Cleaner Services | 5.2.7.3 | Zero deviation from standard |
| PWS: Hardcopy/Printing Services | 5.2.7.4 | Zero deviation from standard |
| Documentation | 5.2.7.5 | Zero deviation from standard |
| Permits | 5.2.7.6 | Zero deviation from standard |
| Spill Supplies | 5.2.7.7 | Zero deviation from standard |
| Storm Water Sampling + Analysis + Reporting | 5.3.1/5.3.5 | Zero deviation from standard |
| Drinking Water Sampling + Analysis + Reporting | 5.3.2/5.3.5 | Zero deviation from standard |
| Wastewater Sampling + Analysis + Reporting | 5.3.3/5.3.5 | Zero deviation from standard |
| Building Material Sampling + Analysis + Reporting | 5.3.6 | Zero deviation from standard |
| Radon Sampling + Analysis + Reporting | 5.3.7 | Zero deviation from standard |
| Emergency Services | 5.3.8 | Zero deviation from standard |
| SCR | 5.4 | Zero deviation from standard |

ATTACHMENT 1

ESTIMATED WORKLOAD DATA

| Item | Service Type | Service Description | Unit | Qty. |
| --- | --- | --- | --- | --- |
| 0001 | Project Management/Advisory Services | Project Management/Advisory Services (paragraph 5.2.1) | hrs | 800 |
| 0002 | Project Management | Mobilization per Event | Job | 100 |
| 0003 | Advisory Services | Compliance Assessment Report (paragraph 5.2.2.5) | 20 Pages | 25 |
| 0004 | Advisory Services | Correspondence with Authorities (paragraph 5.) | Hrs | 15 |
| 0005 | Advisory Services | Meeting with Authorities (paragraph 5.) | Hrs | 15 |
| 0006 | Advisory Services | Hazardous Substance Compliance Program Support (paragraph 5.2.2.1) | Hrs | 260 |
| 0008 | Advisory Services | Environmental Awareness Support - Events (paragraph 5.2.2.2) | Hrs | 10 |
| 0009 | Advisory Services | EPAS Support (paragraph 5.2.2.3) | Hrs | 20 |
| 0010 | Advisory Services | Internal EPAAS Follow Up Support (paragraph 5.2.2.3) | Hrs | 10 |
| 0011 | Advisory Services | Hazard Communication Program (paragraph 5.) | Hrs | 10 |
| 0012 | Management Plan | Update Management Plan (paragraph 5.2.3) | Job | 2 |
| 0013 | Management Plan | Site Visit for a Management Plan (paragraph 5.2.3) | hrs | 20 |
| 0014 | Training | Develop Training (paragraph 5.2.4.1) | Job | 1 |
| 0015 | Training | Update Training - (paragraph 5.2.4.2) | Job | 1 |
| 0016 | Training | Provide Training - Online Seminar (up to 4 hours) (paragraph 5.2.4.3) | Job | 3 |
| 0017 | Training | Provide Training - In-Person Training (up to 4 hours) (paragraph 5.2.4.4) | Job | 3 |
| 0018 | Training | Provide Training - Field Exercise (up to 2 hours) (paragraph 5.2.4.5) | Job | 3 |
| 0019 | Training | Provide training material for students (up to 10 pages) (paragraph 5.2.4.6) | Job | 3 |
| 0020 | Training | Provide Exam (up to 10 Questions) (paragraph 5.2.4.7) | Job | 3 |
| 0021 | Training | Training Certification (1 Training Certificate for up to 10 Students) (paragraph 5.2.4.8) | Job | 5 |
| 0022 | Inspection | Inspection (2 hours) (paragraph 5.2.5.1) | Job | 35 |
| 0023 | Inspection | Technical Inspection (qualified specialist) (paragraph 5.2.5.2) | Job | 5 |
| 0024 | Inspection | Technical Certification Inspection (certified expert, Sachverständiger i.e. TÜV) (paragraph 5.2.5.3) | Job | 5 |
| 0025 | Inspection | Re-Inspection (4 hours) (paragraph 5.2.5.4) | Job | 1 |
| 0026 | Inspection | Site visit (2 hours) (paragraph 5.2.5.5) | Job | 10 |
| 0027 | Surveys | Mapping Survey and a Report (paragraph 5.2.6.1) | 1 000 m² | 1 |
| 0028 | Surveys | Geospatial Data Update (up to 50 pages) (paragraph 5.2.6.2) | Job | 1 |
| 0029 | Surveys | Database Update (up to 50 pages) (paragraph 5.2.6.3) | Job | 1 |
| 0030 | Technical Environmental Services | Air Emission Inventory Update (paragraph 5.2.7.1) | Job | 1 |
| 0031 | Technical Environmental Services | Safety Cabinet Inspection (paragraph 5.2.7.2) | Job | 1 |
| 0032 | Technical Environmental Services | Parts Cleaner Maintenance Services for model 112 (paragraph 5.2.7.3) | Job | 12 |
| 0033 | Technical Environmental Services | Parts Cleaner Maintenance Services for model 100 (paragraph 5.2.7.3) | Job | 12 |
| 0034 | Hard copy / Printing services | Printing service to finalize deliverables required under specific tasks. For each deliverable, for eample booklets, fliers, the Government will specify quantity and quality according to the specifications. (paragraph 5.2.7.4) | Job | 5 |
| 0035 | Documentation | Development of Documentation (up to 2 pages) (paragraph 5.2.7.5) | Job | 5 |
| 0036 | Documentation | Update Documentation (up to 2 pages) (paragraph 5.2.7.5) | Job | 5 |
| 0037 | Permits | Update or reneval of a permit (paragraph 5.2.7.6) | Job | 8 |
| 0038 | Spill Supplies | Provision of Spill Supplies (Paragraph 5.2.7.7) | Job | 2 |
| 0039 | Storm Water | Storm Water Sampling - qualified sample (qualifizierte Stichprobe) including weather conditions, field parameters and observations | Job | 25 |
| 0040 | Storm Water | Storm Water Investigation Report for Panzer Kaserne (English & German) | Job | 1 |
| 0041 | Drinking Water | Drinking Water Sampling - Bromate Sampling | Job | 20 |
| 0042 | Drinking Water | Drinking Water Sampling - Residual Chlorine & Fluoride Sampling | Job | 100 |
| 0043 | Drinking Water | Drinking Water Sampling - Chlorite Sampling | Job | 100 |
| 0044 | Drinking Water | Drinking Water Sampling - Lead Sampling | Job | 20 |
| 0045 | Drinking Water | Drinking Water Sampling - Legionella Sampling | Job | 20 |
| 0046 | Waste Water | Waste Water Sampling | Job | 10 |
| 0047 | Water | Additional Water Sampling | Job | 20 |
| 0048 | Building Materials Support | Building Materials Sampling - collection from a wall tile, wall plaster, insulation materials, wooden floors | Job | 20 |
| 0049 | Building Materials Support | Building Materials Sampling - by drill through floor cores | Job | 5 |
| 0050 | Building Materials Support | Building Materials Sampling - from an existing pile | Job | 20 |
| 0051 | Building Materials Support | Building Materials Sampling Reporting (English & German) | Job | 20 |
| 0055 | Drinking Water Analysis | Bromate | EA | 20 |
| 0056 | Drinking Water Analysis | Fluoride | EA | 100 |
| 0057 | Drinking Water Analysis | Nitrate | EA | 2 |
| 0058 | Drinking Water Analysis | Lead (Pb) | EA | 20 |
| 0059 | Drinking Water Analysis | Legionella | EA | 20 |
| 0060 | Drinking Water Analysis | Copper | EA | 2 |
| 0061 | Drinking Water Analysis | Nitrite | EA | 2 |
| 0062 | Drinking Water Analysis | Carbon Dioxide | EA | 2 |
| 0063 | Drinking Water Analysis | Free Available Chlorine | EA | 100 |
| 0064 | Drinking Water Analysis | Chlorite | EA | 100 |
| 0065 | Drinking Water Analysis | Iron | EA | 2 |
| 0066 | Storm Water Analysis | Lab analysis for stormwater to include: conductivity at 20°C (μS/cm), 25°C (μS/cm), pH, settleable solids (absetzbare Stoffe), chloride, sulfate, magnesium, sodium, potassium, cyanide | EA | 50 |
| 0067 | Waste Water Analysis | Total Dissolved and Suspended and settleable Solids | EA | 5 |
| 0068 | Waste Water Analysis | Total Organic Carbon (TOC), Chemical Oxygen Demand (COD), Biological Oxygen Demand (BOD), pH value, electric conductivity | EA | 5 |
| 0069 | Waste Water Analysis | Inorganic parameters: Calcium (Ca), Potassium (K), Magnesium (Mg), Sodium (Na), Chloride (Cl), Sulfate (SO4), Cyanides | EA | 5 |
| 0070 | Water Analysis | Sum BTEX and single parameters | EA | 1 |
| 0071 | Water Analysis | PAH acc. to EPA incl. Benzo(a)pyrene, Sum PAH (16), Sum PAH (15) w/o Naphthalene, and single parameters | EA | 1 |
| 0072 | Water Analysis | Total Trihalogenmethanes (TTHM) | EA | 1 |
| 0073 | Water Analysis | Hexavalent and Trivalent Chrome (E 1413 Chrome VI, method: DIN 38405-D24) | EA | 1 |
| 0074 | Water Analysis | Sum Total Petroleum Hydrocarbons(TPH), Hydrocarbon Index C10-C40 | EA | 1 |
| 0075 | Water Analysis | Polychlorinated Biphenyls (PCB) : sum PCB (7) congeners and single parameters | EA | 1 |
| 0076 | Water Analysis | Chlorinated Hydrocarbons (CHC) incl. Vinyl Chloride, sum and single parameters | EA | 1 |
| 0077 | Water Analysis | Heavy metals: incl. Arsenic, Lead, Cadmium, Copper, Chromium, Mercury, Nickel, Thallium, Zinc | EA | 1 |
| 0078 | Water Analysis | Perfluorinated Compounds (PFC): Erlass Umweltministerium BW (21Aug18): Anwendung Geringfügig-keitsschwellenwerte für PFC zur Beurteilung nachteiliger Veränderungen der Beschaffenheit des Grund-und Sickerwassers aus schädlichen Bodenveränderungen und Altlasten. Die analytische Bestimmungsgrenze soll < oder = 0,01µg/l betragen. Perfluorbutansäure PFBA, Perfluorpentansäure PFPeA, Perfluorhexan-säure PFHxA, Perfluorheptansäure PFHpA, Perfluoroctansäure PFOA, Perfluornonansäure PFNA, Perfluordecansäure PFDA, Perfluorbutan-sulfonsäure PFBS, Perfluorhexansulfonsäure PFHxS, Perfluorheptan-sulfonsäure PFHpS, Perfluoroctansulfonsäure PFOS, 1H,1H,2H,2H-Perfluoroctansulfonsäure 6:2 FTSA, H4PFOS, Perfluoroctansulfon-amid PFOSA = FOSA, Weitere PFC z.B. GenX, ADONA, u.a. | EA | 1 |
| 0079 | Building Materials Analysis | Asbestos Fibers , VDI 3866, Bl. : 06-2017 | EA | 10 |
| 0080 | Building Materials Analysis | Artificial Mineral Fibers (KMF), KI-Index , VDI 3866, Bl. : 06-2017 | EA | 10 |
| 0081 | Building Materials Analysis | PCB: sum PCB (7) congeners, and single parameters | EA | 10 |
| 0082 | Building Materials Analysis | PAH acc. to EPA incl. Benzo(a)pyrene, Sum PAH (16), Sum PAH (15) w/o Naphthalene, and single parameters | EA | 10 |
| 0083 | Building Materials Analysis | PCP and Lindane | EA | 2 |
| 0084 | Building Materials Analysis | Wood Preservatives: Lindane, DDT, etc. | EA | 2 |
| 0085 | Building Materials Analysis | Heavy metals: incl. Arsenic, Lead, Cadmium, Copper, Chrome, Mercury, Nickel, Thallium, Zinc | EA | 5 |
| 0086 | Radon Sampling + Reporting | confirm regulations and requirements | EA | 5 |
| 0087 | Emergency Services | Emergency Services - Water & Soil Sampling | Job | 15 |
| 0088 | Expedited Analysis - Water Analysis - 24hrs | Analysis within 24 hours | job | 5 |
| 0089 | Expedited Analysis - Water Analysis - 36hrs | Analysis within 36 hours | job | 5 |
| 0090 | eCMRA | Enterprise-Wide Contractor Manpower Reporting Application (eCMRA) | Job | 1 |

ATTACHMENT 2

ENGLISH LANGUAGE FLUENCY CLARIFICATION

# LEVEL 1 Rudimentary Knowledge

At this level an employee is, at most, required to have a rudimentary verbal understanding of a very limited English vocabulary, as might be required in understanding and following instructions of the type that might be given to a motor pool chauffeur. This level of understanding is typically not required for positions such as laborer and trades occupations where contacts are primarily with other local employees.

# LEVEL 2 Limited Knowledge

At this level an employee needs only a limited knowledge of written and spoken English, and a vocabulary limited to the specific occupation. An employee at this level would be expected to understand and carry out verbal instructions of a repetitive character, and to be able to prepare simple reports of the type that might be expected of a motor pool dispatcher.

# LEVEL 3 Good Working Knowledge

At this level an employee is required to have a good working knowledge of both written and spoken English. The employee should be able to read and understand agency regulations, operating instructions, memoranda, and related material concerning the field of work, to prepare correspondence and standardized reports, and to communicate effectively with English speaking staff members and the general public, including both English speaking and non-English speaking persons.

# LEVEL 4 Fluent

At this level an employee is required to possess a high degree of proficiency in both written and spoken English, including the ability to translate the host country language into precise and correct English, and English into the applicable foreign language. On occasion, an employee at this level might be expected to act as an interpreter in situations where considerable importance attaches to proper word meaning.

# LEVEL 5 Professional Translator/ Interpreter or Equivalent

This level is essentially limited to professional translators and interpreters whose proficiency in written and spoken English truly matches that of a well-educated native speaker. This includes the ability to deal effectively with highly technical and sophisticated terminology in which fine nuances of meaning may at times assume major importance in negotiations. At this level an employee should be capable of simultaneous translation, as in the case of conference reporting. An equivalent level of difficulty and responsibility relates to those employees who are required to be fluent in two or more foreign languages, or two or more distinctly different and complex native dialects.

ATTACHMENT 3

Laboratory Analysis Parameters List

All samples shall analyzed according to applicable federal and/or state and/or other legislation and ordinances (e.g. Federal Soil Act, BW State Ordinance Contaminated Sites, Drinking Water Ordinance, Landfill Ordinance) including eluate analysis if necessary

- According to the German Drinking Water Ordinance, Annex 1, Part I (Trinkwasserverordnung, Anlage 1, Teil I)

- According to the German Drinking Water Ordinance, Annex 1, Part II (Trinkwasserverordnung, Anlage 1, Teil II)

- According to the German Drinking Water Ordinance, Annex 2, Part I (Trinkwasserverordnung, Anlage 2, Teil I)

- According to the German Drinking Water Ordinance, Annex 2, Part II (Trinkwasserverordnung, Anlage 2, Teil II)

- According to the German Drinking Water Ordinance, Annex 3, Part I (Trinkwasserverordnung, Anlage 3, Teil I)

- According to the German Drinking Water Ordinance, Annex 3, Part II (Trinkwasserverordnung, Anlage 3, Teil II)

| Service type | Parameter |
| --- | --- |
| Drinking Water Analysis | Bromate |
| Drinking Water Analysis | Fluoride |
| Drinking Water Analysis | Nitrate |
| Drinking Water Analysis | Lead |
| Drinking Water Analysis | Copper |
| Drinking Water Analysis | Nitrite |
| Drinking Water Analysis | Chloride |
| Drinking Water Analysis | Iron |
| Storm Water analysis | Qualified surface water analysis for stormwater to include: conductivity at 20°C (μS/cm), 25°C (μS/cm), pH, removable fabrics (absetzbare stoffe), chloride, sulfate, magnesium, sodium, potassium, cyanide gas |
| Waste Water Analysis | Total Dissolved and Suspended and Settable Solids |
| Waste Water Analysis | Total Organic Carbon, Chemical Oxygen Demand, Biological Oxygen Demand, pH , electric conductivity |
| Waste Water Analysis | Inorganic parameters: Calcium, Potassium, Magnesium, Sodium, Chloride (Cl), Sulfate (SO4), Cyanides |
| Water Analysis | Sum BTEX and single parameters |
| Water Analysis | PAH acc. to EPA incl. Benzo(a)pyrene, Sum PAH (16), Sum PAH (15) w/o Naphthalene, and single parameters |
| Water Analysis | THM (Tri-halogen-methane) |
| Water Analysis | Hexavalent and Trivalent Chromium (E 1413 Chromium VI method: DIN 38405-D24) |
| Water Analysis | Sum Total Petroleum Hydrocarbons (TPH), Hydrocarbon Index (C10-C40) |
| Water Analysis | Polychlorinated Biphenyls (PCB) : sum PCB (7) congeners and single parameters |
| Water Analysis | Chlorinated Hydrocarbons (CHC) incl. Vinyl Chloride, sum CHC and single parameters |
| Water Analysis | Heavy metals: incl. lead, cadmium, chromium, nickel, mercury, zinc, copper, arsenic, thallium |
| Water Analysis | PFCs: Erlass Umweltministerium BW (21Aug18): Anwendung Geringfügig-keitsschwellenwerte für PFC zur Beurteilung nachteiliger Veränderun-gen der Beschaffenheit des Grund-und Sickerwassers aus schädlichen Bodenveränderungen und Altlasten. Die analystische Bestimmungsgrenze soll < oder = 0,01µg/l betragen. Perfluorbutansäure PFBA, Perfluorpentansäure PFPeA, Perfluorhexan-säure PFHxA, Perfluorheptansäure PFHpA, Perfluoroctansäure PFOA, Perfluornonansäure PFNA, Perfluordecansäure PFDA, Perfluorbutan-sulfonsäure PFBS, Perfluorhexansulfonsäure PFHxS, Perfluorheptan-sulfonsäure PFHpS, Perfluoroctansulfonsäure PFOS, 1H,1H,2H,2H-Perfluoroctansulfonsäure 6:2 FTSA, H4PFOS, Perfluoroctansulfon-amid PFOSA = FOSA, Weitere PFC z.B. GenX, ADONA, u.a. |
| Building Material Analyses | Asbestos Fibers , VDI 3866, Bl. : 06-2017 |
| Building Material Analyses | Artificial Mineral Fibers (KMF), KI-Index , VDI 3866, Bl. : 06-2017 |
| Building Material Analyses | PCB: sum PCB (7) congeners, and single parameters |
| Building Material Analyses | PAH acc. to EPA incl. Benzo(a)pyrene, Sum PAH (16), and single parameters |
| Building Material Analyses | PCP and Lindane |
| Building Material Analyses | Wood Preservatives: Lindane, DDT, etc. |
| Building Material Analyses | Heavy metals, incl. lead, cadmium, chromium, nickel, mercury, zinc, copper, arsenic, thallium |
| Radon Analyses |  |