Liquidation Damages Formulation Memo

Solicitation Number: 36C244

Project: Replace Steam, Condensate, and Vaults Phase 1             Project Number: 595-21-103

- Estimated liquidated damages for VISN 4 Contracting, and Legal reviews per day of inexcusable delay (wage rates based upon the General Schedule Locality Pay Table 2022-PIT):

| CLASSIFICATION | GRADE | RATE | HOURS TOTAL | TOTAL RATE |
| --- | --- | --- | --- | --- |
| Contracting Officer Supervisor | GS-13 / 5 | $59.17 | 2 Hours | $118.34 |
| Contracting Officer | GS-12 / 5 | $49.76 | 4 Hours | $199.04 |
| Legal Officer | GS-14 / 5 | $69.92 | 1 Hour | $66.92 |
| TOTAL PER DAY |  |  |  | $384.30 |

- Estimated liquidated damages for Facility Engineering (COR/COTR) per day of inexcusable delay (wage rates based upon the General Schedule Locality Pay Table 2025-HB and Special Rate Table 773):

| CLASSIFICATION | GRADE | RATE | HOURS TOTAL | TOTAL RATE |
| --- | --- | --- | --- | --- |
| Projects Supervisor | GS-13 / 5 | $64.75 | 1 Hours | $64.75 |
| Project Engineer | GS-12 / 5 | $55.69 | 2 Hours | $111.38 |
| Construction Control Rep | GS-11 / 5 | $40.96 | 4 Hours | $163.84 |
| TOTAL PER DAY |  |  |  | $339.97 |

| Grand Total Per Day |  |  |  | $724.27 round up to $725.00 |
| --- | --- | --- | --- | --- |

- The Contractor shall pay liquidated damages to the Government in the amount of $725.00

for each calendar day of delay until the work is completed or accepted. The aforementioned costs were derived based upon historical trends associated with the time required of the parties to perform the additional contract administration which has not been completed by the Contractor within the specified time. The purpose of Liquidated Damages is compensatory only. The government retains the right to seek actual damages so far as they are distinguishable and separate from the Contractor failing to complete the work within the time specified in the contract.

- The formulation of Liquidated Damages as detailed above are in accordance with Federal Acquisition Regulation 36.206 and will be assessed for each calendar day required to complete

the construction work on this project past the scheduled completion date.